## durchut jmr
Mangraura
darchut
ROHIT Enterprises
S.NO | DATE | Start Node | End Node | Type of Road | DI/HDPE | Pipe Length (M) | [5 empty] | Cumulative Length (M) | LHS/RHS | Distance from Road C/L | Site Engineer Sign | Remarks
[6 empty] | 63mm | 75mm | 90mm | 110mm | 140 | 160
1 | 2023-11-07 | j3 | j16 |  |  | 202 | [5 empty] | 202
2 | 2023-11-07 | j16 | j14 |  |  | 103 | [5 empty] | 305
3 | 2023-11-08 | j23 | j15 | [5 empty] | 118 |  |  | 423
4 | 2023-11-08 | j15 | j05 | [5 empty] | 201 |  |  | 624
5 | 2023-11-08 | j5 | j3 | [5 empty] | 93 |  |  | 717
6 | 2023-11-08 | j3 | j2 | [5 empty] | 38 |  |  | 755
7 | 2023-11-08 | j23 | j6 | [5 empty] | 150 |  |  | 905
8 | 2023-11-09 | j66 | j67 |  |  | 405 | [5 empty] | 1310
9 | 2023-11-10 | j140 | j134 |  |  | 128 | [5 empty] | 1438
10 | 2023-11-10 | j134 | j131 |  |  | 95 | [5 empty] | 1533
11 | 2023-11-10 | j131 | j128 |  |  |  | 220 |  |  |  |  | 1753
12 | 2023-11-17 | j67 | j128 |  |  |  | 99 |  |  |  |  | 1852
13 | 2023-11-17 | j23 | j67 |  |  |  |  | 165 |  |  |  | 2017
14 | 2023-11-18 | j131 | j132 |  |  | 67 | [5 empty] | 2084
15 | 2023-11-18 | j132 | j133 |  |  | 209 | [5 empty] | 2293
16 | 2023-11-19 | j110 | j111 |  |  | 11 | [5 empty] | 2304
17 | 2023-11-19 | j111 | j109 |  |  | 58 | [5 empty] | 2362
18 | 2023-11-19 | j109 | j104 |  |  | 130 | [5 empty] | 2492
19 | 2023-11-19 | j104 | j85 |  |  | 148 | [5 empty] | 2640
20 | 2023-11-19 | j85 | j52 |  |  | 225 | [5 empty] | 2865
21 | 2023-11-20 | j52 | j43 |  |  | 23 | [5 empty] | 2888
22 | 2023-11-20 | j43 | j31 |  |  | 63 | [5 empty] | 2951
23 | 2023-11-20 | j31 | j14 |  |  | 62 | [5 empty] | 3013
24 | 2023-11-22 | j148 | j147 |  |  | 25 | [5 empty] | 3038
25 | 2023-11-22 | j147 | j146 |  |  | 33 | [5 empty] | 3071
26 | 2023-11-22 | j146 | j140 |  |  | 89 | [5 empty] | 3160
27 | 2023-11-22 | j14 | j13 |  |  | 44 | [5 empty] | 3204
28 | 2023-11-22 | j13 | j12 |  |  | 36 | [5 empty] | 3240
29 | 2023-11-23 | J96 | J103 |  |  | 112 | [5 empty] | 3352
30 | 2023-11-23 | J103 | J104 |  |  | 78 | [5 empty] | 3430
31 | 2023-11-23 | J103 | J102 |  |  | 161 | [5 empty] | 3591
32 | 2023-11-24 | J94 | J96 |  |  | 22 | [5 empty] | 3613
33 | 2023-11-24 | J102 | J108 |  |  | 60 | [5 empty] | 3673
34 | 2023-11-24 | J80 | J83 |  |  | 56 | [5 empty] | 3729
35 | 2023-11-24 | J137 | J132 |  |  | 129 | [5 empty] | 3858
36 | 2023-11-24 | J137 | J135 |  |  | 12 | [5 empty] | 3870
37 | 2023-11-24 | J135 | J136 |  |  | 17 | [5 empty] | 3887
38 | 2023-11-24 | J134 | J135 |  |  | 65 | [5 empty] | 3952
39 | 2023-11-28 | j132 | j133 |  |  | 209 | [5 empty] | 4161
40 | 2023-12-06 | j86 | j89 |  |  | 22 | [5 empty] | 4183
41 | 2023-12-06 | j86 | j91 |  |  | 77 | [5 empty] | 4260
42 | 2023-12-06 | j91 | j92 |  |  | 26 | [5 empty] | 4286
43 | 2023-12-06 | j91a | j92b |  |  | 40 | [5 empty] | 4326
44 | 2023-12-06 | j79 | j80 |  |  | 40 | [5 empty] | 4366
45 | 2023-12-06 | j81 | j86 |  |  | 53 | [5 empty] | 4419
46 | 2023-12-06 | j81 | j79 |  |  | 30 | [5 empty] | 4449
47 | 2023-12-06 | j80 | j73 |  |  | 37 | [5 empty] | 4486
48 | 2023-12-06 | j65 | j70 |  |  | 59 | [5 empty] | 4545
49 | 2023-12-06 | j146 | j150 |  |  | 48 | [5 empty] | 4593
50 | 2023-12-06 | j150 | j152 |  |  | 20 | [5 empty] | 4613
51 | 2023-12-06 | j152 | j153 |  |  | 39 | [5 empty] | 4652
52 | 2023-12-14 | 70 | 79 |  |  | 14 | [5 empty] | 4666
53 | 2023-12-14 | 64 | 70 |  |  | 42 | [5 empty] | 4708
54 | 2023-12-14 | 57 | 64 |  |  | 33 | [5 empty] | 4741
55 | 2023-12-14 | 56 | 57 |  |  | 33 | [5 empty] | 4774
56 | 2023-12-14 | 53 | 56 |  |  | 19 | [5 empty] | 4793
57 | 2023-12-14 | 45 | 53 |  |  | 41 | [5 empty] | 4834
58 | 2023-12-14 | 45 | 48 |  |  | 87 | [5 empty] | 4921
59 | 2024-01-03 | 48 | 49 |  |  | 26 | [5 empty] | 4947
60 | 2024-01-03 | 49 | 46 |  |  | 11 | [5 empty] | 4958
61 | 2024-01-03 | 43 | 46 |  |  | 32 | [5 empty] | 4990
62 | 2024-01-03 | 46 | 51 |  |  | 62 | [5 empty] | 5052
63 | 2024-01-03 | 128 | 130 |  |  | 88 | [5 empty] | 5140
64 | 2024-01-04 | 96 | 97 |  |  | 82 | [5 empty] | 5222
65 | 2024-01-04 | 97 | 98 |  |  | 20 | [5 empty] | 5242
66 | 2024-01-04 | 88 | 89 |  |  | 47 | [5 empty] | 5289
67 | 2024-01-04 | 83 | 88 |  |  | 56 | [5 empty] | 5345
68 | 2024-01-04 | 69 | 73 |  |  | 28 | [5 empty] | 5373
69 | 2024-01-04 | 60 | 69 |  |  | 66 | [5 empty] | 5439
70 | 2024-01-04 | 58 | 60 |  |  | 141 | [5 empty] | 5580
71 | 2024-01-04 | 55 | 62 |  |  | 90 | [5 empty] | 5670
72 | 2024-01-05 | 15 | 55 |  |  | 206 | [5 empty] | 5876
73 | 2024-01-06 | 68 | 69 |  |  | 66 | [5 empty] | 5942
74 | 2024-01-06 | 144 | 156 |  |  | 82 | [5 empty] | 6024
75 | 2024-01-08 | 58 | 59 |  |  | 54 | [5 empty] | 6078
76 | 2024-01-08 | 153 | 154 |  |  | 55 | [5 empty] | 6133
77 | 2024-01-08 | 145 | 154 |  |  | 70 | [5 empty] | 6203
78 | 2024-01-29 | 5 | 55 |  |  | 206 | [5 empty] | 6409
79 | 2024-01-30 | 55 | 60 |  |  | 52 | [5 empty] | 6461
80 | 2024-01-30 | 96 | 97 |  |  | 82 | [5 empty] | 6543
81 | 2024-01-30 | 97 | 98 |  |  | 20 | [5 empty] | 6563
82 | 2024-02-01 | 19 | 20 |  |  | 41 | [5 empty] | 6604
83 | 2024-02-01 | 20 | 18 |  |  | 38 | [5 empty] | 6642
84 | 2024-02-01 | 18 | 14 |  |  | 76 | [5 empty] | 6718
85 | 2024-02-16 | 36 | 42 |  |  | 139 | [5 empty] | 6857
86 | 2024-02-16 | 39 | 44 |  |  | 147 | [5 empty] | 7004
87 | 2024-02-16 | 17 | 19 |  |  | 251 | [5 empty] | 7255
88 | 2024-02-16 | 8 | 9 |  |  | 33 | [5 empty] | 7288
89 | 2024-02-16 | 9 | 10 |  |  | 25 | [5 empty] | 7313
90 | 2024-02-16 | 12 | 11 |  |  | 47 | [5 empty] | 7360
91 | 2024-02-16 | 14 | 18 |  |  | 76 | [5 empty] | 7436
92 | 2024-02-17 | 49 | 50 |  |  | 36 | [5 empty] | 7472
93 | 2024-02-17 | 31 | 32 |  |  | 9 | [5 empty] | 7481
94 | 2024-02-17 | 42 | 33 |  |  | 23 | [5 empty] | 7504
95 | 2024-02-17 | 33 | 41 |  |  | 30 | [5 empty] | 7534
96 | 2024-02-17 | 73 | 78 |  |  | 46 | [5 empty] | 7580
97 | 2024-02-17 | 80 | 84 |  |  | 40 | [5 empty] | 7620
[6 empty] | 6536 | 319 | 165 | 600 | 0 | 0 | 7620
Representative PMPL - BRCCPL (JV) Pratapgarh | [5 empty] | Representative Medhaj Techno Concept Pvt Ltd (TPI) Pratapgarh | [6 empty] | Representative UP Jal Nigam (Rural) Pratapgarh

## saray jamuari jmr
Block |  | Mangraura
GP |  | SARAY JAMMUVARI
Total Length (M) |  | 20125
FHTC (No's)
Agency Name |  | DR ENTERPRISE
Sl.No | Date | Start Node | End Node | Type of Road | DI/HDPE | Pipe Length (M) | [8 empty] | Cumulative Length (M) | LHS/RHS | Distance from Road C/L | Site Engineer Sign | Remarks
[6 empty] | 63mm | 75mm | 90mm | 110mm | 125mm | 140mm | 160mm | DI 250mm
| 2025-01-23 | J-77 | J-50 | KACHA ROAD | HDPE | 38 | [8 empty] | 38 | LHS | 1.2 | NAGA PHANI
| 2025-01-23 | J-68 | J-52 | KACHA ROAD | HDPE | 36 | [8 empty] | 74 | LHS | 1 | NAGA PHANI
| 2025-01-23 | J-68A | J-68B | KACHA ROAD | HDPE | 43.3 | [8 empty] | 117.3 | LHS | 1 | NAGA PHANI
| 2025-01-23 | J-78A | J-78B | KACHA ROAD | HDPE | 56 | [8 empty] | 173.3 | LHS | 1.2 | NAGA PHANI
| 2025-01-23 | J-41 | J-78B | KACHA ROAD | HDPE | 48 | [8 empty] | 221.3 | LHS | 1.2 | NAGA PHANI
| 2025-01-24 | J-37 | J-53 | BOE | HDPE | 69.7 | [8 empty] | 291 | LHS | 1.2 | NAGA PHANI
| 2025-01-24 | J-53 | J-83 | BOE | HDPE | 86 | [8 empty] | 377 | LHS | 1.2 | NAGA PHANI
| 2025-01-24 | J-83 | J-67 | KACHA ROAD | HDPE | 20 | [8 empty] | 397 | LHS | 1.2 | NAGA PHANI
| 2025-01-24 | J-53 | J-86 | KACHA ROAD | HDPE | 39 | [8 empty] | 436 | LHS | 1.2 | NAGA PHANI
| 2025-01-24 | J-199 | J-233 | KACHA ROAD | HDPE | 19 | [8 empty] | 455 | LHS | 1.2 | NAGA PHANI
| 2025-01-25 | J-199 | J-237 | KACHA ROAD | HDPE | 17 | [8 empty] | 472 | LHS | 1.2 | NAGA PHANI
| 2025-01-25 | J-222 | J-232 | KACHA ROAD | HDPE | 107 | [8 empty] | 579 | LHS | 1.2 | NAGA PHANI | HDD
| 2025-01-25 | J-224 | J-223 | BOE | HDPE | 43 | [8 empty] | 622 | RHS | 1.2 | NAGA PHANI
| 2025-01-25 | J-235 | J-206 | BOE | HDPE | 68 | [8 empty] | 690 | LHS | 1.2 | NAGA PHANI | HDD
| 2025-01-25 | J-214 | J-131 | KACHA ROAD | HDPE | 28 | [8 empty] | 718 | LHS | 1.2 | NAGA PHANI | HDD
| 2025-01-25 | J-131 | J-152 | KACHA ROAD | HDPE | 50 | [8 empty] | 768 | LHS | 1.2 | NAGA PHANI | HDD
| 2025-01-25 | J-214 | J-225 | KACHA ROAD | HDPE | 45 | [8 empty] | 813 | LHS | 1.2 | NAGA PHANI | HDD
| 2025-01-25 | J-141 | J-105 | BOE | HDPE | 54 | [8 empty] | 867 | LHS | 1.2 | NAGA PHANI
| 2025-01-25 | J-141 | J-119 | BOE | HDPE | 16 | [8 empty] | 883 | LHS | 1.2 | NAGA PHANI
| 2025-01-26 | J-146 | J-186 | KACHA ROAD | HDPE | 18 | [8 empty] | 901 | LHS | 1.2 | NAGA PHANI
| 2025-01-26 | J-160 | J-208 | BOE | HDPE | 108.8 | [8 empty] | 1009.8 | LHS | 1.2 | NAGA PHANI
| 2025-01-27 | J-208 | J-211 | BOE | HDPE | 54 | [8 empty] | 1063.8 | LHS | 1.2 | NAGA PHANI
| 2025-01-27 | J-211 | J-211A | KACHA ROAD | HDPE | 28 | [8 empty] | 1091.8 | LHS | 1.2 | NAGA PHANI
| 2025-01-27 | J-208 | J-208A | KACHA ROAD | HDPE | 37 | [8 empty] | 1128.8 | CENTER | 0 | NAGA PHANI
| 2025-01-27 | J-257 | J-243 | KACHA ROAD | HDPE | 160.5 | [8 empty] | 1289.3 | CENTER | 0 | NAGA PHANI
| 2025-01-28 | J-249 | J-243 | KACHA ROAD | HDPE | 49 | [8 empty] | 1338.3 | CENTER | 0 | NAGA PHANI
| 2025-01-28 | J-249 | J-245 | BOE | HDPE | 15.7 | [8 empty] | 1354 | CENTER | 0 | NAGA PHANI
| 2025-01-28 | J-245 | J-247 | KACHA ROAD | HDPE | 12 | [8 empty] | 1366 | CENTER | 0 | NAGA PHANI
| 2025-01-28 | J-245 | J-200 | BOE | HDPE | 104.7 | [8 empty] | 1470.7 | CENTER | 0 | NAGA PHANI
| 2025-01-28 | J-245 | J-200 | KACHA ROAD | HDPE | 31 | [8 empty] | 1501.7 | CENTER | 0 | NAGA PHANI | HDD
| 2025-01-28 | J-245 | J-200 | IL | HDPE | 98.8 | [8 empty] | 1600.5 | CENTER | 0 | NAGA PHANI
| 2025-01-28 | J-251 | J-278 | KACHA ROAD | HDPE | 20 | [8 empty] | 1620.5 | CENTER | 0 | NAGA PHANI
| 2025-01-28 | J-135A | J-135B | KACHA ROAD | HDPE | 19 | [8 empty] | 1639.5 | LHS | 1.2 | NAGA PHANI
| 2025-01-28 | J-135C | J-135D | KACHA ROAD | HDPE | 29 | [8 empty] | 1668.5 | LHS | 1.2 | NAGA PHANI
|  | J-135 | J-114 | BOE | HDPE | 31 | [8 empty] | 1699.5 | LHS | 1.2 | NAGA PHANI | HDD
|  | J-32 | J-03 | BOE | HDPE | 84 | [8 empty] | 1783.5 | LHS | 1 | NAGA PHANI | HDD
|  | J-11 | J-07 | KACHA ROAD | HDPE | 69 | [8 empty] | 1852.5 | LHS | 1 | NAGA PHANI
|  | J-07 | J-55 | BOE | HDPE | 38 | [8 empty] | 1890.5 | LHS | 1 | NAGA PHANI | HDD
|  | J-7 | J-55 | KACHA ROAD | HDPE | 22 | [8 empty] | 1912.5 | LHS | 1 | NAGA PHANI | HDD
|  | J-90 | J-65 | KACHA ROAD | HDPE | 34 | [8 empty] | 1946.5 | LHS | 1 | NAGA PHANI
|  | J-90 | J-203 | KACHA ROAD | HDPE | 103 | [8 empty] | 2049.5 | LHS | 1 | NAGA PHANI
|  | J-90 | J-203 | IL | HDPE | 75 | [8 empty] | 2124.5 | LHS | 1 | NAGA PHANI
|  | J-90 | J-203 | BOE | HDPE | 30 | [8 empty] | 2154.5 | LHS | 1 | NAGA PHANI
|  | J-132 | J-210 | KACHA ROAD | HDPE | 49.6 | [8 empty] | 2204.1 | LHS | 1 | NAGA PHANI
|  | J-210 | J-176 | KACHA ROAD | HDPE | 36 | [8 empty] | 2240.1 | LHS | 1 | NAGA PHANI
|  | J-210 | J-210A | KACHA ROAD | HDPE | 85.6 | [8 empty] | 2325.7 | LHS | 1 | NAGA PHANI
|  | J-210A | J-210B | KACHA ROAD | HDPE | 43.5 | [8 empty] | 2369.2 | LHS | 1 | NAGA PHANI
|  | J-210A | J-156 | KACHA ROAD | HDPE | 62.3 | [8 empty] | 2431.5 | LHS | 1 | NAGA PHANI
|  | J-121 | J-122 | KACHA ROAD | HDPE | 146.6 | [8 empty] | 2578.1 |  | 1.3 | NAGA PHANI
|  | J-122 | J-130 | KACHA ROAD | HDPE | 91 | [8 empty] | 2669.1 |  | 1.3 | NAGA PHANI
|  | J-106 | J-91 | KACHA ROAD | HDPE | 211.5 | [8 empty] | 2880.6 |  | 1.3 | NAGA PHANI
|  | J-104 | J-158 | KACHA ROAD | HDPE | 306.7 | [8 empty] | 3187.3 |  | 1.3 | NAGA PHANI
|  | J-73 | J-95 | KACHA ROAD | HDPE | 105 | [8 empty] | 3292.3 |  | 1.3 | NAGA PHANI
|  | J-35 | J-35A | KACHA ROAD | HDPE | 60 | [8 empty] | 3352.3 |  | 1.3 | NAGA PHANI
|  | J-35A | J-35C | KACHA ROAD | HDPE | 42 | [8 empty] | 3394.3 |  | 1.3 | NAGA PHANI
|  | J-13 | J-36 | KACHA ROAD | HDPE | 88 | [8 empty] | 3482.3 |  | 1.3 | NAGA PHANI
|  | J-30 | J-97 | KACHA ROAD | HDPE | 23 | [8 empty] | 3505.3 |  | 1.3 | NAGA PHANI
|  | J-88 | J-87 | BOE | HDPE | 36 | [8 empty] | 3541.3 |  | 1.3 | NAGA PHANI
|  | J-209 | J-60 | KACHA ROAD | HDPE | 82 | [8 empty] | 3623.3 |  | 1.3 | NAGA PHANI
|  | J-74A | J-74B | KACHA ROAD | HDPE | 20 | [8 empty] | 3643.3 |  | 1.3 | NAGA PHANI
|  | J-160 | J-208 | BOE |  | 108 | [8 empty] | 3751.3 |  |  | NAGA PHANI
|  | J-208 | J-211 | BOE |  | 54 | [8 empty] | 3805.3 |  |  | NAGA PHANI
|  | J-211 | J-211A | KACHA ROAD |  | 28 | [8 empty] | 3833.3 |  |  | NAGA PHANI
|  | J-208 | J-208A | KACHA ROAD |  | 37 | [8 empty] | 3870.3 |  |  | NAGA PHANI
|  | J-257 | J-243 | KACHA ROAD |  | 160 | [8 empty] | 4030.3 |  |  | NAGA PHANI
|  | J-249 | J-243 | KACHA ROAD |  | 49 | [8 empty] | 4079.3 |  |  | NAGA PHANI
|  | J-249 | J-245 | BOE |  | 157 | [8 empty] | 4236.3 |  |  | NAGA PHANI
|  | J-245 | J-247 | KACHA ROAD |  | 12 | [8 empty] | 4248.3 |  |  | NAGA PHANI
|  | J-245 | J-200 | BOE |  | 104 | [8 empty] | 4352.3 |  |  | NAGA PHANI
|  | J-245 | J-200 | BOE |  | 31 | [8 empty] | 4383.3 |  |  | NAGA PHANI | HDD
|  | J-245 | J-200 | IL |  | 98.8 | [8 empty] | 4482.1 |  |  | NAGA PHANI
|  | J-251 | J-278 | KACHA ROAD |  | 20 | [8 empty] | 4502.1 |  |  | NAGA PHANI
|  | J-135A | J-135B | KACHA ROAD |  | 19 | [8 empty] | 4521.1 |  |  | NAGA PHANI
|  | J-135C | J-135D | KACHA ROAD |  | 29 | [8 empty] | 4550.1 |  |  | NAGA PHANI
|  | J-135 | J-114 | BOE |  | 36 | [8 empty] | 4586.1 |  |  | NAGA PHANI | HDD
|  | J-32 | J-3 | BOE |  | 84 | [8 empty] | 4670.1 |  |  | NAGA PHANI | HDD
|  | J-11 | J-7 | KACHA ROAD |  | 69 | [8 empty] | 4739.1 |  |  | NAGA PHANI
|  | J-276 | J-263 | KACHA ROAD |  | 29 | [8 empty] | 4768.1 |  |  | NAGA PHANI
|  | J-263 | J-246 | KACHA ROAD |  | 168.9 | [8 empty] | 4937 |  |  | NAGA PHANI
|  | J-246 | J-194 | KACHA ROAD |  | 110.1 | [8 empty] | 5047.1 |  |  | NAGA PHANI
|  | J-246 | J-240 | KACHA ROAD |  | 96 | [8 empty] | 5143.1 |  |  | NAGA PHANI
|  | J-240 | J-234 | KACHA ROAD |  | 10 | [8 empty] | 5153.1 |  |  | NAGA PHANI
|  | J-234 | J-236 | KACHA ROAD |  | 54.1 | [8 empty] | 5207.2 |  |  | NAGA PHANI
|  | J-234 | J-248 | BOE |  | 104 | [8 empty] | 5311.2 |  |  | NAGA PHANI
|  | J-238 | J-240 | KACHA ROAD |  | 23 | [8 empty] | 5334.2 |  |  | NAGA PHANI
|  | J-238 | J-221 | KACHA ROAD |  | 35 | [8 empty] | 5369.2 |  |  | NAGA PHANI
|  | J-277 | J-267 | BOE |  | 9 | [8 empty] | 5378.2 |  |  | NAGA PHANI
|  | J-277 | J-267 | KACHA ROAD |  | 14 | [8 empty] | 5392.2 |  |  | NAGA PHANI
|  | J-277 | J-268 | KACHA ROAD |  | 35.7 | [8 empty] | 5427.9 |  |  | NAGA PHANI
|  | J-268 | J-279 | KACHA ROAD |  | 31 | [8 empty] | 5458.9 |  |  | NAGA PHANI
|  | J-273 | J-268 | KACHA ROAD |  | 32.1 | [8 empty] | 5491 |  |  | NAGA PHANI
|  | J-268 | J-274 | KACHA ROAD |  | 68.2 | [8 empty] | 5559.2 |  |  | NAGA PHANI
|  | J-268 | J-262 | KACHA ROAD |  | 33.1 | [8 empty] | 5592.3 |  |  | NAGA PHANI
|  | J-262B | J-262C | KACHA ROAD |  | 15 | [8 empty] | 5607.3 |  |  | NAGA PHANI
|  | J-262B | J-262D | KACHA ROAD |  | 14 | [8 empty] | 5621.3 |  |  | NAGA PHANI
|  | J-273 | J-277 | BOE |  | 37.5 | [8 empty] | 5658.8 |  |  | NAGA PHANI
|  | J-249 | J-242 | BT ROAD |  |  | 15 | [7 empty] | 5673.8 |  |  | NAGA PHANI | HDD (ROAD CROSSING)
|  | J-249 | J-242 | BOE |  |  | 140 | [7 empty] | 5813.8 |  |  | NAGA PHANI | HDD
|  | J-249 | J-242 | BT ROAD |  |  | 10 | [7 empty] | 5823.8 |  |  | NAGA PHANI | HDD
|  | J-242 | J-135A | CC ROAD |  |  | 92 | [7 empty] | 5915.8 |  |  | NAGA PHANI | HDD
|  | J-135A | J-135C | CC ROAD |  |  | 17.6 | [7 empty] | 5933.4 |  |  | NAGA PHANI | HDD
|  | J-135C | J-135 | CC ROAD |  |  | 55.4 | [7 empty] | 5988.8 |  |  | NAGA PHANI | HDD
|  | J-135 | J-32 | CC ROAD |  |  | 50 | [7 empty] | 6038.8 |  |  | NAGA PHANI | HDD
|  | J-259 | J-238 | KACHA ROAD |  |  |  | 72 | [6 empty] | 6110.8 |  |  | NAGA PHANI
|  | J-259 | J-238 | BOE |  |  |  | 35 | [6 empty] | 6145.8 |  |  | NAGA PHANI
|  | J-259 | J-238 | CC ROAD |  |  |  | 23 | [6 empty] | 6168.8 |  |  | NAGA PHANI
|  | J-238 | J-202 | BOE |  |  |  | 62 | [6 empty] | 6230.8 |  |  | NAGA PHANI
|  | J-262 | J-262A | KACHA ROAD |  |  |  | 28 | [6 empty] | 6258.8 |  |  | NAGA PHANI
|  | J-262A | J-262B | KACHA ROAD |  |  |  | 14.7 | [6 empty] | 6273.5 |  |  | NAGA PHANI
|  | J-262A | J-273 | KACHA ROAD |  |  |  | 23 | [6 empty] | 6296.5 |  |  | NAGA PHANI
|  | J-251 | J-257 | BT ROAD |  |  |  |  | 78 | [5 empty] | 6374.5 |  |  | NAGA PHANI
|  | J-140 | J-141 | KACHA ROAD | HDPE |  | 135 | [7 empty] | 6509.5 |  | 1.3 | NAGA PHANI
|  | J-140A | J-140B | BOE | HDPE |  | 82 | [7 empty] | 6591.5 |  | 1.3 | NAGA PHANI
|  | J-140A | J-140B | KACHA ROAD | HDPE |  | 18 | [7 empty] | 6609.5 |  | 1.3 | NAGA PHANI
|  | J-140A | J-140C | BOE | HDPE |  | 13 | [7 empty] | 6622.5 |  | 1.3 | NAGA PHANI
|  | J-140A | J-140C | KACHA ROAD | HDPE |  | 42 | [7 empty] | 6664.5 |  | 1 | NAGA PHANI
|  | J-140C | J-140D | KACHA ROAD | HDPE |  | 26 | [7 empty] | 6690.5 |  | 1 | NAGA PHANI
|  | J-140C | J-140E | KACHA ROAD | HDPE |  | 22 | [7 empty] | 6712.5 |  | 1 | NAGA PHANI
|  | J-140E | J-140F | KACHA ROAD | HDPE |  | 16 | [7 empty] | 6728.5 |  | 1 | NAGA PHANI
|  | J-140F | J-140G | KACHA ROAD | HDPE |  | 51 | [7 empty] | 6779.5 |  | 1 | NAGA PHANI
|  | J-179 | J-214 | CC ROAD | HDPE |  | 10 | [7 empty] | 6789.5 |  | 1 | NAGA PHANI | HDD
|  | J-179 | J-214 | BOE | HDPE |  | 26 | [7 empty] | 6815.5 |  | 1 | NAGA PHANI | HDD
|  | J-175 | J-141 | KACHA ROAD | HDPE |  | 40 | [7 empty] | 6855.5 |  | 1 | NAGA PHANI
|  | J-119 | J-159 | BOE | HDPE |  | 17 | [7 empty] | 6872.5 |  | 1 | NAGA PHANI
|  | J-249 | J-242 | BT ROAD | HDPE |  | 15 | [7 empty] | 6887.5 |  | 1 | NAGA PHANI | HDD
|  | J-249 | J-242 | BOE | HDPE |  | 140 | [7 empty] | 7027.5 |  | 1 | NAGA PHANI | HDD
|  | J-249 | J-242 | BT ROAD | HDPE |  | 10 | [7 empty] | 7037.5 |  | 1 | NAGA PHANI | HDD
|  | J-242 | J-135A | CC ROAD | HDPE |  | 92 | [7 empty] | 7129.5 |  | 1 | NAGA PHANI | HDD
|  | J-135A | J-135C | CC ROAD | HDPE |  | 17.6 | [7 empty] | 7147.1 |  | 1 | NAGA PHANI | HDD
|  | J-135C | J-135 | CC ROAD | HDPE |  | 55.4 | [7 empty] | 7202.5 |  | 1 | NAGA PHANI | HDD
|  | J-135 | J-32 | CC ROAD | HDPE |  | 50 | [7 empty] | 7252.5 |  | 1 | NAGA PHANI | HDD
|  | J-118 | J-55 | BOE | HDPE |  | 85 | [7 empty] | 7337.5 |  | 1 | NAGA PHANI | HDD
|  | J-55 | J-32 | CC ROAD | HDPE |  | 88 | [7 empty] | 7425.5 |  | 1 | NAGA PHANI | HDD
|  | J-118 | J-132 | KACHA ROAD | HDPE |  | 136 | [7 empty] | 7561.5 |  | 1 | NAGA PHANI | HDD
|  | J-156 | J-121 | KACHA ROAD | HDPE |  | 52.4 | [7 empty] | 7613.9 |  | 1 | NAGA PHANI
|  | J-121 | J-106 | KACHA ROAD | HDPE |  | 98 | [7 empty] | 7711.9 |  | 1 | NAGA PHANI
|  | J-106 | J-122 | KACHA ROAD | HDPE |  | 138 | [7 empty] | 7849.9 |  | 1 | NAGA PHANI
|  | J-106 | J-104 | IL | HDPE |  | 76.7 | [7 empty] | 7926.6 |  | 1 | NAGA PHANI
|  | J-79 | J-104 | IL | HDPE |  | 197 | [7 empty] | 8123.6 |  | 1 | NAGA PHANI | HDD
|  | J-74 | J-104 | BT ROAD | HDPE |  | 4 | [7 empty] | 8127.6 |  | 1 | NAGA PHANI | HDD
|  | J-84 | J-91 | KACHA ROAD | HDPE |  | 214 | [7 empty] | 8341.6 |  | 1 | NAGA PHANI
|  | J-84 | J-91 | BT ROAD | HDPE |  | 121 | [7 empty] | 8462.6 |  | 1 | NAGA PHANI | HDD
|  | J-281 | J-19 | KACHA ROAD | HDPE |  | 45 | [7 empty] | 8507.6 |  | 1 | NAGA PHANI
|  | J-21 | J-58 | BOE | HDPE |  | 50 | [7 empty] | 8557.6 |  | 1 | NAGA PHANI
|  | J-43 | J-41 | BOE | HDPE |  |  | 31.1 | [6 empty] | 8588.7 |  | 1 | NAGA PHANI | HDD
|  | J-41 | J37 | BOE | HDPE |  |  | 51 | [6 empty] | 8639.7 |  | 1 | NAGA PHANI | HDD
|  | J-111 | J-140 | KACHA ROAD | HDPE |  |  | 36 | [6 empty] | 8675.7 |  | 1 | NAGA PHANI
|  | J-140 | J-141 | KACHA ROAD | HDPE |  |  | 65 | [6 empty] | 8740.7 |  | 1 | NAGA PHANI
|  | J-140 | J-37 | KACHA ROAD | HDPE |  |  | 215 | [6 empty] | 8955.7 |  | 1 | NAGA PHANI
|  | J-262 | J-199 | KACHA ROAD | HDPE |  |  | 48 | [6 empty] | 9003.7 |  | 1 | NAGA PHANI
|  | J-179 | J-175 | CC ROAD | HDPE |  |  | 17 | [6 empty] | 9020.7 |  | 1 | NAGA PHANI | HDD
|  | J-119 | J-144 | KACHA ROAD | HDPE |  |  | 28 | [6 empty] | 9048.7 |  | 1 | NAGA PHANI
|  | J-144 | J-143 | CC ROAD | HDPE |  |  | 12 | [6 empty] | 9060.7 |  | 1 | NAGA PHANI | HDD
|  | J-143 | J-175 | CC ROAD | HDPE |  |  | 36 | [6 empty] | 9096.7 |  | 1 | NAGA PHANI | HDD
|  | J-143 | J-146 | BOE | HDPE |  |  | 54 | [6 empty] | 9150.7 |  | 1 | NAGA PHANI
|  | J-146 | J-166 | KACHA ROAD | HDPE |  |  | 9 | [6 empty] | 9159.7 |  | 1 | NAGA PHANI
|  | J-203 | J-118 | BOE | HDPE |  |  | 30.6 | [6 empty] | 9190.3 |  | 1.5 | NAGA PHANI | HDD
|  | J-77A | J-77B | BOE | HDPE |  |  | 64 | [6 empty] | 9254.3 |  | 1.5 | NAGA PHANI | HDD
|  | J-72 | J-88 | BOE | HDPE |  |  | 40 | [6 empty] | 9294.3 |  | 1.5 | NAGA PHANI
|  | J-88 | J-126 | BOE | HDPE |  |  | 35 | [6 empty] | 9329.3 |  | 1.5 | NAGA PHANI
|  | J-88 | J-126 | KACHA ROAD | HDPE |  |  | 30 | [6 empty] | 9359.3 |  | 1.5 | NAGA PHANI
|  | J-126 | J-111 | KACHA ROAD | HDPE |  |  | 17 | [6 empty] | 9376.3 |  | 1.5 | NAGA PHANI
|  | J-126 | J-111 | BOE | HDPE |  |  | 10 | [6 empty] | 9386.3 |  | 1.5 | NAGA PHANI
|  | J-74 | J-74A | BT ROAD | HDPE |  |  | 129.7 | [6 empty] | 9516 |  | 1.5 | NAGA PHANI | HDD
|  | J-74 | J-74A | BOE | HDPE |  |  | 62.3 | [6 empty] | 9578.3 |  | 1.5 | NAGA PHANI | HDD
|  | J-74 | J-203 | CULVET | HDPE |  |  | 3 | [6 empty] | 9581.3 |  | 1.5 | NAGA PHANI
|  | J-74A | J-203 | BOE | HDPE |  |  | 171 | [6 empty] | 9752.3 |  | 1.5 | NAGA PHANI
|  | J-255 | J-222 | BOE | HDPE |  |  |  | 60 | [5 empty] | 9812.3 |  | 1.5 | NAGA PHANI | HDD
|  | J-224 | J-235 | BT ROAD | HDPE |  |  |  | 31.2 | [5 empty] | 9843.5 |  | 1.5 | NAGA PHANI | HDD
|  | J-224 | J-217 | BT ROAD | HDPE |  |  |  | 14 | [5 empty] | 9857.5 |  | 1.5 | NAGA PHANI | HDD
|  | J-179 | J-235 | BT ROAD | HDPE |  |  |  | 13 | [5 empty] | 9870.5 |  | 2 | NAGA PHANI | HDD
|  | J-179 | J-235 | CC ROAD | HDPE |  |  |  | 106 | [5 empty] | 9976.5 |  | 2 | NAGA PHANI | HDD
|  | J-251 | J-257 | BT ROAD | HDPE |  |  |  | 78 | [5 empty] | 10054.5 |  | 2 | NAGA PHANI | HDD
|  | J-74 | J-90 | BT ROAD | HDPE |  |  |  | 99.1 | [5 empty] | 10153.6 |  | 2 | NAGA PHANI | HDD
|  | J-95 | J-84 | BT ROAD | HDPE |  |  |  | 190.1 | [5 empty] | 10343.7 |  | 2 | NAGA PHANI | HDD
|  | J-95 | J-84 | BOE | HDPE |  |  |  | 10 | [5 empty] | 10353.7 |  | 2 | NAGA PHANI | HDD
|  | J-95 | J-30 | BT ROAD | HDPE |  |  |  | 374.2 | [5 empty] | 10727.9 |  | 2 | NAGA PHANI | HDD
[6 empty] | 63mm | 75mm | 90mm | 110mm | 125mm | 140mm | 160mm
[6 empty] | 5658.9 | 2563.1 | 1452.4 | 1053.6 | 0 | 0 | 0 |  |  | 10728
| Representative PMPL - BRCCPL (JV) Pratapgarh | [5 empty] | Representative Medhaj Techno Concept Pvt Ltd (TPI) Pratapgarh | [6 empty] | Representative UP Jal Nigam (Rural) Pratapgarh