## saray jamuari jmr
Block |  | Mangraura
GP |  | SARAY JAMMUVARI
Total Length (M) |  | 20125
FHTC (No's)
Agency Name |  | DR ENTERPRISE
Sl.No | Date | Start Node | End Node | Type of Road | DI/HDPE | Pipe Length (M) | [8 empty] | Cumulative Length (M) | LHS/RHS | Distance from Road C/L | Site Engineer Sign | Remarks
[6 empty] | 63mm | 75mm | 90mm | 110mm | 125mm | 140mm | 160mm | DI 250mm
1 | 2025-01-23 | J-77 | J-50 | KACHA ROAD | HDPE | 38 | [8 empty] | 38 | LHS | 1.2 | NAGA PHANI
2 | 2025-01-23 | J-68 | J-52 | KACHA ROAD | HDPE | 36 | [8 empty] | 74 | LHS | 1 | NAGA PHANI
3 | 2025-01-23 | J-68A | J-68B | KACHA ROAD | HDPE | 43.3 | [8 empty] | 117.3 | LHS | 1 | NAGA PHANI
4 | 2025-01-23 | J-78A | J-78B | KACHA ROAD | HDPE | 56 | [8 empty] | 173.3 | LHS | 1.2 | NAGA PHANI
5 | 2025-01-23 | J-41 | J-78B | KACHA ROAD | HDPE | 48 | [8 empty] | 221.3 | LHS | 1.2 | NAGA PHANI
6 | 2025-01-24 | J-37 | J-53 | BOE | HDPE | 69.7 | [8 empty] | 291 | LHS | 1.2 | NAGA PHANI
7 | 2025-01-24 | J-53 | J-83 | BOE | HDPE | 86 | [8 empty] | 377 | LHS | 1.2 | NAGA PHANI
8 | 2025-01-24 | J-83 | J-67 | KACHA ROAD | HDPE | 20 | [8 empty] | 397 | LHS | 1.2 | NAGA PHANI
9 | 2025-01-24 | J-53 | J-86 | KACHA ROAD | HDPE | 39 | [8 empty] | 436 | LHS | 1.2 | NAGA PHANI
10 | 2025-01-24 | J-199 | J-233 | KACHA ROAD | HDPE | 19 | [8 empty] | 455 | LHS | 1.2 | NAGA PHANI
11 | 2025-01-25 | J-199 | J-237 | KACHA ROAD | HDPE | 17 | [8 empty] | 472 | LHS | 1.2 | NAGA PHANI
12 | 2025-01-25 | J-222 | J-232 | KACHA ROAD | HDPE | 107 | [8 empty] | 579 | LHS | 1.2 | NAGA PHANI | HDD
13 | 2025-01-25 | J-224 | J-223 | BOE | HDPE | 43 | [8 empty] | 622 | RHS | 1.2 | NAGA PHANI
14 | 2025-01-25 | J-235 | J-206 | BOE | HDPE | 68 | [8 empty] | 690 | LHS | 1.2 | NAGA PHANI | HDD
15 | 2025-01-25 | J-214 | J-131 | KACHA ROAD | HDPE | 28 | [8 empty] | 718 | LHS | 1.2 | NAGA PHANI | HDD
16 | 2025-01-25 | J-131 | J-152 | KACHA ROAD | HDPE | 50 | [8 empty] | 768 | LHS | 1.2 | NAGA PHANI | HDD
17 | 2025-01-25 | J-214 | J-225 | KACHA ROAD | HDPE | 45 | [8 empty] | 813 | LHS | 1.2 | NAGA PHANI | HDD
18 | 2025-01-25 | J-141 | J-105 | BOE | HDPE | 54 | [8 empty] | 867 | LHS | 1.2 | NAGA PHANI
19 | 2025-01-25 | J-141 | J-119 | BOE | HDPE | 16 | [8 empty] | 883 | LHS | 1.2 | NAGA PHANI
20 | 2025-01-26 | J-146 | J-186 | KACHA ROAD | HDPE | 18 | [8 empty] | 901 | LHS | 1.2 | NAGA PHANI
21 | 2025-01-26 | J-160 | J-208 | BOE | HDPE | 108.8 | [8 empty] | 1009.8 | LHS | 1.2 | NAGA PHANI
22 | 2025-01-27 | J-208 | J-211 | BOE | HDPE | 54 | [8 empty] | 1063.8 | LHS | 1.2 | NAGA PHANI
23 | 2025-01-27 | J-211 | J-211A | KACHA ROAD | HDPE | 28 | [8 empty] | 1091.8 | LHS | 1.2 | NAGA PHANI
24 | 2025-01-27 | J-208 | J-208A | KACHA ROAD | HDPE | 37 | [8 empty] | 1128.8 | CENTER | 0 | NAGA PHANI
25 | 2025-01-27 | J-257 | J-243 | KACHA ROAD | HDPE | 160.5 | [8 empty] | 1289.3 | CENTER | 0 | NAGA PHANI
26 | 2025-01-28 | J-249 | J-243 | KACHA ROAD | HDPE | 49 | [8 empty] | 1338.3 | CENTER | 0 | NAGA PHANI
27 | 2025-01-28 | J-249 | J-245 | BOE | HDPE | 15.7 | [8 empty] | 1354 | CENTER | 0 | NAGA PHANI
28 | 2025-01-28 | J-245 | J-247 | KACHA ROAD | HDPE | 12 | [8 empty] | 1366 | CENTER | 0 | NAGA PHANI
29 | 2025-01-28 | J-245 | J-200 | BOE | HDPE | 104.7 | [8 empty] | 1470.7 | CENTER | 0 | NAGA PHANI
30 | 2025-01-28 | J-245 | J-200 | KACHA ROAD | HDPE | 31 | [8 empty] | 1501.7 | CENTER | 0 | NAGA PHANI | HDD
31 | 2025-01-28 | J-245 | J-200 | IL | HDPE | 98.8 | [8 empty] | 1600.5 | CENTER | 0 | NAGA PHANI
32 | 2025-01-28 | J-251 | J-278 | KACHA ROAD | HDPE | 20 | [8 empty] | 1620.5 | CENTER | 0 | NAGA PHANI
33 | 2025-01-28 | J-135A | J-135B | KACHA ROAD | HDPE | 19 | [8 empty] | 1639.5 | LHS | 1.2 | NAGA PHANI
34 | 2025-01-28 | J-135C | J-135D | KACHA ROAD | HDPE | 29 | [8 empty] | 1668.5 | LHS | 1.2 | NAGA PHANI
35 |  | J-135 | J-114 | BOE | HDPE | 31 | [8 empty] | 1699.5 | LHS | 1.2 | NAGA PHANI | HDD
36 |  | J-32 | J-03 | BOE | HDPE | 84 | [8 empty] | 1783.5 | LHS | 1 | NAGA PHANI | HDD
37 |  | J-11 | J-07 | KACHA ROAD | HDPE | 69 | [8 empty] | 1852.5 | LHS | 1 | NAGA PHANI
38 |  | J-07 | J-55 | BOE | HDPE | 38 | [8 empty] | 1890.5 | LHS | 1 | NAGA PHANI | HDD
39 |  | J-7 | J-55 | KACHA ROAD | HDPE | 22 | [8 empty] | 1912.5 | LHS | 1 | NAGA PHANI | HDD
40 |  | J-90 | J-65 | KACHA ROAD | HDPE | 34 | [8 empty] | 1946.5 | LHS | 1 | NAGA PHANI
41 |  | J-90 | J-203 | KACHA ROAD | HDPE | 103 | [8 empty] | 2049.5 | LHS | 1 | NAGA PHANI
42 |  | J-90 | J-203 | IL | HDPE | 75 | [8 empty] | 2124.5 | LHS | 1 | NAGA PHANI
43 |  | J-90 | J-203 | BOE | HDPE | 30 | [8 empty] | 2154.5 | LHS | 1 | NAGA PHANI
44 |  | J-132 | J-210 | KACHA ROAD | HDPE | 49.6 | [8 empty] | 2204.1 | LHS | 1 | NAGA PHANI
45 |  | J-210 | J-176 | KACHA ROAD | HDPE | 36 | [8 empty] | 2240.1 | LHS | 1 | NAGA PHANI
46 |  | J-210 | J-210A | KACHA ROAD | HDPE | 85.6 | [8 empty] | 2325.7 | LHS | 1 | NAGA PHANI
47 |  | J-210A | J-210B | KACHA ROAD | HDPE | 43.5 | [8 empty] | 2369.2 | LHS | 1 | NAGA PHANI
48 |  | J-210A | J-156 | KACHA ROAD | HDPE | 62.3 | [8 empty] | 2431.5 | LHS | 1 | NAGA PHANI
49 |  | J-121 | J-122 | KACHA ROAD | HDPE | 146.6 | [8 empty] | 2578.1 |  | 1.3 | NAGA PHANI
50 |  | J-122 | J-130 | KACHA ROAD | HDPE | 91 | [8 empty] | 2669.1 |  | 1.3 | NAGA PHANI
51 |  | J-106 | J-91 | KACHA ROAD | HDPE | 211.5 | [8 empty] | 2880.6 |  | 1.3 | NAGA PHANI
52 |  | J-104 | J-158 | KACHA ROAD | HDPE | 306.7 | [8 empty] | 3187.3 |  | 1.3 | NAGA PHANI
53 |  | J-73 | J-95 | KACHA ROAD | HDPE | 105 | [8 empty] | 3292.3 |  | 1.3 | NAGA PHANI
54 |  | J-35 | J-35A | KACHA ROAD | HDPE | 60 | [8 empty] | 3352.3 |  | 1.3 | NAGA PHANI
55 |  | J-35A | J-35C | KACHA ROAD | HDPE | 42 | [8 empty] | 3394.3 |  | 1.3 | NAGA PHANI
56 |  | J-13 | J-36 | KACHA ROAD | HDPE | 88 | [8 empty] | 3482.3 |  | 1.3 | NAGA PHANI
57 |  | J-30 | J-97 | KACHA ROAD | HDPE | 23 | [8 empty] | 3505.3 |  | 1.3 | NAGA PHANI
58 |  | J-88 | J-87 | BOE | HDPE | 36 | [8 empty] | 3541.3 |  | 1.3 | NAGA PHANI
59 |  | J-209 | J-60 | KACHA ROAD | HDPE | 82 | [8 empty] | 3623.3 |  | 1.3 | NAGA PHANI
60 |  | J-74A | J-74B | KACHA ROAD | HDPE | 20 | [8 empty] | 3643.3 |  | 1.3 | NAGA PHANI
61 |  | J-160 | J-208 | BOE |  | 108 | [8 empty] | 3751.3 |  |  | NAGA PHANI
62 |  | J-208 | J-211 | BOE |  | 54 | [8 empty] | 3805.3 |  |  | NAGA PHANI
63 |  | J-211 | J-211A | KACHA ROAD |  | 28 | [8 empty] | 3833.3 |  |  | NAGA PHANI
64 |  | J-208 | J-208A | KACHA ROAD |  | 37 | [8 empty] | 3870.3 |  |  | NAGA PHANI
65 |  | J-257 | J-243 | KACHA ROAD |  | 160 | [8 empty] | 4030.3 |  |  | NAGA PHANI
66 |  | J-249 | J-243 | KACHA ROAD |  | 49 | [8 empty] | 4079.3 |  |  | NAGA PHANI
67 |  | J-249 | J-245 | BOE |  | 157 | [8 empty] | 4236.3 |  |  | NAGA PHANI
68 |  | J-245 | J-247 | KACHA ROAD |  | 12 | [8 empty] | 4248.3 |  |  | NAGA PHANI
69 |  | J-245 | J-200 | BOE |  | 104 | [8 empty] | 4352.3 |  |  | NAGA PHANI
70 |  | J-245 | J-200 | BOE |  | 31 | [8 empty] | 4383.3 |  |  | NAGA PHANI | HDD
71 |  | J-245 | J-200 | IL |  | 98.8 | [8 empty] | 4482.1 |  |  | NAGA PHANI
72 |  | J-251 | J-278 | KACHA ROAD |  | 20 | [8 empty] | 4502.1 |  |  | NAGA PHANI
73 |  | J-135A | J-135B | KACHA ROAD |  | 19 | [8 empty] | 4521.1 |  |  | NAGA PHANI
74 |  | J-135C | J-135D | KACHA ROAD |  | 29 | [8 empty] | 4550.1 |  |  | NAGA PHANI
75 |  | J-135 | J-114 | BOE |  | 36 | [8 empty] | 4586.1 |  |  | NAGA PHANI | HDD
76 |  | J-32 | J-3 | BOE |  | 84 | [8 empty] | 4670.1 |  |  | NAGA PHANI | HDD
77 |  | J-11 | J-7 | KACHA ROAD |  | 69 | [8 empty] | 4739.1 |  |  | NAGA PHANI
78 |  | J-276 | J-263 | KACHA ROAD |  | 29 | [8 empty] | 4768.1 |  |  | NAGA PHANI
79 |  | J-263 | J-246 | KACHA ROAD |  | 168.9 | [8 empty] | 4937 |  |  | NAGA PHANI
80 |  | J-246 | J-194 | KACHA ROAD |  | 110.1 | [8 empty] | 5047.1 |  |  | NAGA PHANI
81 |  | J-246 | J-240 | KACHA ROAD |  | 96 | [8 empty] | 5143.1 |  |  | NAGA PHANI
82 |  | J-240 | J-234 | KACHA ROAD |  | 10 | [8 empty] | 5153.1 |  |  | NAGA PHANI
83 |  | J-234 | J-236 | KACHA ROAD |  | 54.1 | [8 empty] | 5207.2 |  |  | NAGA PHANI
84 |  | J-234 | J-248 | BOE |  | 104 | [8 empty] | 5311.2 |  |  | NAGA PHANI
85 |  | J-238 | J-240 | KACHA ROAD |  | 23 | [8 empty] | 5334.2 |  |  | NAGA PHANI
86 |  | J-238 | J-221 | KACHA ROAD |  | 35 | [8 empty] | 5369.2 |  |  | NAGA PHANI
87 |  | J-277 | J-267 | BOE |  | 9 | [8 empty] | 5378.2 |  |  | NAGA PHANI
88 |  | J-277 | J-267 | KACHA ROAD |  | 14 | [8 empty] | 5392.2 |  |  | NAGA PHANI
89 |  | J-277 | J-268 | KACHA ROAD |  | 35.7 | [8 empty] | 5427.9 |  |  | NAGA PHANI
90 |  | J-268 | J-279 | KACHA ROAD |  | 31 | [8 empty] | 5458.9 |  |  | NAGA PHANI
91 |  | J-273 | J-268 | KACHA ROAD |  | 32.1 | [8 empty] | 5491 |  |  | NAGA PHANI
92 |  | J-268 | J-274 | KACHA ROAD |  | 68.2 | [8 empty] | 5559.2 |  |  | NAGA PHANI
93 |  | J-268 | J-262 | KACHA ROAD |  | 33.1 | [8 empty] | 5592.3 |  |  | NAGA PHANI
94 |  | J-262B | J-262C | KACHA ROAD |  | 15 | [8 empty] | 5607.3 |  |  | NAGA PHANI
95 |  | J-262B | J-262D | KACHA ROAD |  | 14 | [8 empty] | 5621.3 |  |  | NAGA PHANI
96 |  | J-273 | J-277 | BOE |  | 37.5 | [8 empty] | 5658.8 |  |  | NAGA PHANI
97 |  | J-249 | J-242 | BT ROAD |  |  | 15 | [7 empty] | 5673.8 |  |  | NAGA PHANI | HDD (ROAD CROSSING)
98 |  | J-249 | J-242 | BOE |  |  | 140 | [7 empty] | 5813.8 |  |  | NAGA PHANI | HDD
99 |  | J-249 | J-242 | BT ROAD |  |  | 10 | [7 empty] | 5823.8 |  |  | NAGA PHANI | HDD
100 |  | J-242 | J-135A | CC ROAD |  |  | 92 | [7 empty] | 5915.8 |  |  | NAGA PHANI | HDD
101 |  | J-135A | J-135C | CC ROAD |  |  | 17.6 | [7 empty] | 5933.4 |  |  | NAGA PHANI | HDD
102 |  | J-135C | J-135 | CC ROAD |  |  | 55.4 | [7 empty] | 5988.8 |  |  | NAGA PHANI | HDD
103 |  | J-135 | J-32 | CC ROAD |  |  | 50 | [7 empty] | 6038.8 |  |  | NAGA PHANI | HDD
104 |  | J-259 | J-238 | KACHA ROAD |  |  |  | 72 | [6 empty] | 6110.8 |  |  | NAGA PHANI
105 |  | J-259 | J-238 | BOE |  |  |  | 35 | [6 empty] | 6145.8 |  |  | NAGA PHANI
106 |  | J-259 | J-238 | CC ROAD |  |  |  | 23 | [6 empty] | 6168.8 |  |  | NAGA PHANI
107 |  | J-238 | J-202 | BOE |  |  |  | 62 | [6 empty] | 6230.8 |  |  | NAGA PHANI
108 |  | J-262 | J-262A | KACHA ROAD |  |  |  | 28 | [6 empty] | 6258.8 |  |  | NAGA PHANI
109 |  | J-262A | J-262B | KACHA ROAD |  |  |  | 14.7 | [6 empty] | 6273.5 |  |  | NAGA PHANI
110 |  | J-262A | J-273 | KACHA ROAD |  |  |  | 23 | [6 empty] | 6296.5 |  |  | NAGA PHANI
111 |  | J-251 | J-257 | BT ROAD |  |  |  |  | 78 | [5 empty] | 6374.5 |  |  | NAGA PHANI
112 |  | J-140 | J-141 | KACHA ROAD | HDPE |  | 135 | [7 empty] | 6509.5 |  | 1.3 | NAGA PHANI
113 |  | J-140A | J-140B | BOE | HDPE |  | 82 | [7 empty] | 6591.5 |  | 1.3 | NAGA PHANI
114 |  | J-140A | J-140B | KACHA ROAD | HDPE |  | 18 | [7 empty] | 6609.5 |  | 1.3 | NAGA PHANI
115 |  | J-140A | J-140C | BOE | HDPE |  | 13 | [7 empty] | 6622.5 |  | 1.3 | NAGA PHANI
116 |  | J-140A | J-140C | KACHA ROAD | HDPE |  | 42 | [7 empty] | 6664.5 |  | 1 | NAGA PHANI
117 |  | J-140C | J-140D | KACHA ROAD | HDPE |  | 26 | [7 empty] | 6690.5 |  | 1 | NAGA PHANI
118 |  | J-140C | J-140E | KACHA ROAD | HDPE |  | 22 | [7 empty] | 6712.5 |  | 1 | NAGA PHANI
119 |  | J-140E | J-140F | KACHA ROAD | HDPE |  | 16 | [7 empty] | 6728.5 |  | 1 | NAGA PHANI
120 |  | J-140F | J-140G | KACHA ROAD | HDPE |  | 51 | [7 empty] | 6779.5 |  | 1 | NAGA PHANI
121 |  | J-179 | J-214 | CC ROAD | HDPE |  | 10 | [7 empty] | 6789.5 |  | 1 | NAGA PHANI | HDD
122 |  | J-179 | J-214 | BOE | HDPE |  | 26 | [7 empty] | 6815.5 |  | 1 | NAGA PHANI | HDD
123 |  | J-175 | J-141 | KACHA ROAD | HDPE |  | 40 | [7 empty] | 6855.5 |  | 1 | NAGA PHANI
124 |  | J-119 | J-159 | BOE | HDPE |  | 17 | [7 empty] | 6872.5 |  | 1 | NAGA PHANI
125 |  | J-249 | J-242 | BT ROAD | HDPE |  | 15 | [7 empty] | 6887.5 |  | 1 | NAGA PHANI | HDD
126 |  | J-249 | J-242 | BOE | HDPE |  | 140 | [7 empty] | 7027.5 |  | 1 | NAGA PHANI | HDD
127 |  | J-249 | J-242 | BT ROAD | HDPE |  | 10 | [7 empty] | 7037.5 |  | 1 | NAGA PHANI | HDD
128 |  | J-242 | J-135A | CC ROAD | HDPE |  | 92 | [7 empty] | 7129.5 |  | 1 | NAGA PHANI | HDD
129 |  | J-135A | J-135C | CC ROAD | HDPE |  | 17.6 | [7 empty] | 7147.1 |  | 1 | NAGA PHANI | HDD
130 |  | J-135C | J-135 | CC ROAD | HDPE |  | 55.4 | [7 empty] | 7202.5 |  | 1 | NAGA PHANI | HDD
131 |  | J-135 | J-32 | CC ROAD | HDPE |  | 50 | [7 empty] | 7252.5 |  | 1 | NAGA PHANI | HDD
132 |  | J-118 | J-55 | BOE | HDPE |  | 85 | [7 empty] | 7337.5 |  | 1 | NAGA PHANI | HDD
133 |  | J-55 | J-32 | CC ROAD | HDPE |  | 88 | [7 empty] | 7425.5 |  | 1 | NAGA PHANI | HDD
134 |  | J-118 | J-132 | KACHA ROAD | HDPE |  | 136 | [7 empty] | 7561.5 |  | 1 | NAGA PHANI | HDD
135 |  | J-156 | J-121 | KACHA ROAD | HDPE |  | 52.4 | [7 empty] | 7613.9 |  | 1 | NAGA PHANI
136 |  | J-121 | J-106 | KACHA ROAD | HDPE |  | 98 | [7 empty] | 7711.9 |  | 1 | NAGA PHANI
137 |  | J-106 | J-122 | KACHA ROAD | HDPE |  | 138 | [7 empty] | 7849.9 |  | 1 | NAGA PHANI
138 |  | J-106 | J-104 | IL | HDPE |  | 76.7 | [7 empty] | 7926.6 |  | 1 | NAGA PHANI
139 |  | J-79 | J-104 | IL | HDPE |  | 197 | [7 empty] | 8123.6 |  | 1 | NAGA PHANI | HDD
140 |  | J-74 | J-104 | BT ROAD | HDPE |  | 4 | [7 empty] | 8127.6 |  | 1 | NAGA PHANI | HDD
141 |  | J-84 | J-91 | KACHA ROAD | HDPE |  | 214 | [7 empty] | 8341.6 |  | 1 | NAGA PHANI
142 |  | J-84 | J-91 | BT ROAD | HDPE |  | 121 | [7 empty] | 8462.6 |  | 1 | NAGA PHANI | HDD
143 |  | J-281 | J-19 | KACHA ROAD | HDPE |  | 45 | [7 empty] | 8507.6 |  | 1 | NAGA PHANI
144 |  | J-21 | J-58 | BOE | HDPE |  | 50 | [7 empty] | 8557.6 |  | 1 | NAGA PHANI
145 |  | J-43 | J-41 | BOE | HDPE |  |  | 31.1 | [6 empty] | 8588.7 |  | 1 | NAGA PHANI | HDD
146 |  | J-41 | J37 | BOE | HDPE |  |  | 51 | [6 empty] | 8639.7 |  | 1 | NAGA PHANI | HDD
147 |  | J-111 | J-140 | KACHA ROAD | HDPE |  |  | 36 | [6 empty] | 8675.7 |  | 1 | NAGA PHANI
148 |  | J-140 | J-141 | KACHA ROAD | HDPE |  |  | 65 | [6 empty] | 8740.7 |  | 1 | NAGA PHANI
149 |  | J-140 | J-37 | KACHA ROAD | HDPE |  |  | 215 | [6 empty] | 8955.7 |  | 1 | NAGA PHANI
150 |  | J-262 | J-199 | KACHA ROAD | HDPE |  |  | 48 | [6 empty] | 9003.7 |  | 1 | NAGA PHANI
151 |  | J-179 | J-175 | CC ROAD | HDPE |  |  | 17 | [6 empty] | 9020.7 |  | 1 | NAGA PHANI | HDD
152 |  | J-119 | J-144 | KACHA ROAD | HDPE |  |  | 28 | [6 empty] | 9048.7 |  | 1 | NAGA PHANI
153 |  | J-144 | J-143 | CC ROAD | HDPE |  |  | 12 | [6 empty] | 9060.7 |  | 1 | NAGA PHANI | HDD
154 |  | J-143 | J-175 | CC ROAD | HDPE |  |  | 36 | [6 empty] | 9096.7 |  | 1 | NAGA PHANI | HDD
155 |  | J-143 | J-146 | BOE | HDPE |  |  | 54 | [6 empty] | 9150.7 |  | 1 | NAGA PHANI
156 |  | J-146 | J-166 | KACHA ROAD | HDPE |  |  | 9 | [6 empty] | 9159.7 |  | 1 | NAGA PHANI
157 |  | J-203 | J-118 | BOE | HDPE |  |  | 30.6 | [6 empty] | 9190.3 |  | 1.5 | NAGA PHANI | HDD
158 |  | J-77A | J-77B | BOE | HDPE |  |  | 64 | [6 empty] | 9254.3 |  | 1.5 | NAGA PHANI | HDD
159 |  | J-72 | J-88 | BOE | HDPE |  |  | 40 | [6 empty] | 9294.3 |  | 1.5 | NAGA PHANI
160 |  | J-88 | J-126 | BOE | HDPE |  |  | 35 | [6 empty] | 9329.3 |  | 1.5 | NAGA PHANI
161 |  | J-88 | J-126 | KACHA ROAD | HDPE |  |  | 30 | [6 empty] | 9359.3 |  | 1.5 | NAGA PHANI
162 |  | J-126 | J-111 | KACHA ROAD | HDPE |  |  | 17 | [6 empty] | 9376.3 |  | 1.5 | NAGA PHANI
163 |  | J-126 | J-111 | BOE | HDPE |  |  | 10 | [6 empty] | 9386.3 |  | 1.5 | NAGA PHANI
164 |  | J-74 | J-74A | BT ROAD | HDPE |  |  | 129.7 | [6 empty] | 9516 |  | 1.5 | NAGA PHANI | HDD
165 |  | J-74 | J-74A | BOE | HDPE |  |  | 62.3 | [6 empty] | 9578.3 |  | 1.5 | NAGA PHANI | HDD
166 |  | J-74 | J-203 | CULVET | HDPE |  |  | 3 | [6 empty] | 9581.3 |  | 1.5 | NAGA PHANI
167 |  | J-74A | J-203 | BOE | HDPE |  |  | 171 | [6 empty] | 9752.3 |  | 1.5 | NAGA PHANI
168 |  | J-255 | J-222 | BOE | HDPE |  |  |  | 60 | [5 empty] | 9812.3 |  | 1.5 | NAGA PHANI | HDD
169 |  | J-224 | J-235 | BT ROAD | HDPE |  |  |  | 31.2 | [5 empty] | 9843.5 |  | 1.5 | NAGA PHANI | HDD
170 |  | J-224 | J-217 | BT ROAD | HDPE |  |  |  | 14 | [5 empty] | 9857.5 |  | 1.5 | NAGA PHANI | HDD
171 |  | J-179 | J-235 | BT ROAD | HDPE |  |  |  | 13 | [5 empty] | 9870.5 |  | 2 | NAGA PHANI | HDD
172 |  | J-179 | J-235 | CC ROAD | HDPE |  |  |  | 106 | [5 empty] | 9976.5 |  | 2 | NAGA PHANI | HDD
173 |  | J-251 | J-257 | BT ROAD | HDPE |  |  |  | 78 | [5 empty] | 10054.5 |  | 2 | NAGA PHANI | HDD
174 |  | J-74 | J-90 | BT ROAD | HDPE |  |  |  | 99.1 | [5 empty] | 10153.6 |  | 2 | NAGA PHANI | HDD
175 |  | J-95 | J-84 | BT ROAD | HDPE |  |  |  | 190.1 | [5 empty] | 10343.7 |  | 2 | NAGA PHANI | HDD
176 |  | J-95 | J-84 | BOE | HDPE |  |  |  | 10 | [5 empty] | 10353.7 |  | 2 | NAGA PHANI | HDD
177 |  | J-95 | J-30 | BT ROAD | HDPE |  |  |  | 374.2 | [5 empty] | 10727.9 |  | 2 | NAGA PHANI | HDD
[6 empty] | 63mm | 75mm | 90mm | 110mm | 125mm | 140mm | 160mm
[6 empty] | 5658.9 | 2563.1 | 1452.4 | 1053.6 | 0 | 0 | 0 |  |  | 10728
| Representative PMPL - BRCCPL (JV) Pratapgarh | [5 empty] | Representative Medhaj Techno Concept Pvt Ltd (TPI) Pratapgarh | [6 empty] | Representative UP Jal Nigam (Rural) Pratapgarh