## SAKRA
SAKRA
Sl.No | Date | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | DI/HDPE | Pipe Length (M) | [6 empty] | Cumulative Length (M) | LHS/RHS | Distance from Road C/L | Site Engineer Sign | FITTINGS | RESTORATION
[8 empty] | 75mm | 90mm | 110mm | 125mm | 140mm | 160mm | [6 empty] | TYPE OF ROAD | 63mm | 75mm | 90mm | 110mm | 125mm | 140mm | 160mm | Cumulative
1 |  | J6 | J59 | KACHA |  | 63 | 197 | [6 empty] | 197 | lhs | 1.8 | SHASHIRANJAN | JN6-63 ENDCAP |  | bt road | 19 | 0 | 7 | 6 | 0 | 0 | 0 | 32
2 |  | J59 | J172 | KACHA |  | 63 | 40 | [6 empty] | 237 | lhs | 1.8 | SHASHIRANJAN |  |  | ccroad | 173 | 0 | 5 | 0 | 0 | 0 | 0 | 178
3 |  | J59 | J172 | B.T road | 0.39 | 63 | 3 | [6 empty] | 240 |  |  | SHASHIRANJAN |  |  | brick road | 661 | 66 | 0 | 243 | 0 | 0 | 0 | 970
4 |  | J59 | J7 | KACHA |  | 63 | 250 | [6 empty] | 490 | lhs | 1.8 | SHASHIRANJAN |  |  | I.L road | 311 | 0 | 217 | 60 | 0 | 0 | 0 | 588
5 |  | J7 | J114 | KACHA |  | 63 | 72 | [6 empty] | 562 | RHS | 1.5 | SHASHIRANJAN | J7-63 TEE,RED-90*63
6 |  | J7 | J114 | bt road | 0.39 | 63 | 3 | [6 empty] | 565 |  |  | SHASHIRANJAN
7 |  | J32 | J111 | KACHA |  | 63 | 54 | [6 empty] | 619 |  |  | SHASHIRANJAN | J11-63ENDCAP
8 |  | J32 | J111 | ccroad | 0.39 | 63 | 45 | [6 empty] | 664 |  |  | SHASHIRANJAN
9 |  | J13 | J78 | ccroad | 0.39 | 63 | 106 | [6 empty] | 770 |  |  | SHASHIRANJAN
10 |  | J13 | J78 | brick road | 0.39 | 63 | 23 | [6 empty] | 793 |  |  | SHASHIRANJAN |  | 23
11 |  | J78 | J171 | brick road | 0.39 | 63 | 44 | [6 empty] | 837 |  |  | SHASHIRANJAN | J171-63ENDCAP | 44
12 |  | J78 | J171 | ccroad | 0.39 | 63 | 3 | [6 empty] | 840 |  |  | SHASHIRANJAN
13 |  | J12 | J42 | KACHA |  | 63 | 101 | [6 empty] | 941 |  |  | SHASHIRANJAN | J101-63EQUAL TEE
14 |  | J42 | J178 | KACHA |  | 63 | 44 | [6 empty] | 985 |  |  | SHASHIRANJAN | J178-ENDCAP
15 |  | J42 | J132 | KACHA |  | 63 | 74 | [6 empty] | 1059 |  |  | SHASHIRANJAN | J132-ENDCAP
16 |  | J49 | J125 | KACHA |  | 63 | 90 | [6 empty] | 1149 |  |  | SHASHIRANJAN | 90*90*90,90*63,ENDCAP
17 |  | J19 | J182 | KACHA |  | 63 | 36 | [6 empty] | 1185 |  |  | SHASHIRANJAN | ENDCAP
18 |  | J19 | J146 | KACHA |  | 63 | 65 | [6 empty] | 1250 |  |  | SHASHIRANJAN | ENDCAP
19 |  | J74 | J150 | KACHA |  | 63 | 64 | [6 empty] | 1314 |  |  | SHASHIRANJAN | 90*63REDUCER
20 |  | J74 | J150 | brick road | 0.39 | 63 | 10 | [6 empty] | 1324 |  |  | SHASHIRANJAN |  | 10
21 |  | J82 | J162 | brick road | 0.39 | 63 | 50 | [6 empty] | 1374 |  |  | SHASHIRANJAN | END CAP | 50
22 |  | J66 | J168 | KACHA |  | 63 | 138 | [6 empty] | 1512 |  |  | SHASHIRANJAN | 110*110*110,110*63,ENDCAP
23 |  | J101 | J203 | KACHA |  | 63 | 33 | [6 empty] | 1545 |  |  | SHASHIRANJAN | END CAP
24 |  | J96 | J123 | bt road | 0.39 | 63 | 3 | [6 empty] | 1548 |  |  | SHASHIRANJAN |  | 3
25 |  | J96 | J123 | KACHA |  | 63 | 39 | [6 empty] | 1587 |  |  | SHASHIRANJAN | END CAP
26 |  | J109 | J170 | KACHA |  | 63 | 46 | [6 empty] | 1633 |  |  | SHASHIRANJAN | END CAP
27 |  | J1 | J76 | KACHA |  | 63 | 49 | [6 empty] | 1682 |  |  | SHASHIRANJAN
28 |  | J76 | J116 | brick road | 0.39 | 63 | 40 | [6 empty] | 1722 |  |  | SHASHIRANJAN |  | 40
29 |  | J1 | J10 | KACHA |  | 63 | 420 | [6 empty] | 2142 |  |  | SHASHIRANJAN | ENDCAP
30 |  | J23 | J37 | KACHA |  | 63 | 104 | [6 empty] | 2246 |  |  | SHASHIRANJAN | ENDCAP
31 |  | J83 | J71 | KACHA |  | 63 | 78 | [6 empty] | 2324 |  |  | SHASHIRANJAN | 63*63*63
32 |  | J66 | J71 | KACHA |  | 63 | 17 | [6 empty] | 2341 |  |  | SHASHIRANJAN | PRIVATELAND-ENDCAP
33 |  | J71 | J94 | brick road | 0.39 | 63 | 50 | [6 empty] | 2391 |  |  | SHASHIRANJAN |  | 50
34 |  | J94 | J11 | KACHA |  | 63 | 66 | [6 empty] | 2457 |  |  | SHASHIRANJAN | 75*75*75,75*63
35 |  | J94 | J11 | ccroad | 0.39 | 63 | 14 | [6 empty] | 2471 |  |  | SHASHIRANJAN |  | 14
36 |  | J11 | J22,J72 | brick road | 0.39 | 63 | 135 | [6 empty] | 2606 |  |  | SHASHIRANJAN | 90*63 | 135
37 |  | J11 | J22,J72 | I.L road | 0.39 | 63 | 34 | [6 empty] | 2640 |  |  | SHASHIRANJAN |  | 34
38 |  | J72 | J199 | KACHA |  | 63 | 13 | [6 empty] | 2653 |  |  | SHASHIRANJAN
39 |  | J9 | J12 | KACHA |  | 75 | 257 | 257 | [5 empty] | 2910 |  |  | SHASHIRANJAN | J12-75*63RED
40 |  | J46 | J19 | KACHA |  | 75 | 202 | 202 | [5 empty] | 3112 |  |  | SHASHIRANJAN | 75*75*75,75*63-2NOS
41 |  | J2 | J129 | KACHA |  | 75 | 98 | 98 | [5 empty] | 3210 |  |  | SHASHIRANJAN | ENDCAP
42 |  | J14 | J44 | brick road | 0.39 | 75 | 66 | 66 | [5 empty] | 3276 |  |  | SHASHIRANJAN | 75*75*63 | 66
43 |  | J14 | J44 | KACHA |  | 75 | 29 | 29 | [5 empty] | 3305 |  |  | SHASHIRANJAN
44 |  | J44 | J130 | KACHA |  | 75 | 66 | 66 | [5 empty] | 3371 |  |  | SHASHIRANJAN | 110*110*110,110*75
45 |  | J11 | J29 | KACHA |  | 75 | 233 | 233 | [5 empty] | 3604 |  |  | SHASHIRANJAN
46 |  | J7 | J32 | KACHA |  | 90 | 94 |  | 94 |  |  |  |  | 3698 | RHS | 1.5 | SHASHIRANJAN | J32-90*90*63
47 |  | J32 | J13 | KACHA |  | 90 | 48 |  | 48 |  |  |  |  | 3746 |  |  | SHASHIRANJAN | J13-90*90*63
48 |  | J13 | J9 | KACHA |  | 90 | 163 |  | 163 |  |  |  |  | 3909 |  |  | SHASHIRANJAN | J9-90TEE,90*75RED
49 |  | J13 | J9 | ccroad | 0.39 | 90 | 5 |  | 5 |  |  |  |  | 3914 |  |  | SHASHIRANJAN
50 |  | J9 | J49 | KACHA |  | 90 | 7 |  | 7 |  |  |  |  | 3921 |  |  | SHASHIRANJAN
51 |  | J49 | J46 | bt road | 0.39 | 90 | 7 |  | 7 |  |  |  |  | 3928 |  |  | SHASHIRANJAN
52 |  | J49 | J2 | KACHA |  | 90 | 107 |  | 107 |  |  |  |  | 4035 |  |  | SHASHIRANJAN | 90*90*63
53 |  | J2 | J4 | KACHA |  | 90 | 402 |  | 402 |  |  |  |  | 4437 |  |  | SHASHIRANJAN
54 |  | J72 | J81 | I.L road | 0.39 | 90 | 50 |  | 50 |  |  |  |  | 4487 |  |  | SHASHIRANJAN |  | 50
55 |  | J48 | J150 | I.L road | 0.39 | 90 | 167 |  | 167 |  |  |  |  | 4654 |  |  | SHASHIRANJAN |  | 167
56 |  | J130 | J74 | brick road | 0.44 | 110 | 68 |  |  | 68 |  |  |  | 4722 |  |  | SHASHIRANJAN | 110*110*110,110*63 | 68
57 |  | J74 | J69/A | brick road | 0.44 | 110 | 44 |  |  | 44 |  |  |  | 4766 |  |  | SHASHIRANJAN | 140*140*110 | 44
58 |  | J130 | J129 | brick road | 0.44 | 110 | 11 |  |  | 11 |  |  |  | 4777 |  |  | SHASHIRANJAN | 110*90REDUCER | 11
59 |  | J129 | J82 | brick road | 0.44 | 110 | 83 |  |  | 83 |  |  |  | 4860 |  |  | SHASHIRANJAN | 110*110*110,110*63 | 83
60 |  | J82 | J66 | KACHA |  | 110 | 176 |  |  | 176 |  |  |  | 5036 |  |  | SHASHIRANJAN
61 |  | J66 | J83 | KACHA |  | 110 | 57 |  |  | 57 |  |  |  | 5093 |  |  | SHASHIRANJAN | 110*110*110,110*63
62 |  | J83 | J101 | I.L road | 0.44 | 110 | 31 |  |  | 31 |  |  |  | 5124 |  |  | SHASHIRANJAN | 110*110*110,110*63 | 31
63 |  | J101 | J96 | brick road | 0.44 | 110 | 37 |  |  | 37 |  |  |  | 5161 |  |  | SHASHIRANJAN | 110*110*110,110*63 | 37
64 |  | J101 | J96 | I.L road | 0.44 | 110 | 29 |  |  | 29 |  |  |  | 5190 |  |  | SHASHIRANJAN |  | 29
65 |  | J96 | J109 | KACHA |  | 110 | 47 |  |  | 47 |  |  |  | 5237 |  |  | SHASHIRANJAN | 110*110*110,110*63
66 |  | J109 | J1 | KACHA |  | 110 | 73 |  |  | 73 |  |  |  | 5310 |  |  | SHASHIRANJAN | 110*110*110,63*63*63,110*63
67 |  | J109 | J1 | bt road | 0.39 | 110 | 3 |  |  | 3 |  |  |  | 5313 |  |  | SHASHIRANJAN
68 |  | J1 | J23 | KACHA |  | 110 | 109 |  |  | 109 |  |  |  | 5422 |  |  | SHASHIRANJAN | 110*110*110
69 |  | J23 | J51 | KACHA |  | 110 | 170 |  |  | 170 |  |  |  | 5592 |  |  | SHASHIRANJAN
70 |  | J23 | J51 | bt road | 0.44 | 110 | 3 |  |  | 3 |  |  |  | 5595 |  |  | SHASHIRANJAN
71 |  | J51 | J61 | KACHA |  | 110 | 53 |  |  | 53 |  |  |  | 5648 |  |  | SHASHIRANJAN | 110*110*110,110*63RED |  |  |  | 8788 | 3444 | 2620 | 1493 | 48 | 3486 | 43
[15 empty] | 9594 | 8643 | 7692 | 9594
63 | 75 | 75 | 90 | 110 | 140 | 160
2653 | 951 | 951 | 1050 | 994 | 0 | 0 | 5648
8788 | 3444 | 3444 | 2620 | 1493 | 3486 | 43 | 19874 | [13 empty] | 63 | 8788 | 5910 | 2878
MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT. |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT. | [11 empty] | 75 | 3444 | 2952 | 492
DESIGNATION |  |  |  |  | DESIGNATION |  |  |  | DESIGNATION | [11 empty] | 90 | 2620 | 2476 | 144
NAME |  |  |  |  | NAME |  |  |  | NAME | [11 empty] | 110 | 1493 | 1086 | 407
SIGN.with date |  |  |  |  | SIGN.with date |  |  |  | SIGN.with date | [11 empty] | 125 | 48 | 48 | 0
[21 empty] | 140 | 3486 | 3402 | 84
[21 empty] | 160 | 43 |  | 43
TYPE OF ROAD | 63mm | 63 | 75 | 110 | 125 | 140 | 160 | Cumulative
I.L road |  | 34 | 0 | 60 | 0 | 0 | 0
bt road |  | 6 | 0 | 6 | 0 | 0 | 0 | [16 empty] | SAKRA-JMR1
brick road |  | 352 | 66 | 243 | 0 | 0 | 0 | [13 empty] | Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | DI/HDPE | Pipe Length (M) | cummulative
|  | 0 | 63mm | 75mm | 90mm | 110mm | 125mm | 140mm | 160mm | Cumulative
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ccroad |  | 168 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 1 | J130 | J74 | brick road | 0.44 | 110 | 68 | 68
[21 empty] | 2 | J74 | J69/A | brick road | 0.44 | 110 | 44 | 112
[21 empty] | 3 | J130 | J129 | brick road | 0.44 | 110 | 11 | 123
SAKRA | [20 empty] | 4 | J129 | J82 | brick road | 0.44 | 110 | 83 | 206
[21 empty] | 5 | J82 | J66 | KACHA |  | 110 | 176 | 382
[21 empty] | 6 | J66 | J83 | KACHA |  | 110 | 57 | 439
Sl.No | Date | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | DI/HDPE | Pipe Length (M) | [6 empty] | Cumulative Length (M) | LHS/RHS | Distance from Road C/L | Site Engineer Sign | FITTINGS | RESTORATION |  | 7 | J83 | J101 | I.L road | 0.44 | 110 | 31 | 470
[8 empty] | 75mm | 90mm | 110mm | 125mm | 140mm | 160mm | [7 empty] | 8 | J101 | J96 | brick road | 0.44 | 110 | 37 | 507
1 |  | J57 | J138 | KACHA |  | 63 | 71 | [6 empty] | 71 | [6 empty] | 9 | J101 | J96 | I.L road | 0.44 | 110 | 29 | 536
2 |  | J3 | J39 | brick road | 0.39 | 63 | 254 | [6 empty] | 325 |  |  |  |  | 254 |  | 10 | J96 | J109 | KACHA |  | 110 | 47 | 583
3 |  | J93 | J186 | KACHA |  | 63 | 36 | [6 empty] | 361 | [6 empty] | 11 | J109 | J1 | KACHA |  | 110 | 73 | 656
4 |  | J93 | J186 | ccroad | 0.39 | 63 | 3 | [6 empty] | 364 |  |  |  |  | 3 |  | 12 | J109 | J1 | bt road | 0.39 | 110 | 3 | 659
5 |  | J52 | J193 | KACHA |  | 63 | 23 | [6 empty] | 387 | [6 empty] | 13 | J1 | J23 | KACHA |  | 110 | 109 | 768
6 |  | J52 | J60 | KACHA |  | 63 | 240 | [6 empty] | 627 | [6 empty] | 14 | J23 | J51 | KACHA |  | 110 | 170 | 938
7 |  | J26 | J63 | KACHA |  | 63 | 168 | [6 empty] | 795 | [6 empty] | 15 | J23 | J51 | bt road | 0.44 | 110 | 3 | 941
8 |  | J74 | J174 | KACHA |  | 63 | 30 | [6 empty] | 825 | [6 empty] | 16 | J51 | J61 | KACHA |  | 110 | 53 | 994
9 |  | J58 | J180 | brick road | 0.39 | 63 | 27 | [6 empty] | 852 | [6 empty] | 17 | J14 | J31 | KACHA |  | 140 | 105 | 1099
10 |  | J5 | J8 | brick road | 0.39 | 63 | 166 | [6 empty] | 1018 | [6 empty] | 18 | J31 | J106 | KACHA |  | 140 | 18 | 1117
11 |  | J5 | J8 | KACHA |  | 63 | 177 | [6 empty] | 1195 | [6 empty] | 19 | J106 | J74A | KACHA |  | 140 | 42 | 1159
12 |  | J98 | J201 | KACHA |  | 63 | 21 | [6 empty] | 1216 | [6 empty] | 20 | J74A | J74 | KACHA |  | 140 | 7 | 1166
13 |  | J163 | J187 | KACHA |  | 63 | 58 | [6 empty] | 1274 | [6 empty] | 21 | J74 | J58 | KACHA |  | 140 | 78 | 1244
14 |  | J17 | J159 | KACHA |  | 63 | 57 | [6 empty] | 1331 | [6 empty] | 22 | J58 | J48 | KACHA |  | 140 | 88 | 1332
15 |  | J159 | J159A | KACHA |  | 63 | 66 | [6 empty] | 1397 | [6 empty] | 23 | J48 | J5 | KACHA |  | 140 | 18 | 1350
16 |  | J3 | J33 | ccroad | 0.39 | 75 | 5 | 5 | [5 empty] | 1402 |  |  |  |  | 5 |  | 24 | J5 | J85 | KACHA |  | 140 | 77 | 1427
17 |  | J3 | J33 | brick road | 0.39 | 75 | 151 | 151 | [5 empty] | 1553 |  |  |  |  | 151 |  | 25 | J29 | J227 | KACHA |  | 140 | 515 | 1942
18 |  | J3 | J33 | KACHA |  | 75 | 54 | 54 | [5 empty] | 1607 | [6 empty] | 26 | J227 | J228 | KACHA |  | 140 | 260 | 2202
19 |  | J33 | J89 | KACHA |  | 75 | 44 | 44 | [5 empty] | 1651 | [6 empty] | 27 | J228 | J188 | KACHA |  | 140 | 641 | 2843
20 |  | J93 | J33 | KACHA |  | 75 | 15 | 15 | [5 empty] | 1666 | [6 empty] | 28 | J77 | J47 | KACHA |  | 140 | 92 | 2935
21 |  | J26 | J32 | KACHA |  | 75 | 47 | 47 | [5 empty] | 1713 | [6 empty] | 29 | J47 | J45 | KACHA |  | 140 | 261 | 3196
22 |  | J89 | J16,J152 | KACHA |  | 75 | 100 | 100 | [5 empty] | 1813 | [6 empty] | 30 | J45 | J102 | KACHA |  | 140 | 64 | 3260
23 |  | J77 | J98 | KACHA |  | 75 | 125 | 125 | [5 empty] | 1938 | [6 empty] | 31 | 102 | 137 | KACHA |  | 140 | 140 | 3400
24 |  | J98 | J165 | KACHA |  | 75 | 87 | 87 | [5 empty] | 2025 | [6 empty] | 32 | 137 | 67 | KACHA |  | 140 | 28 | 3428
25 |  | J47 | J163 | KACHA |  | 75 | 47 | 47 | [5 empty] | 2072 | [6 empty] | 33 | 67 | 24 | KACHA |  | 140 | 196 | 3624
26 |  | J163 | J17 | KACHA |  | 75 | 195 | 195 | [5 empty] | 2267 | [6 empty] | 34 | 24 | 38 | KACHA |  | 140 | 288 | 3912
27 |  | J45 | J127 | KACHA |  | 75 | 68 | 68 | [5 empty] | 2335 | [6 empty] | 35 | 38 | 167 | KACHA |  | 140 | 484 | 4396
28 |  | J127 | J75 | KACHA |  | 75 | 40 | 40 | [5 empty] | 2375 | [8 empty] | 110 | 140 |  |  | 4396
29 |  | J75 | J175 | KACHA |  | 75 | 62 | 62 | [5 empty] | 2437 | [8 empty] | 994 | 3402
30 |  | J61 | J68 | brick road | 0.39 | 90 | 155 |  | 155 |  |  |  |  | 2592 |  |  |  |  | 155 |  |  |  | 1493 | 3486
31 |  | J61 | J68 | bt road | 0.39 | 90 | 11 |  | 11 |  |  |  |  | 2603 |  |  |  |  | 11 |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
32 |  | J79 | J3 | brick road | 0.39 | 90 | 88 |  | 88 |  |  |  |  | 2691 |  |  |  |  | 88 |  | DESIGNATION |  |  |  |  | DESIGNATION
33 |  | J79 | J3 | KACHA |  | 90 | 50 |  | 50 |  |  |  |  | 2741 | [6 empty] | NAME |  |  |  |  | NAME
34 |  | J93 | J28 | ccroad | 0.39 | 90 | 20 |  | 20 |  |  |  |  | 2761 |  |  |  |  | 20 |  | SIGN.with date |  |  |  |  | SIGN.with date
35 |  | J93 | J28 | KACHA |  | 90 | 58 |  | 58 |  |  |  |  | 2819
36 |  | J14 | J31 | KACHA |  | 140 | 105 |  |  |  |  | 105 |  | 2924
37 |  | J31 | J106 | KACHA |  | 140 | 18 |  |  |  |  | 18 |  | 2942
38 |  | J106 | J74A | KACHA |  | 140 | 42 |  |  |  |  | 42 |  | 2984
39 |  | J74A | J74 | KACHA |  | 140 | 7 |  |  |  |  | 7 |  | 2991
40 |  | J74 | J58 | KACHA |  | 140 | 78 |  |  |  |  | 78 |  | 3069
41 |  | J58 | J48 | KACHA |  | 140 | 88 |  |  |  |  | 88 |  | 3157
42 |  | J48 | J5 | KACHA |  | 140 | 18 |  |  |  |  | 18 |  | 3175
43 |  | J5 | J85 | KACHA |  | 140 | 77 |  |  |  |  | 77 |  | 3252
44 |  | J29 | J227 | KACHA |  | 140 | 515 |  |  |  |  | 515 |  | 3767
45 |  | J227 | J228 | KACHA |  | 140 | 260 |  |  |  |  | 260 |  | 4027
46 |  | J228 | J188 | KACHA |  | 140 | 641 |  |  |  |  | 641 |  | 4668
47 |  | J77 | J47 | KACHA |  | 140 | 92 |  |  |  |  | 92 |  | 4760
48 |  | J47 | J45 | KACHA |  | 140 | 261 |  |  |  |  | 261 |  | 5021
63 | 75 | 75 | 90 | 125 | 140 | 160
1397 | 1040 | 1040 | 382 | 0 | 2202 | 0 | 5021
8788 | 3444 | 3444 | 2620 | 48 | 3486 | 43 | 18429
Cummulative
MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT. |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  |  | SIGN.with date |  |  |  | SIGN.with date
TYPE OF ROAD | 63mm | 63 | 75 | 90 | 125 | 140 | 160
I.L road |  | 0 | 0 | 0 | 0 | 0 | 0
bt road |  | 0 | 0 | 11 | 0 | 0 | 0
brick road |  | 447 | 151 | 243 | 0 | 0 | 0
ccroad |  | 3 | 5 | 20 | 0 | 0 | 0
651
880
SAKRA | [20 empty] | 935
Sl.No | Date | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | DI/HDPE | Pipe Length (M) | [6 empty] | Cumulative Length (M) | LHS/RHS | Distance from Road C/L | Site Engineer Sign | FITTINGS | RESTORATION
[8 empty] | 75mm | 90mm | 110mm | 125mm | 140mm | 160mm
1 |  | J104 | J56 | KACHA |  | 63 | 102 | [6 empty] | 102
2 |  | J104 | J56 | I.L road | 0.39 | 63 | 22 | [6 empty] | 124 |  |  |  |  | 22
3 |  | J56 | J220 | KACHA |  | 63 | 76 | [6 empty] | 200
4 |  | 24 | 192 | brick road | 0.39 | 63 | 200 | [6 empty] | 400 |  |  |  |  | 200
5 |  | 24 | 192 | KACHA |  | 63 | 200 | [6 empty] | 600
6 |  | 27 | 84 | KACHA |  | 63 | 280 | [6 empty] | 880
7 |  | 54 | 112 | KACHA |  | 63 | 198 | [6 empty] | 1078
8 |  | 54 | 160 | KACHA |  | 63 | 97 | [6 empty] | 1175
9 |  | 160 | 207 | KACHA |  | 63 | 44 | [6 empty] | 1219
10 |  | 160 | 185 | KACHA |  | 63 | 97 | [6 empty] | 1316
11 |  | 110 | 226 | KACHA |  | 63 | 119 | [6 empty] | 1435
12 |  | 110 | 217 | KACHA |  | 63 | 58 | [6 empty] | 1493
13 |  | 117 | 169 | KACHA |  | 63 | 86 | [6 empty] | 1579
14 |  | 117 | 169 | ccroad | 0.39 | 63 | 2 | [6 empty] | 1581 |  |  |  |  | 2
15 |  | 18 | J139,J191 | KACHA |  | 63 | 47 | [6 empty] | 1628
16 |  | 18 | J139,J191 | I.L road | 0.39 | 63 | 42 | [6 empty] | 1670 |  |  |  |  | 42
17 |  | 18 | 95 | brick road | 0.39 | 63 | 40 | [6 empty] | 1710 |  |  |  |  | 40
18 |  | 18 | 95 | KACHA |  | 63 | 150 | [6 empty] | 1860
19 |  | J75 | J104 | I.L road | 0.39 | 75 | 25 | 25 | [5 empty] | 1885 |  |  |  |  | 25
20 |  | J75 | J104 | KACHA |  | 75 | 60 | 60 | [5 empty] | 1945
21 |  | J102 | J100 | KACHA |  | 75 | 32 | 32 | [5 empty] | 1977
22 |  | 137 | 100 | KACHA |  | 75 | 72 | 72 | [5 empty] | 2049
23 |  | 100 | 102 | KACHA |  | 75 | 29 | 29 | [5 empty] | 2078
24 |  | 100 | 175 | KACHA |  | 75 | 41 | 41 | [5 empty] | 2119
25 |  | 67 | 137 | KACHA |  | 75 | 120 | 120 | [5 empty] | 2239
26 |  | 38 | 202 | KACHA |  | 75 | 45 | 45 | [5 empty] | 2284
27 |  | 144 | 54 | KACHA |  | 75 | 106 | 106 | [5 empty] | 2390
28 |  | 185 | 103 | I.L road | 0.39 | 75 | 86 | 86 | [5 empty] | 2476 |  |  |  |  | 86
29 |  | 103 | 140 | brick road | 0.39 | 75 | 39 | 39 | [5 empty] | 2515 |  |  |  |  | 39
30 |  | 140 | 118 | KACHA |  | 75 | 54 | 54 | [5 empty] | 2569
31 |  | 103 | 110 | KACHA |  | 75 | 75 | 75 | [5 empty] | 2644
32 |  | 217 | J157,J117 | KACHA |  | 75 | 48 | 48 | [5 empty] | 2692
33 |  | 117 | 65 | KACHA |  | 75 | 79 | 79 | [5 empty] | 2771
34 |  | 117 | 65 | ccroad | 0.39 | 75 | 50 | 50 | [5 empty] | 2821 |  |  |  |  | 50
35 |  | 20 | 18 | KACHA |  | 90 | 179 |  | 179 |  |  |  |  | 3000
36 |  | 18 | 139 | KACHA |  | 90 | 23 |  | 23 |  |  |  |  | 3023
37 |  | 113 | 65 | KACHA |  | 90 | 88 |  | 88 |  |  |  |  | 3111
38 |  | 65 | 27 | KACHA |  | 90 | 121 |  | 121 |  |  |  |  | 3232
39 |  | 20 | 40 | KACHA |  | 90 | 314 |  | 314 |  |  |  |  | 3546
40 |  | 40 | 144 | KACHA |  | 90 | 59 |  | 59 |  |  |  |  | 3605
41 |  | 18 | J97,J107,J140 | KACHA |  | 90 | 115 |  | 115 |  |  |  |  | 3720
42 |  | 18 | J97,J107,J140 | brick road | 0.39 | 90 | 145 |  | 145 |  |  |  |  | 3865 |  |  |  |  | 145
43 |  | j57 | 30 | bt road | 0.44 | 110 | 3 |  |  | 3 |  |  |  | 3868 |  |  |  |  | 3
44 |  | j57 | 30 | KACHA |  | 110 | 89 |  |  | 89 |  |  |  | 3957
45 |  | 167 | 20 | KACHA |  | 125 | 48 |  |  |  | 48 |  |  | 4005
46 |  | J45 | J102 | KACHA |  | 140 | 64 |  |  |  |  | 64 |  | 4069
47 |  | 102 | 137 | KACHA |  | 140 | 140 |  |  |  |  | 140 |  | 4209
48 |  | 137 | 67 | KACHA |  | 140 | 28 |  |  |  |  | 28 |  | 4237
49 |  | 67 | 24 | KACHA |  | 140 | 196 |  |  |  |  | 196 |  | 4433
50 |  | 24 | 38 | KACHA |  | 140 | 288 |  |  |  |  | 288 |  | 4721 | [8 empty] | 43
51 |  | 38 | 167 | KACHA |  | 140 | 484 |  |  |  |  | 484 |  | 5205
63 |  | 75 | 90 | 110 | 125 | 140
1860 | 0 | 961 | 1044 | 92 | 48 | 1200 | 5205 |  | 5205
8788 | 3444 | 2620 | 1493 | 48 | 3486 | 43 | 19922 |  | 19922
MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT. |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  |  | SIGN.with date |  |  |  | SIGN.with date
TYPE OF ROAD | 63mm | 63 | 75 | 90 | 125 | 140 | 160
I.L road |  | 64 | 111 | 0 | 0 | 0 | 0
bt road |  | 0 | 0 | 0 | 0 | 0 | 0
brick road |  | 240 | 39 | 145 | 0 | 0 | 0
ccroad |  | 2 | 50 | 0 | 0 | 0 | 0

## sakra 2
SAKRA(JMR 2) BLOCK-MANGRAURA
Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | Dia of pipe(MM) | Pipe Length (M) | CUMMULATIVE | Depth(M) | REMARK
1 | J6 | J59 | KACHA |  | 63 | 197 | 197 | 1.063
2 | J59 | J172 | KACHA |  | 63 | 40 | 237 | 1.063
3 | J59 | J172 | B.T road | 0.36 | 63 | 3 | 240 | 1.063
4 | J59 | J7 | KACHA |  | 63 | 250 | 490 | 1.063
5 | J7 | J114 | KACHA |  | 63 | 72 | 562 | 1.063
6 | J7 | J114 | bt road | 0.36 | 63 | 3 | 565 | 1.063
7 | J32 | J111 | KACHA |  | 63 | 54 | 619 | 1.063
8 | J32 | J111 | ccroad | 0.36 | 63 | 45 | 664 | 1.063
9 | J13 | J78 | ccroad | 0.36 | 63 | 106 | 770 | 1.063
10 | J13 | J78 | brick road | 0.36 | 63 | 23 | 793 | 1.063
11 | J78 | J171 | brick road | 0.36 | 63 | 44 | 837 | 1.063
12 | J78 | J171 | ccroad | 0.36 | 63 | 3 | 840 | 1.063
13 | J12 | J42 | KACHA |  | 63 | 101 | 941 | 1.063
14 | J42 | J178 | KACHA |  | 63 | 44 | 985 | 1.063
15 | J42 | J132 | KACHA |  | 63 | 74 | 1059 | 1.063
16 | J49 | J125 | KACHA |  | 63 | 90 | 1149 | 1.063
17 | J19 | J182 | KACHA |  | 63 | 36 | 1185 | 1.063
18 | J19 | J146 | KACHA |  | 63 | 65 | 1250 | 1.063
19 | J74 | J150 | KACHA |  | 63 | 64 | 1314 | 1.063
20 | J74 | J150 | brick road | 0.36 | 63 | 10 | 1324 | 1.063
21 | J82 | J162 | brick road | 0.36 | 63 | 50 | 1374 | 1.063
22 | J66 | J168 | KACHA |  | 63 | 138 | 1512 | 1.063
23 | J101 | J203 | KACHA |  | 63 | 33 | 1545 | 1.063
24 | J96 | J123 | bt road | 0.36 | 63 | 3 | 1548 | 1.063
25 | J96 | J123 | KACHA |  | 63 | 39 | 1587 | 1.063
26 | J109 | J170 | KACHA |  | 63 | 46 | 1633 | 1.063
27 | J1 | J76 | KACHA |  | 63 | 49 | 1682 | 1.063
28 | J76 | J116 | brick road | 0.36 | 63 | 40 | 1722 | 1.063
29 | J1 | J10 | KACHA |  | 63 | 420 | 2142 | 1.063
30 | J23 | J37 | KACHA |  | 63 | 104 | 2246 | 1.063
31 | J83 | J71 | KACHA |  | 63 | 78 | 2324 | 1.063
32 | J66 | J71 | KACHA |  | 63 | 17 | 2341 | 1.063
33 | J71 | J94 | brick road | 0.36 | 63 | 50 | 2391 | 1.063
34 | J94 | J11 | KACHA |  | 63 | 66 | 2457 | 1.063
35 | J94 | J11 | ccroad | 0.36 | 63 | 14 | 2471 | 1.063
36 | J11 | J22,J72 | brick road | 0.36 | 63 | 135 | 2606 | 1.063
37 | J11 | J22,J72 | I.L road | 0.36 | 63 | 34 | 2640 | 1.063
38 | J72 | J199 | KACHA |  | 63 | 13 | 2653 | 1.063
39 | J57 | J138 | KACHA |  | 63 | 71 | 2724 | 1.063
40 | J3 | J39 | brick road | 0.36 | 63 | 254 | 2978 | 1.063
41 | J93 | J186 | KACHA |  | 63 | 36 | 3014 | 1.063
42 | J93 | J186 | ccroad | 0.36 | 63 | 3 | 3017 | 1.063
43 | J52 | J193 | KACHA |  | 63 | 23 | 3040 | 1.063
44 | J52 | J60 | KACHA |  | 63 | 240 | 3280 | 1.063
45 | J26 | J63 | KACHA |  | 63 | 168 | 3448 | 1.063
46 | J74 | J174 | KACHA |  | 63 | 30 | 3478 | 1.063
47 | J58 | J180 | brick road | 0.36 | 63 | 27 | 3505 | 1.063
48 | J5 | J8 | brick road | 0.36 | 63 | 166 | 3671 | 1.063
49 | J5 | J8 | KACHA |  | 63 | 177 | 3848 | 1.063
50 | J98 | J201 | KACHA |  | 63 | 21 | 3869 | 1.063
51 | J163 | J187 | KACHA |  | 63 | 58 | 3927 | 1.063
52 | J17 | J159 | KACHA |  | 63 | 57 | 3984 | 1.063
53 | J159 | J159A | KACHA |  | 63 | 66 | 4050 | 1.063
54 | J104 | J56 | KACHA |  | 63 | 102 | 4152 | 1.063
55 | J104 | J56 | I.L road | 0.36 | 63 | 22 | 4174 | 1.063
56 | J56 | J220 | KACHA |  | 63 | 76 | 4250 | 1.063
57 | 24 | 192 | brick road | 0.36 | 63 | 200 | 4450 | 1.063
58 | 24 | 192 | KACHA |  | 63 | 200 | 4650 | 1.063
59 | 27 | 84 | KACHA |  | 63 | 280 | 4930 | 1.063
60 | 54 | 112 | KACHA |  | 63 | 198 | 5128 | 1.063
61 | 54 | 160 | KACHA |  | 63 | 97 | 5225 | 1.063
62 | 160 | 207 | KACHA |  | 63 | 44 | 5269 | 1.063
63 | 160 | 185 | KACHA |  | 63 | 97 | 5366 | 1.063
64 | 110 | 226 | KACHA |  | 63 | 119 | 5485 | 1.063
65 | 110 | 217 | KACHA |  | 63 | 58 | 5543 | 1.063
66 | 117 | 169 | KACHA |  | 63 | 86 | 5629 | 1.063
67 | 117 | 169 | ccroad | 0.36 | 63 | 2 | 5631 | 1.063
68 | 18 | J139,J191 | KACHA |  | 63 | 47 | 5678 | 1.063
69 | 18 | J139,J191 | I.L road | 0.46 | 63 | 42 | 5720 | 1.063
70 | 18 | 95 | brick road | 0.36 | 63 | 40 | 5760 | 1.063
71 | 18 | 95 | KACHA |  | 63 | 150 | 5910 | 1.063
72 | J9 | J12 | KACHA |  | 75 | 257 | 6167 | 1.075
73 | J46 | J19 | KACHA |  | 75 | 202 | 6369 | 1.075
74 | J2 | J129 | KACHA |  | 75 | 98 | 6467 | 1.075
75 | J14 | J44 | brick road | 0.37 | 75 | 66 | 6533 | 1.075
76 | J14 | J44 | KACHA |  | 75 | 29 | 6562 | 1.075
77 | J44 | J130 | KACHA |  | 75 | 66 | 6628 | 1.075
78 | J11 | J29 | KACHA |  | 75 | 233 | 6861 | 1.075
79 | J3 | J33 | ccroad | 0.37 | 75 | 5 | 6866 | 1.075
80 | J3 | J33 | brick road | 0.37 | 75 | 151 | 7017 | 1.075
81 | J3 | J33 | KACHA |  | 75 | 54 | 7071 | 1.075
82 | J33 | J89 | KACHA |  | 75 | 44 | 7115 | 1.075
83 | J93 | J33 | KACHA |  | 75 | 15 | 7130 | 1.075
84 | J26 | J32 | KACHA |  | 75 | 47 | 7177 | 1.075
85 | J89 | J16,J152 | KACHA |  | 75 | 100 | 7277 | 1.075
86 | J77 | J98 | KACHA |  | 75 | 125 | 7402 | 1.075
87 | J98 | J165 | KACHA |  | 75 | 87 | 7489 | 1.075
88 | J47 | J163 | KACHA |  | 75 | 47 | 7536 | 1.075
89 | J163 | J17 | KACHA |  | 75 | 195 | 7731 | 1.075
90 | J45 | J127 | KACHA |  | 75 | 68 | 7799 | 1.075
91 | J127 | J75 | KACHA |  | 75 | 40 | 7839 | 1.075
92 | J75 | J175 | KACHA |  | 75 | 62 | 7901 | 1.075
93 | J75 | J104 | I.L road | 0.37 | 75 | 25 | 7926 | 1.075
94 | J75 | J104 | KACHA |  | 75 | 60 | 7986 | 1.075
95 | J102 | J100 | KACHA |  | 75 | 32 | 8018 | 1.075
96 | 137 | 100 | KACHA |  | 75 | 72 | 8090 | 1.075
97 | 100 | 102 | KACHA |  | 75 | 29 | 8119 | 1.075
98 | 100 | 175 | KACHA |  | 75 | 41 | 8160 | 1.075
99 | 67 | 137 | KACHA |  | 75 | 120 | 8280 | 1.075
100 | 38 | 202 | KACHA |  | 75 | 45 | 8325 | 1.075
101 | 144 | 54 | KACHA |  | 75 | 106 | 8431 | 1.075
102 | 185 | 103 | I.L road | 0.37 | 75 | 86 | 8517 | 1.075
103 | 103 | 140 | brick road | 0.37 | 75 | 39 | 8556 | 1.075
104 | 140 | 118 | KACHA |  | 75 | 54 | 8610 | 1.075
105 | 103 | 110 | KACHA |  | 75 | 75 | 8685 | 1.075
106 | 217 | J157,J117 | KACHA |  | 75 | 48 | 8733 | 1.075
107 | 117 | 65 | KACHA |  | 75 | 79 | 8812 | 1.075
108 | 117 | 65 | ccroad | 0.37 | 75 | 50 | 8862 | 1.075
109 | 20 | 18 | KACHA |  | 90 | 179 | 9041 | 1.09
110 | 18 | 139 | KACHA |  | 90 | 23 | 9064 | 1.09
111 | 113 | 65 | KACHA |  | 90 | 88 | 9152 | 1.09
112 | 65 | 27 | KACHA |  | 90 | 121 | 9273 | 1.09
113 | 20 | 40 | KACHA |  | 90 | 314 | 9587 | 1.09
114 | 40 | 144 | KACHA |  | 90 | 59 | 9646 | 1.09
115 | 18 | J97,J107,J140 | KACHA |  | 90 | 115 | 9761 | 1.09
116 | 18 | J97,J107,J140 | brick road | 0.39 | 90 | 145 | 9906 | 1.09
117 | J61 | J68 | brick road | 0.39 | 90 | 155 | 10061 | 1.09
118 | J61 | J68 | bt road | 0.39 | 90 | 11 | 10072 | 1.09
119 | J79 | J3 | brick road | 0.39 | 90 | 88 | 10160 | 1.09 |  | 52
120 | J79 | J3 | KACHA |  | 90 | 50 | 10210 | 1.09
121 | J93 | J28 | ccroad | 0.39 | 90 | 20 | 10230 | 1.09
122 | J93 | J28 | KACHA |  | 90 | 58 | 10288 | 1.09
123 | J7 | J32 | KACHA |  | 90 | 94 | 10382 | 1.09
124 | J32 | J13 | KACHA |  | 90 | 48 | 10430 | 1.09
125 | J13 | J9 | KACHA |  | 90 | 163 | 10593 | 1.09
126 | J13 | J9 | ccroad | 0.39 | 90 | 5 | 10598 | 1.09 |  | 15784
127 | J9 | J49 | KACHA |  | 90 | 7 | 10605 | 1.09
128 | J49 | J46 | bt road | 0.39 | 90 | 7 | 10612 | 1.09
129 | J49 | J2 | KACHA |  | 90 | 107 | 10719 | 1.09
130 | J2 | J4 | KACHA |  | 90 | 402 | 11121 | 1.09
131 | J72 | J81 | I.L road | 0.46 | 90 | 50 | 11171 | 1.09
132 | J48 | J150 | I.L road | 0.46 | 90 | 167 | 11338 | 1.09
|  |  | 63 | 75 | 90 | 11338
|  |  | 5910 | 2952 | 2476 | 11338
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  | SIGN.with date
[5 empty] | 63 | 75 | 90 | 110 | 140
[5 empty] | 5910 | 2952 | 2476 | 994 | 3402

## road restoration
SAKRA(JMR) BLOCK-MANGRAURA AGENCY- SUMIRAN ENTERPRISES
Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | Dia of pipe(MM) | Pipe Length (M) | CUMMULATIVE | sqm |  | sqm
1 | J59 | J172 | B.T road | 0.36 | 63 | 3 | 240 | 1.08
2 | J7 | J114 | I.L | 0.46 | 63 | 72 | 562 | 33.12
3 | J7 | J114 | bt road | 0.36 | 63 | 3 | 565 | 1.08
4 | J32 | J111 | ccroad | 0.36 | 63 | 45 | 664 | 16.2
5 | J13 | J78 | ccroad | 0.36 | 63 | 106 | 770 | 38.16
6 | J13 | J78 | brick road | 0.36 | 63 | 23 | 793 | 8.28
7 | J78 | J171 | brick road | 0.36 | 63 | 44 | 837 | 15.84
8 | J78 | J171 | ccroad | 0.36 | 63 | 3 | 840 | 1.08
9 | J74 | J150 | i.l | 0.46 | 63 | 10 | 1324 | 4.6
10 | J82 | J162 | brick road | 0.36 | 63 | 50 | 1374 | 18
11 | J96 | J123 | bt road | 0.36 | 63 | 3 | 1548 | 1.08
12 | J76 | J116 | brick road | 0.36 | 63 | 40 | 1722 | 14.4
13 | J71 | J94 | brick road | 0.36 | 63 | 50 | 2391 | 18
14 | J94 | J11 | ccroad | 0.36 | 63 | 14 | 2471 | 5.04
15 | J11 | J22 | brick road | 0.36 | 63 | 135 | 2606 | 48.6
16 | J11 | J22 | I.L road | 0.46 | 63 | 34 | 2640 | 15.64
17 | J3 | J39 | brick road | 0.36 | 63 | 254 | 2978 | 91.44
18 | J93 | J186 | ccroad | 0.36 | 63 | 3 | 3017 | 1.08
19 | J58 | J180 | brick road | 0.36 | 63 | 27 | 3505 | 9.72
20 | J5 | J8 | brick road | 0.36 | 63 | 166 | 3671 | 59.76
21 | J104 | J56 | i.l | 0.46 | 63 | 102 | 4152 | 46.92
22 | J104 | J56 | I.L road | 0.46 | 63 | 22 | 4174 | 10.12
23 | J56 | J220 | i.l | 0.46 | 63 | 76 | 4250 | 34.96
24 | 24 | 192 | brick road | 0.36 | 63 | 200 | 4450 | 72
25 | 117 | 169 | ccroad | 0.36 | 63 | 2 | 5631 | 0.72
26 | 18 | J139 | I.L road | 0.46 | 63 | 42 | 5720 | 19.32
27 | 18 | 95 | brick road | 0.36 | 63 | 40 | 5760 | 14.4
28 | J14 | J44 | brick road | 0.37 | 75 | 66 | 6533 | 24.42
29 | J14 | J44 | i.l | 0.46 | 75 | 29 | 6562 | 13.34
30 | J44 | J130 | i.l | 0.46 | 75 | 66 | 6628 | 30.36
31 | J3 | J33 | ccroad | 0.37 | 75 | 5 | 6866 | 1.85
32 | J3 | J33 | brick road | 0.37 | 75 | 151 | 7017 | 55.87
33 | J45 | J127 | i.l | 0.46 | 75 | 68 | 7799 | 31.28
34 | J127 | J75 | i.l | 0.46 | 75 | 40 | 7839 | 18.4
35 | J75 | J104 | I.L road | 0.46 | 75 | 25 | 7926 | 11.5
36 | J75 | J104 | I.L road | 0.46 | 75 | 60 | 7986 | 27.6
37 | 185 | 103 | I.L road | 0.46 | 75 | 86 | 8517 | 39.56
38 | 103 | 140 | brick road | 0.37 | 75 | 39 | 8556 | 14.43
39 | 117 | 65 | ccroad | 0.37 | 75 | 50 | 8862 | 18.5
40 | 18 | J97 | brick road | 0.39 | 90 | 145 | 9906 | 56.55
41 | J61 | J68 | brick road | 0.39 | 90 | 155 | 10061 | 60.45
42 | J61 | J68 | bt road | 0.39 | 90 | 11 | 10072 | 4.29
43 | J79 | J3 | brick road | 0.39 | 90 | 88 | 10160 | 34.32
44 | J93 | J28 | ccroad | 0.39 | 90 | 20 | 10230 | 7.8
45 | J13 | J9 | ccroad | 0.39 | 90 | 5 | 10598 | 1.95
46 | J49 | J46 | bt road | 0.39 | 90 | 7 | 10612 | 2.73
47 | J72 | J81 | I.L road | 0.46 | 90 | 50 | 11171 | 23
48 | J48 | J150 | I.L road | 0.46 | 90 | 167 | 11338 | 76.82
49 | J130 | J74 | I.L road | 0.46 | 110 | 68 | 11406 | 31.28
50 | J74 | J69/A | I.L road | 0.46 | 110 | 44 | 11450 | 20.24
51 | J130 | J129 | I.L road | 0.46 | 110 | 11 | 11461 | 5.06
52 | J129 | J82 | I.L road | 0.46 | 110 | 83 | 11544 | 38.18
53 | J83 | J101 | I.L road | 0.46 | 110 | 31 | 11808 | 14.26
54 | J101 | J96 | brick road | 0.44 | 110 | 37 | 11845 | 16.28
55 | J101 | J96 | I.L road | 0.46 | 110 | 29 | 11874 | 13.34
56 | J109 | J1 | bt road | 0.39 | 110 | 3 | 11997 | 1.17
57 | J23 | J51 | bt road | 0.44 | 110 | 3 | 12279 | 1.32
SAKRA restoration
| Sl. No | Road Type | UNITS | WO/DPR Qty's | Qty Executed Up to Date | Qty Executed Billed up to Date | Qty Billed Up to Previous | This Bill(Executed) | Remarks
| 1 | BRICK ROAD | SQM |  | 632.76 | - | - | 632.76
| 2 | INTERLOCKING | SQM |  | 558.9 | - | - | 558.9
| 3 | B.T. ROAD | SQM
Sub-Contractor Site Engineer (Sr.Eng/ DY.M-SMX ) (Dy.M-PMX ) AGM Project Incharge