## HARDOI fhtc
RURAL WATER SUPPLY PROJECT UNDER JJM, UP - PRAYAGRAJ
GP_______Hardoi______Block_________MANGRAURA__________ FHTC Measurement Sheet
Sl.No | Date | START NODE | END NODE | DIA OF PIPE (MM) | MDPE Pipe Length (m) | Aadhar No /PAN No | House holder name ( as per adhar) | Father/Husband Name | House holder CONTACT NO | house holder signature | Site Engineer Sign | Remarks
1 | 2023-01-02 | J49 | J67 | 63 | 3.5 | 257947449849 | SAVITRI | KAMLESH
2 | 2023-01-02 | J49 | J67 | 63 | 4 | 542284816235 | RAJKUMAR | BHAGELU
3 | 2023-01-02 | J49 | J67 | 63 | 2 | 775358037282 | PARAS | Ramu
4 | 2023-01-02 | J59 | J88 | 63 | 5 | 679874190753 | AMAR NATH | Mothilal
5 | 2023-01-02 | J59 | J88 | 63 | 5 | 774482433349 | MITHAI LAL | ganga ram
6 | 2023-01-19 | J117 | J116 | 90 | 25 | 202397082666 | RANJEET SINGH | Somnath singh
7 | 2023-01-19 | J117 | J116 | 90 | 2.5 | 950504493464 | MOTILAL GUPTA | Mohanlal
8 | 2023-01-19 | J116 | J111 | 90 | 3 | 893683844043 | GAYATRI | Suraj lal
9 | 2023-01-19 | J116 | J111 | 90 | 4.5 | 295873040140 | OM PRAKESH | Ram sundar gupta
10 | 2023-01-19 | J116 | J111 | 90 | 7 | 957746818382 | VIMAL GUPTA | Hajarilal
11 | 2023-01-20 | J111 | J116 | 90 | 4.5 | 959464779553 | VARIS ALI | Miyahdi
12 | 2023-01-20 | J111 | J116 | 90 | 3 | 364278266576 | RUKHSANA | Abdul
13 | 2023-01-20 | J111 | J116 | 90 | 4.5 | 730798604761 | KUSUM | SUBHASH
14 | 2023-01-20 | J38 | J44 | 63 | 7 | 365575922881 | RAM MILIAN | Devdadin | 8419001854
15 | 2023-01-20 | J38 | J44 | 63 | 5 | 622724550931 | GAYATRI DEVI | Manna lal | 6307423448
16 | 2023-01-20 | J38 | J44 | 63 | 3 | 263374187126 | RAM KISHOR | Amarnath
17 | 2023-01-20 | J116 | J107 | 110 | 3 | 40809932358 | SHIVLAL MANGAL | Mangal | 9793359121
18 | 2023-01-21 | j111 | j114 | 63 | 5 | 640974893318 | GANAGA PRASAD PANDEY | Ram kumar | 9956549435
19 | 2023-01-21 | j111 | j114 | 63 | 7 | 504264629081 | SHYAM BIHARTI PANDEY | Ram kumar | 9140202234
20 | 2023-01-21 | j111 | j114 | 63 | 14 | 976963641156 | KRISHNAKANT PANDEY | Radhe shyam | 9452662047
21 | 2023-01-21 | j111 | j114 | 63 | 13 | 268570950742 | RADHESHYAM PANDEY | Ram kumar | 7518581685
22 | 2023-01-21 | j111 | j115 | 63 | 20 | 766697035079 | ASHOK KUMAR PANDEY | Ram kumar | 6390752424
23 | 2023-01-21 | j111 | j115 | 63 | 20 | 909878304489 | AKSHIKA PANDEY | Shyam vihari | 9956549435
24 | 2023-01-21 | j111 | j115 | 63 | 20 | 211662337677 | RAJESH PANDEY | Shyam vihari | 9140202234
25 | 2023-01-21 | j111 | j98 | 90 | 15 | 83774919209 | KAVITHA | Ramesh kumar | 7310879183
26 | 2023-01-21 | j111 | j116 | 90 | 5 | 385552548251 | JAMALUDIN | Miyahdi | 8795652464
27 | 2023-01-21 | j111 | j116 | 90 | 6 | 319674070243 | MR. AMIT | Miyahdi | 9891937849
28 | 2023-01-21 | j111 | j115 | 63 | 5 | 612595700162 | MUNNIPAL | Ram Asrai pal | 7317371361
29 | 2023-01-21 | j18 | j58 | 63 | 6 | 214293777474 | MOHAN PAL | Anand pal | 9839737827
30 | 2023-01-21 | j11 | j12 | 63 | 20 | 787196917633 | RAKESH PANDEY | Shyam vihari
31 | 2023-01-22 | J41 | J53 | 63 | 8 | 941682650376 | RAJESH VARAMA | Ram dhan verma | 9839215598
32 | 2023-01-22 | J35 | J83 | 110 | 7 | 598357886547 | VIDYA VARMA | Dayaram
33 | 2023-01-22 | J76 | J47 | 63 | 5 | 371451295414 | RAM LAKHAN VERMA | Ramadhar | 9792663381
34 | 2023-01-22 | J76 | J28 | 63 | 7 | 471488211653 | NIRAJ VERMA | Surjith verma | 6390060057
35 | 2023-01-22 | J76 | J28 | 63 | 9 | 226288632458 | RAM SUKH VERMA | Nanku verma | 6390060057
36 | 2023-01-22 | J76 | J47 | 63 | 5.5 | 333344228181 | KALURAM | Ram sumedh | 7408527938
37 | 2023-01-22 | J37 | J56 | 63 | 6 | 308631702446 | SUMITRA DEVI | Kamal | 7571947843
38 | 2023-01-22 | J58 | J18 | 63 | 3 | 791782908260 | RAM DULATI | Rama anugrahi
39 | 2023-01-22 | J37 | J56 | 63 | 5 | 994106219435 | PARAS NATH PAL | Ram raj | 9918013552
40 | 2023-01-22 | J58 | J18 | 63 | 2.5 | 569605819261 | Raju pal | Ram chandh pal | 7068493383
41 | 2023-01-22 | J18 | J34 | 63 | 5 | 351949198842 | KIRAN RAM AJOR | Ramajor | 9519765218
42 | 2023-01-22 | J18 | J34 | 63 | 5 | 537425376197 | Nirmala pal | Radhe shyam | 7521982864
43 | 2023-01-22 | J18 | J34 | 63 | 5 | 609013817508 | Kamlesh | Ram shankar | 7379459710
44 | 2023-01-22 | J18 | J34 | 63 | 5 | 463834610681 | Krishna Devi | Rajesh kumar | 7800632118
45 | 2023-01-22 | J34 | J37 | 63 | 6 | 845077254580 | Anara | Ram anandh pal | 7897984350
46 | 2023-01-22 | J35 | J65 | 63 | 2.5 | 853884080220 | Phool Chandra | Nageswar | 7526088655
47 | 2023-01-22 | J35 | J65 | 63 | 3 | 483093245280 | Mukesh Verma | Ramesh verma | 88655731013
48 | 2023-01-23 | J103 | J69 | 90 | 6 | 512436071538 | Manka Ram | Ram nihor | 9793785287
49 | 2023-01-23 | J74 | J97 | 90 | 4 | 989026186037 | Santhi | Satthdev yadav | 9721113801
50 | 2023-01-23 | J35 | J83 | 110 | 7 | 811288918411 | Indravati | Krishna pal | 7307662764
51 | 2023-01-23 | J97 | J62 | 110 | 6.5 | 878163957839 | Satya Narayan | Ram kilavan | 9792656168
52 | 2023-01-23 | J83 | J97 | 110 | 7.2 | 979240606310 | Shobha Yadav | Mothilala | 6387978191
53 | 2023-01-23 | J35 | J65 | 63 | 4 | 676557363238 | Rakesh Kumar Verma | Nageswar verma | 9936203367
54 | 2023-01-23 | J83 | J97 | 110 | 7.5 | 554505884962 | Sharda Devi | Jeeth lal | 9793726394
55 | 2023-01-23 | J35 | J83 | 110 | 3.2 | 240304249090 | Rajaram Verma | Ramlal | 8377922563
56 | 2023-01-23 | J97 | J74 | 90 | 5.5 | 997190513258 | Shakuntla | Dhaya sankar verma | 9918466460
57 | 2023-01-25 | J92 | J100 | 63 | 6 | 406262665670 | Barsati | Dhukathi ram | 7800062228
58 | 2023-01-25 | J92 | J100 | 63 | 6 | 890024837219 | Rajeev Kumar Saroj | Mahaveer | 9794341120
59 | 2023-01-25 | J100 | J102 | 63 | 6 | 748947454756 | Rajesh Kumar Saroj | Ram avilash | 9984197180
60 | 2023-01-27 | J102 | J109 | 63 | 4 | 642267459554 | Ramesh Kumar | Ram avadh
61 | 2023-01-28 | J33 | J51 | 63 | 4 | 583878853572 | Urmila Devi | Munna lal | 9628976818
62 | 2023-01-28 | J61 | J80 | 63 | 6 | 470767456240 | Hari Ram | Buddhu ram
63 | 2023-01-28 | J61 | J67 | 63 | 6 | 444493981149 | Ram Anand | Devatha deen | 8604806590
64 | 2023-01-30 | J83 | J108 | 63 | 5 | 452224351635 | Sunita Devi | Santhram | 9794341012
65 | 2023-01-30 | J83 | J108 | 63 | 4 | 249656632004 | Surendra Verma | Ram sajivan | 7310414574
66 | 2023-01-30 | J83 | J108 | 63 | 3 | 295859784061 | Shitla Prasad Verma | Ganga deen | 9289342481
67 | 2023-01-31 | J88 | J110 | 63 | 6 | 828175832536 | Asha Devi | Mitai lal | 8924939572
68 | 2023-01-31 | J61 | J67 | 63 | 1 | 632367287859 | Usha | Santhalal
69 | 2023-01-31 | J59 | J88 | 63 | 5 | 790148460564 | Shyama Devi | Swamy lal | 9711788329
70 | 2023-01-31 | J61 | J67 | 63 | 6 | 899756187513 | Vimila | Jhoku | 9565073956
71 | 2023-01-31 | J59 | J88 | 63 | 5 | 638877031579 | Meva Lal | Ganga ram | 7703929048
72 | 2023-02-01 | J88 | J81 | 75 | 1 | 759492352529 | Brhma Deen | Jaggu
73 | 2023-02-01 | J88 | J81 | 75 | 2 | 241379964717 | Kanhaiya Lal | Ram adhar | 837688124
74 | 2023-02-01 | J81 | J79 | 90 | 5 | 951861829615 | Sangeeta | Brijesh | 9565071725
75 | 2023-02-01 | J81 | J79 | 90 | 6 | 305611077435 | Ramesh Kumar | Raja ram | 9565110785
76 | 2023-02-01 | J88 | J81 | 75 | 2 | 756702107711 | Rajpati | Ram kishor | 6390060128
77 | 2023-02-01 | J88 | J81 | 75 | 3 | 215915036337 | Rampati Visvkarma | Ram kishor | 9838926573
78 | 2023-02-01 | J88 | J81 | 75 | 1 | 444076672460 | Jagannath Yadav | Nagai
79 | 2023-02-01 | J88 | J81 | 75 | 7 | 344188756716 | Parawati | Sunil | 7081552246
80 | 2023-02-02 | J88 | J81 | 75 | 6 | 491106830863 | Uday Raj | Nagai | 7236046119
81 | 2023-02-02 | J88 | J81 | 75 | 5 | 431612463669 | Sitaram | Ram naresh | 9161921860
82 | 2023-02-02 | J81 | J79 | 90 | 6 | 956995306454 | Pinky | Anil kumar
83 | 2023-02-02 | J81 | J79 | 90 | 6 | 836906189644 | Ram abhilash | Rampal | 6391631332
84 | 2023-02-03 | j79 | j81 | 90 | 6 | 209724356787 | shanti devi | Radhe shyam | 9670791630
85 | 2023-02-03 | J79 | J98 | 90 | 7 | 728226646002 | Suresh Kumar | Nankuram | 9517019122
86 | 2023-02-03 | J88 | J81 | 75 | 6 | 879657049342 | Suresh Kumar Yadav | Jagannath | 8127021946
87 | 2023-02-04 | J41 | J6 | 63 | 6 | 813857582589 | Lalti | Ramnath | 8090969758
88 | 2023-02-04 | J6 | J9 | 63 | 7 | 728764996005 | Jairaji | Dhan prasadh | 9554347292
89 | 2023-02-04 | J6 | J9 | 63 | 6 | 503453283515 | Meva Lal | Gangaram | 7081994051
90 | 2023-02-04 | J9 | J13 | 63 | 7 | 732391185127 | Shayam Shankar sharma | Raja ram | 9838257184
91 | 2023-02-04 | J60 | J31 | 75 | 10 | 330184480050 | Hariram Varma | Bhagavan deen | 9554496386
92 | 2023-02-04 | J60 | J31 | 75 | 5 | 861724015227 | Ramsundar Varma | Bhagavan deen | 8052367712
93 | 2023-02-04 | J60 | J31 | 75 | 6 | 482412088330 | Mithilesh Sharma | shyam lal sharma | 9129631257
94 | 2023-02-04 | J9 | J13 | 63 | 7 | 700636813475 | Pawan Kumar Sharma | Ganag prasadh | 9648150687
95 | 2023-02-04 | J9 | J13 | 63 | 14 | 947840598691 | Mukesh Yadav | Hanuman prasadh | 8956886492
96 | 2023-02-04 | J9 | J13 | 63 | 6 | 844698998442 | Rupa Devi | Ramesh kumar | 8956886492
97 | 2023-02-04 | J9 | J13 | 63 | 8 | 941418560789 | Anil Kumar Yadav | Paras nath | 8948346618
98 | 2023-02-04 | J9 | J13 | 63 | 7 | 388841726211 | Ranjana | Ram narayan | 9910189050
99 | 2023-02-10 | J104 | J94 | 110 | 3 | 561507230371 | Jeetlal | Ram tilavan | 9198022806
100 | 2023-02-10 | J69 | J103 | 90 | 3 | 665188452152 | Rajeev | Santhlal | 9794918741
101 | 2023-02-10 | J104 | J94 | 110 | 4 | 990382731953 | Radheshyam | Rampal | 9792487554
102 | 2023-02-10 | J69 | J76 | 63 | 5 | 634976292810 | Heeralal | Sri ram
103 | 2023-02-10 | J69 | J103 | 90 | 8 | 310946215110 | Bhullari | Ram devi
104 | 2023-02-10 | J104 | J94 | 110 | 4 | 303811262101 | Amritlal | Ram kilavan | 8081466301
105 | 2023-02-10 | J69 | J103 | 90 | 3 | 402000758022 | Rajmani | Jugul verma | 9628110685
106 | 2023-02-10 | J35 | J65 | 63 | 4 | 466252811060 | Phoolchand | Ram sumesh | 7740001697
107 | 2023-02-13 | J94 | J104 | 110 | 4 | 697311869587 | Lalti | Jeeth lal | 8052393765
108 | 2023-02-13 | J92 | J90 | 63 | 4 | 689192486785 | Mithilesh | Suraj lal | 8528495022
109 | 2023-02-13 | J77 | J106 | 90 | 5 | 615783914069 | HarishChandra | Ram Sumer | 8881953554
110 | 2023-02-13 | J104 | J755 | 140 | 6 | Mandhir
111 | 2023-02-13 | J17 | J23 | 63 | 8 | Mandhir
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) | [5 empty] | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION | [5 empty] | DESIGNATION
NAME |  |  |  | NAME | [5 empty] | NAME
SIGN.with date |  |  |  | SIGN.with date | [5 empty] | SIGN.with date
120