## suryagarh jagannath
GOVERNMENT OF UTTAR PRADESH
STATE WATER & SANITATION MISSION ( SWSM )
Joint Measurement Report of Pipe Line
Name of the Work :- Survey , Design Preparation of DPR , Construction , Commissioning and O&M for 10 Years of Various Rural Water Supply Projects in the state of Uttar Pradesh as Per Request for Proposal for Division " Prayagraj "
Name of the Agency : POWER MECH PROJECTS LIMITED – BHOORATHNOM CONSTRUCTIONS COMPANY PRIVATE LIMITED (JV), Hyderabad.
Name OF Scheme |  | : suryagarh jaganath
Block |  | : MANGRAURA
Total Scope |  | :
JMR No. |  | : 2
Date of JMR |  | :
Sr. No. | Start Node | End Node | Dia | Pipe Length (as per Site) | Excavation Width | Depth | Quantity | Type OF Road | Dismantling Length | Dismantling Width | Dismantling Quantity | Restoration Length | Restoration Width | Restoration Quantity | Restoration Status | Remark
1 | j189 | j181 | 63 | 311.8 | 0.363 | 1.063
2 | j181 | j182 | 75 | 102 | 0.375 | 1.075
3 | j61 | j115 | 90 | 199.4 | 0.39 | 1.09
4 | j65 | j62 | 110 | 176 | 0.41 | 1.11
5 | j62 | j53 | 110 | 92.1 | 0.41 | 1.11 |  | I.L
6 | J53 | J51 | 75 | 66.4 | 0.375 | 1.075
7 | J51 | J58 | 63 | 33 | 0.363 | 1.063
8 | J51 | J58 | 63 | 40 | 0.363 | 1.063 |  | BRICK ROAD
9 | J96 | J69 | 140 | 160.6 | 0.44 | 1.14 |  | I.L
10 | J69 | J70 | 63 | 44.8 | 0.363 | 1.063 |  | BRICK ROAD
11 | J69 | J67 | 140 | 27 | 0.44 | 1.14 |  | I.L
12 | J67 | J64 | 90 | 72 | 0.39 | 1.09 |  | I.L
13 | J64 | J49 | 90 | 57.7 | 0.39 | 1.09 |  | BRICK ROAD
14 | J49 | J29 | 90 | 53 | 0.39 | 1.09 |  | BRICK ROAD
15 | J49 | J29 | 90 | 14 | 0.39 | 1.09
16 | J49 | J29 | 90 | 31.5 | 0.39 | 1.09 |  | I.L
17 | J49 | J50 | 63 | 30 | 0.363 | 1.063
18 | J23 | J26 | 63 | 16 | 0.363 | 1.063 |  | I.L
19 | J23 | J26 | 63 | 150 | 0.363 | 1.063
20 | J13 | J14 | 140 | 40 | 0.44 | 1.14
21 | J13 | J67 | 140 | 143 | 0.44 | 1.14 |  | BRICK ROAD
22 | J67 | J102 | 90 | 725 | 0.39 | 1.09 |  | BRICK ROAD
23 | J67 | J102 | 90 | 13 | 0.39 | 1.09
24 | J103 | J102 | 63 | 44 | 0.363 | 1.063
25 | J102 | J113 | 63 | 120 | 0.363 | 1.063
26 | J102 | J107 | 75 | 14.1 | 0.375 | 1.075
27 | J107 | J108 | 63 | 95.2 | 0.363 | 1.063
28 | J107 | J114 | 63 | 70 | 0.363 | 1.063
29 | J114 | J112 | 63 | 83.1 | 0.363 | 1.063
30 | J107 | J109 | 63 | 150.1 | 0.363 | 1.063
31 | J114 | J144A | 63 | 182 | 0.363 | 1.063
32 | J114A | J114B | 63 | 97 | 0.363 | 1.063
33 | J114A | J112 | 63 | 298.9 | 0.363 | 1.063
34 | J119 | J121 | 63 | 68 | 0.363 | 1.063
35 | J121 | J245 | 63 | 25.9 | 0.363 | 1.063
36 | J121 | J120 | 63 | 95 | 0.363 | 1.063
37 | J121 | J120 | 63 | 65 | 0.363 | 1.063 |  | BRICK ROAD
38 | J32 | J10 | 75 | 335.1 | 0.375 | 1.075
39 | J9 | J10 | 110 | 90.5 | 0.41 | 1.11
40 | J9 | J1 | 140 | 360 | 0.44 | 1.14
41 | J9 | J13 | 140 | 25 | 0.44 | 1.14
42 | J9 | J13 | 140 | 66.1 | 0.44 | 1.14 |  | BRICK ROAD
43 | J115 | J118 | 75 | 530.1 | 0.375 | 1.075
44 | J119 | J119A | 63 | 50 | 0.363 | 1.063
45 | J119B | J119C | 63 | 110.7 | 0.363 | 1.063
46 | J61 | J57 | 63 | 145 | 0.363 | 1.063
47 | J60 | J59 | 63 | 18 | 0.363 | 1.063
48 | J60 | J59 | 63 | 48 | 0.363 | 1.063 |  | I.L
49 | J144 | J138 | 110 | 233.1 | 0.41 | 1.11
50 | J71 | J65 | 90 | 316 | 0.39 | 1.09
51 | J71 | J188 | 63 | 125.3 | 0.363 | 1.063
52 | J71 | J74 | 75 | 62 | 0.375 | 1.075
53 | J74 | J76 | 75 | 69 | 0.375 | 1.075
55 | J76 | J78 | 75 | 21 | 0.375 | 1.075
56 | J76 | J79 | 63 | 57 | 0.363 | 1.063 |  | I.L
57 | J79 | J80 | 63 | 49.3 | 0.363 | 1.063 |  | I.L
58 | J76 | J77 | 63 | 56 | 0.363 | 1.063
59 | J74 | J75 | 63 | 54 | 0.363 | 1.063
60 | J75 | J87 | 63 | 502 | 0.363 | 1.063
61 | J75 | J75A | 63 | 65 | 0.363 | 1.063
62 | J71 | J71A | 63 | 68.5 | 0.363 | 1.063
63 | J62 | J32 | 63 | 207 | 0.363 | 1.063
64 | J246 | J242 | 63 | 246.5 | 0.363 | 1.063 |  | BRICK ROAD
65 | J242 | J241 | 63 | 28.6 | 0.363 | 1.063 |  | I.L
66 | J242 | J241 | 63 | 33 | 0.363 | 1.063 |  | BRICK ROAD
67 | J241 | J241A | 63 | 18 | 0.363 | 1.063 |  | BRICK ROAD
68 | J241 | J241A | 63 | 4 | 0.363 | 1.063
69 | J241 | J240 | 63 | 87 | 0.363 | 1.063 |  | BRICK ROAD
70 | J240 | J240A | 63 | 14 | 0.363 | 1.063
71 | J240 | J237 | 63 | 46 | 0.363 | 1.063
72 | J237 | J231 | 63 | 35 | 0.363 | 1.063
73 | J231 | J229 | 63 | 84.2 | 0.363 | 1.063
74 | J231 | J229 | 63 | 16.6 | 0.363 | 1.063
75 | J231 | J229 | 63 | 4 | 0.363 | 1.063 |  | BRICK ROAD
76 | J228 | J226 | 63 | 99 | 0.363 | 1.063 |  | BRICK ROAD
77 | J226 | J227 | 63 | 47 | 0.363 | 1.063
78 | J229 | J228 | 63 | 13.4 | 0.363 | 1.063
79 | J228 | J220 | 63 | 158.3 | 0.363 | 1.063
80 | J220 | J221 | 63 | 59 | 0.363 | 1.063
81 | J220 | J218 | 63 | 55.4 | 0.363 | 1.063
82 | J218 | J213 | 63 | 120.8 | 0.363 | 1.063
83 | J218 | J219 | 75 | 112 | 0.375 | 1.075
84 | J219 | J222A | 75 | 77.7 | 0.375 | 1.075
85 | J219 | J230A | 63 | 164.5 | 0.363 | 1.063
86 | J230A | J230A | 75 | 40.7 | 0.375 | 1.075
87 | J230A | J231 | 63 | 91.7 | 0.363 | 1.063
88 | J230B | J231 | 75 | 50.1 | 0.375 | 1.075 |  | BRICK ROAD
89 | J230B | J231 | 75 | 56 | 0.375 | 1.075
90 | J177 | J179 | 63 | 87.1 | 0.363 | 1.063
91 | J179 | J180 | 63 | 77.9 | 0.363 | 1.063
92 | J179 | J178 | 63 | 160.3 | 0.363 | 1.063
93 | J170 | J171 | 63 | 126 | 0.363 | 1.063
94 | J208 | J115 | 90 | 437 | 0.39 | 1.09
95 | J190 | J206 | 63 | 105 | 0.363 | 1.063 |  | BRICK ROAD
96 | J190 | J206 | 63 | 138 | 0.363 | 1.063
97 | J190 | J206 | 63 | 43 | 0.363 | 1.063
98 | J204 | J205 | 63 | 6 | 0.363 | 1.063 |  | I.L CROSSING
99 | J204 | J205 | 63 | 103 | 0.363 | 1.063
100 | J123 | J135 | 110 | 87 | 0.41 | 1.11
101 | J135 | J148 | 90 | 388 | 0.39 | 1.09
102 | J138 | J135 | 110 | 233.6 | 0.41 | 1.11
103 | J123 | J124 | 90 | 76.6 | 0.39 | 1.09
104 | J124 | J129 | 90 | 100.2 | 0.39 | 1.09 |  | I.L
105 | J130 | J131 | 63 | 16.4 | 0.363 | 1.063 |  | I.L
106 | J131 | J132 | 90 | 20 | 0.39 | 1.09 |  | I.L
107 | J129 | J131 | 90 | 6 | 0.39 | 1.09
108 | J131 | J132 | 90 | 20 | 0.39 | 1.09
111 | J129 | J117 | 63 | 85 | 0.363 | 1.063
112 | J100 | J98 | 90 | 164 | 0.39 | 1.09
113 | J98 | J123 | 110 | 105.8 | 0.41 | 1.11
114 | J139 | J143 | 63 | 57 | 0.363 | 1.063 |  | I.L
115 | 138 | 139 | 90 | 93 | 0.39 | 1.09
116 | J139 | J137 | 90 | 52 | 0.39 | 1.09
117 | J137A | J137B | 63 | 42 | 0.363 | 1.063
118 | J137C | J137D | 63 | 25 | 0.363 | 1.063
119 | J132 | J140 | 75 | 38 | 0.375 | 1.075 |  | BRICK ROAD
120 | J140 | J152 | 75 | 67 | 0.375 | 1.075
121 | J152 | J152A | 63 | 75 | 0.363 | 1.063
122 | J152 | J159 | 63 | 9 | 0.363 | 1.063
123 | J152 | J159 | 63 | 34 | 0.363 | 1.063 |  | BRICK ROAD
124 | JJ159 | J158 | 63 | 37.6 | 0.363 | 1.063
125 | J159 | J159A | 63 | 16 | 0.363 | 1.063 |  | BRICK ROAD
126 | J159A | J159B | 63 | 43 | 0.363 | 1.063
127 | J159A | J162 | 63 | 27 | 0.363 | 1.063
128 | J162 | J166 | 63 | 72 | 0.363 | 1.063
129 | J162 | J163 | 63 | 40 | 0.363 | 1.063
130 | J162 | J164 | 63 | 4 | 0.363 | 1.063
131 | J164 | J165 | 63 | 30 | 0.363 | 1.063
132 | J164 | J169 | 63 | 74.4 | 0.363 | 1.063
133 | J169 | J181 | 75 | 218.5 | 0.375 | 1.075 |  | I.L
134 | J175 | J175A | 63 | 27 | 0.363 | 1.063
135 | J157 | J169 | 75 | 68 | 0.375 | 1.075 |  | I.L
136 | J157 | J152 | 75 | 30 | 0.375 | 1.075
137 | J157 | J153A | 63 | 80 | 0.363 | 1.063
138 | J153A | J153B | 63 | 41.4 | 0.363 | 1.063
139 | J153A | J154 | 63 | 203 | 0.363 | 1.063
140 | J154 | J155 | 63 | 44.7 | 0.363 | 1.063
141 | J154 | J156 | 63 | 130.1 | 0.363 | 1.063 |  | BRICK ROAD
13697.4
Representative PMPL - BRCCPL (JV) Pratapgarh | [6 empty] | Representative Medhaj Techno Concept Pvt Ltd (TPI) Pratapgarh |  |  |  |  | Representative UP Jal Nigam (Rural) Pratapgarh
|  | 63 | 75 | 90 | 110 | 125 | 140 | 160
|  | 7061.5 | 1957.7 | 2838.4 | 1018.1 | 0 | 821.7 | 0