## Sheet1 (2)
S.No | Block | Gram Panchayat | ACTUAL SCOPE | AS PER SITE(SITE &JMR) | JMR BALANCE | HYDRO TEST JMR | BALANCE | agency |  | PPIPE LINE COMPLETED | GAP CLOSING | FHTC |  | PIPE LINE AGENCY | OHT | BW | PH
[12 empty] | DPR | SITE
1 | Mangraura | 1. Amuwahi | 15451 | 14651.4 | 0 | 14651.4 | 799.6 | krishna powers and works( payment issue) |  | COMPLETED | 3 | 320 | 175 | KRISHNA TRIPATI | Not Yet started | Not Yet started | Not Yet started
2 | Mangraura | 1.ATRASAND 2.PARSUPUR | 68790 | 52156.45 |  | 52156.45 | 16633.55 | pr enterprises(left)-15792,khayathi enterprises(left)-19126,ags construction-17525(payment issue),ak enterprises(left)-16260 |  | (WIP)BALANCE | 10,VALVES PENDING | 1666 | 909 | AGS,KAYATHI,AK ENTERPRISES,PR ENTER | Bottom Dome WIP | 140mtr Super structure WIP | Upto slab done
3 | Mangraura | Aurangabad | 22366 | 20175.9 | 0 | 20175.9 | 2190.1 | tanish projects(payment issues) |  | COMPLETED | 2,VALVES CHAMBER | 568 | 192 | TANISH ENTERPRISES | Upto Full staging Completd | 118mtr upto plastering completed | Upto slab done
4 | Mangraura | Barasarai | 23048 | 18833.4 | 0 |  | 4214.6 | AGS CONSTRUCTION(PAYMENT ISSUE) |  | COMPLETED | VALVES PENDING | 538 | 265 | AGS CONSTRUCTION | Not Yet started | 120mtr upto painting done | upto painting done
5 | Mangraura | Barhupur | 24894 | 24314.1 | 0 | 24314.1 | 579.9 | tanish projects(payment issues) |  | COMPLETED | 3,VALVES CHAMBER | 859 | 474 | TANISH ENTERPRISES | Not Yet started | TW-02 70mtr upto platering completed | upto painting done
6 | Mangraura | Bhaedpur | 12750 | 12398.1 | 0 | 12398.1 | 351.9 | SHUKLA CONSTRUCTION(ACTIVE) |  | COMPLETED | VALVES CHAMBER | 356 | 150 | SHUKLA CONSTRUCTION | Not Yet started | Not Yet started | Not Yet started
7 | Mangraura | Bhausiya | 19729 | 16834.1 | 0 | 16834.1 | 2894.9 | SUMIRAN ENTERPRISES(ACTIVE) |  | COMPLETED | VALVES PENDING | 442 | 404 | SUMIRAN ENTERPRISES | Slab completed | Not Yet started | Not Yet started
8 | Mangraura | Choumari | 17656 | 17372.2 | 0 | 17372.2 | 283.8 | MAHADEV ENTERPRISES(PAYMENT ISSUE) |  | COMPLETED | VALVES PENDING | 429 | 192 | MAHADEV ENTERPRISES | Slab completed | Not Yet started | Not Yet started
9 | Mangraura | 1. Darchut | 13800 | 7610 | 7610 |  | 6190 | ROHIT ENTERPRISES(LEFT) |  | BALANCE | 15,VALVES PENDING | 485 | 152 | ROHIT ENTERPRISES | Upto half staging WIP | Not Yet started | Not Yet started
10 | Mangraura | 1. Dehridigar | 19854 | 12154.9 |  | 12154.9 | 7699.1 | tanish projects(payment issues) |  | (WIP)BALANCE | 3,VALVES CHAMBER | 368 | 63 | TANISH ENTERPRISES | Slab & Stair case completed | 107mtr upto super structure done plastering WIP | Not Yet started
11 | Mangraura | Dhraulimufrid,Chanduadih | 21320 | 15757.3 | 2769 | 12988 | 5562.7 | ROHIT ENTERPRISES(LEFT)/14780 | RUDRA ENTERPRISES(TOO MUCH SLOW PROGRESS)/6871 | (WIP)BALANCE | 8,VALVES PENDING | 500 | 171 | ROHIT ENTERPRISES,RUDRA ENTERPRISES | Gl brace WIP | Not Yet started | Not Yet started
12 | Mangraura | Gehrauli | 14296 | 13553 | 0 | 13553 | 743 | OM ENTERPRISES(LEFT) |  | COMPLETED | VALVES PENDING | 553 | 250 | OM ENTERPRISES | Upto Full staging Completd | 80mtr upto plastering completed | Upto plastering done
13 | Mangraura | HARDOI | 8526 | 8054.4 | 0 | - | 471.6 | RAMPRABAV CONSTRUCTION(ACTIVE) |  | COMPLETED | VALVES PENDING | 577 | 150 | UNITY INFRA,RAMPRABAV | completed | 103mtr upto painting Completed | Upto painting done
14 | Mangraura | Hathsara | 24211 | 20731.1 | 0 | 20731.1 | 3479.9 | MADHAV REDDY (ACTIVE) |  | COMPLETED | VALVES CHAMBER | 404 | 400 | MADHAV REDDY CONSTRUCTIONS | Not Yet started | Not Yet started | Not Yet started
15 | Mangraura | Itwa(B2B) | 27655 | 0 |  |  | 27655 | MECH TOOLS B2B |  |  |  | 0 | 0 |  | Bore fail | Bore fail | Bore fail
16 | Mangraura | Kansapatti | 12300 | 12440.9 | 0 | 12440.9 | -140.9 | SHUKLA CONSTRUCTION(ACTIVE) |  | COMPLETED | VALVES CHAMBER | 390 | 134 | SHUKLA CONSTRUCTION | Slab completed | Not Yet started | Not Yet started
17 | Mangraura | 1.KONI 2.SALAHIPUR KANJAS | 52702 | 20237 | 20237 |  | 32465 | RUDRA ENTERPRISES(TOO MUCH SLOW PROGRESS) |  | (WIP)BALANCE | 20,VALVES PENDING | 1255 | 180 | RUDRA ENTERPRISES | Not Yet started | Not Yet started | Not Yet started
18 | Mangraura | 1. Lauli Pokhtakham | 25451 | 23620.9 | 0 | 23620.9 | 1830.1 | SHUKLA CONSTRUCTION(ACTIVE) |  | COMPLETED | VALVES CHAMBER | 619 | 260 | SHUKLA CONSTRUCTION | Slab completed | 120mtr upto Brick work done | Upto Super structure done
19 | Mangraura | MADURA RANIGANJ & SARAULI | 57778 | 52638.7 | 0 | 52638.7 | 5139.3 | tanish projects(payment issues),AGS CONSTRUCTION(PAYMENT ISSUE) | tanish-36500,ags-21278 | (WIP)BALANCE | 5,VALVES PENDING | 1131 | 480 | TANISH ENTERPRISES,AGS CONSTRUCTION | Bottom Dome completed and stair case WIP | TW-01 90mtr Upto plastering done and TW-02 60mtr Super structure done | TW-01 Upto plastering done and TW-02Upto Super structure done
20 | Mangraura | Malaak | 20705 | 17855.5 | 0 | 17855.5 | 2849.5 | SHUKLA CONSTRUCTION(ACTIVE) |  | COMPLETED | VALVES CHAMBER | 562 | 266 | SHUKLA CONSTRUCTION | slab completed and stair case WIP | Not Yet started | Not Yet started
21 | Mangraura | Mandah, Bojhi | 18915 | 13826 | 0 | - | 5089 | tanish projects(payment issues) |  | (WIP)BALANCE | 3,VALVES PENDING | 423 | 200 | TANISH,RAGHU CO ,MAMA CONSTRUCTION | Slab Erection WIP | 78mtr Upto painting done | upto painting done
22 | Mangraura | Mangraura | 18508 | 16317.3 | 0 | - | 2190.7 | RAMPRABAV CONSTRUCTION(ACTIVE) |  | (WIP)BALANCE | 10,VALVES PENDING | 534 | 300 | UNITY INFRA ,RAMPRABAV CONTRACTOR | completed | 137mtr upto painting done | upto painting done
23 | Mangraura | 1. Nevra(B2B) | 13711 | 0 |  |  | 13711 | MECHTOOLS B2B | [6 empty] | Bore fail | Bore fail | Bore fail
24 | Mangraura | Padumpur | 13834 | 11825 | 0 | 11825 | 2009 | MAA SHARDHA CONSTRUCTION(LEFT) |  | COMPLETED | 2 | 390 | 91 | MAA SHARDHA CONSTRUCTION | Gl brace beam WIP | Not Yet started | Not Yet started
25 | Mangraura | Parsanda | 17220 | 7083.9 | 0 | 7083.9 | 10136.1 | SHUKLA CONSTRUCTION(ACTIVE) |  | BALANCE | VALVES PENDING | 248 | 30 | SHUKLA CONSTRUCTION | Slab Erection WIP | Not Yet started | Not Yet started
26 | Mangraura | Purebhikha & Raigarh | 29373 | 26265.5 | 0 | 26265.5 | 3107.5 | tanish projects(payment issues) |  | COMPLETED | 2,VALVES CHAMBER | 507 | 303 | TANISH ENTERPRISES | Slab and Stair case Completed and Zink tank erection WIP | Not Yet started | Not Yet started
27 | Mangraura | 1. Puremanikanth | 11769 | 9732.3 | 0 | 9732.3 | 2036.7 | SHUKLA CONSTRUCTION(ACTIVE) |  | COMPLETED | VALVES CHAMBER | 367 | 235 | SHUKLA CONSTRUCTION | Not Yet started | Not Yet started | Not Yet started
28 | Mangraura | Sakra | 19922 | 17330 | 1596 | 15734 | 2592 | SUMIRAN ENTERPRISES(ACTIVE)(WORK ORDER ISSUE) |  | BALANCE | 2,VALVES PENDING | 624 | 295 | HARIKA INFRA,SUMIRAN ENTERPRISES | Slab & Stair case and Zink tank completed | 112mtr upto painting done | upto painting done
29 | Mangraura | Sarayjmuvari | 30140 | 14770 | 6365.4 | 6365.4 | 15370 | KHAYATHI AND AZADI ENTERPRISES(LEFT) |  | BALANCE | 12,VALVES PENDING | 839 | 67 | KHAYATHI AND AZADI ENTERPRISES | completed | 116 mtr upto painting done | upto painting done
30 | Mangraura | Sheshapur Adharganj | 13374 | 13311.5 | 0 |  | 62.5 | RAMPRABAV CONSTRUCTION(ACTIVE) |  | COMPLETED | VALVES CHAMBER | 385 | 285 | RAMPRABAV CONSTRUCTION,PR ENTERPRISES | completed | 120mtr Upto painting done | upto painting done
31 | Mangraura | 1. Shivpur khurd | 10338 | 9045.6 | 0 | 9045.6 | 1292.4 | SHUKLA CONSTRUCTION(ACTIVE) |  | COMPLETED | VALVES CHAMBER | 272 | 168 | SHUKLA CONSTRUCTION | Slab Completed | Not Yet started | Not Yet started
32 | Mangraura | Sirsidih | 16189 | 10980.6 | 0 | 10980.6 | 5208.4 | DEEP CONSTRUCTION(WORK ORDER ISSUE) |  | BALANCE | 3,VALVES PENDING | 310 | 515 |  | Upto Full staging Completd | 92mtr upto painting done | upto painting done
33 | Mangraura | 1. Suryagarhjagannath | 20625 | 14366 | 14366 | - | 6259 | RAMPRABAV CONSTRUCTION(ACTIVE) |  | (WIP)BALANCE | 10,VALVES PENDING | 499 | 153 | RAMPRABAV CONSTRUCTION,PR ENTERPRISES | Upto half staging WIP | 130mtr upto painting done | upto painting done
34 | Mangraura | Utras | 31839 | 28338.5 | 0 | - | 3500.5 | RAMPRABAV CONSTRUCTION(ACTIVE) |  | (WIP)BALANCE | 3,VALVES PENDING | 564 | 160 | RAMPRABAV CONSTRUCTION | Slab Completed | Not Yet started | Not Yet started
TOTAL |  |  | 769039 | 574581.55 | 52943.4 | 420917.55 | 194457.45 |  |  |  |  | 17984 | 8069
Note on H5: 12km is in land disputes and the balance 04 KM is DI pipeline.
Note on H13: Out of 7.66KM we can execute only 01KM of Pipeline and the balance pipline was executed by Jalnigam .