## AMUVAHI
AMUWAHI(JMR) BLOCK-MANGRAURA
Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | Dia of pipe(MM) | Pipe Length (M) | CUMMULATIVE | Depth(M) | REMARK
1 | J1 | J2 |  |  | 110 | 384.4 | 384.4 | 1.11
2 | J2 | J5 |  |  | 63 | 97.9 | 482.3 | 1.06 |  |  |  | 700
3 | J5 | J4 | B.T. ROAD | 0.36 | 63 | 3.1 | 485.4 | 1.06 | Crossing
4 | J5 | J4 |  |  | 63 | 26.2 | 511.6 | 1.06
5 | J8 | J7 |  |  | 63 | 113.4 | 625 | 1.06
6 | J7 | J2 |  |  | 63 | 6.6 | 631.6 | 1.06
7 | J7 | J2 |  |  | 63 | 8.6 | 640.2 | 1.06 | CULVERT
8 | J7 | J2 |  |  | 63 | 110.9 | 751.1 | 1.06
9 | J7 | J12 |  |  | 63 | 206.4 | 957.5 | 1.06
10 | J7 | J14 |  |  | 63 | 442.4 | 1399.9 | 1.06
11 | J14 | J15 |  |  | 63 | 43 | 1442.9 | 1.06
12 | J14 | J16 |  |  | 63 | 76.5 | 1519.4 | 1.06
13 | J14 | J16 | B.T. ROAD | 0.36 | 63 | 3.8 | 1523.2 | 1.06 | Crossing
14 | J16 | J17 | Brick road | 0.46 | 63 | 5.8 | 1529 | 1.06
15 | J16 | J17 |  |  | 63 | 137.3 | 1666.3 | 1.06
16 | J16 | J17 | Brick road | 0.46 | 63 | 5.9 | 1672.2 | 1.06 | Crossing
17 | J16 | J17 |  |  | 63 | 34.8 | 1707 | 1.06
18 | J16 | J18 |  |  | 63 | 255.3 | 1962.3 | 1.06
19 | J5 | J21 |  |  | 63 | 287.1 | 2249.4 | 1.06
20 | J21 | J20 | B.T. ROAD | 0.36 | 63 | 3.2 | 2252.6 | 1.06 | Crossing
21 | J21 | J20 |  |  | 63 | 37.8 | 2290.4 | 1.06
22 | J21 | J23 |  |  | 63 | 181.4 | 2471.8 | 1.06
23 | J21 | J23 | Interlocking | 0.46 | 63 | 4.6 | 2476.4 | 1.06 | Crossing
24 | J23 | J24 |  |  | 63 | 53.1 | 2529.5 | 1.06
25 | J23 | J26 |  |  | 63 | 45.2 | 2574.7 | 1.06
26 | J23 | J26 | Brick road | 0.46 | 63 | 21.9 | 2596.6 | 1.06
27 | J26 | J27 | B.T. ROAD | 0.36 | 63 | 4.9 | 2601.5 | 1.06 | Crossing
28 | J5 | J6 |  |  | 63 | 84.9 | 2686.4 | 1.06
29 | J26 | J27 |  |  | 63 | 52 | 2738.4 | 1.06
30 | J26 | J40 |  |  | 63 | 48.9 | 2787.3 | 1.06
31 | J26 | J40 | Brick road | 0.46 | 63 | 15.8 | 2803.1 | 1.06
32 | J40 | J41 |  |  | 63 | 98.7 | 2901.8 | 1.06
33 | J40 | J52 |  |  | 63 | 12.9 | 2914.7 | 1.06
34 | J40 | J52 | Brick road | 0.46 | 63 | 17.4 | 2932.1 | 1.06
35 | J40 | J52 |  |  | 63 | 8.6 | 2940.7 | 1.06
36 | J40 | J52 | Brick road | 0.46 | 63 | 4.9 | 2945.6 | 1.06 | Crossing
37 | J52 | J53 | Brick road | 0.46 | 63 | 44.3 | 2989.9 | 1.06
38 | J52 | J52A | Brick road | 0.46 | 63 | 15.2 | 3005.1 | 1.06
39 | J52A | J52B |  |  | 63 | 61.6 | 3066.7 | 1.06
40 | J52A | J73 | Brick road | 0.46 | 63 | 22.9 | 3089.6 | 1.06
41 | J52A | J73 |  |  | 63 | 73 | 3162.6 | 1.06
42 | J52A | J73 | B.T. ROAD | 0.36 | 63 | 3.7 | 3166.3 | 1.06 | Crossing
43 | J73 | J74 |  |  | 63 | 96.3 | 3262.6 | 1.06
44 | J73 | J77 |  |  | 63 | 137 | 3399.6 | 1.06
45 | J77 | J79 |  |  | 63 | 217.4 | 3617 | 1.06
46 | J99 | J104 |  |  | 63 | 429.7 | 4046.7 | 1.06
47 | J99 | J104 | Brick road | 0.46 | 63 | 79.5 | 4126.2 | 1.06
48 | J104 | J103 | Brick road | 0.46 | 63 | 216.6 | 4342.8 | 1.06
49 | J103 | J99 |  |  | 63 | 277.1 | 4619.9 | 1.06
50 | J77 | J80 |  |  | 63 | 136.4 | 4756.3 | 1.06
51 | J80 | J89 |  |  | 63 | 120.4 | 4876.7 | 1.06
52 | J90 | J103 | Brick road | 0.46 | 63 | 240 | 5116.7 | 1.06
53 | J104 | J122 | Brick road | 0.46 | 63 | 4.5 | 5121.2 | 1.06 | Crossing
54 | J104 | J122 | Brick road | 0.46 | 63 | 212.6 | 5333.8 | 1.06
55 | J122 | J123 |  |  | 63 | 81 | 5414.8 | 1.06
56 | J122 | J126 | Brick road | 0.46 | 63 | 219.5 | 5634.3 | 1.06
57 | J122 | J126 |  |  | 63 | 147.9 | 5782.2 | 1.06
58 | J126 | J127 |  |  | 63 | 136.2 | 5918.4 | 1.06
59 | J126 | J120 |  |  | 63 | 345 | 6263.4 | 1.06
60 | J120 | J121 |  |  | 63 | 73 | 6336.4 | 1.06
61 | J120 | J105 |  |  | 63 | 151.6 | 6488 | 1.06
62 | j90 | j89 |  |  | 63 | 22.5 | 6510.5 | 1.06
63 | j90 | j91 |  |  | 63 | 108.8 | 6619.3 | 1.06
64 | j91 | j98 |  |  | 63 | 152.8 | 6772.1 | 1.06
65 | j98 | j105 |  |  | 63 | 265.1 | 7037.2 | 1.06
66 | j98 | j105 | INTERLOCKING | 0.36 | 63 | 5.7 | 7042.9 | 1.06
67 | j116 | j117 |  |  | 63 | 25.6 | 7068.5 | 1.06
68 | j105 | j114 |  |  | 63 | 265.6 | 7334.1 | 1.06
69 | j114 | j113 | B.T ROAD | 0.36 | 63 | 3.5 | 7337.6 | 1.06
70 | j114 | j113 |  |  | 63 | 291.5 | 7629.1 | 1.06
71 | j114 | j113 | BRICK ROAD | 0.36 | 63 | 67.5 | 7696.6 | 1.06
72 | J113 | J115 | BRICK ROAD | 0.36 | 63 | 75.7 | 7772.3 | 1.06
73 | J113 | J111 | BRICK ROAD | 0.36 | 63 | 97.1 | 7869.4 | 1.06
74 | J111 | J110 | BRICK ROAD | 0.36 | 63 | 24.1 | 7893.5 | 1.06
75 | J111 | J108 | BRICK ROAD | 0.36 | 63 | 43.7 | 7937.2 | 1.06
76 | J108 | J109 |  |  | 63 | 78.9 | 8016.1 | 1.06
77 | J108 | J106 | BRICK ROAD | 0.36 | 63 | 22.1 | 8038.2 | 1.06
78 | J108 | J106 |  |  | 63 | 17.1 | 8055.3 | 1.06
79 | J106 | J107 |  |  | 63 | 14.5 | 8069.8 | 1.06
80 | J106 | J101 |  |  | 63 | 143.7 | 8213.5 | 1.06
81 | J106 | J107 | INTERLOCKING | 0.36 | 63 | 23.8 | 8237.3 | 1.06
82 | J106 | J101 | INTERLOCKING | 0.36 | 63 | 23.4 | 8260.7 | 1.06
83 | J106 | J101 | INTERLOCKING | 0.36 | 63 | 106.7 | 8367.4 | 1.06
84 | J101 | J100 |  |  | 63 | 17.7 | 8385.1 | 1.06
85 | J101 | J100 | BRICK ROAD | 0.36 | 63 | 64.7 | 8449.8 | 1.06
86 | J101 | J100 | INTERLOCKING | 0.36 | 63 | 11.1 | 8460.9 | 1.06
87 | J101 | J100 | BRICK ROAD | 0.36 | 63 | 27.7 | 8488.6 | 1.06
88 | J101 | J100 | INTERLOCKING | 0.36 | 63 | 18.4 | 8507 | 1.06
89 | J100 | J105 |  |  | 63 | 235.3 | 8742.3 | 1.06
90 | J101 | J92 |  |  | 63 | 93.5 | 8835.8 | 1.06
91 | J92 | J93 |  |  | 63 | 228.7 | 9064.5 | 1.06
92 | J92 | J72A | BRICK ROAD | 0.36 | 63 | 110.4 | 9174.9 | 1.06
93 | J92 | J72A |  |  | 63 | 129.2 | 9304.1 | 1.06
94 | J72A | J72B |  |  | 63 | 35.7 | 9339.8 | 1.06
95 | J72A | J72B | BRICK ROAD | 0.36 | 63 | 49.4 | 9389.2 | 1.06
96 | J72A | J100 |  |  | 63 | 92.5 | 9481.7 | 1.06
97 | J100 | J72 |  |  | 63 | 263.1 | 9744.8 | 1.06
98 | J72A | J64 | BRICK ROAD | 0.36 | 63 | 18 | 9762.8 | 1.06
99 | J64 | J65 | BRICK ROAD | 0.36 | 63 | 15.5 | 9778.3 | 1.06
100 | J65 | J66 | BRICK ROAD | 0.36 | 63 | 13.6 | 9791.9 | 1.06
101 | J65 | J66 |  |  | 63 | 11.6 | 9803.5 | 1.06
102 | J65 | J67 | BRICK ROAD | 0.36 | 63 | 46.4 | 9849.9 | 1.06
103 | J67 | J68 | BRICK ROAD | 0.36 | 63 | 26.9 | 9876.8 | 1.06
104 | J67 | J68 |  |  | 63 | 21.4 | 9898.2 | 1.06
105 | J67 | J70 | BRICK ROAD | 0.36 | 63 | 39.7 | 9937.9 | 1.06
106 | J67 | J70 |  |  | 63 | 58.2 | 9996.1 | 1.06
107 | J64 | J61 | BRICK ROAD | 0.36 | 63 | 42.4 | 10038.5 | 1.06
108 | J61 | J59 | BRICK ROAD | 0.36 | 63 | 53.7 | 10092.2 | 1.06
109 | J59 | J60 |  |  | 63 | 47.6 | 10139.8 | 1.06
110 | J59 | J57 | BRICK ROAD | 0.36 | 63 | 118.5 | 10258.3 | 1.06
111 | J57 | J58 |  |  | 63 | 127.6 | 10385.9 | 1.06
112 | J57 | J55 | BRICK ROAD | 0.36 | 63 | 286 | 10671.9 | 1.06
113 | J55 | J56 |  |  | 63 | 229.3 | 10901.2 | 1.06
114 | J55 | J44 |  |  | 63 | 178.3 | 11079.5 | 1.06
115 | J44 | J45 |  |  | 63 | 148.4 | 11227.9 | 1.06
116 | J44 | J45 | BRICK ROAD | 0.36 | 63 | 142 | 11369.9 | 1.06
117 | J49 | J37 | INTERLOCKING | 0.36 | 63 | 10.4 | 11380.3 | 1.06
118 | J49 | J61 |  |  | 63 | 75.7 | 11456 | 1.06
119 | J49 | J61 | BRICK ROAD | 0.36 | 63 | 3.2 | 11459.2 | 1.06
120 | J34 | J49 | BRICK ROAD | 0.36 | 63 | 35.3 | 11494.5 | 1.06
121 | J28 | J35 |  |  | 63 | 58.2 | 11552.7 | 1.06
122 | J35 | J36 | B.T ROAD | 0.36 | 63 | 4 | 11556.7 | 1.06
123 | J35 | J36 |  |  | 63 | 69 | 11625.7 | 1.06
124 | J35 | J44A |  |  | 63 | 75.7 | 11701.4 | 1.06
125 | J44A | J44 |  |  | 63 | 83.2 | 11784.6 | 1.06
126 | J71 | J84 |  |  | 63 | 155.8 | 11940.4 | 1.06
127 | J84 | 87 |  |  | 63 | 50.1 | 11990.5 | 1.06
128 | J87 | 91 |  |  | 63 | 108.1 | 12098.6 | 1.06
129 | J87 | 91 | B.T ROAD | 0.36 | 63 | 4.5 | 12103.1 | 1.06
130 | J90 | J90A | B.T ROAD | 0.36 | 63 | 4 | 12107.1 | 1.06
131 | J90 | J90A | INTERLOCKING | 0.36 | 63 | 51 | 12158.1 | 1.06
132 | J86 | J85 |  |  | 63 | 52.4 | 12210.5 | 1.06
133 | J86 | J85 | INTERLOCKING | 0.36 | 63 | 2.8 | 12213.3 | 1.06
134 | J85 | J89 | INTERLOCKING | 0.36 | 63 | 30.3 | 12243.6 | 1.06
135 | J83 | J85 | INTERLOCKING | 0.36 | 63 | 32.6 | 12276.2 | 1.06
136 | J83 | J78 | INTERLOCKING | 0.36 | 63 | 57.3 | 12333.5 | 1.06
137 | J83 | J78 |  |  | 63 | 2.2 | 12335.7 | 1.06
138 | J83 | J78 | BRICK ROAD | 0.36 | 63 | 46.9 | 12382.6 | 1.06
139 | J83 | J78 |  |  | 63 | 138.5 | 12521.1 | 1.06
140 | J78 | J71 | BRICK ROAD | 0.36 | 63 | 234.5 | 12755.6 | 1.06
141 | J29 | J30 | B.T ROAD | 0.36 | 63 | 4.8 | 12760.4 | 1.06
142 | J29 | J30 | BRICK ROAD | 0.36 | 63 | 9 | 12769.4 | 1.06
143 | J30 | J32 | BRICK ROAD | 0.36 | 63 | 107 | 12876.4 | 1.06
144 | J32 | J33 | BRICK ROAD | 0.36 | 63 | 16.6 | 12893 | 1.06
145 | J31 | J32 | BRICK ROAD | 0.36 | 63 | 8.4 | 12901.4 | 1.06
146 | J30 | J37 | BRICK ROAD | 0.36 | 63 | 44.6 | 12946 | 1.06
147 | J3 | J10 | BRICK ROAD | 0.36 | 63 | 82.5 | 13028.5 | 1.06
148 | J3 | J10 |  |  | 63 | 24.3 | 13052.8 | 1.06
149 | J3 | J10 | BRICK ROAD | 0.36 | 63 | 31 | 13083.8 | 1.06
150 | J87 | J88 | BRICK ROAD | 0.36 | 63 | 49.5 | 13133.3 | 1.06
151 | J84 | J94 | B.T ROAD | 0.36 | 63 | 4 | 13137.3 | 1.06
152 | J84 | J94 |  |  | 63 | 151.7 | 13289 | 1.06
153 | J94 | J95 |  |  | 63 | 39.9 | 13328.9 | 1.06
154 | J95 | J96 |  |  | 63 | 10 | 13338.9 | 1.06
155 | J95 | J97 |  |  | 63 | 173 | 13511.9 | 1.06
156 | J97 | J94 |  |  | 63 | 75.3 | 13587.2 | 1.06
157 | J97 | J98 |  |  | 63 | 60.6 | 13647.8 | 1.06
158 | J97 | J98 | B.T ROAD | 0.36 | 63 | 4 | 13651.8 | 1.06
159 | J45 | J49 | BRICK ROAD | 0.36 | 75 | 38.6 | 13690.4 | 1.07
160 | J45 | J49 | BR/I.L | 0.36 | 75 | 41.1 | 13731.5 | 1.07
161 | J49 | J61 | INTERLOCKING | 0.36 | 75 | 4 | 13735.5 | 1.07
162 | J49 | J61 |  |  | 75 | 34.7 | 13770.2 | 1.07
163 | J45 | J34 | BRICK ROAD | 0.36 | 75 | 56.1 | 13826.3 | 1.07
164 | J45 | J34 |  |  | 75 | 91.3 | 13917.6 | 1.07
165 | J38 | J71 |  |  | 75 | 34.2 | 13951.8 | 1.07 |  |  |  | 164.3
166 | J34 | J28 | BRICK ROAD | 0.36 | 90 | 79 | 14030.8 | 1.09
167 | J34 | J28 | B.T ROAD | 0.36 | 90 | 3.1 | 14033.9 | 1.09
168 | J28 | J23 |  |  | 90 | 34.6 | 14068.5 | 1.09
169 | J28 | J23 | BRICK ROAD | 0.36 | 90 | 3.1 | 14071.6 | 1.09
170 | J25 | J29 |  |  | 90 | 60.3 | 14131.9 | 1.09
171 | J29 | J38 |  |  | 90 | 19.9 | 14151.8 | 1.09
172 | J25 | J3 | BRICK ROAD | 0.36 | 110 | 242 | 14393.8 | 1.11
173 | J3 | J1 |  |  | 110 | 73.6 | 14467.4 | 1.11
| 63 | 75 | 90 | 110
| 13267.4 | 300 | 200 | 700 | 14467.4
Abstract (Bill Breakup)
1 | Dia of Pipe | WO/DPR Qty's | Laying, Jointing, Backfilling - 60% |  |  |  | Gap Closing- 5% |  |  |  | Hydro Test - 15% |  |  |  | FHTC Stretch - 10%
|  |  | Laying Up to Date | Laying Qty Billed up to Date | Qty Billed Up to Previous | This Bill Qty (Laying) | WO/DPR Qty's | GAP Closing Billed Qty up to Date | GAP Closing Qty Up to Previous | This Bill Qty (GAP Closing) | WO/DPR Qty's | Hydro Test Qty Billed up to Date | Hydro Test Qty Up to Previous | This Bill Qty (Hydro Test ) | FHTC Stretch Qty Billed up to Date | FHTC Stretch Qty Billed Up to Previous | This Bill Qty (FHTC Stretch Billed )
1.1 | 63 mm HDPE | 14095 | 13267.4 | 13267.4 | 11794 | 1473.4 | 14095 |  | 6088 | -
1.2 | 75 mm HDPE | 413 | 300 | 300 |  | 300 | 413 |  |  | -
1.3 | 90 mm HDPE | 222 | 200 | 200 |  | 200 | 222 |  |  | -
1.4 | 110mm HDPE | 682 | 700 | 700.8 | 388 | 312 | 682 |  |  | -
1.5 | 125mm HDPE | [8 empty] | -
1.6 | 140mm HDPE | [8 empty] | -
1.7 | 160mm HDPE | [8 empty] | -
1.8 | 180mm HDPE | [8 empty] | -
1.9 | 200mm HDPE | [8 empty] | -
Sub Total = |  | 15412 | 14467.4 | 14468.2 | 12182 | 2285.4 | 15412 |  | 6088
Sub-Contractor Site Engineer (Sr.Eng/ DY.M-SMX ) (Dy.M-PMX ) AGM Project Incharge
161

## Recon Sheet
POWER MECH PROJECTS.LIMITED | [11 empty] | FHTC
RURAL WATER SUPPLY PROJECT UNDER JJM, UP - PRAYAGRAJ
Reconciliation Statement - Issued Vs Certification Qty.
| Contractor Name-KRISHNA POWER |  | MONTH: | march | Block: | MANGRAURA
| ABC Limited |  | BILL NO: |  | GP: | AMUVAHI
Sl NO | Description | Units |  |  |  |  | Balance Qty | SAP Entry | Remarks | Upto date Consumption
|  |  | Total Issued Qty | Cumulative Consumption | Upto Pre Consumed Qty | This Bill Consumed Qty |  |  |  | GP | GP | GP | GP | Total Consumption upto This Bill |  | Entry Qty
A | HDPE Pipe :- | [8 empty] | BLOCK | BLOCK | BLOCK | BLOCK
1 | HDPE PIPE-63MM,PN-6,CLASS:PE-100,IS:4984 | Rmt | 13607 | 13267.4 | 11794 | 1473.4 |  | 4474 | [5 empty] | 0 | 1200000251 | -11794
2 | HDPE PIPE-75MM,PN-6,CLASS:PE-100 | Rmt | 300 | 300 |  | 300 | [7 empty] | 0 | 1200000332 | 0
3 | HDPE PIPE-90MM,PN-6,CLASS:PE-100 | Rmt | 200 | 200 |  | 200 | [7 empty] | 0 | 1200000333 | 0
4 | HDPE PIPE-110MM,PN-6,CLASS:PE-100 | Rmt | 700 | 700 | 388 | 312 | [7 empty] | 0 | 1200000334 | -388
5 | HDPE PIPE-125MM,PN-6,CLASS:PE-100,IS4984 | Rmt | [11 empty] | 0 | 1200000252 | 0
6 | HDPE PIPE-140MM,PN-6,CLASS:PE-100,IS4984 | Rmt | [11 empty] | 0 | 1200000253 | 0
7 | HDPE PIPE-160MM,PN-6,CLASS:PE-100 | Rmt | [11 empty] | 0 | 1200000335 | 0
8 | HDPE PIPE-200MM,PN-6,CLASS:PE-100,IS4984 | Rmt | [11 empty] | 0 | 1200000255 | 0
9 | DI PIPE-Ø200MM , K7,IS:8329 | Rmt | [11 empty] | 0 | 900007097 | 0
10 | HDPE PIPE-250MM,PN-6,CLASS:PE-100,IS4984 | Rmt | [11 empty] | 0 | 1200000256 | 0
| Total Qty In ( Rmt ) = |  | 14807 |  |  | 2285.4
B | Specials :-
| Equal Tee | [12 empty] | 0 |  | 0
1 | HDPE-63X63X63MM,PN-6,R-TEE,CLASS:PE-100 | Nos | 50 | 49 |  | 18 |  | 4474 | [5 empty] | 0 | 200030286 | 0
2 | HDPE-75X75X75MM,PN-6,R-TEE,CLASS:PE-100 | Nos | [11 empty] | 0 | 200030287 | 0
3 | HDPE-90X90X90MM,PN-6,R-TEE,CLASS:PE-100 | Nos | 5 | 4 |  | 4 | [7 empty] | 0 | 200030288 | 0
4 | HDPE-110X110X110MM,PN-6,R-TEE,CL:PE-100 | Nos | 3 | 3 |  | 3 | [7 empty] | 0 | 200030289 | 0
5 | HDPE 125mm X 125mm X 125mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032212 | 0
6 | HDPE-140X140X140MM,PN-6,R-TEE,CL:PE-100 | Nos | [11 empty] | 0 | 200030291 | 0
7 | HDPE-160X160X160MM,PN-6,R-TEE,CL:PE-100 | Nos | [11 empty] | 0 | 200030293 | 0
8 | HDPE 200X200X200 MM, PN-6, R-TEE, CLASS: | Nos | [11 empty] | 0 | 200030300 | 0
| Total Qty In ( Rmt ) = |  | 58
C | Branch TEE | [14 empty] | 0
1 | HDPE BRANCH TEE 63MM X 63MM X 50MM | Nos | 0 |  |  |  |  | 4474 | [5 empty] | 0 | 200032593 | 0
2 | HDPE 75MM X 75MM X 50MM PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032575 | 0
3 | HDPE 75mm X 75mm X 63mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032202 | 0
4 | HDPE 90mm X 90mm X 50mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032233 | 0
5 | HDPE 90mm X 90mm X 63mm, PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032203 | 0
6 | HDPE 90mm X 90mm X 75mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032204 | 0
7 | HDPE 110mm X 110mm X 50mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032234 | 0
8 | HDPE 110mm X 110mm X 63mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032205 | 0
9 | HDPE 110mm X 110mm X 75mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032206 | 0
10 | HDPE 110mm X 110mm X 90mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032207 | 0
11 | HDPE 125mm X 125mm X 50mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032235 | 0
12 | HDPE 125mm X 125mm X 63mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032208 | 0
13 | HDPE 125mm X 125mm X 75mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032209 | 0
14 | HDPE 125mm X 125mm X 90mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032210 | 0
15 | HDPE 125mm X 125mm X 110mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032211 | 0
16 | HDPE Branch TEE 140mm X 140mm X 50mm | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032236 | 0
17 | HDPE 140mm X 140mm X 63mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032213 | 0
18 | HDPE 140mm X 140mm X 75mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032214 | 0
19 | HDPE 140mm X 140mm X 110mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032215 | 0
20 | HDPE Branch TEE 140mm X 140mm X 125mm | Nos | [11 empty] | 0 | 200032216 | 0
21 | HDPE-140X90X140MM,PN-6,R-TEE,CL:PE-100 | Nos | [11 empty] | 0 | 200030290 | 0
22 | HDPE 160mm X 160mm X 50mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032237 | 0
23 | HDPE 160mm X 160mm X 63mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032217 | 0
24 | HDPE 160mm X 160mm X 75mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032218 | 0
25 | HDPE 160mm X 160mm X 90mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032219 | 0
26 | HDPE-160X110X160MM,PN-6,R-TEE,CL:PE-100 | Nos | [11 empty] | 0 | 200030292 | 0
27 | HDPE 160mm X 160mm X 125mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032220 | 0
28 | HDPE 200mm X 200mm X 63mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032222 | 0
29 | HDPE 200X75X200 MM, PN-6, R-TEE, CLASS:P | Nos | [11 empty] | 0 | 200030297 | 0
30 | HDPE 200X90X200 MM, PN-6, R-TEE, CLASS:P | Nos | [11 empty] | 0 | 200030298 | 0
31 | HDPE 200mm X 200mm X 110mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032223 | 0
32 | HDPE 200mm X 200mm X 160mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032225 | 0
33 | HDPE 250mm X 250mm X 90mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032228 | 0
| Total Qty In ( Rmt ) = |  | 0
D | 4 Way Tee | [14 empty] | 0
1 | HDPE 63MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030301 | 0
2 | HDPE 75MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [11 empty] | 0 | 200030302 | 0
3 | HDPE 90MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030303 | 0
4 | HDPE 110MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [11 empty] | 0 | 200030304 | 0
5 | HDPE125MM,PN6,4WAY CROSS FITTING,CLPE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032584 | 0
6 | HDPE 140MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [11 empty] | 0 | 200030305 | 0
7 | HDPE 160MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030306 | 0
8 | HDPE200MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [11 empty] | 0 | 200030308 | 0
Total Qty In ( No's ) =
E | Reducers
1 | HDPE-75MM,PN6, 63MM,ENLARGER,CLASS:PE100 | Nos | 15 | 8 |  | 8 |  | 4474 | [5 empty] | 0 | 200030309 | 0
2 | HDPE-90MM,PN6, 63MM,ENLARGER,CLASS:PE100 | Nos | 10 | 4 |  | 4 | [7 empty] | 0 | 200030311 | 0
3 | HDPE-90MM,PN6, 75MM,ENLARGER,CLASS:PE100 | Nos | [11 empty] | 0 | 200030310 | 0
4 | HDPE-110MM,PN6,63MM,ENLARGER,CLASS:PE100 | Nos | 9 | 3 |  | 3 |  | 4474 | [5 empty] | 0 | 200030314 | 0
5 | HDPE-110MM,PN6,75MM,ENLARGER,CLASS:PE100 | Nos | 4 | [10 empty] | 0 | 200030312 | 0
6 | HDPE-110MM,PN6,90MM,ENLARGER,CLASS:PE100 | Nos | 6 | 2 |  | 2 | [7 empty] | 0 | 200030313 | 0
7 | HDPE-125MM,PN6, 63MM Reducer PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032241 | 0
8 | HDPE-125MM,PN6, 75MM Reducer PE100 | Nos | [11 empty] | 0 | 200032239 | 0
9 | HDPE-125MM,PN6, 90MM Reducer PE100 | Nos | [11 empty] | 0 | 200032240 | 0
10 | HDPE-125MM,PN6, 110MM Reducer PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032242 | 0
11 | HDPE-140MM,PN6,63MM,ENLARGER,CL:PE100 | Nos | [11 empty] | 0 | 200030320 | 0
12 | HDPE-140MM,PN6, 75MM Reducer PE100 | Nos | [11 empty] | 0 | 200032243 | 0
13 | HDPE-140MM,PN6,90MM,ENLARGER,CL:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030317 | 0
14 | HDPE-140MM,PN6,110MM,ENLARGER,CL:PE100 | Nos | [11 empty] | 0 | 200030315 | 0
15 | HDPE-140MM,PN6,125MM,ENLARGER,CL:PE100 | Nos | [11 empty] | 0 | 200030316 | 0
16 | HDPE-160MM,PN6,63MM Reducer PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032247 | 0
17 | HDPE-160MM,PN6,75MM Reducer PE100 | Nos | [11 empty] | 0 | 200032246 | 0
18 | HDPE-160MM,PN6,90MM Reducer PE100 | Nos | [11 empty] | 0 | 200032245 | 0
19 | HDPE-160MM,PN6,110MM,ENLARGER,CL:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030319 | 0
20 | HDPE-160MM,PN6, 125MM Reducer PE100 | Nos | [11 empty] | 0 | 200032244 | 0
21 | HDPE-160MM,PN6,140MM,ENLARGER,CL:PE100 | Nos | [11 empty] | 0 | 200030318 | 0
22 | HDPE-200MM,PN6,75MM Reducer PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032249 | 0
23 | HDPE-200MM,PN6,90MM,ENLARGER,CLASS:PE100 | Nos | [11 empty] | 0 | 200030326 | 0
24 | HDPE-200MM,PN6,110MM Reducer PE100 | Nos | [11 empty] | 0 | 200032248 | 0
25 | HDPE-200MM,PN6,140MM,ENLARGER,CL:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030325 | 0
26 | HDPE-200MM,PN6,160MM,ENLARGER,CL:PE100 | Nos | [11 empty] | 0 | 200030328 | 0
27 | HDPE-200MM,PN6,63MM,ENLARGER,CLASS:PE100 | Nos | [11 empty] | 0 | 200030327 | 0
28 | HDPE Reducer 200mm X 125mm | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200034192 | 0
Total Qty In ( No's ) =
F | Bends 45 Degree
1 | HDPE BEND-63MM,PN6 45DEG PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032193 | 0
2 | HDPE BEND-90MM, PN6 45DEG PE100 | Nos | [11 empty] | 0 | 200032195 | 0
3 | HDPE BEND-110MM, PN6 45DEG PE100 | Nos | [11 empty] | 0 | 200032196 | 0
4 | HDPE BEND-75MM,PN6 45DEG PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032194 | 0
5 | HDPE BEND-125MM,PN-6,90DEG,CLASS:PE-100 | Nos | [11 empty] | 0 | 200030270 | 0
6 | HDPE BEND-125MM, PN6 45DEG PE100 | Nos | [11 empty] | 0 | 200032197 | 0
7 | HDPE BEND-140MM,PN-6,45DEG,CLASS:PE-100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030275 | 0
8 | HDPE BEND-160MM,PN-6,45DEG,CLASS:PE-100 | Nos | [11 empty] | 0 | 200030276 | 0
Total Qty In ( No's ) =
G | Bends 90Degree
1 | HDPE BEND-63MM,PN-6,90DEG,CLASS:PE-100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030266 | 0
2 | HDPE BEND-75MM,PN-6,90DEG,CLASS:PE-100 | Nos | [11 empty] | 0 | 200030267 | 0
3 | HDPE BEND-90MM,PN-6,90DEG,CLASS:PE-100 | Nos | [11 empty] | 0 | 200030268 | 0
4 | HDPE BEND-110MM,PN-6,90DEG,CLASS:PE-100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030269 | 0
5 | HDPE BEND-140MM,PN-6,90DEG,CLASS:PE-100 | Nos | [11 empty] | 0 | 200030271 | 0
6 | HDPE BEND-160MM,PN-6,90DEG,CLASS:PE-100 | Nos | [11 empty] | 0 | 200030272 | 0
7 | HDPE BEND-200MM,PN-6,90DEG,CLASS:PE-100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030274 | 0
Total Qty In ( No's ) =
H | End Caps
1 | HDPE-63MM,PN6,END CAP,CLASS:PE100 | Nos | 50 | 39 |  | 39 |  | 4474 | [5 empty] | 0 | 200030277 | 0
2 | HDPE-75MM,PN6,END CAP,CLASS:PE100 | Nos | [11 empty] | 0 | 200030278 | 0
3 | HDPE-90MM,PN6,END CAP,CLASS:PE100 | Nos | [11 empty] | 0 | 200030279 | 0
4 | HDPE-110MM,PN6,END CAP,CLASS:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030280 | 0
5 | HDPE-140MM,PN6,END CAP,CLASS:PE100 | Nos | [11 empty] | 0 | 200030282 | 0
Total Qty In ( No's ) =
1 | FHTC
1 | GI PIPE-15MM | Rmt | [5 empty] | 4474 |  | 0 | 0 |  |  | 0 | 1200000409 | 0
2 | MDPE PIPE-20MM | Rmt | [7 empty] | 0 | 0 |  |  | 0 | 1200000408 | 0
3 | BRASS TAP | Nos | [5 empty] | 4474 |  | 0 | 0 |  |  | 0 | 1200000231 | 0
4 | PP CLAMP SADLLE-63MM | Nos | [7 empty] | 0 |  |  |  | 0 | 1200000410 | 0
5 | PP CLAMP SADDLE-75MM | Nos | [11 empty] | 0 | 1200000425 | 0
6 | PP CLAMP SADLLE-90MM | Nos | [5 empty] | 4474 | [5 empty] | 0 | 1200000411 | 0
7 | PP CLAMP SADDLE-140MM | Nos | [11 empty] | 0 | 900008156 | 0
8 | PP CLAMP SADDLE-160MM | Nos | [11 empty] | 0 | 900008157 | 0
9 | PP CLAMP SADDLE-200MM | Nos | [5 empty] | 4474 | [5 empty] | 0 | 900008159 | 0
10 | PP CLAMP SADDLE 125MM WITH M8 FASTNERS | Nos | [11 empty] | 0 | 900008617 | 0
11 | PP CLAMP SADLLE-110MM | Nos | [11 empty] | 0 | 900007416 | 0
12 | G.I ELBOW 15 MM | Nos | [7 empty] | 0 | 0 |  |  | 0 | 1200000419 | 0
13 | GI SOCKET-15MM | Nos | [7 empty] | 0 | 0 |  |  | 0 | 1200000416 | 0
14 | WALL MOUNT SADDLE GI PIPE-15MM | Nos | [5 empty] | 4474 | [5 empty] | 0 | 1200000418 | 0
15 | 15MM GI NIPPLE - 0.3MTR LENGTH | Nos | [7 empty] | 0 | 0 |  |  | 0 | 1200000450 | 0
16 | 15MM GI NIPPLE - 0.5MTR LENGTH | Nos | [7 empty] | 0 | 0 |  |  | 0 | 1200000451 | 0
17 | 20MM MDPE COMPRESSION ELBOW | Nos | [7 empty] | 0 | 0 |  |  | 0 | 1200000448 | 0
18 | SS FLOW CONTROL VAlVE | Nos | [5 empty] | 4474 |  | 0 | 0 |  |  | 0 | 1200000417 | 0
19 | MDPE FEMLE THREADED ASSEMBLY-20MM | Nos | [7 empty] | 0 | 0 |  |  | 0 | 1200000414 | 0
20 | MDPE ELBOW-20MM | Nos | [11 empty] | 0 | 1200000415 | 0
21 | TEFLAN TAPE | Nos |  |  |  | 0 | 0 | [6 empty] | 0 | 200001364 | 0
22 | [6 empty] | 0 | [6 empty] | 0 | #N/A | 0
Total Qty In ( No's ) =
Sub Contractor Site Engineer Block incharge AGM DM PMX Project Incharge
ENTRY NO:

## Details
POWER MECH PROJECTS.LIMITED | [10 empty] | FHTC
RURAL WATER SUPPLY PROJECT UNDER JJM, UP - PRAYAGRAJ
Reconciliation Statement - Issued Vs Certification Qty.
| Contractor Name-KRISHNA POWER |  | MONTH: | march | Block: | MANGRAURA
| ABC Limited |  | BILL NO: |  | GP: | AMUVAHI
Sl NO | Description | Units | Consumption Details (Node/Junction) |  |  |  | Total Consumed upto Date | Remarks | Upto date Consumption
[9 empty] | GP | GP | GP | GP | Total Consumption upto This Bill |  | Entry Qty
B | Specials :-
| Equal Tee | [11 empty] | 0 |  | 0
1 | HDPE-63X63X63MM,PN-6,R-TEE,CLASS:PE-100 | Nos | j55,54,35,45,57,59,65,67,72a,30,32,78,113,111,108,106,101,92,100,98,97,94,95,84,87,91,90,89,85,83,116,126,120,122,104,103,99,90,73,52a,52,40,26,23,21,5,7,14,16 |  |  |  | 49 | [5 empty] | 0 | 200030286 | 0
2 | HDPE-75X75X75MM,PN-6,R-TEE,CLASS:PE-100 | Nos | j71,37,49,61,64,72 |  |  |  | 6 | [5 empty] | 0 | 200030287 | 0
3 | HDPE-90X90X90MM,PN-6,R-TEE,CLASS:PE-100 | Nos | j28,34,29,38 |  |  |  | 4 | [5 empty] | 0 | 200030288 | 0
4 | HDPE-110X110X110MM,PN-6,R-TEE,CL:PE-100 | Nos | j2,25,3 |  |  |  | 3 | [5 empty] | 0 | 200030289 | 0
5 | HDPE 125mm X 125mm X 125mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032212 | 0
6 | HDPE-140X140X140MM,PN-6,R-TEE,CL:PE-100 | Nos | [10 empty] | 0 | 200030291 | 0
7 | HDPE-160X160X160MM,PN-6,R-TEE,CL:PE-100 | Nos | [10 empty] | 0 | 200030293 | 0
8 | HDPE 200X200X200 MM, PN-6, R-TEE, CLASS: | Nos | [10 empty] | 0 | 200030300 | 0
C | Branch TEE | [13 empty] | 0
1 | HDPE BRANCH TEE 63MM X 63MM X 50MM | Nos | [10 empty] | 0 | 200032593 | 0
2 | HDPE 75MM X 75MM X 50MM PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032575 | 0
3 | HDPE 75mm X 75mm X 63mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032202 | 0
4 | HDPE 90mm X 90mm X 50mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032233 | 0
5 | HDPE 90mm X 90mm X 63mm, PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032203 | 0
6 | HDPE 90mm X 90mm X 75mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032204 | 0
7 | HDPE 110mm X 110mm X 50mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032234 | 0
8 | HDPE 110mm X 110mm X 63mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032205 | 0
9 | HDPE 110mm X 110mm X 75mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032206 | 0
10 | HDPE 110mm X 110mm X 90mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032207 | 0
11 | HDPE 125mm X 125mm X 50mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032235 | 0
12 | HDPE 125mm X 125mm X 63mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032208 | 0
13 | HDPE 125mm X 125mm X 75mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032209 | 0
14 | HDPE 125mm X 125mm X 90mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032210 | 0
15 | HDPE 125mm X 125mm X 110mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032211 | 0
16 | HDPE Branch TEE 140mm X 140mm X 50mm | Nos | [10 empty] | 0 | 200032236 | 0
17 | HDPE 140mm X 140mm X 63mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032213 | 0
18 | HDPE 140mm X 140mm X 75mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032214 | 0
19 | HDPE 140mm X 140mm X 110mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032215 | 0
20 | HDPE Branch TEE 140mm X 140mm X 125mm | Nos | [10 empty] | 0 | 200032216 | 0
21 | HDPE-140X90X140MM,PN-6,R-TEE,CL:PE-100 | Nos | [10 empty] | 0 | 200030290 | 0
22 | HDPE 160mm X 160mm X 50mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032237 | 0
23 | HDPE 160mm X 160mm X 63mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032217 | 0
24 | HDPE 160mm X 160mm X 75mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032218 | 0
25 | HDPE 160mm X 160mm X 90mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032219 | 0
26 | HDPE-160X110X160MM,PN-6,R-TEE,CL:PE-100 | Nos | [10 empty] | 0 | 200030292 | 0
27 | HDPE 160mm X 160mm X 125mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032220 | 0
28 | HDPE 200mm X 200mm X 63mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032222 | 0
29 | HDPE 200X75X200 MM, PN-6, R-TEE, CLASS:P | Nos | [10 empty] | 0 | 200030297 | 0
30 | HDPE 200X90X200 MM, PN-6, R-TEE, CLASS:P | Nos | [10 empty] | 0 | 200030298 | 0
31 | HDPE 200mm X 200mm X 110mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032223 | 0
32 | HDPE 200mm X 200mm X 160mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032225 | 0
33 | HDPE 250mm X 250mm X 90mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032228 | 0
D | 4 Way Tee | [13 empty] | 0
1 | HDPE 63MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [10 empty] | 0 | 200030301 | 0
2 | HDPE 75MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [10 empty] | 0 | 200030302 | 0
3 | HDPE 90MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [10 empty] | 0 | 200030303 | 0
4 | HDPE 110MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [10 empty] | 0 | 200030304 | 0
5 | HDPE125MM,PN6,4WAY CROSS FITTING,CLPE100 | Nos | [10 empty] | 0 | 200032584 | 0
6 | HDPE 140MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [10 empty] | 0 | 200030305 | 0
7 | HDPE 160MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [10 empty] | 0 | 200030306 | 0
8 | HDPE200MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [10 empty] | 0 | 200030308 | 0
E | Reducers
1 | HDPE-75MM,PN6, 63MM,ENLARGER,CLASS:PE100 | Nos | j71,71(1),37,49,61,64,72,72(1) |  |  |  | 8 | [5 empty] | 0 | 200030309 | 0
2 | HDPE-90MM,PN6, 63MM,ENLARGER,CLASS:PE100 | Nos | j28,34,29,38 |  |  |  | 4 | [5 empty] | 0 | 200030311 | 0
3 | HDPE-90MM,PN6, 75MM,ENLARGER,CLASS:PE100 | Nos | [10 empty] | 0 | 200030310 | 0
4 | HDPE-110MM,PN6,63MM,ENLARGER,CLASS:PE100 | Nos | j2,2,3 |  |  |  | 3 | [5 empty] | 0 | 200030314 | 0
5 | HDPE-110MM,PN6,75MM,ENLARGER,CLASS:PE100 | Nos | [10 empty] | 0 | 200030312 | 0
6 | HDPE-110MM,PN6,90MM,ENLARGER,CLASS:PE100 | Nos | j25,25(1) |  |  |  | 2 | [5 empty] | 0 | 200030313 | 0
7 | HDPE-125MM,PN6, 63MM Reducer PE100 | Nos | [10 empty] | 0 | 200032241 | 0
8 | HDPE-125MM,PN6, 75MM Reducer PE100 | Nos | [10 empty] | 0 | 200032239 | 0
9 | HDPE-125MM,PN6, 90MM Reducer PE100 | Nos | [10 empty] | 0 | 200032240 | 0
10 | HDPE-125MM,PN6, 110MM Reducer PE100 | Nos | [10 empty] | 0 | 200032242 | 0
11 | HDPE-140MM,PN6,63MM,ENLARGER,CL:PE100 | Nos | [10 empty] | 0 | 200030320 | 0
12 | HDPE-140MM,PN6, 75MM Reducer PE100 | Nos | [10 empty] | 0 | 200032243 | 0
13 | HDPE-140MM,PN6,90MM,ENLARGER,CL:PE100 | Nos | [10 empty] | 0 | 200030317 | 0
14 | HDPE-140MM,PN6,110MM,ENLARGER,CL:PE100 | Nos | [10 empty] | 0 | 200030315 | 0
15 | HDPE-140MM,PN6,125MM,ENLARGER,CL:PE100 | Nos | [10 empty] | 0 | 200030316 | 0
16 | HDPE-160MM,PN6,63MM Reducer PE100 | Nos | [10 empty] | 0 | 200032247 | 0
17 | HDPE-160MM,PN6,75MM Reducer PE100 | Nos | [10 empty] | 0 | 200032246 | 0
18 | HDPE-160MM,PN6,90MM Reducer PE100 | Nos | [10 empty] | 0 | 200032245 | 0
19 | HDPE-160MM,PN6,110MM,ENLARGER,CL:PE100 | Nos | [10 empty] | 0 | 200030319 | 0
20 | HDPE-160MM,PN6, 125MM Reducer PE100 | Nos | [10 empty] | 0 | 200032244 | 0
21 | HDPE-160MM,PN6,140MM,ENLARGER,CL:PE100 | Nos | [10 empty] | 0 | 200030318 | 0
22 | HDPE-200MM,PN6,75MM Reducer PE100 | Nos | [10 empty] | 0 | 200032249 | 0
23 | HDPE-200MM,PN6,90MM,ENLARGER,CLASS:PE100 | Nos | [10 empty] | 0 | 200030326 | 0
24 | HDPE-200MM,PN6,110MM Reducer PE100 | Nos | [10 empty] | 0 | 200032248 | 0
25 | HDPE-200MM,PN6,140MM,ENLARGER,CL:PE100 | Nos | [10 empty] | 0 | 200030325 | 0
26 | HDPE-200MM,PN6,160MM,ENLARGER,CL:PE100 | Nos | [10 empty] | 0 | 200030328 | 0
27 | HDPE-200MM,PN6,63MM,ENLARGER,CLASS:PE100 | Nos | [10 empty] | 0 | 200030327 | 0
28 | HDPE Reducer 200mm X 125mm | Nos | [10 empty] | 0 | 200034192 | 0
F | Bends 45 Degree
1 | HDPE BEND-63MM,PN6 45DEG PE100 | Nos | [10 empty] | 0 | 200032193 | 0
2 | HDPE BEND-90MM, PN6 45DEG PE100 | Nos | [10 empty] | 0 | 200032195 | 0
3 | HDPE BEND-110MM, PN6 45DEG PE100 | Nos | [10 empty] | 0 | 200032196 | 0
4 | HDPE BEND-75MM,PN6 45DEG PE100 | Nos | [10 empty] | 0 | 200032194 | 0
5 | HDPE BEND-125MM,PN-6,90DEG,CLASS:PE-100 | Nos | [10 empty] | 0 | 200030270 | 0
6 | HDPE BEND-125MM, PN6 45DEG PE100 | Nos | [10 empty] | 0 | 200032197 | 0
7 | HDPE BEND-140MM,PN-6,45DEG,CLASS:PE-100 | Nos | [10 empty] | 0 | 200030275 | 0
8 | HDPE BEND-160MM,PN-6,45DEG,CLASS:PE-100 | Nos | [10 empty] | 0 | 200030276 | 0
G | Bends 90Degree
1 | HDPE BEND-63MM,PN-6,90DEG,CLASS:PE-100 | Nos | [10 empty] | 0 | 200030266 | 0
2 | HDPE BEND-75MM,PN-6,90DEG,CLASS:PE-100 | Nos | [10 empty] | 0 | 200030267 | 0
3 | HDPE BEND-90MM,PN-6,90DEG,CLASS:PE-100 | Nos | [10 empty] | 0 | 200030268 | 0
4 | HDPE BEND-110MM,PN-6,90DEG,CLASS:PE-100 | Nos | [10 empty] | 0 | 200030269 | 0
5 | HDPE BEND-140MM,PN-6,90DEG,CLASS:PE-100 | Nos | [10 empty] | 0 | 200030271 | 0
6 | HDPE BEND-160MM,PN-6,90DEG,CLASS:PE-100 | Nos | [10 empty] | 0 | 200030272 | 0
7 | HDPE BEND-200MM,PN-6,90DEG,CLASS:PE-100 | Nos | [10 empty] | 0 | 200030274 | 0
H | End Caps
1 | HDPE-63MM,PN6,END CAP,CLASS:PE100 | Nos | j50,58,60,93,72(b),66,68,70,31,33,36,10,115,110,109,107,96,88,90(a),86,117,127,121,123,74,52(b),53,41,27,24,20,4,6,8,12,15,18,17,99 |  |  |  | 39 | [5 empty] | 0 | 200030277 | 0
2 | HDPE-75MM,PN6,END CAP,CLASS:PE100 | Nos | [10 empty] | 0 | 200030278 | 0
3 | HDPE-90MM,PN6,END CAP,CLASS:PE100 | Nos | [10 empty] | 0 | 200030279 | 0
4 | HDPE-110MM,PN6,END CAP,CLASS:PE100 | Nos | [10 empty] | 0 | 200030280 | 0
5 | HDPE-140MM,PN6,END CAP,CLASS:PE100 | Nos | [10 empty] | 0 | 200030282 | 0
Sub Contractor Site Engineer Block incharge AGM DM PMX Project Incharge
ENTRY NO: