## aurangabad HT
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | AURANGABAD | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | 137 | 138 | 63 | 92.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
2 | 137 | 128 | 75 | 142.8 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
3 | 137 | 128 | 75 | 11.7 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
4 | 128 | 135 | 63 | 121.9 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
5 | 128 | 135 | 63 | 37 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
6 | 135a | 135b | 63 | 55.4 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
7 | 135a | 135b | 63 | 6 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
8 | 136 | 135 | 63 | 134 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
9 | 135 | 130 | 63 | 40.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
10 | 130 | 132 | 63 | 84.5 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
11 | 130a | 130b | 63 | 61.4 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
12 | 130 | 126 | 63 | 50.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
13 | 130 | 126 | 63 | 28.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
14 | 130 | 126 | 63 | 148.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
15 | 128 | 126 | 75 | 20 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
16 | 128 | 126 | 75 | 19.7 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
17 | 128 | 126 | 75 | 88.4 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
18 | 126 | 56 | 75 | 2.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
19 | 126 | 56 | 75 | 128.5 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
20 | 126 | 56 | 75 | 7 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
21 | 56 | 38 | 160 | 298.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
22 | 56 | 122 | 160 | 91.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
23 | 56 | 122 | 160 | 56.9 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
24 | 56 | 122 | 160 | 76.4 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
25 | 56 | 122 | 160 | 4.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
26 | 122 | 124 | 160 | 6 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
27 | 122 | 124 | 160 | 170 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
28 | 124 | 125 | 63 | 92.6 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
29 | 124 | 124a | 160 | 14.9 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
30 | 124a | 143 | 160 | 174.3 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
31 | 124a | 124b | 63 | 39.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
32 | 143 | 142 | 63 | 200.5 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
33 | 143 | 145 | 160 | 113 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
34 | 143 | 145 | 160 | 5.9 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
35 | 146 | 145 | 160 | 7.6 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
36 | 145 | 144 | 75 | 230.6 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
37 | 145 | 144 | 75 | 9.8 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
38 | 144 | 149 | 140 | 298.6 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | AURANGABAD | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | 144 | 149 | 140 | 63.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
2 | 149 | 154 | 140 | 6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
3 | 149 | 154 | 140 | 152.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
4 | 149 | 154 | 140 | 14.7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
5 | 154 | 164 | 110 | 91.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
6 | 154 | 164 | 110 | 140 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
7 | 164 | 166 | 160 | 68.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
8 | 164 | 166 | 160 | 31 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
9 | 166 | 166a | 75 | 20 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
10 | 166a | 170 | 75 | 276 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
11 | 170 | 172 | 75 | 92.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
12 | 172 | 166 | 160 | 128.7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
13 | 166a | 167 | 75 | 29.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
14 | 164 | 160 | 160 | 100.9 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
15 | 154 | 160 | 63 | 110.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
16 | 154 | 160 | 63 | 92.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
17 | 154 | 153 | 140 | 51 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
18 | 153 | 158 | 160 | 292.9 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
19 | 153 | 146 | 160 | 214.9 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
20 | 144 | 122 | 140 | 47 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
21 | 144 | 122 | 140 | 6.8 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
22 | 144 | 122 | 140 | 192 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
23 | 144 | 122 | 140 | 8 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
24 | 144 | 122 | 140 | 80.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
25 | 224 | 228 | 90 | 53.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
26 | 228 | 231 | 90 | 10.8 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
27 | 228 | 225 | 63 | 3.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
28 | 228 | 225 | 63 | 89.4 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
29 | 231 | 232 | 63 | 59.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
30 | 231 | 233 | 63 | 162.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
31 | 225 | 228 | 90 | 5.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
32 | 224 | 227 | 90 | 51.7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
33 | 227 | 227a | 63 | 22.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
34 | 227 | 230 | 90 | 103.4 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
35 | 230 | 230a | 90 | 45.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
36 | 230 | 226 | 90 | 62.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
37 | 226 | 229 | 63 | 175.9 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | AURANGABAD | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | 230 | 236 | 90 | 177.4 | 5.5 | 3.3 | 1 | 4.3 | no
2 | 236 | 239 | 63 | 204.7 | 5.5 | 3.3 | 1 | 4.3 | no
3 | 236 | 223a | 90 | 225.4 | 5.5 | 3.3 | 1 | 4.3 | no
4 | 223a | 223b | 90 | 68.7 | 5.5 | 3.3 | 1 | 4.3 | no
5 | 223a | 223 | 90 | 172.4 | 5.5 | 3.3 | 1 | 4.3 | no
6 | 223 | 234a | 90 | 182.9 | 5.5 | 3.3 | 1 | 4.3 | no
7 | 234a | 234b | 75 | 205.8 | 5.5 | 3.3 | 1 | 4.3 | no
8 | 234 | 234c | 75 | 27.3 | 5.5 | 3.3 | 1 | 4.3 | no
9 | 234 | 234d | 75 | 70.1 | 5.5 | 3.3 | 1 | 4.3 | no
10 | 237 | 234 | 63 | 45.5 | 5.5 | 3.3 | 1 | 4.3 | no
11 | 234 | 234a | 75 | 55.3 | 5.5 | 3.3 | 1 | 4.3 | no
12 | 223 | 193 | 90 | 447.9 | 5.5 | 3.3 | 1 | 4.3 | no
13 | 223 | 193 | 90 | 7 | 5.5 | 3.3 | 1 | 4.3 | no
14 | 193 | 195 | 140 | 7.4 | 5.5 | 3.3 | 1 | 4.3 | no
15 | 193 | 195 | 140 | 88.9 | 5.5 | 3.3 | 1 | 4.3 | no
16 | 195 | 196 | 140 | 29.1 | 5.5 | 3.3 | 1 | 4.3 | no
17 | 196 | 197 | 63 | 54.4 | 5.5 | 3.3 | 1 | 4.3 | no
18 | 192 | 195 | 140 | 98.4 | 5.5 | 3.3 | 1 | 4.3 | no
19 | 192 | 193 | 90 | 65.6 | 5.5 | 3.3 | 1 | 4.3 | no
20 | 192 | 192a | 140 | 45.8 | 5.5 | 3.3 | 1 | 4.3 | no
21 | 192a | 192b | 63 | 24.3 | 5.5 | 3.3 | 1 | 4.3 | no
22 | 192a | 181 | 140 | 172.5 | 5.5 | 3.3 | 1 | 4.3 | no
23 | 181 | 187 | 140 | 44.7 | 5.5 | 3.3 | 1 | 4.3 | no
24 | 187 | 193 | 140 | 171.1 | 5.5 | 3.3 | 1 | 4.3 | no
25 | 187 | 193 | 140 | 5 | 5.5 | 3.3 | 1 | 4.3 | no
26 | 181 | 179 | 160 | 29.7 | 5.5 | 3.3 | 1 | 4.3 | no
27 | 181 | 179 | 160 | 55.3 | 5.5 | 3.3 | 1 | 4.3 | no
28 | 179 | 180 | 75 | 160.3 | 5.5 | 3.3 | 1 | 4.3 | no
29 | 179 | 178 | 160 | 151.5 | 5.5 | 3.3 | 1 | 4.3 | no
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | AURANGABAD | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | 178 | 206 | 160 | 373.2 | 6KG/CM2 | 4 | 1 | 5 | NO
2 | 206 | 213 | 160 | 184.5 | 6KG/CM2 | 4 | 1 | 5 | NO
3 | 213 | 214 | 90 | 52.2 | 6KG/CM2 | 4 | 1 | 5 | NO
4 | 214 | 215 | 63 | 114.5 | 6KG/CM2 | 4 | 1 | 5 | NO
5 | 214 | 215 | 63 | 61.2 | 6KG/CM2 | 4 | 1 | 5 | NO
6 | 213 | 218 | 140 | 31 | 6KG/CM2 | 4 | 1 | 5 | NO
7 | 213 | 218 | 140 | 139.3 | 6KG/CM2 | 4 | 1 | 5 | NO
8 | 224 | 218 | 110 | 206.1 | 6KG/CM2 | 4 | 1 | 5 | NO
9 | 172 | 178 | 160 | 423.2 | 6KG/CM2 | 4 | 1 | 5 | NO
10 | 217 | 223 | 90 | 366.3 | 6KG/CM2 | 4 | 1 | 5 | NO
11 | 196 | 198 | 140 | 252.2 | 6KG/CM2 | 4 | 1 | 5 | NO
12 | 198 | 199 | 140 | 141.5 | 6KG/CM2 | 4 | 1 | 5 | NO
13 | 199 | 207 | 75 | 29 | 6KG/CM2 | 4 | 1 | 5 | NO
14 | 199 | 207 | 75 | 5 | 6KG/CM2 | 4 | 1 | 5 | NO
15 | 199 | 207 | 75 | 95 | 6KG/CM2 | 4 | 1 | 5 | NO
16 | 199 | 207 | 75 | 41 | 6KG/CM2 | 4 | 1 | 5 | NO
17 | 199 | 207 | 75 | 29 | 6KG/CM2 | 4 | 1 | 5 | NO
18 | 210 | 204 | 75 | 56 | 6KG/CM2 | 4 | 1 | 5 | NO
19 | 19 | 11 | 63 | 61.7 | 6KG/CM2 | 4 | 1 | 5 | NO
20 | 11 | 12 | 63 | 95.3 | 6KG/CM2 | 4 | 1 | 5 | NO
21 | 11 | 14 | 63 | 93.2 | 6KG/CM2 | 4 | 1 | 5 | NO
22 | 5 | 6 | 63 | 183.4 | 6KG/CM2 | 4 | 1 | 5 | NO
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | AURANGABAD | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | 9 | 17 | 200 | 228.3 | 5 | 3.3 | 1 | 4.3 | NO
2 | 17 | 23 | 63 | 101.2 | 5 | 3.3 | 1 | 4.3 | NO
3 | 23 | 22 | 200 | 40.2 | 5 | 3.3 | 1 | 4.3 | NO
4 | 22 | 20 | 200 | 35.4 | 5 | 3.3 | 1 | 4.3 | NO
5 | 20 | 21 | 63 | 50.5 | 5 | 3.3 | 1 | 4.3 | NO
6 | 20 | 17 | 200 | 42.4 | 5 | 3.3 | 1 | 4.3 | NO
7 | 22 | 38 | 160 | 177.2 | 5 | 3.3 | 1 | 4.3 | NO
8 | 22 | 38 | 160 | 5 | 5 | 3.3 | 1 | 4.3 | NO
9 | 1 | 3 | 63 | 67.2 | 5 | 3.3 | 1 | 4.3 | NO
10 | 1 | 3 | 63 | 82.2 | 5 | 3.3 | 1 | 4.3 | NO
11 | 23 | 27 | 200 | 158.8 | 5 | 3.3 | 1 | 4.3 | NO
12 | 27 | 30 | 63 | 5 | 5 | 3.3 | 1 | 4.3 | NO
13 | 27 | 30 | 63 | 273.3 | 5 | 3.3 | 1 | 4.3 | NO
14 | 27 | 37 | 200 | 172.3 | 5 | 3.3 | 1 | 4.3 | NO
15 | 37 | 39 | 63 | 34.1 | 5 | 3.3 | 1 | 4.3 | NO
16 | 37 | 37a | 63 | 115.6 | 5 | 3.3 | 1 | 4.3 | NO
17 | 37a | 37b | 63 | 106.8 | 5 | 3.3 | 1 | 4.3 | NO
18 | 37 | 42 | 200 | 481.1 | 5 | 3.3 | 1 | 4.3 | NO
19 | 42 | 43 | 200 | 98 | 5 | 3.3 | 1 | 4.3 | NO
20 | 42 | 43 | 200 | 88.1 | 5 | 3.3 | 1 | 4.3 | NO
21 | 43 | 43a | 63 | 136.4 | 5 | 3.3 | 1 | 4.3 | NO
22 | 43 | 41 | 200 | 303.2 | 5 | 3.3 | 1 | 4.3 | NO
23 | 41 | 36 | 75 | 137 | 5 | 3.3 | 1 | 4.3 | NO
24 | 36 | 34 | 63 | 67.2 | 5 | 3.3 | 1 | 4.3 | NO
25 | 36 | 28 | 63 | 207.8 | 5 | 3.3 | 1 | 4.3 | NO
26 | 41 | 122 | 140 | 472 | 5 | 3.3 | 1 | 4.3 | NO
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | AURANGABAD | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | 42 | 48 | 140 | 211.8 | 5.5 | 3.2 | 1 | 4.2 | NO
2 | 48 | 49 | 63 | 156.5 | 5.5 | 3.2 | 1 | 4.2 | NO
3 | 48 | 57 | 140 | 110.5 | 5.5 | 3.2 | 1 | 4.2 | NO
4 | 48 | 57 | 140 | 25.6 | 5.5 | 3.2 | 1 | 4.2 | NO
5 | 57 | 58 | 63 | 55.8 | 5.5 | 3.2 | 1 | 4.2 | NO
6 | 63 | 68 | 75 | 114.9 | 5.5 | 3.2 | 1 | 4.2 | NO
7 | 68 | 69 | 75 | 33.4 | 5.5 | 3.2 | 1 | 4.2 | NO
8 | 67 | 69 | 63 | 185 | 5.5 | 3.2 | 1 | 4.2 | NO
9 | 82 | 71 | 75 | 62 | 5.5 | 3.2 | 1 | 4.2 | NO
10 | 66 | 67 | 75 | 81.2 | 5.5 | 3.2 | 1 | 4.2 | NO
11 | 57 | 62 | 140 | 139.1 | 5.5 | 3.2 | 1 | 4.2 | NO
12 | 62 | 90 | 63 | 310 | 5.5 | 3.2 | 1 | 4.2 | NO
13 | 62 | 92 | 140 | 220 | 5.5 | 3.2 | 1 | 4.2 | NO
14 | 92 | 95 | 75 | 93.6 | 5.5 | 3.2 | 1 | 4.2 | NO
15 | 95 | 98 | 63 | 135.9 | 5.5 | 3.2 | 1 | 4.2 | NO
16 | 95 | 96 | 63 | 5 | 5.5 | 3.2 | 1 | 4.2 | NO
17 | 95 | 96 | 63 | 39 | 5.5 | 3.2 | 1 | 4.2 | NO
18 | 92 | 94 | 110 | 201.7 | 5.5 | 3.2 | 1 | 4.2 | NO
19 | 92 | 101 | 110 | 142.2 | 5.5 | 3.2 | 1 | 4.2 | NO
20 | 101 | 104 | 110 | 70.2 | 5.5 | 3.2 | 1 | 4.2 | NO
21 | 104 | 106 | 110 | 119.6 | 5.5 | 3.2 | 1 | 4.2 | NO
22 | 106 | 107 | 110 | 15.6 | 5.5 | 3.2 | 1 | 4.2 | NO
23 | 107 | 109 | 63 | 20.7 | 5.5 | 3.2 | 1 | 4.2 | NO
24 | 107 | 112 | 63 | 88.9 | 5.5 | 3.2 | 1 | 4.2 | NO
25 | 116 | 119 | 63 | 3 | 5.5 | 3.2 | 1 | 4.2 | NO
26 | 116 | 119 | 63 | 69 | 5.5 | 3.2 | 1 | 4.2 | NO
27 | 116 | 113 | 63 | 89 | 5.5 | 3.2 | 1 | 4.2 | NO
28 | 116 | 108 | 63 | 41.6 | 5.5 | 3.2 | 1 | 4.2 | NO
29 | 108 | 109 | 75 | 48 | 5.5 | 3.2 | 1 | 4.2 | NO
30 | 109 | 115 | 63 | 20.8 | 5.5 | 3.2 | 1 | 4.2 | NO
31 | 109 | 106 | 75 | 39.6 | 5.5 | 3.2 | 1 | 4.2 | NO
32 | 108 | 103 | 75 | 111 | 5.5 | 3.2 | 1 | 4.2 | NO
33 | 108 | 103 | 75 | 6 | 5.5 | 3.2 | 1 | 4.2 | NO
34 | 105 | 104 | 75 | 203.2 | 5.5 | 3.2 | 1 | 4.2 | NO
35 | 163 | 161 | 75 | 89.6 | 5.5 | 3.2 | 1 | 4.2 | NO
36 | 161 | 162 | 63 | 112.3 | 5.5 | 3.2 | 1 | 4.2 | NO
37 | 173 | 174 | 63 | 107.5 | 5.5 | 3.2 | 1 | 4.2 | NO
38 | 59 | 61 | 140 | 75.1 | 5.5 | 3.2 | 1 | 4.2 | NO
39 | 85 | 86 | 63 | 41.1 | 5.5 | 3.2 | 1 | 4.2 | NO
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date

## aurangabad
GOVERNMENT OF UTTAR PRADESH
STATE WATER & SANITATION MISSION ( SWSM )
Joint Measurement Report of Pipe Line
Name of the Work :- Survey , Design Preparation of DPR , Construction , Commissioning and O&M for 10 Years of Various Rural Water Supply Projects in the state of Uttar Pradesh as Per Request for Proposal for Division " Prayagraj "
Name of the Agency : POWER MECH PROJECTS LIMITED – BHOORATHNOM CONSTRUCTIONS COMPANY PRIVATE LIMITED (JV), Hyderabad.
Name OF Scheme |  | :aurangabad
Block |  | : Mangraura
Total Scope |  | :
JMR No. |  | : 1
Date of JMR |  | :
Sr. No. | Start Node | End Node | Dia | Pipe Length (as per Drawing) | Pipe Length (as per Site) | Width | Depth | Quantity | Type OF Road | Dismantling Length | Dismantling Width | Dismantling Quantity | Restoration Length | Restoration Width | Restoration Quantity | Restoration Status | Remark
1 | 137 | 138 | 63 | 86 | 92.2 | 0.36 | 1.06
2 | 137 | 128 | 75 | 145 | 142.8 | 0.375 | 1.07
3 | 137 | 128 | 75 |  | 11.7 | 0.375 | 1.07 |  | interlocking | 11.7 | 0.46 | 5.382 | 11.7 | 0.46 | 5.382
4 | 128 | 135 | 63 | 206 | 121.9 | 0.36 | 1.06 |  | interlocking | 121.9 | 0.46 | 56.074 | 121.9 | 0.46 | 56.074
5 | 128 | 135 | 63 |  | 37 | 0.36 | 1.06
6 | 135a | 135b | 63 |  | 55.4 | 0.36 | 1.06
7 | 135a | 135b | 63 |  | 6 | 0.36 | 1.06 |  | interlocking | 6 | 0.46 | 2.76 | 6 | 0.46 | 2.76
8 | 136 | 135 | 63 | 41 | 134 | 0.36 | 1.06
9 | 135 | 130 | 63 | 40 | 40.1 | 0.36 | 1.06
10 | 130 | 132 | 63 | 66 | 84.5 | 0.36 | 1.06
11 | 130a | 130b | 63 |  | 61.4 | 0.36 | 1.06
12 | 130 | 126 | 63 | 247 | 50.2 | 0.36 | 1.06 |  | brick road | 50.2 | 0.36 | 18.072 | 50.2 | 0.36 | 18.072
13 | 130 | 126 | 63 |  | 28.1 | 0.36 | 1.06
14 | 130 | 126 | 63 |  | 148.1 | 0.36 | 1.06
15 | 128 | 126 | 75 | 133 | 20 | 0.375 | 1.07 |  | interlocking | 20 | 0.46 | 9.2 | 20 | 0.46 | 9.2
16 | 128 | 126 | 75 |  | 19.7 | 0.375 | 1.07 |  | culvert
17 | 128 | 126 | 75 |  | 88.4 | 0.375 | 1.07
18 | 126 | 56 | 75 | 198 | 2.1 | 0.375 | 1.07
19 | 126 | 56 | 75 |  | 128.5 | 0.375 | 1.07 |  | b.t road | 128.5 | 0.375 | 48.1875 | 128.5 | 0.375 | 48.1875
20 | 126 | 56 | 75 |  | 7 | 0.375 | 1.07 |  | b.t road crossing | 7 | 0.375 | 2.625 | 7 | 0.375 | 2.625
21 | 56 | 38 | 160 | 299 | 298.2 | 0.46 | 1.16
22 | 56 | 122 | 160 | 223 | 91.1 | 0.46 | 1.16
23 | 56 | 122 | 160 |  | 56.9 | 0.46 | 1.16 |  | interlocking | 56.9 | 0.46 | 26.174 | 56.9 | 0.46 | 26.174
24 | 56 | 122 | 160 |  | 76.4 | 0.46 | 1.16
25 | 56 | 122 | 160 |  | 4.2 | 0.46 | 1.16 |  | brick road | 4.2 | 0.46 | 1.932 | 4.2 | 0.46 | 1.932
26 | 122 | 124 | 160 | 129 | 6 | 0.46 | 1.16 |  | b.t road crossing | 6 | 0.46 | 2.76 | 6 | 0.46 | 2.76
27 | 122 | 124 | 160 |  | 170 | 0.46 | 1.16
28 | 124 | 125 | 63 | 13 | 92.6 | 0.36 | 1.06
29 | 124 | 124a | 160 | 162 | 14.9 | 0.46 | 1.16
30 | 124a | 143 | 160 |  | 174.3 | 0.46 | 1.16
31 | 124a | 124b | 63 |  | 39.1 | 0.36 | 1.06
32 | 143 | 142 | 63 | 9 | 200.5 | 0.36 | 1.06
33 | 143 | 145 | 160 | 182 | 113 | 0.46 | 1.16
34 | 143 | 145 | 160 |  | 5.9 | 0.46 | 1.16 |  | b.t crossing | 5.9 | 0.46 | 2.714 | 5.9 | 0.46 | 2.714
35 | 146 | 145 | 160 | 9 | 7.6 | 0.46 | 1.16
36 | 145 | 144 | 75 | 235 | 230.6 | 0.375 | 1.07
37 | 145 | 144 | 75 |  | 9.8 | 0.375 | 1.07 |  | b.t crossing | 9.8 | 0.375 | 3.675 | 9.8 | 0.375 | 3.675
38 | 144 | 149 | 140 | 345 | 298.6 | 0.44 | 1.14
39 | 144 | 149 | 140 |  | 63.2 | 0.44 | 1.14 |  | interlocking | 63.2 | 0.46 | 29.072 | 63.2 | 0.46 | 29.072
40 | 149 | 154 | 140 | 351 | 6 | 0.44 | 1.14 |  | b.t crossing | 6 | 0.44 | 2.64 | 6 | 0.44 | 2.64
41 | 149 | 154 | 140 |  | 152.1 | 0.44 | 1.14 |  | brick road | 152.1 | 0.44 | 66.924 | 152.1 | 0.44 | 66.924
42 | 149 | 154 | 140 |  | 14.7 | 0.44 | 1.14 |  | brick road | 14.7 | 0.44 | 6.468 | 14.7 | 0.44 | 6.468
43 | 154 | 164 | 110 | 232 | 91.6 | 0.41 | 1.1 |  | brick road | 91.6 | 0.41 | 37.556 | 91.6 | 0.41 | 37.556
44 | 154 | 164 | 110 |  | 140 | 0.41 | 1.1
45 | 164 | 166 | 160 | 92 | 68.6 | 0.46 | 1.14
46 | 164 | 166 | 160 |  | 31 | 0.46 | 1.14 |  | brick road | 31 | 0.46 | 14.26 | 31 | 0.46 | 14.26
47 | 166 | 166a | 75 |  | 20 | 0.375 | 1.07
48 | 166a | 170 | 75 |  | 276 | 0.375 | 1.07
49 | 170 | 172 | 75 | 88 | 92.3 | 0.375 | 1.07
50 | 172 | 166 | 160 | 129 | 128.7 | 0.46 | 1.14 |  | brick road | 128.7 | 0.46 | 59.202 | 128.7 | 0.46 | 59.202
51 | 166a | 167 | 75 |  | 29.1 | 0.375 | 1.07
52 | 164 | 160 | 160 | 84 | 100.9 | 0.46 | 1.14
53 | 154 | 160 | 63 | 198 | 110.1 | 0.36 | 1.06
54 | 154 | 160 | 63 |  | 92.2 | 0.36 | 1.06 |  | brick road | 92.2 | 0.36 | 33.192 | 92.2 | 0.36 | 33.192
55 | 154 | 153 | 140 | 50 | 51 | 0.44 | 1.14
56 | 153 | 158 | 160 | 301 | 292.9 | 0.46 | 1.16
57 | 153 | 146 | 160 | 216 | 214.9 | 0.46 | 1.16
58 | 144 | 122 | 140 | 325 | 47 | 0.44 | 1.14
59 | 144 | 122 | 140 |  | 6.8 | 0.44 | 1.14 |  | culvert
60 | 144 | 122 | 140 |  | 192 | 0.44 | 1.14 |  | interlocking | 192 | 0.46 | 88.32 | 192 | 0.46 | 88.32
61 | 144 | 122 | 140 |  | 8 | 0.44 | 1.14 |  | culvert
62 | 144 | 122 | 140 |  | 80.6 | 0.44 | 1.14
63 | 224 | 228 | 90 | 55 | 53.2 | 0.39 | 1.09 |  | brick road | 53.2 | 0.39 | 20.748 | 53.2 | 0.39 | 20.748
64 | 228 | 231 | 90 | 10 | 10.8 | 0.39 | 1.09 |  | brick road | 10.8 | 0.39 | 4.212 | 10.8 | 0.39 | 4.212
65 | 228 | 225 | 63 | 98 | 3.1 | 0.36 | 1.06 |  | brick road | 3.1 | 0.36 | 1.116 | 3.1 | 0.36 | 1.116
66 | 228 | 225 | 63 |  | 89.4 | 0.36 | 1.06
67 | 231 | 232 | 63 | 162 | 59.5 | 0.36 | 1.06
68 | 231 | 233 | 63 | 155 | 162.5 | 0.36 | 1.06
69 | 225 | 228 | 90 | 47 | 5.6 | 0.39 | 1.09 |  | b.t road crossing | 5.6 | 0.39 | 2.184 | 5.6 | 0.39 | 2.184
70 | 224 | 227 | 90 |  | 51.7 | 0.39 | 1.09
71 | 227 | 227a | 63 |  | 22.3 | 0.36 | 1.06
72 | 227 | 230 | 90 | 27 | 103.4 | 0.39 | 1.09
73 | 230 | 230a | 90 |  | 45.2 | 0.39 | 1.09
74 | 230 | 226 | 90 | 101 | 62.1 | 0.39 | 1.09
75 | 226 | 229 | 63 | 124 | 175.9 | 0.36 | 1.06
76 | 230 | 236 | 90 | 259 | 177.4 | 0.39 | 1.09 |  | brick road | 177.4 | 0.39 | 69.186 | 177.4 | 0.39 | 69.186
77 | 236 | 239 | 63 | 216 | 204.7 | 0.36 | 1.06
78 | 236 | 223a | 90 | 398 | 225.4 | 0.39 | 1.09
79 | 223a | 223b | 90 |  | 68.7 | 0.39 | 1.09
80 | 223a | 223 | 90 |  | 172.4 | 0.39 | 1.09
81 | 223 | 234a | 90 | 234 | 182.9 | 0.39 | 1.09
82 | 234a | 234b | 75 |  | 205.8 | 0.375 | 1.07
83 | 234 | 234c | 75 |  | 27.3 | 0.375 | 1.07
84 | 234 | 234d | 75 |  | 70.1 | 0.375 | 1.07
85 | 237 | 234 | 63 | 231 | 45.5 | 0.36 | 1.06
86 | 234 | 234a | 75 |  | 55.3 | 0.375 | 1.07
87 | 223 | 193 | 90 | 444 | 447.9 | 0.39 | 1.09
88 | 223 | 193 | 90 |  | 7 | 0.39 | 1.09 |  | b.t crossing | 7 | 0.39 | 2.73 | 7 | 0.39 | 2.73 |  |  | 203.2
89 | 193 | 195 | 140 | 93 | 7.4 | 0.44 | 1.14 |  | culvert | [8 empty] | 89.6
90 | 193 | 195 | 140 |  | 88.9 | 0.44 | 1.14 | [10 empty] | 112.3
91 | 195 | 196 | 140 | 31 | 29.1 | 0.44 | 1.14 | [10 empty] | 107.5
92 | 196 | 197 | 63 | 17 | 54.4 | 0.36 | 1.06 | [10 empty] | 75.1
93 | 192 | 195 | 140 | 98 | 98.4 | 0.44 | 1.14 | [10 empty] | 41.1
94 | 192 | 193 | 90 | 61 | 65.6 | 0.39 | 1.09
95 | 192 | 192a | 140 |  | 45.8 | 0.44 | 1.14
96 | 192a | 192b | 63 |  | 24.3 | 0.36 | 1.06
97 | 192a | 181 | 140 |  | 172.5 | 0.44 | 1.14
98 | 181 | 187 | 140 | 113 | 44.7 | 0.44 | 1.14 |  | interlockng | 44.7 | 0.46 | 20.562 | 44.7 | 0.46 | 20.562
99 | 187 | 193 | 140 | 134 | 171.1 | 0.44 | 1.14
100 | 187 | 193 | 140 |  | 5 | 0.44 | 1.14 |  | b.t crossing | 5 | 0.44 | 2.2 | 5 | 0.44 | 2.2
101 | 181 | 179 | 160 | 55 | 29.7 | 0.46 | 1.16 |  | interlocking | 29.7 | 0.46 | 13.662 | 29.7 | 0.46 | 13.662
102 | 181 | 179 | 160 |  | 55.3 | 0.46 | 1.16 |  | cc road | 55.3 | 0.46 | 25.438 | 55.3 | 0.46 | 25.438
103 | 179 | 180 | 75 | 142 | 160.3 | 0.375 | 1.07
104 | 179 | 178 | 160 | 148 | 151.5 | 0.46 | 1.16 |  | cc road | 151.5 | 0.46 | 69.69 | 151.5 | 0.46 | 69.69
105 | 178 | 206 | 160 | 361 | 373.2 | 0.46 | 1.16 |  | cc road | 373.2 | 0.46 | 171.672 | 373.2 | 0.46 | 171.672
106 | 206 | 213 | 160 | 130 | 184.5 | 0.46 | 1.16 |  | b.t road | 184.5 | 0.46 | 84.87 | 184.5 | 0.46 | 84.87
107 | 213 | 214 | 90 | 57 | 52.2 | 0.39 | 1.09
108 | 214 | 215 | 63 | 82 | 114.5 | 0.36 | 1.06
109 | 214 | 215 | 63 | 36 | 61.2 | 0.36 | 1.06
110 | 213 | 218 | 140 | 179 | 31 | 0.44 | 1.14 |  | b.t road | 31 | 0.44 | 13.64 | 31 | 0.44 | 13.64
111 | 213 | 218 | 140 |  | 139.3 | 0.44 | 1.14
112 | 224 | 218 | 110 | 156 | 206.1 | 0.41 | 1.1
113 | 172 | 178 | 160 | 424 | 423.2 | 0.46 | 1.16 |  | cc road | 423.2 | 0.46 | 194.672 | 423.2 | 0.46 | 194.672
114 | 217 | 223 | 90 | 362 | 366.3 | 0.39 | 1.09
115 | 196 | 198 | 140 | 216 | 252.2 | 0.44 | 1.14
116 | 198 | 199 | 140 | 138 | 141.5 | 0.44 | 1.14 |  | brick road | 141.5 | 0.44 | 62.26 | 141.5 | 0.44 | 62.26
117 | 199 | 207 | 75 | 148 | 29 | 0.375 | 1.07 |  | brick road | 29 | 0.375 | 10.875 | 29 | 0.375 | 10.875
118 | 199 | 207 | 75 |  | 5 | 0.375 | 1.07 |  | interlocking | 5 | 0.46 | 2.3 | 5 | 0.46 | 2.3
119 | 199 | 207 | 75 |  | 95 | 0.375 | 1.07
120 | 199 | 207 | 75 |  | 41 | 0.375 | 1.07 |  | brick road | 41 | 0.375 | 15.375 | 41 | 0.375 | 15.375
121 | 199 | 207 | 75 |  | 29 | 0.375 | 1.07
122 | 210 | 204 | 75 |  | 56 | 0.375 | 1.07
123 | 19 | 11 | 63 | 184 | 61.7 | 0.36 | 1.06
124 | 11 | 12 | 63 | 83 | 95.3 | 0.36 | 1.06
125 | 11 | 14 | 63 | 12 | 93.2 | 0.36 | 1.06
126 | 5 | 6 | 63 | 54 | 183.4 | 0.36 | 1.06
127 | 9 | 17 | 200 | 103 | 228.3 | 0.5 | 1.2
128 | 17 | 23 | 63 | 200 | 101.2 | 0.36 | 1.06
129 | 23 | 22 | 200 | 108 | 40.2 | 0.5 | 1.2
130 | 22 | 20 | 200 | 40 | 35.4 | 0.5 | 1.2
131 | 20 | 21 | 63 | 36 | 50.5 | 0.36 | 1.06
132 | 20 | 17 | 200 | 51 | 42.4 | 0.5 | 1.2
133 | 22 | 38 | 160 | 56 | 177.2 | 0.46 | 1.16
134 | 22 | 38 | 160 |  | 5 | 0.46 | 1.16 |  | b.t crossing | 5 | 0.46 | 2.3 | 5 | 0.46 | 2.3
135 | 1 | 3 | 63 | 167 | 67.2 | 0.36 | 1.06
136 | 1 | 3 | 63 |  | 82.2 | 0.36 | 1.06 |  | brick road | 82.2 | 0.36 | 29.592 | 82.2 | 0.36 | 29.592
137 | 23 | 27 | 200 | 152 | 158.8 | 0.46 | 1.2 |  | b.t road | 158.8 | 0.46 | 73.048 | 158.8 | 0.46 | 73.048
138 | 27 | 30 | 63 | 322 | 5 | 0.36 | 1.06 |  | b.t crossing | 5 | 0.36 | 1.8 | 5 | 0.36 | 1.8
139 | 27 | 30 | 63 |  | 273.3 | 0.36 | 1.06
140 | 27 | 37 | 200 | 168 | 172.3 | 0.46 | 1.2 |  | b.t road | 172.3 | 0.46 | 79.258 | 172.3 | 0.46 | 79.258
141 | 37 | 39 | 63 | 146 | 34.1 | 0.36 | 1.06
142 | 37 | 37a | 63 |  | 115.6 | 0.36 | 1.06
143 | 37a | 37b | 63 |  | 106.8 | 0.36 | 1.06
144 | 37 | 42 | 200 | 472 | 481.1 | 0.46 | 1.2 |  | b.t road | 481.1 | 0.46 | 221.306 | 481.1 | 0.46 | 221.306
145 | 42 | 43 | 200 | 14 | 98 | 0.46 | 1.2 |  | interlocking | 98 | 0.46 | 45.08 | 98 | 0.46 | 45.08
146 | 42 | 43 | 200 |  | 88.1 | 0.46 | 1.2
147 | 43 | 43a | 63 |  | 136.4 | 0.36 | 1.06
148 | 43 | 41 | 200 | 305 | 303.2 | 0.46 | 1.2
149 | 41 | 36 | 75 | 138 | 137 | 0.375 | 1.07
150 | 36 | 34 | 63 | 42 | 67.2 | 0.36 | 1.06
151 | 36 | 28 | 63 | 175 | 207.8 | 0.36 | 1.06
152 | 41 | 122 | 140 | 453 | 472 | 0.44 | 1.14 |  | brick road | 472 | 0.44 | 207.68 | 472 | 0.44 | 207.68
153 | 42 | 48 | 140 | 203 | 211.8 | 0.44 | 1.14 |  | b.t road | 211.8 | 0.44 | 93.192 | 211.8 | 0.44 | 93.192
154 | 48 | 49 | 63 | 160 | 156.5 | 0.36 | 1.06
155 | 48 | 57 | 140 | 136 | 110.5 | 0.44 | 1.14 |  | b.t road | 110.5 | 0.44 | 48.62 | 110.5 | 0.44 | 48.62
156 | 48 | 57 | 140 |  | 25.6 | 0.44 | 1.14 |  | interlocking | 25.6 | 0.46 | 11.776 | 25.6 | 0.46 | 11.776
157 | 57 | 58 | 63 | 115 | 55.8 | 0.36 | 1.06 |  | brick road | 55.8 | 0.36 | 20.088 | 55.8 | 0.36 | 20.088
158 | 63 | 68 | 75 | 194 | 114.9 | 0.375 | 1.07
159 | 68 | 69 | 75 | 40 | 33.4 | 0.375 | 1.07
160 | 67 | 69 | 63 | 121 | 185 | 0.36 | 1.06
161 | 82 | 71 | 75 | 69 | 62 | 0.375 | 1.07 |  | brick road | 62 | 0.375 | 23.25 | 62 | 0.375 | 23.25
162 | 66 | 67 | 75 | 46 | 81.2 | 0.375 | 1.07
163 | 57 | 62 | 140 | 142 | 139.1 | 0.44 | 1.07 |  | interlocking | 139.1 | 0.46 | 63.986 | 139.1 | 0.46 | 63.986
164 | 62 | 90 | 63 | 242 | 310 | 0.36 | 1.06
165 | 62 | 92 | 140 | 213 | 220 | 0.44 | 1.14 |  | b.t road | 220 | 0.44 | 96.8 | 220 | 0.44 | 96.8
166 | 92 | 95 | 75 | 93 | 93.6 | 0.375 | 1.07
167 | 95 | 98 | 63 | 116 | 135.9 | 0.36 | 1.06
168 | 95 | 96 | 63 | 48 | 5 | 0.36 | 1.06 |  | b.t crossing | 5 | 0.36 | 1.8 | 5 | 0.36 | 1.8
169 | 95 | 96 | 63 |  | 39 | 0.36 | 1.06
170 | 92 | 94 | 110 | 197 | 201.7 | 0.41 | 1.1
171 | 92 | 101 | 110 | 138 | 142.2 | 0.41 | 1.1 |  | brick road | 142.2 | 0.41 | 58.302 | 142.2 | 0.41 | 58.302
172 | 101 | 104 | 110 | 68 | 70.2 | 0.41 | 1.1
173 | 104 | 106 | 110 | 116 | 119.6 | 0.41 | 1.1 |  | brick road | 119.6 | 0.41 | 49.036 | 119.6 | 0.41 | 49.036
174 | 106 | 107 | 110 | 12 | 15.6 | 0.41 | 1.1
175 | 107 | 109 | 63 | 75 | 20.7 | 0.36 | 1.06
176 | 107 | 112 | 63 | 89 | 88.9 | 0.36 | 1.06
177 | 116 | 119 | 63 | 35 | 3 | 0.36 | 1.06 |  | brick road | 3 | 0.36 | 1.08 | 3 | 0.36 | 1.08
178 | 116 | 119 | 63 |  | 69 | 0.36 | 1.06
179 | 116 | 113 | 63 | 95 | 89 | 0.36 | 1.06
180 | 116 | 108 | 63 | 39 | 41.6 | 0.36 | 1.06
181 | 108 | 109 | 75 | 45 | 48 | 0.375 | 1.07 |  | brick road | 48 | 0.375 | 18 | 48 | 0.375 | 18
182 | 109 | 115 | 63 | 41 | 20.8 | 0.36 | 1.06
183 | 109 | 106 | 75 | 75 | 39.6 | 0.375 | 1.07
184 | 108 | 103 | 75 | 112 | 111 | 0.375 | 1.07
185 | 108 | 103 | 75 |  | 6 | 0.375 | 1.07 |  | culvert
186 | 105 | 104 | 75 | 197 | 203.2 | 0.375 | 1.07
187 | 163 | 161 | 75 | 92 | 89.6 | 0.375 | 1.07
188 | 161 | 162 | 63 | 76 | 112.3 | 0.36 | 1.06
189 | 173 | 174 | 63 | 83 | 107.5 | 0.36 | 1.06 |  | interlocking | 107.5 | 0.46 | 49.45 | 107.5 | 0.46 | 49.45
190 | 59 | 61 | 140 | 40 | 75.1 | 0.44 | 1.14 |  | interlocking | 75.1 | 0.46 | 34.546 | 75.1 | 0.46 | 34.546
191 | 85 | 86 | 63 | 44 | 41.1 | 0.36 | 1.06
[5 empty] | 19832.7 | [6 empty] | 2534.5715 |  |  | 2534.5715
Representative PMPL - BRCCPL (JV) Pratapgarh | [6 empty] | Representative Medhaj Techno Concept Pvt Ltd (TPI) Pratapgarh |  |  |  |  | Representative UP Jal Nigam (Rural) Pratapgarh

## AURANGABAD R.R
GOVERNMENT OF UTTAR PRADESH
STATE WATER & SANITATION MISSION ( SWSM )
Joint Measurement Report of Pipe Line
Name of the Work :- Survey , Design Preparation of DPR , Construction , Commissioning and O&M for 10 Years of Various Rural Water Supply Projects in the state of Uttar Pradesh as Per Request for Proposal for Division " Prayagraj "
Name of the Agency : POWER MECH PROJECTS LIMITED – BHOORATHNOM CONSTRUCTIONS COMPANY PRIVATE LIMITED (JV), Hyderabad.
Name OF Scheme |  | :aurangabad
Block |  | : Mangraura
Total Scope |  | :
JMR No. |  | : 1
Date of JMR |  | :
Sr. No. | Start Node | End Node | Dia | Pipe Length (as per Drawing) | Pipe Length (as per Site) | Width | Depth | Quantity | Type OF Road | Dismantling Length | Dismantling Width | Dismantling Quantity | Restoration Length | Restoration Width | Restoration Quantity | Restoration Status | Remark
1 | 137 | 128 | 75 |  | 11.7 | 0.375 | 1.07 |  | interlocking | 11.7 | 0.46 | 5.382 | 11.7 | 0.46 | 5.382
2 | 128 | 135 | 63 |  | 121.9 | 0.36 | 1.06 |  | interlocking | 121.9 | 0.46 | 56.074 | 121.9 | 0.46 | 56.074
3 | 135a | 135b | 63 |  | 6 | 0.36 | 1.06 |  | interlocking | 6 | 0.46 | 2.76 | 6 | 0.46 | 2.76
4 | 130 | 126 | 63 |  | 50.2 | 0.36 | 1.06 |  | brick road | 50.2 | 0.36 | 18.072 | 50.2 | 0.36 | 18.072
5 | 128 | 126 | 75 |  | 20 | 0.375 | 1.07 |  | interlocking | 20 | 0.46 | 9.2 | 20 | 0.46 | 9.2
7 | 126 | 56 | 75 |  | 128.5 | 0.375 | 1.07 |  | b.t road | 128.5 | 0.375 | 48.1875 | 128.5 | 0.375 | 48.1875
8 | 126 | 56 | 75 |  | 7 | 0.375 | 1.07 |  | b.t road crossing | 7 | 0.375 | 2.625 | 7 | 0.375 | 2.625
9 | 56 | 122 | 160 |  | 56.9 | 0.46 | 1.16 |  | interlocking | 56.9 | 0.46 | 26.174 | 56.9 | 0.46 | 26.174
10 | 56 | 122 | 160 |  | 4.2 | 0.46 | 1.16 |  | brick road | 4.2 | 0.46 | 1.932 | 4.2 | 0.46 | 1.932
11 | 122 | 124 | 160 |  | 6 | 0.46 | 1.16 |  | b.t road crossing | 6 | 0.46 | 2.76 | 6 | 0.46 | 2.76
12 | 143 | 145 | 160 |  | 5.9 | 0.46 | 1.16 |  | b.t crossing | 5.9 | 0.46 | 2.714 | 5.9 | 0.46 | 2.714
13 | 145 | 144 | 75 |  | 9.8 | 0.375 | 1.07 |  | b.t crossing | 9.8 | 0.375 | 3.675 | 9.8 | 0.375 | 3.675
14 | 144 | 149 | 140 |  | 63.2 | 0.44 | 1.14 |  | interlocking | 63.2 | 0.46 | 29.072 | 63.2 | 0.46 | 29.072
15 | 149 | 154 | 140 |  | 6 | 0.44 | 1.14 |  | b.t crossing | 6 | 0.44 | 2.64 | 6 | 0.44 | 2.64
16 | 149 | 154 | 140 |  | 152.1 | 0.44 | 1.14 |  | brick road | 152.1 | 0.44 | 66.924 | 152.1 | 0.44 | 66.924
17 | 149 | 154 | 140 |  | 14.7 | 0.44 | 1.14 |  | brick road | 14.7 | 0.44 | 6.468 | 14.7 | 0.44 | 6.468
18 | 154 | 164 | 110 |  | 91.6 | 0.41 | 1.1 |  | brick road | 91.6 | 0.41 | 37.556 | 91.6 | 0.41 | 37.556
19 | 164 | 166 | 160 |  | 31 | 0.46 | 1.14 |  | brick road | 31 | 0.46 | 14.26 | 31 | 0.46 | 14.26
20 | 172 | 166 | 160 |  | 128.7 | 0.46 | 1.14 |  | brick road | 128.7 | 0.46 | 59.202 | 128.7 | 0.46 | 59.202
21 | 154 | 160 | 63 |  | 92.2 | 0.36 | 1.06 |  | brick road | 92.2 | 0.36 | 33.192 | 92.2 | 0.36 | 33.192
22 | 144 | 122 | 140 |  | 192 | 0.44 | 1.14 |  | interlocking | 192 | 0.46 | 88.32 | 192 | 0.46 | 88.32
23 | 224 | 228 | 90 |  | 53.2 | 0.39 | 1.09 |  | brick road | 53.2 | 0.39 | 20.748 | 53.2 | 0.39 | 20.748
24 | 228 | 231 | 90 |  | 10.8 | 0.39 | 1.09 |  | brick road | 10.8 | 0.39 | 4.212 | 10.8 | 0.39 | 4.212
25 | 228 | 225 | 63 |  | 3.1 | 0.36 | 1.06 |  | brick road | 3.1 | 0.36 | 1.116 | 3.1 | 0.36 | 1.116
26 | 225 | 228 | 90 |  | 5.6 | 0.39 | 1.09 |  | b.t road crossing | 5.6 | 0.39 | 2.184 | 5.6 | 0.39 | 2.184
27 | 230 | 236 | 90 |  | 177.4 | 0.39 | 1.09 |  | brick road | 177.4 | 0.39 | 69.186 | 177.4 | 0.39 | 69.186
28 | 223 | 193 | 90 |  | 7 | 0.39 | 1.09 |  | b.t crossing | 7 | 0.39 | 2.73 | 7 | 0.39 | 2.73
30 | 181 | 187 | 140 |  | 44.7 | 0.44 | 1.14 |  | interlockng | 44.7 | 0.46 | 20.562 | 44.7 | 0.46 | 20.562
31 | 187 | 193 | 140 |  | 5 | 0.44 | 1.14 |  | b.t crossing | 5 | 0.44 | 2.2 | 5 | 0.44 | 2.2
32 | 181 | 179 | 160 |  | 29.7 | 0.46 | 1.16 |  | interlocking | 29.7 | 0.46 | 13.662 | 29.7 | 0.46 | 13.662
33 | 181 | 179 | 160 |  | 55.3 | 0.46 | 1.16 |  | cc road | 55.3 | 0.46 | 25.438 | 55.3 | 0.46 | 25.438
34 | 179 | 178 | 160 |  | 151.5 | 0.46 | 1.16 |  | cc road | 151.5 | 0.46 | 69.69 | 151.5 | 0.46 | 69.69
35 | 178 | 206 | 160 |  | 373.2 | 0.46 | 1.16 |  | cc road | 373.2 | 0.46 | 171.672 | 373.2 | 0.46 | 171.672
36 | 206 | 213 | 160 |  | 184.5 | 0.46 | 1.16 |  | b.t road | 184.5 | 0.46 | 84.87 | 184.5 | 0.46 | 84.87
37 | 213 | 218 | 140 |  | 31 | 0.44 | 1.14 |  | b.t road | 31 | 0.44 | 13.64 | 31 | 0.44 | 13.64
38 | 172 | 178 | 160 |  | 423.2 | 0.46 | 1.16 |  | cc road | 423.2 | 0.46 | 194.672 | 423.2 | 0.46 | 194.672
39 | 198 | 199 | 140 |  | 141.5 | 0.44 | 1.14 |  | brick road | 141.5 | 0.44 | 62.26 | 141.5 | 0.44 | 62.26
40 | 199 | 207 | 75 |  | 29 | 0.375 | 1.07 |  | brick road | 29 | 0.375 | 10.875 | 29 | 0.375 | 10.875
41 | 199 | 207 | 75 |  | 5 | 0.375 | 1.07 |  | interlocking | 5 | 0.46 | 2.3 | 5 | 0.46 | 2.3
42 | 199 | 207 | 75 |  | 41 | 0.375 | 1.07 |  | brick road | 41 | 0.375 | 15.375 | 41 | 0.375 | 15.375
43 | 22 | 38 | 160 |  | 5 | 0.46 | 1.16 |  | b.t crossing | 5 | 0.46 | 2.3 | 5 | 0.46 | 2.3
44 | 1 | 3 | 63 |  | 82.2 | 0.36 | 1.06 |  | brick road | 82.2 | 0.36 | 29.592 | 82.2 | 0.36 | 29.592
45 | 23 | 27 | 200 |  | 158.8 | 0.46 | 1.2 |  | b.t road | 158.8 | 0.46 | 73.048 | 158.8 | 0.46 | 73.048
46 | 27 | 30 | 63 |  | 5 | 0.36 | 1.06 |  | b.t crossing | 5 | 0.36 | 1.8 | 5 | 0.36 | 1.8
47 | 27 | 37 | 200 |  | 172.3 | 0.46 | 1.2 |  | b.t road | 172.3 | 0.46 | 79.258 | 172.3 | 0.46 | 79.258
48 | 37 | 42 | 200 |  | 481.1 | 0.46 | 1.2 |  | b.t road | 481.1 | 0.46 | 221.306 | 481.1 | 0.46 | 221.306
49 | 42 | 43 | 200 |  | 98 | 0.46 | 1.2 |  | interlocking | 98 | 0.46 | 45.08 | 98 | 0.46 | 45.08
50 | 41 | 122 | 140 |  | 472 | 0.44 | 1.14 |  | brick road | 472 | 0.44 | 207.68 | 472 | 0.44 | 207.68
51 | 42 | 48 | 140 |  | 211.8 | 0.44 | 1.14 |  | b.t road | 211.8 | 0.44 | 93.192 | 211.8 | 0.44 | 93.192
52 | 48 | 57 | 140 |  | 110.5 | 0.44 | 1.14 |  | b.t road | 110.5 | 0.44 | 48.62 | 110.5 | 0.44 | 48.62
53 | 48 | 57 | 140 |  | 25.6 | 0.44 | 1.14 |  | interlocking | 25.6 | 0.46 | 11.776 | 25.6 | 0.46 | 11.776
54 | 57 | 58 | 63 |  | 55.8 | 0.36 | 1.06 |  | brick road | 55.8 | 0.36 | 20.088 | 55.8 | 0.36 | 20.088
55 | 82 | 71 | 75 |  | 62 | 0.375 | 1.07 |  | brick road | 62 | 0.375 | 23.25 | 62 | 0.375 | 23.25
56 | 57 | 62 | 140 |  | 139.1 | 0.44 | 1.07 |  | interlocking | 139.1 | 0.46 | 63.986 | 139.1 | 0.46 | 63.986
57 | 62 | 92 | 140 |  | 220 | 0.44 | 1.14 |  | b.t road | 220 | 0.44 | 96.8 | 220 | 0.44 | 96.8
58 | 95 | 96 | 63 |  | 5 | 0.36 | 1.06 |  | b.t crossing | 5 | 0.36 | 1.8 | 5 | 0.36 | 1.8
59 | 92 | 101 | 110 |  | 142.2 | 0.41 | 1.1 |  | brick road | 142.2 | 0.41 | 58.302 | 142.2 | 0.41 | 58.302
60 | 104 | 106 | 110 |  | 119.6 | 0.41 | 1.1 |  | brick road | 119.6 | 0.41 | 49.036 | 119.6 | 0.41 | 49.036
61 | 116 | 119 | 63 |  | 3 | 0.36 | 1.06 |  | brick road | 3 | 0.36 | 1.08 | 3 | 0.36 | 1.08
62 | 108 | 109 | 75 |  | 48 | 0.375 | 1.07 |  | brick road | 48 | 0.375 | 18 | 48 | 0.375 | 18
63 | 173 | 174 | 63 |  | 107.5 | 0.36 | 1.06 |  | interlocking | 107.5 | 0.46 | 49.45 | 107.5 | 0.46 | 49.45
64 | 59 | 61 | 140 |  | 75.1 | 0.44 | 1.14 |  | interlocking | 75.1 | 0.46 | 34.546 | 75.1 | 0.46 | 34.546
[5 empty] | 5818.8 | [6 empty] | 2534.5715 |  |  | 2534.5715
Representative PMPL - BRCCPL (JV) Pratapgarh | [6 empty] | Representative Medhaj Techno Concept Pvt Ltd (TPI) Pratapgarh |  |  |  |  | Representative UP Jal Nigam (Rural) Pratapgarh