## brahapur jmr ,road resto
GOVERNMENT OF UTTAR PRADESH
STATE WATER & SANITATION MISSION ( SWSM )
Joint Measurement Report of Pipe Line
Name of the Work :- Survey , Design Preparation of DPR , Construction , Commissioning and O&M for 10 Years of Various Rural Water Supply Projects in the state of Uttar Pradesh as Per Request for Proposal for Division " Prayagraj "
Name of the Agency : POWER MECH PROJECTS LIMITED – BHOORATHNOM CONSTRUCTIONS COMPANY PRIVATE LIMITED (JV), Hyderabad.
Name OF Scheme |  | :brahapur
Block |  | : Mangraura
Total Scope |  | :
JMR No. |  | : 1
Date of JMR |  | :
Sr. No. | Start Node | End Node | Dia | Pipe Length (as per Drawing) | Pipe Length (as per Site) | Width | Depth | Quantity | Type OF Road | Dismantling Length | Dismantling Width | Dismantling Quantity | Restoration Length | Restoration Width | Restoration Quantity | Restoration Status | Remark
1 | j167 | j229 | 140 | 225 | 231.3 | 0.44 | 1.14
2 | j229 | j216 | 140 | 20 | 10 | 0.44 | 1.14
3 | j216 | j41 | 140 |  | 338 | 0.44 | 1.14
4 | j41 | j50 | 125 |  | 129.7 | 0.42 | 1.12 |  | B.T | 129.7 | 0.46 | 59.662 | 129.7 | 0.46 | 59.662 | Done
5 | j50 | j111 | 63 |  | 111.8 | 0.36 | 1.06
6 | j41 | j7 | 160 |  | 565 | 0.46 | 1.16
7 | j7 | j1 | 200 | 1418 | 1502.2 | 0.5 | 1.2
8 | j7 | j1 | 200 |  | 7.8 | 0.5 | 1.2 |  | b.t crossing | 7.8 | 0.5 | 3.9 | 7.8 | 0.5 | 3.9 | Done
9 | j6 | j159 | 63 |  | 1113.3 | 0.36 | 1.06
10 | j159 | j115 | 63 |  | 489.6 | 0.36 | 1.06 |  | B.T | 489.6 | 0.46 | 225.216 | 489.6 | 0.46 | 225.216 | Done
11 | j115 | j101 | 63 |  | 123.3 | 0.36 | 1.06
12 | j115 | j93 | 63 |  | 150.8 | 0.36 | 1.06
13 | j93 | j103 | 63 |  | 130.7 | 0.36 | 1.06
14 | j93 | j144 | 63 |  | 37 | 0.36 | 1.06
15 | j144 | j90 | 63 |  | 35.3 | 0.31 | 1.06
16 | j143 | j165 | 63 |  | 10 | 0.36 | 1.06 |  | B.T | 10 | 0.46 | 4.6 | 10 | 0.46 | 4.6 | Done
17 | j165 | j158 | 63 |  | 68 | 0.36 | 1.06 |  | B.T | 68 | 0.46 | 31.28 | 68 | 0.46 | 31.28 | Done
18 | j111 | j112 | 63 |  | 215 | 0.36 | 1.06
19 | j143 | j163 | 63 |  | 180 | 0.36 | 1.06 |  | B.T | 180 | 0.46 | 82.8 | 180 | 0.46 | 82.8 | Done
20 | j143 | j53 | 63 |  | 5 | 0.36 | 1.06 |  | b.t crossing | 5 | 0.36 | 1.8 | 5 | 0.36 | 1.8 | Done
21 | j93 | 92 | 63 |  | 7 | 0.46 | 1.06 |  | interlocking | 7 | 0.46 | 3.22 | 7 | 0.46 | 3.22 | Done
22 | j111 | j240 | 63 |  | 83.3 | 0.36 | 1.06 |  | brick road | 83.3 | 0.36 | 29.988 | 83.3 | 0.36 | 29.988 | Done
23 | j186 | j141 | 63 |  | 65 | 0.36 | 1.06
24 | j186 | j179 | 63 |  | 26.8 | 0.28 | 1.06
25 | j232 | j179 | 63 | 39 | 53 | 0.32 | 1.06
26 | j179 | j163 | 63 |  | 76.2 | 0.36 | 1.06 |  | B.T | 76.2 | 0.46 | 35.052 | 76.2 | 0.46 | 35.052 | Done
27 | j179 | j163 | 63 |  | 5 | 0.36 | 1.06 |  | b.t crossing | 5 | 0.36 | 1.8 | 5 | 0.36 | 1.8 | Done
28 | j93 | j117 | 63 |  | 5 | 0.36 | 1.06 |  | b.t crossing | 5 | 0.36 | 1.8 | 5 | 0.36 | 1.8 | Done
29 | j93 | j163 | 63 |  | 161 | 0.36 | 1.06 |  | b.t | 161 | 0.36 | 57.96 | 161 | 0.36 | 57.96 | Done
30 | j50 | j51 | 63 |  | 208.3 | 0.36 | 1.06
31 | j5 | j4 | 63 |  | 94.6 | 0.36 | 1.06
32 | j8 | j9 | 63 |  | 6 | 0.36 | 1.06 |  | b.t crossing | 6 | 0.36 | 2.16 | 6 | 0.36 | 2.16 | Done
33 | j8 | j9 | 63 |  | 76 | 0.36 | 1.06 |  | brick road | 76 | 0.36 | 27.36 | 76 | 0.36 | 27.36 | Done
34 | j79 A | j7 A | 63 |  | 815.3 | 0.36 | 1.06 |  | B.T | 815.3 | 0.46 | 375.038 | 815.3 | 0.46 | 375.038 | Done
35 | j79 | j35 | 63 |  | 46.3 | 0.34 | 1.06
36 | j47 | j254 | 63 |  | 112.3 | 0.36 | 1.06
37 | j24 | j254 | 63 |  | 161 | 0.36 | 1.06 |  | brick road | 161 | 0.36 | 57.96 | 161 | 0.36 | 57.96 | Done
38 | j32 | j65 | 63 |  | 25 | 0.46 | 1.06 |  | interlocking | 25 | 0.46 | 11.5 | 25 | 0.46 | 11.5 | Done
39 | j65 | j54 | 63 |  | 30 | 0.36 | 1.06
40 | j65 | j151 | 63 |  | 23.4 | 0.29 | 1.06
41 | j256 | j267 | 63 |  | 104.3 | 0.36 | 1.06
42 | j267 | j187 | 63 |  | 53.2 | 0.36 | 1.06
43 | j267 | j315 | 63 |  | 123.2 | 0.36 | 1.06
44 | j315 | j271 | 63 |  | 40 | 0.34 | 1.06
45 | j315 | j271 | 63 |  | 11.1 | 0.36 | 1.06
46 | j315 | j321 | 63 |  | 186.8 | 0.36 | 1.06
47 | j216 | j265 | 63 |  | 315.6 | 0.36 | 1.06
48 | j321 | j19 | 63 |  | 753.3 | 0.36 | 1.06
49 | j19 | j21 | 90 |  | 60.3 | 0.39 | 1.09
50 | j19 | j49 | 75 |  | 120 | 0.46 | 1.07 |  | interlocking | 120 | 0.46 | 55.2 | 120 | 0.46 | 55.2 | Done
51 | j66 | j55 | 63 |  | 26 | 0.36 | 1.06
52 | j49 | j66 | 75 |  | 30 | 0.37 | 1.07
53 | j55 | j119 | 63 |  | 21.1 | 0.33 | 1.06
54 | j88 | j66 | 63 |  | 30.2 | 0.46 | 1.06 |  | interlocking | 30.2 | 0.46 | 13.892 | 30.2 | 0.46 | 13.892 | Done
55 | j58 | j88 | 63 |  | 27.2 | 0.36 | 1.06
56 | j55 | j56 | 63 |  | 20.5 | 0.46 | 1.06 |  | interlocking | 20.5 | 0.46 | 9.43 | 20.5 | 0.46 | 9.43 | Done
57 | j88 | j72 | 63 |  | 24.7 | 0.46 | 1.06 |  | interlocking | 24.7 | 0.46 | 11.362 | 24.7 | 0.46 | 11.362 | Done
58 | j72 | j84 | 63 |  | 54.5 | 0.36 | 1.06
59 | j27 | j84 | 63 |  | 48.5 | 0.36 | 1.06
60 | j27 | j45 | 63 |  | 46.8 | 0.36 | 1.06
61 | j45 | j64 | 63 |  | 41.5 | 0.36 | 1.06
62 | j45 | j155 | 63 |  | 62.6 | 0.36 | 1.06
63 | j45 | j155 | 63 |  | 34 | 0.36 | 1.06 |  | brick road | 34 | 0.36 | 12.24 | 34 | 0.36 | 12.24 | Done
64 | j155 | j254 | 63 |  | 26 | 0.29 | 1.06
65 | j254 | j45 | 63 |  | 71.3 | 0.36 | 1.06 |  | brick road | 71.3 | 0.36 | 25.668 | 71.3 | 0.36 | 25.668 | Done
66 | j254 | j151 | 63 |  | 19 | 0.36 | 1.06 |  | brick road | 19 | 0.36 | 6.84 | 19 | 0.36 | 6.84 | Done
67 | j151 | j72 | 63 |  | 80.2 | 0.46 | 1.06 |  | interlocking | 80.2 | 0.46 | 36.892 | 80.2 | 0.46 | 36.892 | Done
68 | j254 | j207 | 63 |  | 198.3 | 0.36 | 1.06 |  | brick road | 198.3 | 0.36 | 71.388 | 198.3 | 0.36 | 71.388 | Done
69 | j254 | j207 | 63 |  | 38.7 | 0.46 | 1.06 |  | interlocking | 38.7 | 0.46 | 17.802 | 38.7 | 0.46 | 17.802 | Done
70 | j254 | j207 | 63 |  | 51.5 | 0.36 | 1.06
71 | j212 | j126 | 63 |  | 394.9 | 0.36 | 1.06 |  | brick road | 394.9 | 0.46 | 181.654 | 394.9 | 0.46 | 181.654 | Done
72 | j126 | j56 | 63 |  | 170 | 0.36 | 1.06 |  | brick road | 170 | 0.46 | 78.2 | 170 | 0.46 | 78.2 | Done
73 | j126 | j134 | 63 |  | 193 | 0.36 | 1.06 |  | brick road | 193 | 0.46 | 88.78 | 193 | 0.46 | 88.78 | Done
74 | j311 | j134 | 63 |  | 648.3 | 0.36 | 1.06
75 | j134 | j211 | 63 |  | 332.2 | 0.36 | 1.06 |  | brick road | 332.2 | 0.46 | 152.812 | 332.2 | 0.46 | 152.812 | Done
76 | j161 | j161a | 63 |  | 61.3 | 0.36 | 1.06
77 | j276 | j306 | 63 | 106 | 78 | 0.36 | 1.06
78 | j306 | j215 | 63 | 49 | 65.5 | 0.36 | 1.06
79 | j306 | j324 | 63 |  | 7 | 0.46 | 1.06 |  | interlocking | 7 | 0.46 | 3.22 | 7 | 0.46 | 3.22 | Done
80 | j324 | j206 | 63 | 65 | 55 | 0.36 | 1.06
81 | j206 | j142 | 63 | 45 | 106 | 0.36 | 1.06
82 | j206 | j184 | 63 | 88 | 85.1 | 0.36 | 1.06
83 | j184 | j120 | 63 | 26 | 50 | 0.36 | 1.06
84 | j184 | j319 | 63 | 38 | 79 | 0.36 | 1.06
85 | j292 | j300 | 63 |  | 41 | 0.36 | 1.06
86 | j309 | j309a | 63 |  | 51 | 0.46 | 1.06 |  | interlocking | 51 | 0.46 | 23.46 | 51 | 0.46 | 23.46 | Done
87 | j322 | j309 | 63 |  | 91.3 | 0.36 | 1.06
88 | j322a | j285 | 63 |  | 103 | 0.36 | 1.06
89 | j324 | j233 | 63 | 112 | 113.3 | 0.36 | 1.06
90 | j233 | j339 | 63 | 104 | 65.4 | 0.36 | 1.06
91 | j233 | j259 | 63 |  | 368.3 | 0.36 | 1.06
92 | j233 | j259 | 63 |  | 7 | 0.36 | 1.06 |  | b.t crossing | 7 | 0.36 | 2.52 | 7 | 0.36 | 2.52 | Done
93 | j259 | j102 | 110 | 356 | 311.1 | 0.41 | 1.1
94 | j246 | j102 | 63 |  | 413.1 | 0.36 | 1.06
95 | j246 | j102 | 63 |  | 10 | 0.36 | 1.06 |  | culvert
96 | j80 | j339 | 63 |  | 307.7 | 0.36 | 1.06
97 | j259 | j216 | 125 |  | 211 | 0.42 | 1.12
98 | j306 | j259 | 63 |  | 803.2 | 0.36 | 1.06
99 | j207 | j204 | 63 | 79 | 72.3 | 0.36 | 1.06
100 | j198 | j107 | 63 | 121 | 133 | 0.36 | 1.06 |  | brick road | 133 | 0.36 | 47.88 | 133 | 0.36 | 47.88 | Done
101 | j107 | j132 | 63 | 64 | 102.3 | 0.36 | 1.06
102 | j132 | j60 | 63 |  | 23.2 | 0.29 | 1.06
103 | j107 | j305 | 63 |  | 76.5 | 0.36 | 1.06
104 | j279 | j152 | 63 |  | 37.2 | 0.34 | 1.06
105 | j355 | j20 | 63 |  | 157.2 | 0.36 | 1.06
106 | j86 | j162 | 63 | 105 | 98.2 | 0.36 | 1.06
107 | j162 | j42 | 63 |  | 82.3 | 0.36 | 1.06
108 | j42 | j40 | 63 |  | 78 | 0.36 | 1.06
109 | j42 | j61 | 63 |  | 73.2 | 0.36 | 1.06
110 | j162 | j109 | 63 |  | 45 | 0.36 | 1.06
111 | j145 | j146 | 63 |  | 69.3 | 0.36 | 1.06
112 | j224 | j274 | 63 | 126 | 125.1 | 0.36 | 1.06
113 | j224 | j274 | 63 |  | 5 | 0.36 | 1.06 |  | b.t crossing | 5 | 0.36 | 1.8 | 5 | 0.36 | 1.8 | Done
114 | j274 | j326 | 63 | 167 | 148.8 | 0.36 | 1.06 |  | brick road | 148.8 | 0.36 | 53.568 | 148.8 | 0.36 | 53.568 | Done
115 | j274 | j291 | 63 |  | 248.6 | 0.36 | 1.06
116 | j291 | j347 | 63 |  | 15 | 0.36 | 1.06 |  | brick road | 15 | 0.36 | 5.4 | 15 | 0.36 | 5.4 | Done
117 | j347 | j190 | 63 |  | 162.3 | 0.36 | 1.06
118 | j228 | j338 | 63 |  | 65 | 0.36 | 1.06
119 | j346 | j330 | 63 |  | 47.7 | 0.36 | 1.06
120 | j327 | j323 | 63 |  | 30.3 | 0.36 | 1.06
121 | j327 | j323 | 63 |  | 46.4 | 0.36 | 1.06
122 | j291 | j327 | 63 |  | 51 | 0.36 | 1.06 |  | brick road | 51 | 0.36 | 18.36 | 51 | 0.36 | 18.36 | Done
123 | j327 | j349 | 63 |  | 33.3 | 0.36 | 1.06 |  | brick road | 33.3 | 0.36 | 11.988 | 33.3 | 0.36 | 11.988 | Done
124 | j327a | j327b | 63 |  | 35 | 0.36 | 1.06
125 | j349 | j225 | 63 |  | 29 | 0.36 | 1.06 |  | brick road | 29 | 0.36 | 10.44 | 29 | 0.36 | 10.44 | Done
126 | j225 | j223 | 63 |  | 16 | 0.35 | 1.06
127 | j225 | j262 | 63 |  | 21.3 | 0.36 | 1.06 |  | brick road | 21.3 | 0.36 | 7.668 | 21.3 | 0.36 | 7.668 | Done
128 | j225 | j218 | 63 |  | 46.6 | 0.36 | 1.06 |  | brick road | 46.6 | 0.36 | 16.776 | 46.6 | 0.36 | 16.776 | Done
129 | j220 | j349 | 63 |  | 56.3 | 0.36 | 1.06 |  | brick road | 56.3 | 0.36 | 20.268 | 56.3 | 0.36 | 20.268 | Done
130 | j270 | j277 | 63 |  | 30.1 | 0.36 | 1.06
131 | j220 | j234 | 63 |  | 41 | 0.36 | 1.06
132 | j234 | j224 | 63 |  | 118.3 | 0.36 | 1.06
133 | j234 | j224 | 63 |  | 5 | 0.36 | 1.06 |  | b.t crossing | 5 | 0.36 | 1.8 | 5 | 0.36 | 1.8 | Done
134 | j122 | j73 | 63 |  | 75 | 0.36 | 1.06
135 | j278 | j345 | 63 |  | 30.1 | 0.36 | 1.06
136 | j345 | j157 | 63 |  | 65 | 0.36 | 1.06 |  | brick road | 65 | 0.36 | 23.4 | 65 | 0.36 | 23.4 | Done
137 | j345 | j194 | 63 |  | 44.2 | 0.36 | 1.06 |  | brick road | 44.2 | 0.36 | 15.912 | 44.2 | 0.36 | 15.912 | Done
138 | j304 | j283 | 63 |  | 15 | 0.36 | 1.06 |  | brick road | 15 | 0.36 | 5.4 | 15 | 0.36 | 5.4 | Done
139 | j350 | j318 | 63 |  | 34.3 | 0.36 | 1.06 |  | brick road | 34.3 | 0.36 | 12.348 | 34.3 | 0.36 | 12.348 | Done
140 | j296 | j350 | 63 |  | 30.1 | 0.36 | 1.06 |  | brick road | 30.1 | 0.36 | 10.836 | 30.1 | 0.36 | 10.836 | Done
141 | j356 | j314 | 63 |  | 30.3 | 0.36 | 1.06 |  | brick road | 30.3 | 0.36 | 10.908 | 30.3 | 0.36 | 10.908 | Done
142 | j314 | j258 | 63 |  | 15.2 | 0.36 | 1.06 |  | brick road | 15.2 | 0.36 | 5.472 | 15.2 | 0.36 | 5.472 | Done
143 | j314 | j258 | 63 |  | 45.5 | 0.36 | 1.06
144 | j202 | j129 | 63 |  | 31.1 | 0.36 | 1.06
145 | j314 | j296 | 63 |  | 41 | 0.36 | 1.06
146 | j350 | j147 | 63 |  | 31.1 | 0.36 | 1.06 |  | brick road | 31.1 | 0.36 | 11.196 | 31.1 | 0.36 | 11.196 | Done
147 | j350 | j147 | 63 |  | 18 | 0.36 | 1.06 |  | brick road | 18 | 0.36 | 6.48 | 18 | 0.36 | 6.48 | Done
148 | j109 | j255 | 63 |  | 50 | 0.36 | 1.06
149 | j255 | j59 | 63 |  | 54.3 | 0.36 | 1.06
150 | j123 | j255 | 63 |  | 51 | 0.36 | 1.06 |  | brick road | 51 | 0.36 | 18.36 | 51 | 0.36 | 18.36 | Done
151 | j255 | j357 | 63 |  | 23.5 | 0.36 | 1.06 |  |  | 23.5 | 0.36 | 8.46 | 23.5 | 0.36 | 8.46 | Done
152 | j208 | j342 | 63 |  | 65.3 | 0.36 | 1.06
153 | j235 | j266 | 63 |  | 278.3 | 0.36 | 1.06
154 | j266 | j189 | 63 |  | 51.3 | 0.36 | 1.06
155 | j266 | j234 | 63 |  | 48.1 | 0.36 | 1.06
156 | j235 | j266 | 63 |  | 7 | 0.36 | 1.06 |  | b.t crossing | 7 | 0.36 | 2.52 | 7 | 0.36 | 2.52 | Done
157 | j266 | j189 | 63 |  | 5 | 0.36 | 1.06 |  | b.t crossing | 5 | 0.36 | 1.8 | 5 | 0.36 | 1.8 | Done
158 | j326 | j264 | 63 |  | 48 | 0.36 | 1.06
159 | j326 | j287 | 63 |  | 52 | 0.36 | 1.06
160 | j287 | j286 | 63 |  | 29 | 0.36 | 1.06
161 | j286 | j282 | 63 |  | 50 | 0.36 | 1.06
162 | j182 | j159 | 63 |  | 69 | 0.36 | 1.06
163 | j159 | j173 | 63 |  | 89 | 0.36 | 1.06
164 | j167 | j158 | 63 |  | 43 | 0.36 | 1.06 |  | brickroad | 43 | 0.36 | 15.48 | 43 | 0.36 | 15.48 | Done
165 | j321 | j365 | 63 |  | 200 | 0.36 | 1.06
166 | j315 | j315a | 63 |  | 50 | 0.36 | 1.06
167 | j134 | j134a | 63 |  | 50 | 0.36 | 1.06
168 | j117 | j118 | 63 |  | 37 | 0.36 | 1.06 |  | brick road | 37 | 0.36 | 13.32 | 37 | 0.36 | 13.32 | Done
169 | j117 | j121 | 63 |  | 20 | 0.36 | 1.06
170 | j121 | j127 | 63 |  | 28 | 0.36 | 1.06
171 | j128 | j130 | 63 |  | 30 | 0.36 | 1.06
172 | j229 | j197 | 125 |  | 48 | 0.42 | 1.12
173 | j264 | j209 | 63 |  | 29 | 0.36 | 1.06
174 | j209 | j289 | 63 |  | 22 | 0.36 | 1.06
175 | j209 | j169 | 63 |  | 22 | 0.36 | 1.06
176 | j205 | j181 | 63 |  | 119 | 0.36 | 1.06
177 | j181 | j202 | 63 |  | 72 | 0.36 | 1.06
178 | j181 | j181a | 63 |  | 198 | 0.36 | 1.06
179 | j205 | j202 | 63 |  | 3.5 | 0.36 | 1.06 |  | b.t crossing | 3.5 | 0.36 | 1.26 | 3.5 | 0.36 | 1.26 | Done
180 | j205 | j202 | 63 |  | 89.1 | 0.36 | 1.06 |  | brick road | 89.1 | 0.36 | 32.076 | 89.1 | 0.36 | 32.076 | Done
181 | j205 | j202 | 63 |  | 105.3 | 0.36 | 1.06
182 | j234 | j220 | 63 |  | 61.1 | 0.36 | 1.06
183 | j220 | j218 | 63 |  | 27 | 0.36 | 1.06 |  | brick road | 27 | 0.36 | 9.72 | 27 | 0.36 | 9.72 | Done
184 | j218 | j200 | 63 |  | 83.3 | 0.36 | 1.06
185 | j291 | j263 | 63 |  | 51.1 | 0.36 | 1.06 |  | brick road | 51.1 | 0.36 | 18.396 | 51.1 | 0.36 | 18.396 | Done
186 | j326 | 286 | 63 |  | 96.3 | 0.36 | 1.06 |  | brick road | 96.3 | 0.36 | 34.668 | 96.3 | 0.36 | 34.668 | Done
187 | j286 | j282 | 63 |  | 35 | 0.36 | 1.06
188 | j286 | j293 | 63 |  | 36.1 | 0.36 | 1.06
189 | j326 | j169 | 63 |  | 98.1 | 0.36 | 1.06
190 | j224 | j273 | 63 |  | 70.2 | 0.36 | 1.06 |  | brick road | 70.2 | 0.36 | 25.272 | 70.2 | 0.36 | 25.272 | Done
191 | j175 | j273 | 63 |  | 77.1 | 0.36 | 1.06
192 | j224 | j273 | 63 |  | 7 | 0.36 | 1.06 |  | b.t road crossing | 7 | 0.36 | 2.52 | 7 | 0.36 | 2.52 | Done
193 | j273 | j247 | 63 |  | 56 | 0.36 | 1.06 |  | brick road | 56 | 0.36 | 20.16 | 56 | 0.36 | 20.16 | Done
194 | j247 | j303 | 63 |  | 30.9 | 0.36 | 1.06
195 | j247 | j294 | 63 |  | 9.6 | 0.36 | 1.06
196 | j246 | j294 | 63 |  | 246.3 | 0.36 | 1.06
197 | j259 | j102 | 110 |  | 53.4 | 0.36 | 1.06
198 | j246 | j294 | 63 |  | 5 | 0.36 | 1.06 |  | b.t road crossing | 63 | 5 | 315 | 63 | 5 | 315 | Done
199 | j248 | j171 | 110 |  | 89.1 | 0.36 | 1.06 |  | brick road | 110 | 89.1 | 9801 | 110 | 89.1 | 9801 | Done
200 | j109 | j145 | 63 |  | 110.7 | 0.36 | 1.06
201 | j194 | j122 | 63 |  | 29.3 | 0.36 | 1.06
202 | j122 | j170 | 63 |  | 11.2 | 0.36 | 1.06 |  | brick road | 11.2 | 0.36 | 4.032 | 11.2 | 0.36 | 4.032 | Done
203 | j122 | j170 | 63 |  | 21.7 | 0.36 | 1.06
204 | j170 | j296 | 63 |  | 62.2 | 0.36 | 1.06 |  | brick road | 62.2 | 0.36 | 22.392 | 62.2 | 0.36 | 22.392 | Done
205 | j296 | j145 | 63 |  | 19.3 | 0.36 | 1.06
206 | j229 | j197 | 140 |  | 39.1 | 0.36 | 1.06
207 | j177 | j168 | 63 |  | 55.3 | 0.36 | 1.06
208 | j138 | j48 | 63 |  | 56.3 | 0.36 | 1.06
209 | j159 | j173 | 63 |  | 66.8 | 0.36 | 1.06
210 | j235 | j158 | 63 |  | 290.3 | 0.36 | 1.06
211 | j158 | j167 | 63 |  | 4.7 | 0.36 | 1.06 |  | b.t road crossing | 4.7 | 0.36 | 1.692 | 4.7 | 0.36 | 1.692 | Done
212 | j158 | j167 | 63 |  | 46 | 0.36 | 1.06
213 | j138 | j48 | 63 |  | 4 | 0.36 | 1.06 |  | road crossing | 4 | 0.36 | 1.44 | 4 | 0.36 | 1.44 | Done
214 | j92 | j329 | 63 | 174 | 157 | 0.36 | 1.06
215 | j271(1) | j271(2) | 63 |  | 270 | 0.36 | 1.06
216 | j155 | j155(1) | 63 |  | 105 | 0.36 | 1.06
217 | j265 | j284 | 63 | 33 | 46 | 0.36 | 1.06
218 | j265 | j280 | 63 | 29 | 49 | 0.36 | 1.06
219 | j265 | j314 | 63 | 15 | 19 | 0.36 | 1.06
220 | j138 | j48 | 63 |  | 270 | 0.36 | 1.06
[5 empty] | 23409.3 | [9 empty] | 2162.296
Abstract (Bill Breakup)
1 | Dia of Pipe | WO/DPR Qty's | Laying, Jointing, Backfilling - 60% |  |  |  | Gap Closing- 5% |  |  |  | Hydro Test - 15% |  |  |  | FHTC Stretch - 10%
|  |  | Laying Up to Date | Laying Qty Billed up to Date | Qty Billed Up to Previous | This Bill Qty (Laying) | WO/DPR Qty's | GAP Closing Billed Qty up to Date | GAP Closing Qty Up to Previous | This Bill Qty (GAP Closing) | WO/DPR Qty's | Hydro Test Qty Billed up to Date | Hydro Test Qty Up to Previous | This Bill Qty (Hydro Test ) | FHTC Stretch Qty Billed up to Date | FHTC Stretch Qty Billed Up to Previous | This Bill Qty (FHTC Stretch Billed )
1.1 | 63 mm HDPE |  | 19663.3 | 3896 | 16781.5 | 2881.8 |  | 19663.3 | 16781.5 | 2881.8 |  | 19663.3 | 16781.5 | 2881.8
1.2 | 75 mm HDPE |  | 150 |  | 150 | 0 |  | 150 | 150 | 0 |  | 150 | 150 | 0
1.3 | 90 mm HDPE |  | 60.3 |  | 60.3 | 0 |  | 60.3 | 60.3 | 0 |  | 60.3 | 60.3 | 0
1.4 | 110mm HDPE |  | 453.6 |  | 311.1 | 142.5 |  | 453.6 | 311.1 | 142.5 |  | 453.6 | 311.1 | 142.5
1.5 | 125mm HDPE |  | 388.7 |  | 388.7 | 0 |  | 388.7 | 388.7 | 0 |  | 388.7 | 388.7 | 0
1.6 | 140mm HDPE |  | 618.4 |  | 579.3 | 39.1 |  | 618.4 | 579.3 | 39.1 |  | 618.4 | 579.3 | 39.1
1.7 | 160mm HDPE |  | 565 |  | 565 | 0 |  | 565 | 565 | 0 |  | 565 | 565 | 0
1.8 | 180mm HDPE |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
1.9 | 200mm HDPE |  | 1510 |  | 1510 | 0 |  | 1510 | 1510 | 0 |  | 1510 | 1510 | 0
Sub Total = |  |  | 23409.3 | 3896 | 20345.9 | 3063.4 |  | 23409.3 | 20345.9 | 3063.4 |  | 23409.3 | 20345.9 | 3063.4
Sub-Contractor Site Engineer (Sr.Eng/ DY.M-SMX ) (Dy.M-PMX ) AGM Project Incharge
|  |  | 63 |  | 75 | 90 | 110 | 125 | 140 | 160 | 200
|  |  | 19663.3 | 0 | 150 | 60.3 | 453.6 | 388.7 | 618.4 | 565 | 1510 | 23409.3
10404
9259.3
6377
20192

## lakh BRAHUPUR
HYDRO TEST/ GAP CLOSING/ FHTC STRETCH/VALVE FITTING/COMMISIONING ACKNOWLEDGEMENT
Contractor Name:tanish project company
Block:mangraura |  |  | GP: brahapur
Billing Month:june |  |  | RAB No:7
Approved for RAB Quantities : (Tick Whichever is Proposing)
| Hydrotest |  |  |  | √
GAP Closing
FHTC Stretch
Valve Fitting
Commisioning
S. No. | Pipe Dia | Scope Qty | Upto date Laying Quantity | This Bill Quantity for Above Tic Marked Item | Cumm upto This Bill Quantity of Above Tic Marked Item | Remarks
1 | 63 |  | 19663.3 | 16781.5 | 2881.8
2 | 75 |  | 150 | 150 | 0
3 | 90 |  | 60.3 | 60.3 | 0
4 | 110 |  | 453.6 | 311.1 | 142.5
5 | 125 |  | 388.7 | 388.7 | 0
6 | 140 |  | 618.4 | 579.3 | 39.1
7 | 160 |  | 565 | 565 | 0
8 | 180 |  |  | 0 | 0
9 | 200 |  | 1510 | 1510 | 0
Note:
Sub-Contractor Site Engineer Block-incharge AGM PMX Incharge Project Incharge

## Recon Sheet
POWER MECH PROJECTS.LIMITED | [11 empty] | FHTC
RURAL WATER SUPPLY PROJECT UNDER JJM, UP - PRAYAGRAJ
Reconciliation Statement - Issued Vs Certification Qty.
| Contractor Name-tanish project limited |  | MONTH: | july | Block: | mangraura
| ABC Limited |  | BILL NO: |  | GP: | brahupur
Sl NO | Description | Units |  |  |  |  | Balance Qty | SAP Entry | Remarks | Upto date Consumption
|  |  | Total Issued Qty | Cumulative Consumption | Upto Pre Consumed Qty | This Bill Consumed Qty |  |  |  | GP | GP | GP | GP | Total Consumption upto This Bill |  | Entry Qty
A | HDPE Pipe :- | [8 empty] | BLOCK | BLOCK | BLOCK | BLOCK
1 | HDPE PIPE-63MM,PN-6,CLASS:PE-100,IS:4984 | Rmt | 11136 | 9259.3 | 6377.5 | 2881.8 | 1876.7 | 4474 | [5 empty] | 0 | 1200000251 | -6377.5 |  | 2481.5
2 | HDPE PIPE-75MM,PN-6,CLASS:PE-100 | Rmt |  |  |  | 0 | [7 empty] | 0 | 1200000332 | 0 |  | 100
3 | HDPE PIPE-90MM,PN-6,CLASS:PE-100 | Rmt |  |  |  | 0 | [7 empty] | 0 | 1200000333 | 0 |  | 60.3
4 | HDPE PIPE-110MM,PN-6,CLASS:PE-100 | Rmt |  |  |  | 142.5 | [7 empty] | 0 | 1200000334 | 0 |  | 11.1
5 | HDPE PIPE-125MM,PN-6,CLASS:PE-100,IS4984 | Rmt | 252 |  |  | 0 | [7 empty] | 0 | 1200000252 | 0 |  | 187.7
6 | HDPE PIPE-140MM,PN-6,CLASS:PE-100,IS4984 | Rmt | 498 |  |  | 39.1 | [7 empty] | 0 | 1200000253 | 0 |  | 383.3
7 | HDPE PIPE-160MM,PN-6,CLASS:PE-100 | Rmt | 360 |  |  | 0 | [7 empty] | 0 | 1200000335 | 0 |  | 360
8 | HDPE PIPE-200MM,PN-6,CLASS:PE-100,IS4984 | Rmt | 153 |  |  | 0 | [7 empty] | 0 | 1200000255 | 0
9 | DI PIPE-Ø200MM , K7,IS:8329 | Rmt | [11 empty] | 0 | 900007097 | 0 |  | -153
10 | HDPE PIPE-250MM,PN-6,CLASS:PE-100,IS4984 | Rmt | [11 empty] | 0 | 1200000256 | 0 |  | 7633
| Total Qty In ( Rmt ) = |  | 12399 | 9259.3 |  | 3063.4
B | Specials :-
| Equal Tee | [12 empty] | 0 |  | 0 | 3450
1 | HDPE-63X63X63MM,PN-6,R-TEE,CLASS:PE-100 | Nos | 55 | 55 |  | 55 |  | 4474 | [5 empty] | 0 | 200030286 | 0 | 3135
2 | HDPE-75X75X75MM,PN-6,R-TEE,CLASS:PE-100 | Nos | [11 empty] | 0 | 200030287 | 0 | 1140
3 | HDPE-90X90X90MM,PN-6,R-TEE,CLASS:PE-100 | Nos | [11 empty] | 0 | 200030288 | 0 | 796
4 | HDPE-110X110X110MM,PN-6,R-TEE,CL:PE-100 | Nos | [11 empty] | 0 | 200030289 | 0 | 830
5 | HDPE 125mm X 125mm X 125mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032212 | 0 | 900
6 | HDPE-140X140X140MM,PN-6,R-TEE,CL:PE-100 | Nos | [11 empty] | 0 | 200030291 | 0 | 485
7 | HDPE-160X160X160MM,PN-6,R-TEE,CL:PE-100 | Nos | [11 empty] | 0 | 200030293 | 0 | 400
8 | HDPE 200X200X200 MM, PN-6, R-TEE, CLASS: | Nos | [11 empty] | 0 | 200030300 | 0
Total Qty In ( Rmt ) =
C | Branch TEE | [14 empty] | 0
1 | HDPE BRANCH TEE 63MM X 63MM X 50MM | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032593 | 0
2 | HDPE 75MM X 75MM X 50MM PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032575 | 0
3 | HDPE 75mm X 75mm X 63mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032202 | 0
4 | HDPE 90mm X 90mm X 50mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032233 | 0
5 | HDPE 90mm X 90mm X 63mm, PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032203 | 0
6 | HDPE 90mm X 90mm X 75mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032204 | 0
7 | HDPE 110mm X 110mm X 50mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032234 | 0
8 | HDPE 110mm X 110mm X 63mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032205 | 0
9 | HDPE 110mm X 110mm X 75mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032206 | 0
10 | HDPE 110mm X 110mm X 90mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032207 | 0
11 | HDPE 125mm X 125mm X 50mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032235 | 0
12 | HDPE 125mm X 125mm X 63mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032208 | 0
13 | HDPE 125mm X 125mm X 75mm PN6 TEE PE100 | Nos | 3 |  |  |  |  | 4474 | [5 empty] | 0 | 200032209 | 0
14 | HDPE 125mm X 125mm X 90mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032210 | 0
15 | HDPE 125mm X 125mm X 110mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032211 | 0
16 | HDPE Branch TEE 140mm X 140mm X 50mm | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032236 | 0
17 | HDPE 140mm X 140mm X 63mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032213 | 0
18 | HDPE 140mm X 140mm X 75mm PN6 TEE PE100 | Nos | 2 | [10 empty] | 0 | 200032214 | 0
19 | HDPE 140mm X 140mm X 110mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032215 | 0
20 | HDPE Branch TEE 140mm X 140mm X 125mm | Nos | [11 empty] | 0 | 200032216 | 0
21 | HDPE-140X90X140MM,PN-6,R-TEE,CL:PE-100 | Nos | [11 empty] | 0 | 200030290 | 0
22 | HDPE 160mm X 160mm X 50mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032237 | 0
23 | HDPE 160mm X 160mm X 63mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032217 | 0
24 | HDPE 160mm X 160mm X 75mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032218 | 0
25 | HDPE 160mm X 160mm X 90mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032219 | 0
26 | HDPE-160X110X160MM,PN-6,R-TEE,CL:PE-100 | Nos | [11 empty] | 0 | 200030292 | 0
27 | HDPE 160mm X 160mm X 125mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032220 | 0
28 | HDPE 200mm X 200mm X 63mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032222 | 0
29 | HDPE 200X75X200 MM, PN-6, R-TEE, CLASS:P | Nos | [11 empty] | 0 | 200030297 | 0
30 | HDPE 200X90X200 MM, PN-6, R-TEE, CLASS:P | Nos | [11 empty] | 0 | 200030298 | 0
31 | HDPE 200mm X 200mm X 110mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032223 | 0
32 | HDPE 200mm X 200mm X 160mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032225 | 0
33 | HDPE 250mm X 250mm X 90mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032228 | 0
Total Qty In ( Rmt ) =
D | 4 Way Tee | [14 empty] | 0
1 | HDPE 63MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030301 | 0
2 | HDPE 75MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | 7 | [10 empty] | 0 | 200030302 | 0
3 | HDPE 90MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030303 | 0
4 | HDPE 110MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | 8 | [10 empty] | 0 | 200030304 | 0
5 | HDPE125MM,PN6,4WAY CROSS FITTING,CLPE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032584 | 0
6 | HDPE 140MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [11 empty] | 0 | 200030305 | 0
7 | HDPE 160MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030306 | 0
8 | HDPE200MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [11 empty] | 0 | 200030308 | 0
Total Qty In ( No's ) =
E | Reducers
1 | HDPE-75MM,PN6, 63MM,ENLARGER,CLASS:PE100 | Nos | 1 |  |  |  |  | 4474 | [5 empty] | 0 | 200030309 | 0
2 | HDPE-90MM,PN6, 63MM,ENLARGER,CLASS:PE100 | Nos | [11 empty] | 0 | 200030311 | 0
3 | HDPE-90MM,PN6, 75MM,ENLARGER,CLASS:PE100 | Nos | [11 empty] | 0 | 200030310 | 0
4 | HDPE-110MM,PN6,63MM,ENLARGER,CLASS:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030314 | 0
5 | HDPE-110MM,PN6,75MM,ENLARGER,CLASS:PE100 | Nos | 5 | [10 empty] | 0 | 200030312 | 0
6 | HDPE-110MM,PN6,90MM,ENLARGER,CLASS:PE100 | Nos | 5 | [10 empty] | 0 | 200030313 | 0
7 | HDPE-125MM,PN6, 63MM Reducer PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032241 | 0
8 | HDPE-125MM,PN6, 75MM Reducer PE100 | Nos | [11 empty] | 0 | 200032239 | 0
9 | HDPE-125MM,PN6, 90MM Reducer PE100 | Nos | [11 empty] | 0 | 200032240 | 0
10 | HDPE-125MM,PN6, 110MM Reducer PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032242 | 0
11 | HDPE-140MM,PN6,63MM,ENLARGER,CL:PE100 | Nos | 4 | [10 empty] | 0 | 200030320 | 0
12 | HDPE-140MM,PN6, 75MM Reducer PE100 | Nos | [11 empty] | 0 | 200032243 | 0
13 | HDPE-140MM,PN6,90MM,ENLARGER,CL:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030317 | 0
14 | HDPE-140MM,PN6,110MM,ENLARGER,CL:PE100 | Nos | [11 empty] | 0 | 200030315 | 0
15 | HDPE-140MM,PN6,125MM,ENLARGER,CL:PE100 | Nos | [11 empty] | 0 | 200030316 | 0
16 | HDPE-160MM,PN6,63MM Reducer PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032247 | 0
17 | HDPE-160MM,PN6,75MM Reducer PE100 | Nos | [11 empty] | 0 | 200032246 | 0
18 | HDPE-160MM,PN6,90MM Reducer PE100 | Nos | [11 empty] | 0 | 200032245 | 0
19 | HDPE-160MM,PN6,110MM,ENLARGER,CL:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030319 | 0
20 | HDPE-160MM,PN6, 125MM Reducer PE100 | Nos | [11 empty] | 0 | 200032244 | 0
21 | HDPE-160MM,PN6,140MM,ENLARGER,CL:PE100 | Nos | [11 empty] | 0 | 200030318 | 0
22 | HDPE-200MM,PN6,75MM Reducer PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032249 | 0
23 | HDPE-200MM,PN6,90MM,ENLARGER,CLASS:PE100 | Nos | [11 empty] | 0 | 200030326 | 0
24 | HDPE-200MM,PN6,110MM Reducer PE100 | Nos | [11 empty] | 0 | 200032248 | 0
25 | HDPE-200MM,PN6,140MM,ENLARGER,CL:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030325 | 0
26 | HDPE-200MM,PN6,160MM,ENLARGER,CL:PE100 | Nos | [11 empty] | 0 | 200030328 | 0
27 | HDPE-200MM,PN6,63MM,ENLARGER,CLASS:PE100 | Nos | [11 empty] | 0 | 200030327 | 0
28 | HDPE Reducer 200mm X 125mm | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200034192 | 0
Total Qty In ( No's ) =
F | Bends 45 Degree
1 | HDPE BEND-63MM,PN6 45DEG PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032193 | 0
2 | HDPE BEND-90MM, PN6 45DEG PE100 | Nos | [11 empty] | 0 | 200032195 | 0
3 | HDPE BEND-110MM, PN6 45DEG PE100 | Nos | [11 empty] | 0 | 200032196 | 0
4 | HDPE BEND-75MM,PN6 45DEG PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032194 | 0
5 | HDPE BEND-125MM,PN-6,90DEG,CLASS:PE-100 | Nos | [11 empty] | 0 | 200030270 | 0
6 | HDPE BEND-125MM, PN6 45DEG PE100 | Nos | [11 empty] | 0 | 200032197 | 0
7 | HDPE BEND-140MM,PN-6,45DEG,CLASS:PE-100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030275 | 0
8 | HDPE BEND-160MM,PN-6,45DEG,CLASS:PE-100 | Nos | [11 empty] | 0 | 200030276 | 0
Total Qty In ( No's ) =
G | Bends 90Degree
1 | HDPE BEND-63MM,PN-6,90DEG,CLASS:PE-100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030266 | 0
2 | HDPE BEND-75MM,PN-6,90DEG,CLASS:PE-100 | Nos | [11 empty] | 0 | 200030267 | 0
3 | HDPE BEND-90MM,PN-6,90DEG,CLASS:PE-100 | Nos | [11 empty] | 0 | 200030268 | 0
4 | HDPE BEND-110MM,PN-6,90DEG,CLASS:PE-100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030269 | 0
5 | HDPE BEND-140MM,PN-6,90DEG,CLASS:PE-100 | Nos | [11 empty] | 0 | 200030271 | 0
6 | HDPE BEND-160MM,PN-6,90DEG,CLASS:PE-100 | Nos | [11 empty] | 0 | 200030272 | 0
7 | HDPE BEND-200MM,PN-6,90DEG,CLASS:PE-100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030274 | 0
Total Qty In ( No's ) =
H | End Caps
1 | HDPE-63MM,PN6,END CAP,CLASS:PE100 | Nos | 89 | 53 |  | 55 |  | 4474 | [5 empty] | 0 | 200030277 | #REF!
2 | HDPE-75MM,PN6,END CAP,CLASS:PE100 | Nos | [11 empty] | 0 | 200030278 | 0
3 | HDPE-90MM,PN6,END CAP,CLASS:PE100 | Nos | [11 empty] | 0 | 200030279 | 0
4 | HDPE-110MM,PN6,END CAP,CLASS:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030280 | 0
5 | HDPE-140MM,PN6,END CAP,CLASS:PE100 | Nos | [11 empty] | 0 | 200030282 | 0
Total Qty In ( No's ) =
1 | FHTC
1 | GI PIPE-15MM | Rmt | [5 empty] | 4474 |  | 0 | 0 |  |  | 0 | 1200000409 | 0
2 | MDPE PIPE-20MM | Rmt | [7 empty] | 0 | 0 |  |  | 0 | 1200000408 | 0
3 | BRASS TAP | Nos | [5 empty] | 4474 |  | 0 | 0 |  |  | 0 | 1200000231 | 0
4 | PP CLAMP SADLLE-63MM | Nos | [7 empty] | 0 |  |  |  | 0 | 1200000410 | 0
5 | PP CLAMP SADDLE-75MM | Nos | [11 empty] | 0 | 1200000425 | 0
6 | PP CLAMP SADLLE-90MM | Nos | [5 empty] | 4474 | [5 empty] | 0 | 1200000411 | 0
7 | PP CLAMP SADDLE-140MM | Nos | [11 empty] | 0 | 900008156 | 0
8 | PP CLAMP SADDLE-160MM | Nos | [11 empty] | 0 | 900008157 | 0
9 | PP CLAMP SADDLE-200MM | Nos | [5 empty] | 4474 | [5 empty] | 0 | 900008159 | 0
10 | PP CLAMP SADDLE 125MM WITH M8 FASTNERS | Nos | [11 empty] | 0 | 900008617 | 0
11 | PP CLAMP SADLLE-110MM | Nos | [11 empty] | 0 | 900007416 | 0
12 | G.I ELBOW 15 MM | Nos | [7 empty] | 0 | 0 |  |  | 0 | 1200000419 | 0
13 | GI SOCKET-15MM | Nos | [7 empty] | 0 | 0 |  |  | 0 | 1200000416 | 0
14 | WALL MOUNT SADDLE GI PIPE-15MM | Nos | [5 empty] | 4474 | [5 empty] | 0 | 1200000418 | 0
15 | 15MM GI NIPPLE - 0.3MTR LENGTH | Nos | [7 empty] | 0 | 0 |  |  | 0 | 1200000450 | 0
16 | 15MM GI NIPPLE - 0.5MTR LENGTH | Nos | [7 empty] | 0 | 0 |  |  | 0 | 1200000451 | 0
17 | 20MM MDPE COMPRESSION ELBOW | Nos | [7 empty] | 0 | 0 |  |  | 0 | 1200000448 | 0
18 | SS FLOW CONTROL VAlVE | Nos | [5 empty] | 4474 |  | 0 | 0 |  |  | 0 | 1200000417 | 0
19 | MDPE FEMLE THREADED ASSEMBLY-20MM | Nos | [7 empty] | 0 | 0 |  |  | 0 | 1200000414 | 0
20 | MDPE ELBOW-20MM | Nos | [11 empty] | 0 | 1200000415 | 0
21 | TEFLAN TAPE | Nos | [11 empty] | 0 | 200001364 | 0
22 | [13 empty] | 0 | #N/A | 0
Total Qty In ( No's ) =
Sub Contractor Site Engineer Block incharge AGM DM PMX Project Incharge
ENTRY NO:

## aurangabad 2
GOVERNMENT OF UTTAR PRADESH
STATE WATER & SANITATION MISSION ( SWSM )
Joint Measurement Report of Pipe Line
Name of the Work :- Survey , Design Preparation of DPR , Construction , Commissioning and O&M for 10 Years of Various Rural Water Supply Projects in the state of Uttar Pradesh as Per Request for Proposal for Division " Prayagraj "
Name of the Agency : POWER MECH PROJECTS LIMITED – BHOORATHNOM CONSTRUCTIONS COMPANY PRIVATE LIMITED (JV), Hyderabad.
Name OF Scheme |  | :aurangabad
Block |  | : Mangraura
Total Scope |  | :
JMR No. |  | : 2
Date of JMR |  | :
Sr. No. | Start Node | End Node | Dia | Pipe Length (as per Site) | Width | Depth | Quantity | Type OF Road | Dismantling Length | Dismantling Width | Dismantling Quantity | Restoration Length | Restoration Width | Restoration Quantity | Restoration Status | Remark
1 | j4 | j5 | 250 | 239 | 0.55 | 1.25 | [11 empty] | 55
2 | j5 | j7 | 250 | 54 | 0.55 | 1.25 | [11 empty] | 66
3 | j7 | j9 | 250 | 159 | 0.55 | 1.25 | [11 empty] | 44
4 | j91 | j91(1) | 63 | 200 | 0.363 | 1.06 | [11 empty] | 33
5 | 176 | 177 | 63 | 143.2 | 0.363 | 1.06 | [11 empty] | 55
54
Abstract (Bill Breakup) | [17 empty] | 33
1 | Dia of Pipe | WO/DPR Qty's | Laying, Jointing, Backfilling - 60% |  |  |  | Gap Closing- 5% |  |  |  | Hydro Test - 15% |  |  |  | FHTC Stretch - 10% |  |  | 44
|  |  | Laying Up to Date | Laying Qty Billed up to Date | Qty Billed Up to Previous | This Bill Qty (Laying) | WO/DPR Qty's | GAP Closing Billed Qty up to Date | GAP Closing Qty Up to Previous | This Bill Qty (GAP Closing) | WO/DPR Qty's | Hydro Test Qty Billed up to Date | Hydro Test Qty Up to Previous | This Bill Qty (Hydro Test ) | FHTC Stretch Qty Billed up to Date | FHTC Stretch Qty Billed Up to Previous | This Bill Qty (FHTC Stretch Billed ) | 384
1.1 | 63 mm HDPE |  |  | 5915.9 | 4192.7 | 343.2 |  |  |  | 343.2 |  |  | 343.2
1.2 | 75 mm HDPE |  |  | 2871.3 | 2160.3 |  |  |  |  | 0 |  |  | 0
1.3 | 90 mm HDPE |  |  | 2097.8 | 610.8 |  |  |  |  | 0 |  |  | 0 | [5 empty] | 4192.7
1.4 | 110mm HDPE |  |  | 987 | 587 |  |  |  |  | 0 |  |  | 0
1.5 | 125mm HDPE |  |  |  | 0 |  |  |  |  | 0 |  |  | 0 | [5 empty] | 5915.9
1.6 | 140mm HDPE |  |  | 3401 | 3401 |  |  |  |  | 0 |  |  | 0 | [5 empty] | 4535.9 | 4192.7
1.7 | 160mm HDPE |  |  | 3255.1 | 3255.1 |  |  |  |  | 0 |  |  | 0 | [6 empty] | 343.2
1.8 | 180mm HDPE |  |  |  | 0 |  |  |  |  | 0 |  |  | 0
1.9 | 200mm HDPE |  |  | 1647.8 | 1647.8 |  |  |  |  | 0 |  |  | 0
2 | 250mm HDPE |  |  | 472 |  | 452 |  |  |  | 452 |  |  | 452
Sub Total = |  |  |  | 20647.9 | 15854.7 | 795.2 |  |  |  | 795.2 |  |  | 795.2
Sub-Contractor Site Engineer (Sr.Eng/ DY.M-SMX ) (Dy.M-PMX ) AGM Project Incharge

## aurangabad rec
POWER MECH PROJECTS.LIMITED | [11 empty] | FHTC
RURAL WATER SUPPLY PROJECT UNDER JJM, UP - PRAYAGRAJ
Reconciliation Statement - Issued Vs Certification Qty.
| Contractor Name-TANISH ENTERPRISES |  | MONTH: | march | Block: | mangraura
| ABC Limited |  | BILL NO: |  | GP: | AURANGABAD
Sl NO | Description | Units |  |  |  |  | Balance Qty | SAP Entry | Remarks | Upto date Consumption
|  |  | Total Issued Qty | Cumulative Consumption | Upto Pre Consumed Qty | This Bill Consumed Qty |  |  |  | GP | GP | GP | GP | Total Consumption upto This Bill |  | Entry Qty
A | HDPE Pipe :- | [8 empty] | BLOCK | BLOCK | BLOCK | BLOCK
1 | HDPE PIPE-63MM,PN-6,CLASS:PE-100,IS:4984 | Rmt | 3670 | 5572.7 | 4272.7 | 343.2 |  | 4474 | 600metr shifted from madhura rani ganj and brahupur |  |  |  |  | 0 | 1200000251 | #REF! |  | 1902.7
2 | HDPE PIPE-75MM,PN-6,CLASS:PE-100 | Rmt | 2800 | 2871.3 |  |  |  |  | 1000 kavize shifted to tanish |  |  |  |  | 0 | 1200000332 | #REF!
3 | HDPE PIPE-90MM,PN-6,CLASS:PE-100 | Rmt | 701 | 2097.8 |  |  |  |  | 450 kavize shifted to tanish |  |  |  |  | 0 | 1200000333 | #REF!
4 | HDPE PIPE-110MM,PN-6,CLASS:PE-100 | Rmt | 925 | 987 | [9 empty] | 0 | 1200000334 | 0
5 | HDPE PIPE-125MM,PN-6,CLASS:PE-100,IS4984 | Rmt | [11 empty] | 0 | 1200000252 | 0
6 | HDPE PIPE-140MM,PN-6,CLASS:PE-100,IS4984 | Rmt | 3522 | 3401 | [9 empty] | 0 | 1200000253 | 0
7 | HDPE PIPE-160MM,PN-6,CLASS:PE-100 | Rmt | 2976 | 3255.1 | [9 empty] | 0 | 1200000335 | 0 | -279.1 | -279.1
8 | HDPE PIPE-200MM,PN-6,CLASS:PE-100,IS4984 | Rmt | 1668 | 1647.8 | [9 empty] | 0 | 1200000255 | #REF!
9 | DI PIPE-Ø200MM , K7,IS:8329 | Rmt | [11 empty] | 0 | 900007097 | 0
10 | HDPE PIPE-250MM,PN-6,CLASS:PE-100,IS4984 | Rmt | 487 |  |  | 452 |  |  | indent no-19391,19390 |  |  |  |  | 0 | 1200000256 | 0 | 1300
| Total Qty In ( Rmt ) = |  |  | 19832.7 |  | 795.2
B | Specials :-
| Equal Tee | [12 empty] | 0 |  | 0
1 | HDPE-63X63X63MM,PN-6,R-TEE,CLASS:PE-100 | Nos | 13 | 9 | - | 9 |  | 4474 | [5 empty] | 0 | 200030286 | #VALUE!
2 | HDPE-75X75X75MM,PN-6,R-TEE,CLASS:PE-100 | Nos | 5 | 3 |  | 3 | [7 empty] | 0 | 200030287 | 0
3 | HDPE-90X90X90MM,PN-6,R-TEE,CLASS:PE-100 | Nos | [11 empty] | 0 | 200030288 | 0
4 | HDPE-110X110X110MM,PN-6,R-TEE,CL:PE-100 | Nos | 5 | [10 empty] | 0 | 200030289 | 0
5 | HDPE 125mm X 125mm X 125mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032212 | 0
6 | HDPE-140X140X140MM,PN-6,R-TEE,CL:PE-100 | Nos | 5 | 5 |  | 5 | [7 empty] | 0 | 200030291 | 0
7 | HDPE-160X160X160MM,PN-6,R-TEE,CL:PE-100 | Nos | 5 | [10 empty] | 0 | 200030293 | 0
8 | HDPE 200X200X200 MM, PN-6, R-TEE, CLASS: | Nos | 5 | [10 empty] | 0 | 200030300 | 0
Total Qty In ( Rmt ) =
C | Branch TEE | [14 empty] | 0
1 | HDPE BRANCH TEE 63MM X 63MM X 50MM | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032593 | 0
2 | HDPE 75MM X 75MM X 50MM PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032575 | 0
3 | HDPE 75mm X 75mm X 63mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032202 | 0
4 | HDPE 90mm X 90mm X 50mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032233 | 0
5 | HDPE 90mm X 90mm X 63mm, PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032203 | 0
6 | HDPE 90mm X 90mm X 75mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032204 | 0
7 | HDPE 110mm X 110mm X 50mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032234 | 0
8 | HDPE 110mm X 110mm X 63mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032205 | 0
9 | HDPE 110mm X 110mm X 75mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032206 | 0
10 | HDPE 110mm X 110mm X 90mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032207 | 0
11 | HDPE 125mm X 125mm X 50mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032235 | 0
12 | HDPE 125mm X 125mm X 63mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032208 | 0
13 | HDPE 125mm X 125mm X 75mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032209 | 0
14 | HDPE 125mm X 125mm X 90mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032210 | 0
15 | HDPE 125mm X 125mm X 110mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032211 | 0
16 | HDPE Branch TEE 140mm X 140mm X 50mm | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032236 | 0
17 | HDPE 140mm X 140mm X 63mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032213 | 0
18 | HDPE 140mm X 140mm X 75mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032214 | 0
19 | HDPE 140mm X 140mm X 110mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032215 | 0
20 | HDPE Branch TEE 140mm X 140mm X 125mm | Nos | [11 empty] | 0 | 200032216 | 0
21 | HDPE-140X90X140MM,PN-6,R-TEE,CL:PE-100 | Nos | [11 empty] | 0 | 200030290 | 0
22 | HDPE 160mm X 160mm X 50mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032237 | 0
23 | HDPE 160mm X 160mm X 63mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032217 | 0
24 | HDPE 160mm X 160mm X 75mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032218 | 0
25 | HDPE 160mm X 160mm X 90mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032219 | 0
26 | HDPE-160X110X160MM,PN-6,R-TEE,CL:PE-100 | Nos | [11 empty] | 0 | 200030292 | 0
27 | HDPE 160mm X 160mm X 125mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032220 | 0
28 | HDPE 200mm X 200mm X 63mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032222 | 0
29 | HDPE 200X75X200 MM, PN-6, R-TEE, CLASS:P | Nos | [11 empty] | 0 | 200030297 | 0
30 | HDPE 200X90X200 MM, PN-6, R-TEE, CLASS:P | Nos | [11 empty] | 0 | 200030298 | 0
31 | HDPE 200mm X 200mm X 110mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032223 | 0
32 | HDPE 200mm X 200mm X 160mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032225 | 0
33 | HDPE 250mm X 250mm X 90mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032228 | 0
Total Qty In ( Rmt ) =
D | 4 Way Tee | [14 empty] | 0
1 | HDPE 63MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030301 | 0
2 | HDPE 75MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [11 empty] | 0 | 200030302 | 0
3 | HDPE 90MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030303 | 0
4 | HDPE 110MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [11 empty] | 0 | 200030304 | 0
5 | HDPE125MM,PN6,4WAY CROSS FITTING,CLPE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032584 | 0
6 | HDPE 140MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [11 empty] | 0 | 200030305 | 0
7 | HDPE 160MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030306 | 0
8 | HDPE200MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [11 empty] | 0 | 200030308 | 0
Total Qty In ( No's ) =
E | Reducers
1 | HDPE-75MM,PN6, 63MM,ENLARGER,CLASS:PE100 | Nos | 5 |  |  |  |  | 4474 | [5 empty] | 0 | 200030309 | 0
2 | HDPE-90MM,PN6, 63MM,ENLARGER,CLASS:PE100 | Nos | [11 empty] | 0 | 200030311 | 0
3 | HDPE-90MM,PN6, 75MM,ENLARGER,CLASS:PE100 | Nos | [11 empty] | 0 | 200030310 | 0
4 | HDPE-110MM,PN6,63MM,ENLARGER,CLASS:PE100 | Nos | 10 |  |  |  |  | 4474 | [5 empty] | 0 | 200030314 | 0
5 | HDPE-110MM,PN6,75MM,ENLARGER,CLASS:PE100 | Nos | 5 | [10 empty] | 0 | 200030312 | 0
6 | HDPE-110MM,PN6,90MM,ENLARGER,CLASS:PE100 | Nos | 5 | [10 empty] | 0 | 200030313 | 0
7 | HDPE-125MM,PN6, 63MM Reducer PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032241 | 0
8 | HDPE-125MM,PN6, 75MM Reducer PE100 | Nos | [11 empty] | 0 | 200032239 | 0
9 | HDPE-125MM,PN6, 90MM Reducer PE100 | Nos | [11 empty] | 0 | 200032240 | 0
10 | HDPE-125MM,PN6, 110MM Reducer PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032242 | 0
11 | HDPE-140MM,PN6,63MM,ENLARGER,CL:PE100 | Nos | 10 | 5 |  | 5 | [7 empty] | 0 | 200030320 | 0
12 | HDPE-140MM,PN6, 75MM Reducer PE100 | Nos | [11 empty] | 0 | 200032243 | 0
13 | HDPE-140MM,PN6,90MM,ENLARGER,CL:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030317 | 0
14 | HDPE-140MM,PN6,110MM,ENLARGER,CL:PE100 | Nos | [11 empty] | 0 | 200030315 | 0
15 | HDPE-140MM,PN6,125MM,ENLARGER,CL:PE100 | Nos | [11 empty] | 0 | 200030316 | 0
16 | HDPE-160MM,PN6,63MM Reducer PE100 | Nos | 5 |  |  |  |  | 4474 | [5 empty] | 0 | 200032247 | 0
17 | HDPE-160MM,PN6,75MM Reducer PE100 | Nos | [11 empty] | 0 | 200032246 | 0
18 | HDPE-160MM,PN6,90MM Reducer PE100 | Nos | [11 empty] | 0 | 200032245 | 0
19 | HDPE-160MM,PN6,110MM,ENLARGER,CL:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030319 | 0
20 | HDPE-160MM,PN6, 125MM Reducer PE100 | Nos | [11 empty] | 0 | 200032244 | 0
21 | HDPE-160MM,PN6,140MM,ENLARGER,CL:PE100 | Nos | [11 empty] | 0 | 200030318 | 0
22 | HDPE-200MM,PN6,75MM Reducer PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032249 | 0
23 | HDPE-200MM,PN6,90MM,ENLARGER,CLASS:PE100 | Nos | [11 empty] | 0 | 200030326 | 0
24 | HDPE-200MM,PN6,110MM Reducer PE100 | Nos | [11 empty] | 0 | 200032248 | 0
25 | HDPE-200MM,PN6,140MM,ENLARGER,CL:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030325 | 0
26 | HDPE-200MM,PN6,160MM,ENLARGER,CL:PE100 | Nos | [11 empty] | 0 | 200030328 | 0
27 | HDPE-200MM,PN6,63MM,ENLARGER,CLASS:PE100 | Nos | [11 empty] | 0 | 200030327 | 0
28 | HDPE Reducer 200mm X 125mm | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200034192 | 0
Total Qty In ( No's ) =
F | Bends 45 Degree
1 | HDPE BEND-63MM,PN6 45DEG PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032193 | 0
2 | HDPE BEND-90MM, PN6 45DEG PE100 | Nos | [11 empty] | 0 | 200032195 | 0
3 | HDPE BEND-110MM, PN6 45DEG PE100 | Nos | [11 empty] | 0 | 200032196 | 0
4 | HDPE BEND-75MM,PN6 45DEG PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032194 | 0
5 | HDPE BEND-125MM,PN-6,90DEG,CLASS:PE-100 | Nos | [11 empty] | 0 | 200030270 | 0
6 | HDPE BEND-125MM, PN6 45DEG PE100 | Nos | [11 empty] | 0 | 200032197 | 0
7 | HDPE BEND-140MM,PN-6,45DEG,CLASS:PE-100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030275 | 0
8 | HDPE BEND-160MM,PN-6,45DEG,CLASS:PE-100 | Nos | [11 empty] | 0 | 200030276 | 0
Total Qty In ( No's ) =
G | Bends 90Degree
1 | HDPE BEND-63MM,PN-6,90DEG,CLASS:PE-100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030266 | 0
2 | HDPE BEND-75MM,PN-6,90DEG,CLASS:PE-100 | Nos | [11 empty] | 0 | 200030267 | 0
3 | HDPE BEND-90MM,PN-6,90DEG,CLASS:PE-100 | Nos | [11 empty] | 0 | 200030268 | 0
4 | HDPE BEND-110MM,PN-6,90DEG,CLASS:PE-100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030269 | 0
5 | HDPE BEND-140MM,PN-6,90DEG,CLASS:PE-100 | Nos | 5 | [10 empty] | 0 | 200030271 | 0
6 | HDPE BEND-160MM,PN-6,90DEG,CLASS:PE-100 | Nos | 5 | [10 empty] | 0 | 200030272 | 0
7 | HDPE BEND-200MM,PN-6,90DEG,CLASS:PE-100 | 2-03-20424 | [5 empty] | 4474 | [5 empty] | 0 | 200030274 | 0
Total Qty In ( No's ) =
H | End Caps
1 | HDPE-63MM,PN6,END CAP,CLASS:PE100 | Nos |  | 13 |  | 13 |  | 4474 | [5 empty] | 0 | 200030277 | 0
2 | HDPE-75MM,PN6,END CAP,CLASS:PE100 | Nos | [11 empty] | 0 | 200030278 | 0
3 | HDPE-90MM,PN6,END CAP,CLASS:PE100 | Nos | [11 empty] | 0 | 200030279 | 0
4 | HDPE-110MM,PN6,END CAP,CLASS:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030280 | 0
5 | HDPE-140MM,PN6,END CAP,CLASS:PE100 | Nos | [11 empty] | 0 | 200030282 | 0
Total Qty In ( No's ) =
1 | FHTC
1 | GI PIPE-15MM | Rmt | [5 empty] | 4474 |  | 0 | 0 |  |  | 0 | 1200000409 | 0
2 | MDPE PIPE-20MM | Rmt | [7 empty] | 0 | 0 |  |  | 0 | 1200000408 | 0
3 | BRASS TAP | Nos | [5 empty] | 4474 |  | 0 | 0 |  |  | 0 | 1200000231 | 0
4 | PP CLAMP SADLLE-63MM | Nos | [7 empty] | 0 |  |  |  | 0 | 1200000410 | 0
5 | PP CLAMP SADDLE-75MM | Nos | [11 empty] | 0 | 1200000425 | 0
6 | PP CLAMP SADLLE-90MM | Nos | [5 empty] | 4474 | [5 empty] | 0 | 1200000411 | 0
7 | PP CLAMP SADDLE-140MM | Nos | [11 empty] | 0 | 900008156 | 0
8 | PP CLAMP SADDLE-160MM | Nos | [11 empty] | 0 | 900008157 | 0
9 | PP CLAMP SADDLE-200MM | Nos | [5 empty] | 4474 | [5 empty] | 0 | 900008159 | 0
10 | PP CLAMP SADDLE 125MM WITH M8 FASTNERS | Nos | [11 empty] | 0 | 900008617 | 0
11 | PP CLAMP SADLLE-110MM | Nos | [11 empty] | 0 | 900007416 | 0
12 | G.I ELBOW 15 MM | Nos | [7 empty] | 0 | 0 |  |  | 0 | 1200000419 | 0
13 | GI SOCKET-15MM | Nos | [7 empty] | 0 | 0 |  |  | 0 | 1200000416 | 0
14 | WALL MOUNT SADDLE GI PIPE-15MM | Nos | [5 empty] | 4474 | [5 empty] | 0 | 1200000418 | 0
15 | 15MM GI NIPPLE - 0.3MTR LENGTH | Nos | [7 empty] | 0 | 0 |  |  | 0 | 1200000450 | 0
16 | 15MM GI NIPPLE - 0.5MTR LENGTH | Nos | [7 empty] | 0 | 0 |  |  | 0 | 1200000451 | 0
17 | 20MM MDPE COMPRESSION ELBOW | Nos | [7 empty] | 0 | 0 |  |  | 0 | 1200000448 | 0
18 | SS FLOW CONTROL VAlVE | Nos | [5 empty] | 4474 |  | 0 | 0 |  |  | 0 | 1200000417 | 0
19 | MDPE FEMLE THREADED ASSEMBLY-20MM | Nos | [7 empty] | 0 | 0 |  |  | 0 | 1200000414 | 0
20 | MDPE ELBOW-20MM | Nos | [11 empty] | 0 | 1200000415 | 0
21 | TEFLAN TAPE | Nos |  |  |  |  | 0 | [6 empty] | 0 | 200001364 | 0
22 | [6 empty] | 0 | [6 empty] | 0 | #N/A | 0
Total Qty In ( No's ) =
Sub Contractor Site Engineer Block incharge AGM DM PMX Project Incharge
ENTRY NO:

## madhura arani ganj 4
GOVERNMENT OF UTTAR PRADESH
STATE WATER & SANITATION MISSION ( SWSM )
Joint Measurement Report of Pipe Line
Name of the Work :- Survey , Design Preparation of DPR , Construction , Commissioning and O&M for 10 Years of Various Rural Water Supply Projects in the state of Uttar Pradesh as Per Request for Proposal for Division " Prayagraj "
Name of the Agency : POWER MECH PROJECTS LIMITED – BHOORATHNOM CONSTRUCTIONS COMPANY PRIVATE LIMITED (JV), Hyderabad.
Name OF Scheme |  | :madhura rani ganj
Block |  | : Mangraura
Total Scope |  | :
JMR No. |  | : 1
Date of JMR |  | :
Sr. No. | Start Node | End Node | Dia | Pipe Length (as per Drawing) | Pipe Length (as per Site) | Width | Depth | Quantity | Type OF Road | Dismantling Length | Dismantling Width | Dismantling Quantity | Restoration Length | Restoration Width | Restoration Quantity | Restoration Status | Remark
1 | j1(1) | j1 | 200 |  | 171 | 0.5 | 1.2
2 | j2 | j23 | 200 |  | 106 | 0.5 | 1.2
3 | j590 | j592 | 63 |  | 219 | 0.36 | 1.06
4 | j162 | j230 | 63 |  | 525 | 0.36 | 1.06
5 | j38 | j138 | 63 |  | 325.4 | 0.36 | 1.06
6 | j21 | j22 | 63 |  | 300 | 0.36 | 1.06
7 | j44 | j44(1) | 63 |  | 156.2 | 0.36 | 1.06
8 | j112 | j112(1) | 63 |  | 205.3 | 0.36 | 1.06
[5 empty] | 2007.9 | [12 empty] | 2502.9
Abstract (Bill Breakup)
1 | Dia of Pipe | WO/DPR Qty's | Laying, Jointing, Backfilling - 60% |  |  |  | Gap Closing- 5% |  |  |  | Hydro Test - 15% |  |  |  | FHTC Stretch - 10%
|  |  | Laying Up to Date | Laying Qty Billed up to Date | Qty Billed Up to Previous | This Bill Qty (Laying) | WO/DPR Qty's | GAP Closing Billed Qty up to Date | GAP Closing Qty Up to Previous | This Bill Qty (GAP Closing) | WO/DPR Qty's | Hydro Test Qty Billed up to Date | Hydro Test Qty Up to Previous | This Bill Qty (Hydro Test ) | FHTC Stretch Qty Billed up to Date | FHTC Stretch Qty Billed Up to Previous | This Bill Qty (FHTC Stretch Billed )
1.1 | 63 mm HDPE |  |  | 22013.3 | 20282.4 | 1730.9 |  |  |  | 1730.9 |  |  |  | 1730.9
1.2 | 75 mm HDPE |  |  |  | 0 | 0 |  |  |  | 0 |  |  |  | 0
1.3 | 90 mm HDPE |  |  | 258.1 | 258.1 | 0 |  |  |  | 0 |  |  |  | 0
1.4 | 110mm HDPE |  |  | 858.7 | 858.7 | 0 |  |  |  | 0 |  |  |  | 0
1.5 | 125mm HDPE |  |  | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0
1.6 | 140mm HDPE |  |  | 2913.9 | 2913.9 | 0 |  |  |  | 0 |  |  |  | 0
1.7 | 160mm HDPE |  |  | 5126.3 | 5126.3 | 0 |  |  |  | 0 |  |  |  | 0
1.8 | 180mm HDPE |  |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0
1.9 | 200mm HDPE |  |  | 5016 | 4748.4 | 267.6 |  |  |  | 267.6 |  |  |  | 267.6
2 | 250HDPE
Sub Total = |  |  |  | 36186.3 | 34187.8 | 1998.5 |  |  |  | 1998.5 |  |  |  | 1998.5
Sub-Contractor Site Engineer (Sr.Eng/ DY.M-SMX ) (Dy.M-PMX ) AGM Project Incharge

## madhura rec
POWER MECH PROJECTS.LIMITED | [11 empty] | FHTC
RURAL WATER SUPPLY PROJECT UNDER JJM, UP - PRAYAGRAJ | [17 empty] | 3492
Reconciliation Statement - Issued Vs Certification Qty.
| Contractor Name-tanish project ltd |  | MONTH: | march | Block: | mangraura
| ABC Limited |  | BILL NO: |  | GP: | madhura rani ganj
Sl NO | Description | Units |  |  |  |  | Balance Qty | SAP Entry | Remarks | Upto date Consumption
|  |  | Total Issued Qty | Cumulative Consumption | Upto Pre Consumed Qty | This Bill Consumed Qty |  |  |  | GP | GP | GP | GP | Total Consumption upto This Bill |  | Entry Qty
A | HDPE Pipe :- | [8 empty] | BLOCK | BLOCK | BLOCK | BLOCK
1 | HDPE PIPE-63MM,PN-6,CLASS:PE-100,IS:4984 | Rmt | 22460 | 22013.3 | 20282.4 | 1730.9 | 446.7 | 4474 | shifted to aurangabad |  |  |  |  | 0 | 1200000251 | #REF! |  | 22013.3 | 63
2 | HDPE PIPE-75MM,PN-6,CLASS:PE-100 | Rmt | [11 empty] | 0 | 1200000332 | #REF! |  | 2913.9 | 140
3 | HDPE PIPE-90MM,PN-6,CLASS:PE-100 | Rmt | 270 | 258.1 | 258.1 | [8 empty] | 0 | 1200000333 | #REF! |  | 5485.4 | 200
4 | HDPE PIPE-110MM,PN-6,CLASS:PE-100 | Rmt | 858 | 858.7 | 858.7 |  |  |  | 333m shifted from aurangabad to madhura rani ganj |  |  |  |  | 0 | 1200000334 | #REF! |  | 35 | 250
5 | HDPE PIPE-125MM,PN-6,CLASS:PE-100,IS4984 | Rmt | [11 empty] | 0 | 1200000252 | #REF! |  | 258.1 | 90
6 | HDPE PIPE-140MM,PN-6,CLASS:PE-100,IS4984 | Rmt | 3201 | 2913.9 | 2913.3 | [8 empty] | 0 | 1200000253 | #REF! | 287.7 | 858.7 | 110
7 | HDPE PIPE-160MM,PN-6,CLASS:PE-100 | Rmt | 4932 | 5126.3 | 5126 |  |  |  | 206meter shfted from auragabad to madura rani ganj |  |  |  |  | 0 | 1200000335 | #REF! |  | 5126.3 | 160
8 | HDPE PIPE-200MM,PN-6,CLASS:PE-100,IS4984 | Rmt | 5016 | 5016 | 4748 | 268 |  |  | 600m shfted from ags agency to tanish project ltd |  |  |  |  | 0 | 1200000255 | #REF! |  | 36690.7
9 | DI PIPE-Ø200MM , K7,IS:8329 | Rmt | [11 empty] | 0 | 900007097 | #REF! | 169
10 | HDPE PIPE-250MM,PN-6,CLASS:PE-100,IS4984 | Rmt | [11 empty] | 0 | 1200000256 | #REF! |  | 11935 | 22460 | 10525
| Total Qty In ( Rmt ) = |  | 36737 | 36186.3 | 34186.5 | 1998.9 | [10 empty] | 2874
B | Specials :-
| Equal Tee | [12 empty] | 0 |  | 0 |  | 22460
1 | HDPE-63X63X63MM,PN-6,R-TEE,CLASS:PE-100 | Nos | 140 | 85 |  | 69 |  | 4474 | [5 empty] | 0 | 200030286 | 0 |  | 2760
2 | HDPE-75X75X75MM,PN-6,R-TEE,CLASS:PE-100 | Nos | [11 empty] | 0 | 200030287 | 0 |  | 3492 | 4932 | 1440 | 1234
3 | HDPE-90X90X90MM,PN-6,R-TEE,CLASS:PE-100 | Nos | [11 empty] | 0 | 200030288 | 0 |  | 4416
4 | HDPE-110X110X110MM,PN-6,R-TEE,CL:PE-100 | Nos | [11 empty] | 0 | 200030289 | 0
5 | HDPE 125mm X 125mm X 125mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032212 | 0 |  | 55
6 | HDPE-140X140X140MM,PN-6,R-TEE,CL:PE-100 | Nos | [11 empty] | 0 | 200030291 | 0
7 | HDPE-160X160X160MM,PN-6,R-TEE,CL:PE-100 | Nos | [11 empty] | 0 | 200030293 | 0 |  |  | 55
8 | HDPE 200X200X200 MM, PN-6, R-TEE, CLASS: | Nos | [11 empty] | 0 | 200030300 | 0
9 | 250*250*250 | Nos | 1
Total Qty In ( Rmt ) =
C | Branch TEE | [14 empty] | 0
1 | HDPE BRANCH TEE 63MM X 63MM X 50MM | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032593 | 0
2 | HDPE 75MM X 75MM X 50MM PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032575 | 0
3 | HDPE 75mm X 75mm X 63mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032202 | 0
4 | HDPE 90mm X 90mm X 50mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032233 | 0
5 | HDPE 90mm X 90mm X 63mm, PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032203 | 0
6 | HDPE 90mm X 90mm X 75mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032204 | 0
7 | HDPE 110mm X 110mm X 50mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032234 | 0
8 | HDPE 110mm X 110mm X 63mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032205 | 0
9 | HDPE 110mm X 110mm X 75mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032206 | 0
10 | HDPE 110mm X 110mm X 90mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032207 | 0
11 | HDPE 125mm X 125mm X 50mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032235 | 0
12 | HDPE 125mm X 125mm X 63mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032208 | 0
13 | HDPE 125mm X 125mm X 75mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032209 | 0
14 | HDPE 125mm X 125mm X 90mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032210 | 0
15 | HDPE 125mm X 125mm X 110mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032211 | 0
16 | HDPE Branch TEE 140mm X 140mm X 50mm | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032236 | 0
17 | HDPE 140mm X 140mm X 63mm PN6 TEE PE100 | Nos | 10 | 5 | 5 | 5 | [7 empty] | 0 | 200032213 | -5
18 | HDPE 140mm X 140mm X 75mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032214 | 0
19 | HDPE 140mm X 140mm X 110mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032215 | 0
20 | HDPE Branch TEE 140mm X 140mm X 125mm | Nos | [11 empty] | 0 | 200032216 | 0
21 | HDPE-140X90X140MM,PN-6,R-TEE,CL:PE-100 | Nos | [11 empty] | 0 | 200030290 | 0
22 | HDPE 160mm X 160mm X 50mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032237 | 0
23 | HDPE 160mm X 160mm X 63mm PN6 TEE PE100 | Nos | 22 | 26 |  | 26 | [7 empty] | 0 | 200032217 | 0
24 | HDPE 160mm X 160mm X 75mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032218 | 0
25 | HDPE 160mm X 160mm X 90mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032219 | 0
26 | HDPE-160X110X160MM,PN-6,R-TEE,CL:PE-100 | Nos | [11 empty] | 0 | 200030292 | 0
27 | HDPE 160mm X 160mm X 125mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032220 | 0
28 | HDPE 200mm X 200mm X 63mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032222 | 0
29 | HDPE 200X75X200 MM, PN-6, R-TEE, CLASS:P | Nos | [11 empty] | 0 | 200030297 | 0
30 | HDPE 200X90X200 MM, PN-6, R-TEE, CLASS:P | Nos | [11 empty] | 0 | 200030298 | 0
31 | HDPE 200mm X 200mm X 110mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032223 | 0
32 | HDPE 200mm X 200mm X 160mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032225 | 0
33 | HDPE 250mm X 250mm X 90mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032228 | 0
Total Qty In ( Rmt ) =
D | 4 Way Tee | [14 empty] | 0
1 | HDPE 63MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030301 | 0
2 | HDPE 75MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [11 empty] | 0 | 200030302 | 0
3 | HDPE 90MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030303 | 0
4 | HDPE 110MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [11 empty] | 0 | 200030304 | 0
5 | HDPE125MM,PN6,4WAY CROSS FITTING,CLPE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032584 | 0
6 | HDPE 140MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [11 empty] | 0 | 200030305 | 0
7 | HDPE 160MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030306 | 0
8 | HDPE200MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [11 empty] | 0 | 200030308 | 0
Total Qty In ( No's ) =
E | Reducers
1 | HDPE-75MM,PN6, 63MM,ENLARGER,CLASS:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030309 | 0
2 | HDPE-90MM,PN6, 63MM,ENLARGER,CLASS:PE100 | Nos | [11 empty] | 0 | 200030311 | 0
3 | HDPE-90MM,PN6, 75MM,ENLARGER,CLASS:PE100 | Nos | [11 empty] | 0 | 200030310 | 0
4 | HDPE-110MM,PN6,63MM,ENLARGER,CLASS:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030314 | 0
5 | HDPE-110MM,PN6,75MM,ENLARGER,CLASS:PE100 | Nos | [11 empty] | 0 | 200030312 | 0
6 | HDPE-110MM,PN6,90MM,ENLARGER,CLASS:PE100 | Nos | [11 empty] | 0 | 200030313 | 0
7 | HDPE-125MM,PN6, 63MM Reducer PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032241 | 0
8 | HDPE-125MM,PN6, 75MM Reducer PE100 | Nos | [11 empty] | 0 | 200032239 | 0
9 | HDPE-125MM,PN6, 90MM Reducer PE100 | Nos | [11 empty] | 0 | 200032240 | 0
10 | HDPE-125MM,PN6, 110MM Reducer PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032242 | 0
11 | HDPE-140MM,PN6,63MM,ENLARGER,CL:PE100 | Nos | [11 empty] | 0 | 200030320 | 0
12 | HDPE-140MM,PN6, 75MM Reducer PE100 | Nos | [11 empty] | 0 | 200032243 | 0
13 | HDPE-140MM,PN6,90MM,ENLARGER,CL:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030317 | 0
14 | HDPE-140MM,PN6,110MM,ENLARGER,CL:PE100 | Nos | [11 empty] | 0 | 200030315 | 0
15 | HDPE-140MM,PN6,125MM,ENLARGER,CL:PE100 | Nos | [11 empty] | 0 | 200030316 | 0
16 | HDPE-160MM,PN6,63MM Reducer PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032247 | 0
17 | HDPE-160MM,PN6,75MM Reducer PE100 | Nos | [11 empty] | 0 | 200032246 | 0
18 | HDPE-160MM,PN6,90MM Reducer PE100 | Nos | [11 empty] | 0 | 200032245 | 0
19 | HDPE-160MM,PN6,110MM,ENLARGER,CL:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030319 | 0
20 | HDPE-160MM,PN6, 125MM Reducer PE100 | Nos | [11 empty] | 0 | 200032244 | 0
21 | HDPE-160MM,PN6,140MM,ENLARGER,CL:PE100 | Nos | 10 | [10 empty] | 0 | 200030318 | 0
22 | HDPE-200MM,PN6,75MM Reducer PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032249 | 0
23 | HDPE-200MM,PN6,90MM,ENLARGER,CLASS:PE100 | Nos | [11 empty] | 0 | 200030326 | 0
24 | HDPE-200MM,PN6,110MM Reducer PE100 | Nos | [11 empty] | 0 | 200032248 | 0
25 | HDPE-200MM,PN6,140MM,ENLARGER,CL:PE100 | Nos | 5 |  |  |  |  | 4474 | [5 empty] | 0 | 200030325 | 0
26 | HDPE-200MM,PN6,160MM,ENLARGER,CL:PE100 | Nos | 5 | [10 empty] | 0 | 200030328 | 0
27 | HDPE-200MM,PN6,63MM,ENLARGER,CLASS:PE100 | Nos | [11 empty] | 0 | 200030327 | 0
28 | HDPE Reducer 200mm X 125mm | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200034192 | 0
Total Qty In ( No's ) =
F | Bends 45 Degree
1 | HDPE BEND-63MM,PN6 45DEG PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032193 | 0
2 | HDPE BEND-90MM, PN6 45DEG PE100 | Nos | [11 empty] | 0 | 200032195 | 0
3 | HDPE BEND-110MM, PN6 45DEG PE100 | Nos | [11 empty] | 0 | 200032196 | 0
4 | HDPE BEND-75MM,PN6 45DEG PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032194 | 0
5 | HDPE BEND-125MM,PN-6,90DEG,CLASS:PE-100 | Nos | [11 empty] | 0 | 200030270 | 0
6 | HDPE BEND-125MM, PN6 45DEG PE100 | Nos | [11 empty] | 0 | 200032197 | 0
7 | HDPE BEND-140MM,PN-6,45DEG,CLASS:PE-100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030275 | 0
8 | HDPE BEND-160MM,PN-6,45DEG,CLASS:PE-100 | Nos | [11 empty] | 0 | 200030276 | 0
Total Qty In ( No's ) =
G | Bends 90Degree
1 | HDPE BEND-63MM,PN-6,90DEG,CLASS:PE-100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030266 | 0
2 | HDPE BEND-75MM,PN-6,90DEG,CLASS:PE-100 | Nos | [11 empty] | 0 | 200030267 | 0
3 | HDPE BEND-90MM,PN-6,90DEG,CLASS:PE-100 | Nos | [11 empty] | 0 | 200030268 | 0
4 | HDPE BEND-110MM,PN-6,90DEG,CLASS:PE-100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030269 | 0
5 | HDPE BEND-140MM,PN-6,90DEG,CLASS:PE-100 | Nos | [11 empty] | 0 | 200030271 | 0
6 | HDPE BEND-160MM,PN-6,90DEG,CLASS:PE-100 | Nos | [11 empty] | 0 | 200030272 | 0
7 | HDPE BEND-200MM,PN-6,90DEG,CLASS:PE-100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030274 | 0
8 | HDPE BEND-250MM,PN-6,90DEG,CLASS:PE-100 | Nos | 1
Total Qty In ( No's ) =
H | End Caps
1 | HDPE-63MM,PN6,END CAP,CLASS:PE100 | Nos | 150 | 61 |  | 14 |  | 4474 | [5 empty] | 0 | 200030277 | 0 |  | 14
2 | HDPE-75MM,PN6,END CAP,CLASS:PE100 | Nos | [11 empty] | 0 | 200030278 | 0 |  | 89
3 | HDPE-90MM,PN6,END CAP,CLASS:PE100 | Nos | [11 empty] | 0 | 200030279 | 0
4 | HDPE-110MM,PN6,END CAP,CLASS:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030280 | 0
5 | HDPE-140MM,PN6,END CAP,CLASS:PE100 | Nos | [11 empty] | 0 | 200030282 | 0
Total Qty In ( No's ) =
1 | FHTC
1 | GI PIPE-15MM | Rmt | [5 empty] | 4474 |  | 0 | 0 |  |  | 0 | 1200000409 | 0
2 | MDPE PIPE-20MM | Rmt | [7 empty] | 0 | 0 |  |  | 0 | 1200000408 | 0
3 | BRASS TAP | Nos | [5 empty] | 4474 |  | 0 | 0 |  |  | 0 | 1200000231 | 0
4 | PP CLAMP SADLLE-63MM | Nos | [7 empty] | 0 |  |  |  | 0 | 1200000410 | 0
5 | PP CLAMP SADDLE-75MM | Nos | [11 empty] | 0 | 1200000425 | 0
6 | PP CLAMP SADLLE-90MM | Nos | [5 empty] | 4474 | [5 empty] | 0 | 1200000411 | 0
7 | PP CLAMP SADDLE-140MM | Nos | [11 empty] | 0 | 900008156 | 0
8 | PP CLAMP SADDLE-160MM | Nos | [11 empty] | 0 | 900008157 | 0
9 | PP CLAMP SADDLE-200MM | Nos | [5 empty] | 4474 | [5 empty] | 0 | 900008159 | 0
10 | PP CLAMP SADDLE 125MM WITH M8 FASTNERS | Nos | [11 empty] | 0 | 900008617 | 0
11 | PP CLAMP SADLLE-110MM | Nos | [11 empty] | 0 | 900007416 | 0
12 | G.I ELBOW 15 MM | Nos | [7 empty] | 0 | 0 |  |  | 0 | 1200000419 | 0
13 | GI SOCKET-15MM | Nos | [7 empty] | 0 | 0 |  |  | 0 | 1200000416 | 0
14 | WALL MOUNT SADDLE GI PIPE-15MM | Nos | [5 empty] | 4474 | [5 empty] | 0 | 1200000418 | 0
15 | 15MM GI NIPPLE - 0.3MTR LENGTH | Nos | [7 empty] | 0 | 0 |  |  | 0 | 1200000450 | 0
16 | 15MM GI NIPPLE - 0.5MTR LENGTH | Nos | [7 empty] | 0 | 0 |  |  | 0 | 1200000451 | 0
17 | 20MM MDPE COMPRESSION ELBOW | Nos | [7 empty] | 0 | 0 |  |  | 0 | 1200000448 | 0
18 | SS FLOW CONTROL VAlVE | Nos | [5 empty] | 4474 |  | 0 | 0 |  |  | 0 | 1200000417 | 0
19 | MDPE FEMLE THREADED ASSEMBLY-20MM | Nos | [7 empty] | 0 | 0 |  |  | 0 | 1200000414 | 0
20 | MDPE ELBOW-20MM | Nos | [11 empty] | 0 | 1200000415 | 0
21 | TEFLAN TAPE | Nos | [11 empty] | 0 | 200001364 | 0
22 | [13 empty] | 0 | #N/A | 0
Total Qty In ( No's ) =
Sub Contractor Site Engineer Block incharge AGM DM PMX Project Incharge
ENTRY NO:

## MADHU REC AND VALVE FIXING
POWER MECH PROJECTS.LIMITED
RURAL WATER SUPPLY PROJECT UNDER JJM, UP - PRAYAGRAJ
Reconciliation Statement - Issued Vs Certification Qty.
| Contractor Name- |  | MONTH: | SEPT | Block: | MANGRAURA
| TANISH PROJECT LTD |  | BILL NO: |  | GP: | MADHURA RANI GANJ
Sl NO | Description | Units |  |  |  |  | Balance Qty | SAP Entry | Remarks
|  |  | Total Issued Qty | Cumulative Consumption | Upto Pre Consumed Qty | This Bill Consumed Qty
A | VALVE FITTING MATERIALS
1 | 160 MM DIA SLUICE VALVE | Nos. | 3 | 3 | 0 | 3 | 0
2 | 200 MM DIA SLUICE VALVE | Nos. | 2 | 2 | 0 | 2 | 0
3 | 80 MM DIA SLUICE VALVE | Nos. | 2 | 2 | 0 | 2 | 0
4 | 50 MM DIA AIR VALVE | Nos. |  |  |  |  | 0
5 | 125 MM HDPE STUB BEND | Nos. |  |  | 0 |  | 0
6 | 110 MM HDPE STUB BEND | Nos. |  |  | 0 |  | 0
7 | 63 MM HDPE STUB BEND | Nos. |  |  | 0 |  | 0
8 | 160MM MS FLANGE | Nos. | 8 | 8 | 0 | 8 | 0
9 | 200 MM MS FLANGE | Nos. | 6 | 6 | 0 | 6 | 0
10 | 90 MM MS FLANGE | Nos. | 4 | 4 | 0 | 4 | 0
11 | 90 MM HDPE STUB BEND | Nos. | 4 | 4 | 0 | 4 | 0
12 | 200 MM HDPE STUB BEND | Nos. | 6 | 6 | 0 | 6 | 0
13 | 160MM HDPE STUB BEND | Nos. | 8 | 8 | 0 | 8 | 0
14 | 110 MM MS FLANGE | Nos. |  |  | 0 |  | 0
15 | 16/75 NUTT BOLT | Nos. | 16 | 16 | 0 | 16 | 0
16 | 16/100 NUTT BOLT | Nos. | 112 | 112 | 0 | 112 | 0
17 | RUBBER GASKET | KG | 7 | 7 |  | 7 | 0
Sub Contractor Site Engineer Block incharge AGM DM PMX Project Incharge
ENTRY NO:

## AURANGABADvalves
POWER MECH PROJECTS.LIMITED
RURAL WATER SUPPLY PROJECT UNDER JJM, UP - PRAYAGRAJ
Reconciliation Statement - Issued Vs Certification Qty.
| Contractor Name- |  | MONTH: | SEPT | Block: | MANGRAURA
| TANISH PROJECT LTD |  | BILL NO: |  | GP: | AURANGABAD
Sl NO | Description | Units |  |  |  |  | Balance Qty | SAP Entry | Remarks
|  |  | Total Issued Qty | Cumulative Consumption | Upto Pre Consumed Qty | This Bill Consumed Qty
A | VALVE FITTING MATERIALS
1 | 125 MM DIA SLUICE VALVE | Nos. | 0 | 0 | 0 | 0 | 0
2 | 200 MM DIA SLUICE VALVE | Nos. | 1 | 1 |  | 1 | 0
3 | 160 MM DIA SLUICE VALVE | Nos. | 1 | 1 | 0 | 1 | 0
4 | 90 MM DIA SLUICE VALVE | Nos. | 3 | 3 | 0 | 3
4 | 160 MM DIA AIR VALVE | Nos. | 1 | 1 | 0 | 1 | 0
5 | 200SCOUR VALVE | Nos. | 1 | 1 | 0 | 1 | 0
6 | 160 SCOUR VALVE | Nos. | 1 | 1 | 0 | 1 | 0
7 | 125 MM HDPE STUB BEND | Nos. |  |  | 0 |  | 0
8 | 110 MM HDPE STUB BEND | Nos. |  |  | 0 |  | 0
9 | 63 MM HDPE STUB BEND | Nos. |  |  | 0 |  | 0
10 | 150MM MS FLANGE | Nos. | 6 | 6 | 0 | 6 | 0
11 | 80 MM MS FLANGE | Nos. | 9 | 9 | 0 | 9 | 0
12 | 50 MM MS FLANGE | Nos. | 1 | 1 | 0 | 1 | 0
13 | 80 MM HDPE STUB BEND | Nos. | 9 | 9 |  | 9 | 0
14 | 200 MM HDPE STUB BEND | Nos. |  |  |  |  | 0
15 | 160MM HDPE STUB BEND | Nos. | 5 | 5 | 0 | 5 | 0
16 | 110 MM MS FLANGE | Nos. |  |  | 0 |  | 0
17 | 16/75 NUTT BOLT | Nos. | 88 | 88 | 0 | 88 | 0
18 | 16/100 NUTT BOLT | Nos. |  |  |  |  | 0
19 | RUBBER GASKET | KG | 6 | 6 |  | 6 | 0
Sub Contractor Site Engineer Block incharge AGM DM PMX Project Incharge

## mandah & bhoji (hidden)
GOVERNMENT OF UTTAR PRADESH
STATE WATER & SANITATION MISSION ( SWSM )
Joint Measurement Report of Pipe Line
Name of the Work :- Survey , Design Preparation of DPR , Construction , Commissioning and O&M for 10 Years of Various Rural Water Supply Projects in the state of Uttar Pradesh as Per Request for Proposal for Division " Prayagraj "
Name of the Agency : POWER MECH PROJECTS LIMITED – BHOORATHNOM CONSTRUCTIONS COMPANY PRIVATE LIMITED (JV), Hyderabad.
Name OF Scheme |  | :mandah & bhoji
Block |  | : Mangraura
Total Scope |  | :
JMR No. |  | : 1
Date of JMR |  | :
Sr. No. | Start Node | End Node | Dia | Pipe Length (as per Drawing) | Pipe Length (as per Site) | Width | Depth | Quantity | Type OF Road | Dismantling Length | Dismantling Width | Dismantling Quantity | Restoration Length | Restoration Width | Restoration Quantity | Restoration Status | Remark
1 | j179 | j169 | 63 | 65 | 72.5 | 0.363 | 1.063
2 | j169 | j170 | 63 | 52 | 45.4 | 0.363 | 1.063
3 | j169 | j167 | 63 | 20 | 8.8 | 0.363 | 1.063
4 | j167 | j168 | 63 | 53 | 32.2 | 0.363 | 1.063
5 | j167 | j165 | 63 | 37 | 44.2 | 0.363 | 1.063
6 | j165 | j166 | 63 | 32 | 35.7 | 0.363 | 1.063
7 | j179 | j199 | 63 | 83 | 82.7 | 0.363 | 1.063
8 | j199 | j203 | 63 | 11 | 9.7 | 0.363 | 1.063
9 | j203 | j206 | 63 | 225 | 38.7 | 0.363 | 1.063
10 | j203 | j206 | 63 |  | 13.6 | 0.363 | 1.063 |  | i.l | 13.6 | 0.363 | 4.9368 | 13.6 | 0.363 | 4.9368
11 | j203 | j206 | 63 |  | 43.1 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
12 | j200 | j200a | 63 |  | 2 | 0.363 | 1.063 |  | c.c road crossing | 2 | 0.363 | 0.726 | 2 | 0.363 | 0.726
13 | j200a | j200b | 63 |  | 33 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
14 | j202 | j197 | 63 |  | 22.4 | 0.363 | 1.063 |  | i.l | 22.4 | 0.363 | 8.1312 | 22.4 | 0.363 | 8.1312
15 | j197 | j191 | 63 | 46 | 46.5 | 0.363 | 1.063 |  | i.l | 46.5 | 0.363 | 16.8795 | 46.5 | 0.363 | 16.8795
16 | j191 | j192 | 63 | 17 | 50.8 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
17 | j191 | j187 | 63 | 37 | 25.4 | 0.363 | 1.063 |  | i.l | 25.4 | 0.363 | 9.2202 | 25.4 | 0.363 | 9.2202
18 | j191 | j187 | 63 |  | 31.1 | 0.363 | 1.063 |  | brick road | 31.1 | 0.363 | 11.2893 | 31.1 | 0.363 | 11.2893
19 | j187 | j180 | 63 |  | 29.2 | 0.363 | 1.063 |  | brick road | 29.2 | 0.363 | 10.5996 | 29.2 | 0.363 | 10.5996
20 | j180 | j178 | 63 | 46 | 49.9 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
21 | j180 | j178 | 63 |  | 5.8 | 0.363 | 1.063 |  | b.t road crossing | 5.8 | 0.363 | 2.1054 | 5.8 | 0.363 | 2.1054
22 | j178 | j182 | 63 |  | 19.3 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
23 | j182 | j183 | 63 | 13 | 10.3 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
24 | j178 | j173 | 63 | 21 | 24 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
25 | j178 | j173 | 63 |  | 2 | 0.363 | 1.063 |  | b.t road crossing | 2 | 0.363 | 0.726 | 2 | 0.363 | 0.726
26 | j173 | j176 | 63 |  | 64.4 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
27 | j173 | j159 | 63 | 128 | 126.1 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
28 | j159 | j158 | 63 | 46 | 49.9 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
29 | j158 | j158(1) | 63 |  | 3.8 | 0.363 | 1.063 |  | brick road | 3.8 | 0.363 | 1.3794 | 3.8 | 0.363 | 1.3794
30 | j158 | j171 | 63 | 121 | 111.5 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
31 | j171 | j172 | 63 | 28 | 20.7 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
32 | j177 | j171 | 63 | 37 | 46.3 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
33 | j158 | j157 | 63 | 130 | 125.6 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
34 | j157 | j151 | 63 |  | 7 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
35 | j157 | j210 | 63 | 194 | 188 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
36 | j157 | j101 | 75 | 180 | 174.7 | 0.375 | 1.075 |  |  |  |  | 0 |  |  | 0
37 | j101 | j101(1) | 75 |  | 9 | 0.375 | 1.075 |  | b.t road crossing | 9 | 0.375 | 3.375 | 9 | 0.375 | 3.375
38 | j101 | j108 | 75 |  | 8.2 | 0.375 | 1.075 |  | b.t road crossing | 8.2 | 0.375 | 3.075 | 8.2 | 0.375 | 3.075
39 | j101 | j108 | 75 | 125 | 125 | 0.375 | 1.075 |  |  |  |  | 0 |  |  | 0
40 | j108 | j158 | 63 | 198 | 198 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
41 | j158 | j158(1) | 63 |  | 6.5 | 0.363 | 1.063 |  | b.t road crossing | 6.5 | 0.363 | 2.3595 | 6.5 | 0.363 | 2.3595
42 | j108 | j102 | 63 | 51 | 53 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
43 | j102 | j103 | 63 | 98 | 59 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
44 | j102 | j103 | 63 |  | 3 | 0.363 | 1.063 |  | b.t road crossing | 3 | 0.363 | 1.089 | 3 | 0.363 | 1.089
45 | j102 | j98 | 63 | 76 | 80.3 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
46 | j98 | j82 | 63 |  | 2.5 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
47 | j98 | j82 | 63 | 118 | 124.3 | 0.363 | 1.063 |  | brick road crossing | 124.3 | 0.363 | 45.1209 | 124.3 | 0.363 | 45.1209
48 | j98 | j165 | 63 | 429 | 421.1 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
49 | j101 | j134 | 63 | 556 | 542.4 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
50 | j134 | j134(1) | 63 |  | 7 | 0.363 | 1.063 |  | i.l | 7 | 0.363 | 2.541 | 7 | 0.363 | 2.541
51 | j134 | j141 | 63 | 87 | 95.8 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
52 | j141 | j141(1) | 63 |  | 3 | 0.363 | 1.063 |  | road crossing | 3 | 0.363 | 1.089 | 3 | 0.363 | 1.089
53 | j141 | j145 | 63 | 78 | 75.1 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
54 | j145 | j144 | 63 | 56 | 62.4 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
55 | j144 | j146 | 63 | 23 | 71 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
56 | j144 | j142 | 63 | 81 | 71.5 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
57 | j142 | j143 | 63 | 74 | 74.3 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
58 | j142 | j140 | 63 | 50 | 50.3 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
59 | j140 | j137 | 63 | 88 | 87.3 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
60 | j141 | j153 | 63 | 143 | 138.7 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
61 | j153 | j154 | 63 | 28 | 61.1 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
62 | j153 | j155 | 63 | 139 | 141.6 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
63 | j134 | j99 | 63 | 192 | 196.3 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
64 | j99 | j132 | 63 |  | 3.6 | 0.363 | 1.063 |  | i.l road crossing | 3.6 | 0.363 | 1.3068 | 3.6 | 0.363 | 1.3068
65 | j99 | j132 | 63 | 94 | 89.9 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
66 | j132 | j135 | 63 | 64 | 67.3 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
67 | j99 | j93 | 63 | 170 | 168.6 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
68 | j93 | j94 | 63 | 114 | 107.2 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
69 | j93 | j94 | 63 |  | 3.2 | 0.363 | 1.063 |  | i.l road crossing | 3.2 | 0.363 | 1.1616 | 3.2 | 0.363 | 1.1616
70 | j94 | j95 | 63 | 108 | 76.1 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
71 | j95 | j96 | 63 | 16 | 53.7 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
72 | j94 | j113 | 63 | 340 | 344.5 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
73 | j113 | j124 | 63 | 258 | 249 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
74 | j124 | j125 | 63 |  | 31.5 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
75 | 130 | 127 | 63 | 166 | 276.1 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
76 | 127 | 121 | 63 |  | 24.6 | 0.363 | 1.063 |  | brick road | 24.6 | 0.363 | 8.9298 | 24.6 | 0.363 | 8.9298
77 | j121a | j121b | 63 |  | 13.9 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
78 | j121a | j117 | 63 | 20 | 23.2 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
79 | j117 | j118 | 63 | 37 | 34.8 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
80 | j117 | j104 | 63 | 118 | 16.3 | 0.363 | 1.063 |  | brick road | 16.3 | 0.363 | 5.9169 | 16.3 | 0.363 | 5.9169
81 | j117 | j109 | 63 |  | 74.4 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
82 | j117 | j109 | 63 |  | 29.1 | 0.363 | 1.063 |  | brick road | 29.1 | 0.363 | 10.5633 | 29.1 | 0.363 | 10.5633
83 | j109 | j116 | 63 | 38 | 37 | 0.363 | 1.063 |  | brick road | 37 | 0.363 | 13.431 | 37 | 0.363 | 13.431
84 | j116 | j123 | 63 | 118 | 125.1 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
85 | j109 | j100 | 63 | 27 | 21.9 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
86 | j100 | j104 | 63 | 24 | 23.7 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
87 | j105 | j105 | 63 | 89 | 72.4 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
88 | j104 | j106 | 63 | 17 | 17.9 | 0.363 | 1.063 |  | brick road | 17.9 | 0.363 | 6.4977 | 17.9 | 0.363 | 6.4977
89 | j106 | j110 | 63 |  | 57.6 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
90 | j110 | j114 | 63 |  |  | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
91 | j100 | j89 | 63 | 90 | 101.8 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
92 | j89 | j83 | 63 | 30 | 22.5 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
93 | j83 | j56 | 63 | 79 | 76.5 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
94 | j56 | j56(1) | 63 |  | 5.7 | 0.363 | 1.063 |  | b.t road crossing | 5.7 | 0.363 | 2.0691 | 5.7 | 0.363 | 2.0691
95 | j56 | j79 | 90 | 56 | 67.1 | 0.39 | 1.09 |  |  |  |  | 0 |  |  | 0
96 | j79 | j85 | 90 | 44 | 30.1 | 0.39 | 1.09 |  |  |  |  | 0 |  |  | 0
97 | j85 | j93 | 90 | 170 | 167.7 | 0.39 | 1.09 |  |  |  |  | 0 |  |  | 0
98 | j122 | j119 | 63 | 126 | 121 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
99 | j119a | j119b | 63 |  | 63 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
100 | j56 | j41 | 110 | 512 | 508.6 | 0.41 | 1.11 |  |  |  |  | 0 |  |  | 0
101 | j101 | j61 | 90 |  | 280.4 | 0.39 | 1.09 |  |  |  |  | 0 |  |  | 0
102 | j61 | j47 | 110 |  | 183.6 | 0.41 | 1.11 |  |  |  |  | 0 |  |  | 0
103 | j47 | j47(1) | 63 |  | 7.1 | 0.363 | 1.063 |  | b.t road crossing | 7.1 | 0.41 | 2.911 | 7.1 | 0.41 | 2.911
104 | j50 | j48 | 63 | 98 | 70.4 | 0.363 | 1.063 |  | b.t | 70.4 | 0.363 | 25.5552 | 70.4 | 0.363 | 25.5552
105 | j48 | j49 | 63 |  | 7.4 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
106 | j48 | j49 | 63 | 58 | 54.9 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
107 | j48 | j47 | 63 | 60 | 57 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
108 | j47 | j25 | 110 | 264 | 272.2 | 0.41 | 1.11 |  |  |  |  | 0 |  |  | 0
109 | j25 | j41 | 110 | 445 | 440 | 0.41 | 1.11 |  |  |  |  | 0 |  |  | 0
110 | j41 | j41(1) | 110 |  | 9 | 0.41 | 1.11 |  | b.t crossing | 9 | 0.41 | 3.69 | 9 | 0.41 | 3.69
111 | j41 | j40 | 63 | 13 | 23 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
112 | j25 | j8 | 140 |  | 5.6 | 0.44 | 1.14 |  | b.t road crossing | 5.6 | 0.363 | 2.0328 | 5.6 | 0.363 | 2.0328
113 | j25 | j8 | 140 | 608 | 612.9 | 0.44 | 1.14 |  |  |  |  | 0 |  |  | 0
114 | j8 | j4 | 160 | 125 | 122 | 0.46 | 1.16 |  | brick road | 122 | 0.44 | 53.68 | 122 | 0.44 | 53.68
115 | j4 | j1 | 160 | 24 | 34 | 0.46 | 1.16 |  |  |  |  | 0 |  |  | 0
116 | j4 | j5 | 63 |  | 139.4 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
117 | j5a | j5b | 63 |  | 55.3 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
118 | j8 | j9 | 63 |  | 149.2 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
119 | j9 | j2 | 63 |  | 67.3 | 0.363 | 1.063 |  | brick road | 67.3 | 0.363 | 24.4299 | 67.3 | 0.363 | 24.4299
120 | j2 | j3 | 63 |  | 50.9 | 0.363 | 1.063 |  |  |  |  | 0 |  |  | 0
121 | j2 | j1 | 110 |  | 152.1 | 0.41 | 1.11 |  |  |  |  | 0 |  |  | 0
122 | j14 | j16 | 63 |  | 20.3 | 0.363 | 1.063 |  | brick road | 20.3 | 0.41 | 8.323 | 20.3 | 0.41 | 8.323
123 | j16 | j18 | 63 | 316 | 322.4 | 0.363 | 1.063
124 | j18 | j18(1) | 63 |  | 4.9 | 0.363 | 1.063
125 | j18 | j20 | 63 | 325 | 355 | 0.363 | 1.063
126 | j20 | j22 | 63 | 369 | 359 | 0.363 | 1.063
127 | j22 | j23 | 63 | 49 | 51.4 | 0.363 | 1.063
128 | j23 | j28 | 63 | 391 | 380 | 0.363 | 1.063
129 | j28 | j29 | 63 | 25 | 129.1 | 0.363 | 1.063
130 | j28 | j31 | 63 | 31 | 134.1 | 0.363 | 1.063
131 | j31 | j32 | 63 |  | 65.1 | 0.363 | 1.063
132 | j32 | j33 | 63 |  | 39.6 | 0.363 | 1.063
133 | j32 | j34 | 63 |  | 275.1 | 0.363 | 1.063
134 | j34 | j42 | 63 |  | 262.3 | 0.363 | 1.063
135 | j42 | j44 | 63 |  | 92 | 0.363 | 1.063
136 | j34 | j35 | 63 |  | 132 | 0.363 | 1.063
137 | j35 | j37 | 63 |  | 10 | 0.363 | 1.063
138 | j35 | j65 | 63 |  | 45 | 0.363 | 1.063
139 | j37 | j38 | 63 |  | 39 | 0.363 | 1.063
140 | j37 | j39 | 63 |  | 81 | 0.363 | 1.063
141 | j31 | j30 | 63 |  | 146 | 0.363 | 1.063
[5 empty] | 13407.6 | [6 empty] | 295.1409 |  |  | 295.1409
Abstract (Bill Breakup)
1 | Dia of Pipe | WO/DPR Qty's | Laying, Jointing, Backfilling - 60% |  |  |  | Gap Closing- 5% |  |  |  | Hydro Test - 15% |  |  |  | FHTC Stretch - 10%
|  |  | Laying Up to Date | Laying Qty Billed up to Date | Qty Billed Up to Previous | This Bill Qty (Laying) | WO/DPR Qty's | GAP Closing Billed Qty up to Date | GAP Closing Qty Up to Previous | This Bill Qty (GAP Closing) | WO/DPR Qty's | Hydro Test Qty Billed up to Date | Hydro Test Qty Up to Previous | This Bill Qty (Hydro Test ) | FHTC Stretch Qty Billed up to Date | FHTC Stretch Qty Billed Up to Previous | This Bill Qty (FHTC Stretch Billed )
1.1 | 63 mm HDPE |  | 0 | 10132.9 | 3223
1.2 | 75 mm HDPE |  | 0 | 316.9
1.3 | 90 mm HDPE |  | 0 | 545.3
1.4 | 110mm HDPE |  | 0 | 1565.5
1.5 | 125mm HDPE |  | 0 | 0
1.6 | 140mm HDPE |  | 0 | 618.5
1.7 | 160mm HDPE |  | 0 | 156
1.8 | 180mm HDPE
1.9 | 200mm HDPE |  | 0
Sub Total = |  |  | 0 | 13335.1 | 3223 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Sub-Contractor Site Engineer (Sr.Eng/ DY.M-SMX ) (Dy.M-PMX ) AGM Project Incharge
|  | 63 | 75 | 90 | 110 | 125 | 140 | 160 | 200
|  | 10132.9 | 316.9 | 545.3 | 1565.5 | 0 | 618.5 | 156 | 0 |  | 13335.1

## reconsilation (hidden)
POWER MECH PROJECTS.LIMITED
RURAL WATER SUPPLY PROJECT UNDER JJM, UP - PRAYAGRAJ
Reconciliation Statement - Issued Vs Certification Qty.
| Contractor Name-tanish project limited |  | MONTH: | june | Block: | mangraura
| ABC Limited |  | BILL NO: |  | GP: | mandah boji
Sl NO | Description | Units |  |  |  |  | Balance Qty | SAP Entry | Remarks
|  |  | Total Issued Qty | Cumulative Consumption | Upto Pre Consumed Qty | This Bill Consumed Qty
A | HDPE Pipe :-
1 | HDPE PIPE-63MM,PN-6,CLASS:PE-100,IS:4984 | Rmt | 3412 |  | 3223
2 | HDPE PIPE-75MM,PN-6,CLASS:PE-100 | Rmt | 375 |  |  | 0
3 | HDPE PIPE-90MM,PN-6,CLASS:PE-100 | Rmt | 540 |  |  | 0
4 | HDPE PIPE-110MM,PN-6,CLASS:PE-100 | Rmt |  |  |  | 0
5 | HDPE PIPE-125MM,PN-6,CLASS:PE-100,IS4984 | Rmt
6 | HDPE PIPE-140MM,PN-6,CLASS:PE-100,IS4984 | Rmt
7 | HDPE PIPE-160MM,PN-6,CLASS:PE-100 | Rmt
8 | HDPE PIPE-200MM,PN-6,CLASS:PE-100,IS4984 | Rmt
9 | DI PIPE-Ø200MM , K7,IS:8329 | Rmt
10 | HDPE PIPE-250MM,PN-6,CLASS:PE-100,IS4984 | Rmt
Total Qty In ( Rmt ) =
B | Specials :-
Equal Tee
1 | HDPE-63X63X63MM,PN-6,R-TEE,CLASS:PE-100 | Nos
2 | HDPE-75X75X75MM,PN-6,R-TEE,CLASS:PE-100 | Nos
3 | HDPE-90X90X90MM,PN-6,R-TEE,CLASS:PE-100 | Nos
4 | HDPE-110X110X110MM,PN-6,R-TEE,CL:PE-100 | Nos
5 | HDPE 125mm X 125mm X 125mm PN6 TEE PE100 | Nos
6 | HDPE-140X140X140MM,PN-6,R-TEE,CL:PE-100 | Nos
7 | HDPE-160X160X160MM,PN-6,R-TEE,CL:PE-100 | Nos
8 | HDPE 200X200X200 MM, PN-6, R-TEE, CLASS: | Nos
Total Qty In ( Rmt ) =
C | Branch TEE
1 | HDPE BRANCH TEE 63MM X 63MM X 50MM | Nos
2 | HDPE 75MM X 75MM X 50MM PN6 TEE PE100 | Nos
3 | HDPE 75mm X 75mm X 63mm PN6 TEE PE100 | Nos
4 | HDPE 90mm X 90mm X 50mm PN6 TEE PE100 | Nos
5 | HDPE 90mm X 90mm X 63mm, PN6 TEE PE100 | Nos
6 | HDPE 90mm X 90mm X 75mm PN6 TEE PE100 | Nos
7 | HDPE 110mm X 110mm X 50mm PN6 TEE PE100 | Nos
8 | HDPE 110mm X 110mm X 63mm PN6 TEE PE100 | Nos
9 | HDPE 110mm X 110mm X 75mm PN6 TEE PE100 | Nos
10 | HDPE 110mm X 110mm X 90mm PN6 TEE PE100 | Nos
11 | HDPE 125mm X 125mm X 50mm PN6 TEE PE100 | Nos
12 | HDPE 125mm X 125mm X 63mm PN6 TEE PE100 | Nos
13 | HDPE 125mm X 125mm X 75mm PN6 TEE PE100 | Nos
14 | HDPE 125mm X 125mm X 90mm PN6 TEE PE100 | Nos
15 | HDPE 125mm X 125mm X 110mm PN6 TEE PE100 | Nos
16 | HDPE Branch TEE 140mm X 140mm X 50mm | Nos
17 | HDPE 140mm X 140mm X 63mm PN6 TEE PE100 | Nos
18 | HDPE 140mm X 140mm X 75mm PN6 TEE PE100 | Nos
19 | HDPE 140mm X 140mm X 110mm PN6 TEE PE100 | Nos
20 | HDPE Branch TEE 140mm X 140mm X 125mm | Nos
21 | HDPE-140X90X140MM,PN-6,R-TEE,CL:PE-100 | Nos
22 | HDPE 160mm X 160mm X 50mm PN6 TEE PE100 | Nos
23 | HDPE 160mm X 160mm X 63mm PN6 TEE PE100 | Nos
24 | HDPE 160mm X 160mm X 75mm PN6 TEE PE100 | Nos
25 | HDPE 160mm X 160mm X 90mm PN6 TEE PE100 | Nos
26 | HDPE-160X110X160MM,PN-6,R-TEE,CL:PE-100 | Nos
27 | HDPE 160mm X 160mm X 125mm PN6 TEE PE100 | Nos
28 | HDPE 200mm X 200mm X 63mm PN6 TEE PE100 | Nos
29 | HDPE 200X75X200 MM, PN-6, R-TEE, CLASS:P | Nos
30 | HDPE 200X90X200 MM, PN-6, R-TEE, CLASS:P | Nos
31 | HDPE 200mm X 200mm X 110mm PN6 TEE PE100 | Nos
32 | HDPE 200mm X 200mm X 160mm PN6 TEE PE100 | Nos
33 | HDPE 250mm X 250mm X 90mm PN6 TEE PE100 | Nos
Total Qty In ( Rmt ) =
D | 4 Way Tee
1 | HDPE 63MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos
2 | HDPE 75MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos
3 | HDPE 90MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos
4 | HDPE 110MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos
5 | HDPE125MM,PN6,4WAY CROSS FITTING,CLPE100 | Nos
6 | HDPE 140MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos
7 | HDPE 160MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos
8 | HDPE200MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos
Total Qty In ( No's ) =
E | Reducers
1 | HDPE-75MM,PN6, 63MM,ENLARGER,CLASS:PE100 | Nos
2 | HDPE-90MM,PN6, 63MM,ENLARGER,CLASS:PE100 | Nos
3 | HDPE-90MM,PN6, 75MM,ENLARGER,CLASS:PE100 | Nos
4 | HDPE-110MM,PN6,63MM,ENLARGER,CLASS:PE100 | Nos
5 | HDPE-110MM,PN6,75MM,ENLARGER,CLASS:PE100 | Nos
6 | HDPE-110MM,PN6,90MM,ENLARGER,CLASS:PE100 | Nos
7 | HDPE-125MM,PN6, 63MM Reducer PE100 | Nos
8 | HDPE-125MM,PN6, 75MM Reducer PE100 | Nos
9 | HDPE-125MM,PN6, 90MM Reducer PE100 | Nos
10 | HDPE-125MM,PN6, 110MM Reducer PE100 | Nos
11 | HDPE-140MM,PN6,63MM,ENLARGER,CL:PE100 | Nos
12 | HDPE-140MM,PN6, 75MM Reducer PE100 | Nos
13 | HDPE-140MM,PN6,90MM,ENLARGER,CL:PE100 | Nos
14 | HDPE-140MM,PN6,110MM,ENLARGER,CL:PE100 | Nos
15 | HDPE-140MM,PN6,125MM,ENLARGER,CL:PE100 | Nos
16 | HDPE-160MM,PN6,63MM Reducer PE100 | Nos
17 | HDPE-160MM,PN6,75MM Reducer PE100 | Nos
18 | HDPE-160MM,PN6,90MM Reducer PE100 | Nos
19 | HDPE-160MM,PN6,110MM,ENLARGER,CL:PE100 | Nos
20 | HDPE-160MM,PN6, 125MM Reducer PE100 | Nos
21 | HDPE-160MM,PN6,140MM,ENLARGER,CL:PE100 | Nos
22 | HDPE-200MM,PN6,75MM Reducer PE100 | Nos
23 | HDPE-200MM,PN6,90MM,ENLARGER,CLASS:PE100 | Nos
24 | HDPE-200MM,PN6,110MM Reducer PE100 | Nos
25 | HDPE-200MM,PN6,140MM,ENLARGER,CL:PE100 | Nos
26 | HDPE-200MM,PN6,160MM,ENLARGER,CL:PE100 | Nos
27 | HDPE-200MM,PN6,63MM,ENLARGER,CLASS:PE100 | Nos
28 | HDPE Reducer 200mm X 125mm | Nos
Total Qty In ( No's ) =
F | Bends 45 Degree
1 | HDPE BEND-63MM,PN6 45DEG PE100 | Nos
2 | HDPE BEND-90MM, PN6 45DEG PE100 | Nos
3 | HDPE BEND-110MM, PN6 45DEG PE100 | Nos
4 | HDPE BEND-75MM,PN6 45DEG PE100 | Nos
5 | HDPE BEND-125MM,PN-6,90DEG,CLASS:PE-100 | Nos
6 | HDPE BEND-125MM, PN6 45DEG PE100 | Nos
7 | HDPE BEND-140MM,PN-6,45DEG,CLASS:PE-100 | Nos
8 | HDPE BEND-160MM,PN-6,45DEG,CLASS:PE-100 | Nos
Total Qty In ( No's ) =
G | Bends 90Degree
1 | HDPE BEND-63MM,PN-6,90DEG,CLASS:PE-100 | Nos
2 | HDPE BEND-75MM,PN-6,90DEG,CLASS:PE-100 | Nos
3 | HDPE BEND-90MM,PN-6,90DEG,CLASS:PE-100 | Nos
4 | HDPE BEND-110MM,PN-6,90DEG,CLASS:PE-100 | Nos
5 | HDPE BEND-140MM,PN-6,90DEG,CLASS:PE-100 | Nos
6 | HDPE BEND-160MM,PN-6,90DEG,CLASS:PE-100 | Nos
7 | HDPE BEND-200MM,PN-6,90DEG,CLASS:PE-100 | Nos
Total Qty In ( No's ) =
H | End Caps
1 | HDPE-63MM,PN6,END CAP,CLASS:PE100 | Nos
2 | HDPE-75MM,PN6,END CAP,CLASS:PE100 | Nos
3 | HDPE-90MM,PN6,END CAP,CLASS:PE100 | Nos
4 | HDPE-110MM,PN6,END CAP,CLASS:PE100 | Nos
5 | HDPE-140MM,PN6,END CAP,CLASS:PE100 | Nos
Total Qty In ( No's ) =
1 | FHTC
1 | GI PIPE-15MM | Rmt
2 | MDPE PIPE-20MM | Rmt
3 | BRASS TAP | Nos
4 | PP CLAMP SADLLE-63MM | Nos
5 | PP CLAMP SADDLE-75MM | Nos
6 | PP CLAMP SADLLE-90MM | Nos
7 | PP CLAMP SADDLE-140MM | Nos
8 | PP CLAMP SADDLE-160MM | Nos
9 | PP CLAMP SADDLE-200MM | Nos
10 | PP CLAMP SADDLE 125MM WITH M8 FASTNERS | Nos
11 | PP CLAMP SADLLE-110MM | Nos
12 | G.I ELBOW 15 MM | Nos
13 | GI SOCKET-15MM | Nos
14 | WALL MOUNT SADDLE GI PIPE-15MM | Nos
15 | 15MM GI NIPPLE - 0.3MTR LENGTH | Nos
16 | 15MM GI NIPPLE - 0.5MTR LENGTH | Nos
17 | 20MM MDPE COMPRESSION ELBOW | Nos
18 | SS FLOW CONTROL VAlVE | Nos
19 | MDPE FEMLE THREADED ASSEMBLY-20MM | Nos
20 | MDPE ELBOW-20MM | Nos
21 | TEFLAN TAPE | Nos
22
Total Qty In ( No's ) =
Sub Contractor Site Engineer Block incharge AGM DM PMX Project Incharge

## BRAHUPUR valves
POWER MECH PROJECTS.LIMITED
RURAL WATER SUPPLY PROJECT UNDER JJM, UP - PRAYAGRAJ
Reconciliation Statement - Issued Vs Certification Qty.
| Contractor Name- |  | MONTH: | SEPT | Block: | MANGRAURA
| TANISH PROJECT LTD |  | BILL NO: |  | GP: | BRAHUPUR
Sl NO | Description | Units |  |  |  |  | Balance Qty | SAP Entry | Remarks
|  |  | Total Issued Qty | Cumulative Consumption | Upto Pre Consumed Qty | This Bill Consumed Qty
A | VALVE FITTING MATERIALS
1 | 125MM DIA SLUICE VALVE | Nos. | 1 | 1 | 0 | 1
2 | 140 MM DIA SLUICE VALVE | Nos. | 1 | 1 | 0 | 1
3 | 110 MM DIA SLUICE VALVE | Nos. | 1 | 1 | 0 | 1
4 | 90 MM DIA SLUICE VALVE | Nos. | 1 | 1 | 0 | 1
4 | 200 MM DIA AIR VALVE | Nos. | 1 | 1 | 0 | 1
| 160 MM HDPE STUB BEND | Nos. | 2 | 2 | 0 | 2
5 | 125 MM HDPE STUB BEND | Nos. | 2 | 2 | 0 | 2
6 | 110 MM HDPE STUB BEND | Nos. | 2 | 2 | 0 | 2
7 | 90 MM HDPE STUB BEND | Nos. | 8 | 8 | 0 | 8
8 | 150MM MS FLANGE | Nos. | 2 | 2 | 0 | 2
9 | 125MM MS FLANGE | Nos. | 2 | 2 | 0 | 2
10 | 110MM MS FLANGE | Nos. | 2 | 2 | 0 | 2
11 | 90MM MS FLANGE | Nos. | 8 | 8 | 0 | 8
12 | 75 MM MS FLANGE | Nos. | 1 | 1 | 0 | 1
13 | 80 MM HDPE STUB BEND | Nos. |  |  | 0 | 0
14 | 200 MM HDPE STUB BEND | Nos. |  |  | 0 | 0
15 | 160MM HDPE STUB BEND | Nos. |  |  | 0 | 0
16 | 110 MM MS FLANGE | Nos. |  |  | 0 | 0
17 | 16/75 NUTT BOLT | Nos. | 16 | 16 | 0 | 16
18 | 16/100 NUTT BOLT | Nos. | 60 | 60 | 0 | 60
19 | RUBBER GASKET | KG | 5 | 5 | 0 | 5
Sub Contractor Site Engineer Block incharge AGM DM PMX Project Incharge

## brahupur fhtc
BARHUPUR CONNECTION
S.NO | DATE | start node | end node | DAI OF PIPE | MDPE PIPE | SITE | OWENAR NAME | AADHAR CARD NUMBER | MOBILE NUMBER
1 | 2024-09-06 | j205 | j202 | 63 | 5 | BARHUPUR | KALLU | 3852 2153 0995 | 9919818905
2 | 2024-09-06 | j205 | j202 | 63 | 5 | BARHUPUR | VIJAYKUMAR RAJARAM SAROJ | 2370 7553 4747 | 8097061154
3 | 2024-09-06 | j205 | j202 | 63 | 6 | BARHUPUR | ABDUL RASID | 3632 0481 0243 | 8601306823
4 | 2024-09-06 | j234 | j220 | 63 | 6 | BARHUPUR | MOHAMMAD RAKIB | 4632 1304 6609 | 9792616895 | description | units | ISSUED QTY | 9473 | 9479 | 9481 | 17487 | 17488 | 17493 | 17499 | 10850 | 19360 | 19361 | 19362 | 9483 | 17473 | TOTAL | CONSUMED P.BILL | BALANCE | PRESENT BILL
5 | 2024-09-06 | j220 | j218 | 63 | 5 | BARHUPUR | SALIM KHAN | 8213 9823 7336 | 9336046164 | G.I PIPE | MTRS | 1 | 200 | 200 |  | 300 |  |  | 200 |  |  | 200 |  |  |  | 1100 | 903 | 197 | 191
6 | 2024-09-06 | j218 | j200 | 63 | 5 | BARHUPUR | CHAD BABU | 5739 5814 7600 | 9004034332 | MDPE PIPE 20MM COIL-500MTRS | MTRS | 5 | 500 | 1000 |  |  |  | 2000 |  |  |  |  | 500 | 500 | 500 | 5000 | 5300 | -300 | 1170
7 | 2024-09-06 | j291 | j263 | 63 | 5 | BARHUPUR | ANJUM BEGUM | 5532 5670 4017 | 8081880990 | PPCLamps saddle-63*1/2" | nos | 1 | 200 |  | 150 | 300 |  |  | 200 | 25 | 100 |  |  | 70 |  | 1045 | 844 | 201 | 191
8 | 2024-09-06 | j326 | 286 | 63 | 5 | BARHUPUR | SHABA BANO | 9135 8383 1989 | 9555352378 | PPCLamps saddle-75*1/2" | nos | [8 empty] | 25 |  | 50 |  |  |  | 75 | 41 | 34
9 | 2024-09-06 | j326 | 286 | 63 | 5 | BARHUPUR | VASEEM KHAN | 7268 1976 2459 |  | PPCLamps saddle-90*1/2" | nos | [8 empty] | 25 | [5 empty] | 25 | 8 | 17
10 | 2024-09-06 | j326 | 286 | 63 | 6 | BARHUPUR | NASEEM KHAN | 5537 3469 6246 | 9219134554 | PPCLamps saddle-110*1/2" | nos | [8 empty] | 25 | [5 empty] | 25 | 0 | 25
11 | 2024-09-06 | j326 | 286 | 63 | 5 | BARHUPUR | JASEEM | 3536 8758 3150 | 9839747104 | PPCLamps saddle-125*1/2" | nos | [14 empty] | 0 | 0 | 0
12 | 2024-09-06 | j326 | 286 | 63 | 5 | BARHUPUR | JAMIL KHAN | 8026 1425 0886 | 9648886074 | PPCLamps saddle-140*1/2" | nos | [14 empty] | 0 | 4 | -4
13 | 2024-09-06 | j326 | 286 | 63 | 8 | BARHUPUR | KAIYUM ULLA | 5379 8661 9531 |  | PPCLamps saddle-160*1/2" | nos | [14 empty] | 0 | 6 | -6
14 | 2024-09-06 | j326 | 286 | 63 | 8 | BARHUPUR | NOOR SUBHA | 9249 5536 6292 | 8874757221 | PPCLamps saddle-200*1/2" | nos | [14 empty] | 0 | 0 | 0
15 | 2024-09-06 | j326 | 286 | 63 | 5 | BARHUPUR | NISHAR KHAN | 7702 3144 5145 | 9628964146 | pp comp fm theard adapter-20mm*1/2" | nos | 1 | 200 | 200 |  | 300 |  |  | 200 |  | 100 | 200 |  |  |  | 1200 | 903 | 297 | 191
16 | 2024-09-06 | j326 | 286 | 63 | 5 | BARHUPUR | SALMA BEGUM TAUHEED KHAN | 2287 6850 4215 | 9324910975 | pp comp fm theard elb off taken-20mm*1/2" | nos | 1 | 200 | 200 |  | 300 |  |  | 200 |  | 100 | 200 |  |  |  | 1200 | 903 | 297 | 191
17 | 2024-09-06 | j326 | 286 | 63 | 5 | BARHUPUR | IRFAN QAYYUM KHAN | 5653 9219 9473 | 7860509418 | threaded fcv-1/2"(15nb) | nos | 1 | 200 | 200 |  | 300 |  |  | 200 |  | 100 | 200 |  |  |  | 1200 | 903 | 297 | 191
18 | 2024-09-06 | j326 | 286 | 63 | 5 | BARHUPUR | NIYAJ NAIM KHAN | 5756 9752 2947 |  | GI elbow | nos | 2 | 400 | 400 |  | 600 |  |  | 400 | [5 empty] | 100 | 1900 | 1462 | 438 | 382
19 | 2024-09-06 | j246 | j294 | 63 | 5 | BARHUPUR | SANYOGITA SINGH | 6150 9308 6357 | 8010191772 | GI socket | nos | 1 | 200 | 200 |  | 300 |  |  | 200 |  | 100 |  |  |  | 100 | 1100 | 903 | 197 | 191
20 | 2024-10-06 | j109 | j145 | 63 | 5 | BARHUPUR | PHOTO DEVI | 5716 3928 1346 | 9120838454 | saddle g.i pipe-15mm(clamps) | nos | 2 | [13 empty] | 0 | 0 | 0
21 | 2024-10-06 | j194 | j122 | 63 | 6 | BARHUPUR | NANHELAL RAJAK | 4666 4082 4891 | 9554141025 | 15mm nipple-0.3mm | nos | 1 | 200 | 200 |  | 300 |  |  | 200 |  |  | 200 |  |  | 100 | 1200 | 903 | 297 | 191
22 | 2024-10-06 | j122 | j170 | 63 | 6 | BARHUPUR | NAGEENA BEGAM | 7704 0308 8913 | 9545100546 | 15mm nipple-0.3mm | nos | 1 | 200 | 200 |  | 300 |  |  | 200 |  |  | 200 |  |  |  | 1100 | 903 | 197 | 191
23 | 2024-10-06 | j122 | j170 | 63 | 5 | BARHUPUR | PEER MOHAMMD | 9808 2444403 3815 | 9839313362 | bib cock ptmt(taps) | nos | 1 | 200 | 200 |  |  | 300 |  | 200 |  |  | 200 |  |  | 100 | 1200 | 903 | 297 | 191
24 | 2024-10-06 | j170 | j296 | 63 | 5 | BARHUPUR | SHAKIR ALI | 8510 2879 9725 | 7666189243 | teflon tape | nos | 1 | 100 | [11 empty] | 40 | 140 | 0 | 140
25 | 2024-10-06 | j296 | j145 | 63 | 5 | BARHUPUR | MUNNE LAL RAM PRASAD | 7507 5755 5647 | 9867037316 | g.inails | nos | 4 | [13 empty] | 0
26 | 2024-10-06 | j177 | j168 | 63 | 5 | BARHUPUR | MUKTAR AHMAD | 6436 0288 5598 | 7237804693
27 | 2024-10-06 | j138 | j48 | 63 | 5 | BARHUPUR | SWAMI NATH | 3718 8120 0262 | 8874417360
28 | 2024-10-06 | j159 | j173 | 63 | 6 | BARHUPUR | GANGA DIN | 6952 1253 1856 | 9888891690
29 | 2024-10-06 | j235 | j158 | 63 | 5 | BARHUPUR | PERMA DEVI | 6610 8572 2753 | 6388500424
30 | 2024-10-06 | j158 | j167 | 63 | 5 | BARHUPUR | KANCHAN | 7646 5962 3862 | 9839615590
31 | 2024-10-06 | j158 | j167 | 63 | 8 | BARHUPUR | NIRAJ DEVI | 9677 3783 8169 | 7408835849 |  |  |  |  | brahupur | aurangabad | madhura rani
32 | 2024-11-06 | j138 | j48 | 63 | 8 | BARHUPUR | JHARI RAM | 3916 1866 8301 | 9918293929 |  |  |  |  | consumed | consumed | consumed
33 | 2024-11-06 | j92 | j329 | 63 | 5 | BARHUPUR | UMA DEVI | 6969 8599 7091 | 9651506275 |  |  |  |  | 326 | 172 | 405 | 903
34 | 2024-11-06 | j271(1) | j271(2) | 63 | 5 | BARHUPUR | ASHIYA BANO | 4433 7147 6866 | [5 empty] | 2187 | 880 | 2233 | 5300
35 | 2024-11-06 | j155 | j155(1) | 63 | 5 | BARHUPUR | BUBUNA BEGAM | 8073 7652 9059 | 9579935380 |  |  |  |  | 326 | 113 | 405 | 844
36 | 2024-11-06 | j265 | j284 | 63 | 5 | BARHUPUR | PHOOL CHANDRA | 2808 4341 5923 | 7897323307 | [5 empty] | 41 |  | 41
37 | 2024-11-06 | j265 | j280 | 63 | 5 | BARHUPUR | RAJ KUMAR | 4045 5401 1772 | 9721593746 | [5 empty] | 8 |  | 8
38 | 2024-11-06 | j265 | j314 | 63 | 5 | BARHUPUR | PUSHPA DEVI | 2240 2205 5811 | 9621318551 | [7 empty] | 0
39 | 2024-11-06 | j102 | j80 | 63 | 6 | BARHUPUR | SHILA DEVI | 8096 1894 2240 | 7379261058 | [7 empty] | 0
40 | 2024-11-06 | j307 | j308 | 63 | 6 | BARHUPUR | SHYAM PRAKASH UPADHYAY | 9038 6892 3858 | 9919271486 | [5 empty] | 4 |  | 4
41 | 2024-11-06 | j6(1) | j6(2) | 63 | 5 | BARHUPUR | MO SAIF | 4388 0753 2583 | 9699716505 | [5 empty] | 6 |  | 6
42 | 2024-11-06 | j20 | j20(1) | 63 | 5 | BARHUPUR | BEENA SHARMA | 4496 9480 0146 | 9651511022 | [7 empty] | 0
43 | 2024-12-06 | j246 | j351 | 63 | 5 | BARHUPUR | KRISHNA UPADHYAY | 3215 3000 4437 | 7887913936 |  |  |  |  | 326 | 172 | 405 | 903
44 | 2024-12-06 | j286 | j282 | 63 | 5 | BARHUPUR | ALOK UPADHYAY | 8152 5828 3731 | 9935721910 |  |  |  |  | 326 | 172 | 405 | 903
45 | 2024-12-06 | j286 | j293 | 63 | 5 | BARHUPUR | SURYAMANI | 7670 4688 5655 | 7408916660 |  |  |  |  | 326 | 172 | 405 | 903
46 | 2024-12-06 | j326 | j169 | 63 | 6 | BARHUPUR | CHANDRAMANI UPADHYAY | 8019 7344 7615 | 8948162995 |  |  |  |  | 652 |  | 810 | 1462
47 | 2024-12-06 | j224 | j273 | 63 | 5 | BARHUPUR | YASMEEN BEGAM | 2369 7842 5312 | 9580612216 |  |  |  |  | 326 | 172 | 405 | 903
48 | 2024-12-06 | j175 | j273 | 63 | 5 | BARHUPUR | SAROJA DEVI | 2497 3624 3789 | 9918770795 | [7 empty] | 0
49 | 2024-12-06 | j224 | j273 | 63 | 8 | BARHUPUR | SUSHILA DEVI | 8757 2290 3921 | [5 empty] | 326 | 172 | 405 | 903
50 | 2024-12-06 | j273 | j247 | 63 | 8 | BARHUPUR | MANJU | 7496 7942 0460 | [5 empty] | 326 | 172 | 405 | 903
51 | 2024-12-06 | j247 | j303 | 63 | 5 | BARHUPUR | POOJA DEVI | 4711 8996 9637 | 8470853205 |  |  |  |  | 326 | 172 | 405 | 903
52 | 2024-12-06 | j247 | j294 | 63 | 5 | BARHUPUR | SANJU DEVI | 3427 8505 8556 | 9792994519 |  |  |  |  | 100
53 | 2024-12-06 | j246 | j294 | 63 | 5 | BARHUPUR | ASHOK KUMAR | 5434 1403 6538 | 6387792635
54 | 13/6/2024 | j271(1) | j271(2) | 63 | 5 | BARHUPUR | NILAM | 7518 7893 3502 | 8948534272
55 | 13/6/2024 | j155 | j155(1) | 63 | 5 | BARHUPUR | KANHAIYA LAL | 5566 7456 5230 | 8948534272
56 | 13/6/2024 | j265 | j284 | 63 | 5 | BARHUPUR | SANTOSH KUMAR | 7329 6493 8219 | 6388500424
57 | 13/6/2024 | j265 | j280 | 63 | 6 | BARHUPUR | JAGDEESH PATEL | 4166 6564 8599 | 9721190550
58 | 13/6/2024 | j265 | j314 | 63 | 6 | BARHUPUR | FULECHAND SAROJ | 8647 1571 5765 | 9830184247
59 | 13/6/2024 | j102 | j80 | 63 | 5 | BARHUPUR | GUDIYA DEVI | 2087 0297 0879 | 9648021303
60 | 13/6/2024 | j307 | j308 | 63 | 5 | BARHUPUR | ANVARI BANO | 2658 3579 2354 | 9919568043
61 | 13/6/2024 | j6(1) | j6(2) | 63 | 5 | BARHUPUR | SONU ALI | 6314 2033 4291 | 6394353399
62 | 13/6/2024 | j20 | j20(1) | 63 | 5 | BARHUPUR | RAHMAN | 6368 2282 3111 | 9307177198
63 | 13/6/2024 | j246 | j351 | 63 | 5 | BARHUPUR | FIRAJ ALI | 4843 4076 4660 | 8421340515
64 | 13/6/2024 | j246 | j351 | 63 | 6 | BARHUPUR | RUBINA BANO | 6975 7346 0985 | 9565029319
65 | 14/6/2024 | j246 | j351 | 63 | 6 | BARHUPUR | SAHIDUL NISHA | 9487 6017 6749 | 9305255640
66 | 14/6/2024 | j246 | j351 | 63 | 5 | BARHUPUR | JAHIR KHAN | 6845 9399 2370 | 7084091598
67 | 14/6/2024 | j246 | j351 | 63 | 8 | BARHUPUR | SAHANA BANO | 6787 2891 8133 | 7084091598
68 | 14/6/2024 | j246 | j351 | 63 | 8 | BARHUPUR | TAUPHIK ALI | 7877 6719 1323 | 9028589863
69 | 14/6/2024 | j246 | j351 | 63 | 5 | BARHUPUR | ISLAM ALI | 6117 1953 4470 | 8874553740
70 | 14/6/2024 | j246 | j351 | 63 | 5 | BARHUPUR | MO SIRAZ | 2797 5930 3089 | 7860617824
71 | 14/6/2024 | j246 | j351 | 63 | 5 | BARHUPUR | TAUHID SHAH | 2474 0017 7613 | 8109369576
72 | 14/6/2024 | j246 | j351 | 63 | 5 | BARHUPUR | MOBIN ANSARI | 6350 8317 6535 | 9554150648
73 | 14/6/2024 | j246 | j351 | 63 | 5 | BARHUPUR | RAJ IYA BEGUM | 9964 0653 4885 | 9984922401
74 | 14/6/2024 | j246 | j351 | 63 | 5 | BARHUPUR | SANT PRADAD | 7496 6134 5952 | 9648980605
75 | 14/6/2024 | j246 | j351 | 63 | 6 | BARHUPUR | HUSEEN ANSARI | 3136 0596 5727 | 7408971984
76 | 15/6/2024 | j246 | j351 | 63 | 6 | BARHUPUR | MO JAINUL ABDIN | 4842 6485 8823 | 7738416905
77 | 15/6/2024 | j246 | j351 | 63 | 5 | BARHUPUR | ASALAM ANSARI | 5163 9035 9838 | 9918890978
78 | 15/6/2024 | j246 | j351 | 63 | 5 | BARHUPUR | HUSENA BANO | 6526 3470 7106 | 9670659412
79 | 15/6/2024 | j271(1) | j271(2) | 63 | 5 | BARHUPUR | KHALIL AHMAD | 8285 6738 4337 | 8948326183
80 | 15/6/2024 | j155 | j155(1) | 63 | 5 | BARHUPUR | MAHTAB JAHAN | 6168 3369 1218 | 8983993075
81 | 15/6/2024 | j271(1) | j271(2) | 63 | 5 | BARHUPUR | SHAKEEL AHMAD | 5228 6448 5777 | 7388691231
82 | 15/6/2024 | j156 | j155(1) | 63 | 6 | BARHUPUR | SIDDEK ANSARI | 3046 6143 5257 | 9628675936
83 | 16/6/2024 | j271(1) | j271(2) | 63 | 6 | BARHUPUR | JAMILA BANO | 3499 5565 2978 | 9792482639
84 | 16/6/2024 | j157 | j155(1) | 63 | 6 | BARHUPUR | SAHIDA BANO | 2004 3753 3928 | 9161290184
85 | 16/6/2024 | j271(1) | j271(2) | 63 | 8 | BARHUPUR | RASHEED AHMED | 8611 7697 6759 | 8007209704
86 | 16/6/2024 | j158 | j155(1) | 63 | 8 | BARHUPUR | GULSHAN BANO | 8943 1651 7783 | 7874740688
87 | 16/6/2024 | j271(1) | j271(2) | 63 | 6 | BARHUPUR | MO ILIYAS ANSARI | 4624 0136 9126 | 9919727064
88 | 16/6/2024 | j159 | j155(1) | 63 | 5 | BARHUPUR | SAMEER ANSARI | 2275 2104 3616 | 7228993820
89 | 16/6/2024 | j271(1) | j271(2) | 63 | 5 | BARHUPUR | TABASSUM BANO | 2859 5708 6690 | 9173059736
90 | 16/6/2024 | j160 | j155(1) | 63 | 5 | BARHUPUR | KAMARUL NISHA | 9448 5765 5983 | 7850045525
91 | 17/6/2024 | j271(1) | j271(2) | 63 | 5 | BARHUPUR | MALTI | 6412 5085 7415 | 6306185805
92 | 17/6/2024 | j161 | j155(1) | 63 | 5 | BARHUPUR | RAMBEER SAROJ | 8762 0462 1972
93 | 17/6/2024 | j271(1) | j271(2) | 63 | 6 | BARHUPUR | LALJI SAROJ | 7329 8741 8830
94 | 17/6/2024 | j162 | j155(1) | 63 | 6 | BARHUPUR | RAM SUKH | 6663 9422 3243 | 6928933382
95 | 17/6/2024 | j205 | j202 | 63 | 5 | BARHUPUR | SANJAY KUMAR | 7232 9160 0198
96 | 17/6/2024 | j205 | j202 | 63 | 5 | BARHUPUR | KAMLESH KUMAR | 4075 8377 8515 | 9721287160
97 | 17/6/2024 | j205 | j202 | 63 | 5 | BARHUPUR | ANARA DEVI | 8623 8639 1630
98 | 17/6/2024 | j234 | j220 | 63 | 5 | BARHUPUR | ANANT PRASAD SING | 3442 9281 3118 | 7607009282
99 | 17/6/2024 | j220 | j218 | 63 | 5 | BARHUPUR | RAMSEVAK | 8052 8176 9426 | 9839533089
100 | 18/6/2024 | j218 | j200 | 63 | 6 | BARHUPUR | RASIYA | 9376 8655 6378 | 9670349116
101 | 18/6/2024 | j291 | j263 | 63 | 8 | BARHUPUR | TAHIR | 2713 9405 9034 | 9651544397
102 | 18/6/2024 | j291 | j263 | 63 | 8 | BARHUPUR | NAJRIN BANO | 3696 1575 6107 | 9918685380
103 | 18/6/2024 | j291 | j263 | 63 | 6 | BARHUPUR | SHAMIM KHAN | 4514 3954 0599 | 6392186462
104 | 18/6/2024 | j291 | j263 | 63 | 5 | BARHUPUR | TAHAMMUL KHAN | 2279 9139 3283 | 8291128938
105 | 18/6/2024 | j291 | j263 | 63 | 5 | BARHUPUR | SHAKINA BEGAM | 8877 7815 1495 | 9321488927
106 | 18/6/2024 | j291 | j263 | 63 | 5 | BARHUPUR | TAHASIN BEGAM | 3057 2400 7662 | 7408465611
107 | 18/6/2024 | j291 | j263 | 63 | 5 | BARHUPUR | VAHEED SHEKH | 2061 7167 4934 | 9026270209
108 | 18/6/2024 | j291 | j263 | 63 | 5 | BARHUPUR | MANRAJI SAROJ | 4374 9315 6474 | 9559519193
109 | 18/6/2024 | j291 | j263 | 63 | 6 | BARHUPUR | RABBUL KHAN | 5326 9342 9327 | 8052477158
110 | 18/6/2024 | j291 | j263 | 63 | 6 | BARHUPUR | KHAN ABDULLAH MOHAMMAD TAKI | 2447 8042 1668
111 | 18/6/2024 | j291 | j263 | 63 | 5 | BARHUPUR | TASUAR BHOLAN KHAN | 2453 7654 8290 | 8108955634
112 | 18/6/2024 | j291 | j263 | 63 | 5 | BARHUPUR | SHAHIN BANO | 9312 8676 4236 | 9794892337
113 | 18/6/2024 | j291 | j263 | 63 | 5 | BARHUPUR | SHABNAM BANO | 7936 2065 3915 | 7084416196
114 | 19/6/2024 | j291 | j263 | 63 | 5 | BARHUPUR | SAHIMUL NISHA | 6670 2021 7381 | 8052896520
115 | 19/6/2024 | j291 | j263 | 63 | 5 | BARHUPUR | TASLIM KHAN | 8772 4693 1535 | 7596882605
116 | 19/6/2024 | j162 | j155(1) | 63 | 6 | BARHUPUR | BAKARIDAN KHAN | 5564 8841 2909 | 8601506664
117 | 19/6/2024 | j163 | j155(1) | 63 | 8 | BARHUPUR | USMAN | 2130 6199 5313 | 9161823518
118 | 19/6/2024 | j164 | j155(1) | 63 | 8 | BARHUPUR | FAHMEEDA BEGAM | 3784 0948 5902 | 8874250394
119 | 19/6/2024 | j165 | j155(1) | 63 | 5 | BARHUPUR | OMVEER SINGH | 8255 9414 9635 | 9936227985
120 | 19/6/2024 | j166 | j155(1) | 63 | 5 | BARHUPUR | SABIR SHEKH | 5007 5272 5655 | 9919222037
121 | 19/6/2024 | j286 | j282 | 63 | 5 | BARHUPUR | TAFIRUL | 2699 7671 0866 | 9454471036
122 | 19/6/2024 | j286 | j282 | 63 | 5 | BARHUPUR | FIROJ | 7908 3481 0628 | 9628192527
123 | 19/6/2024 | j286 | j282 | 63 | 5 | BARHUPUR | OM PRAKASH | 8304 6190 7708 | 7897781146
124 | 19/6/2024 | j286 | j282 | 63 | 5 | BARHUPUR | SAIYAD MOINUDDIN | 5775 6081 6142 | 9838781203
125 | 19/6/2024 | j286 | j282 | 63 | 6 | BARHUPUR | JAUVAD KHAN | 4529 6302 2215 | 9792861728
126 | 20/6/2024 | j286 | j282 | 63 | 6 | BARHUPUR | ASHIK ALI | 7137 4786 5476 | 9619651486
127 | 21/6/2024 | j286 | j282 | 63 | 5 | BARHUPUR | NURULLAH KHAN | 7732 5392 9570 | 8799511960
128 | 2024-05-07 | j286 | j282 | 63 | 5 | BARHUPUR | SAHJAHAN | 5283 8100 5683 | 8795610099
710
191
454

## dehri digarfhtc
DEHARI DIGAR
SN.NO | DATE | start node | end node | DAI OF PIPE | MDPE PIPE | SITE | OWENAR NAME | AADHAR CARD NUMBER | MOBILE NUMBER
1 | 2024-05-02 | J230 | J224 | 63MM | 5 | DEHARI DIGAR | PARMILA | 2882 3787 3124 | 8318185483
2 | 2024-05-02 | J224 | J225 | 63MM | 5 | DEHARI DIGAR | AMRAWATI | 3411 6641 6331 | 9984647567
3 | 2024-05-02 | J224 | J222 | 63MM | 5 | DEHARI DIGAR | GANGADEEN | 2402 7645 8185 | 9554491136
4 | 2024-05-02 | J222 | J223 | 63MM | 8 | DEHARI DIGAR | KUSUM DEVI | 9447 0546 6773
5 | 2024-05-02 | J222 | J221A | 63MM | 8 | DEHARI DIGAR | SHEELA DEVI | 3550 2848 4072 | 9151443230
6 | 2024-05-02 | J221A | J221B | 63MM | 12 | DEHARI DIGAR | RENU DEVI | 7590 8970 1783 | 9918138017
7 | 2024-05-02 | J221A | J221 | 63MM | 12 | DEHARI DIGAR | HARI LAL | 8946 7864 7031 | 9721749821
8 | 2024-05-02 | J221C | J221D | 63MM | 6 | DEHARI DIGAR | PARMILA DEVI | 7081 8173 8389 | 8874132869
9 | 2024-05-02 | J213 | J214 | 63MM | 6 | DEHARI DIGAR | PREMA DEVI | 5559 1353 5236 | 7696981625
10 | 2024-05-02 | J213 | J220 | 63MM | 5 | DEHARI DIGAR | LALMANI | 8907 6271 4775 | 7530947442
11 | 2024-05-02 | J213 | J220 | 63MM | 5 | DEHARI DIGAR | RAM SHIROMANI | 3191 8375 2858
12 | 2024-06-02 | J218 | J219 | 63MM | 5 | DEHARI DIGAR | SUDAMA DEVI | 8212 1781 1183
13 | 2024-06-02 | J220 | J239 | 63MM | 5 | DEHARI DIGAR | ANKIT PATEL | 9831 4247 3876
14 | 2024-06-02 | J239 | J243 | 63MM | 5 | DEHARI DIGAR | SAMAR BAHADUR VERMA | 3459 8339 7571
15 | 2024-06-02 | J239 | J241 | 63MM | 8 | DEHARI DIGAR | GANGA RAM | 5153 3914 0331
16 | 2024-06-02 | J241 | J242 | 63MM | 8 | DEHARI DIGAR | ANUJ KUMAR | 7206 4108 3787 | 8172938867
17 | 2024-06-02 | J241 | J241A | 63MM | 12 | DEHARI DIGAR | RAMPRATAP | 8033 8638 8800 | 9838775002
18 | 2024-06-02 | J241A | J241B | 63MM | 12 | DEHARI DIGAR | RANJEET PATEL | 5584 2286 1043
19 | 2024-06-02 | J241A | J241B | 63MM | 12 | DEHARI DIGAR | RAM LAKHAN | 8261 9171 3264
20 | 2024-06-02 | J241A | J240 | 63MM | 12 | DEHARI DIGAR | RAM ACHAL | 9111 6412 2279
21 | 2024-07-02 | J240 | J245 | 63MM | 5 | DEHARI DIGAR | GEETA | 7539 00253485 | 983848773
22 | 2024-07-02 | J240 | J235 | 63MM | 5 | DEHARI DIGAR | URMILA | XXXX XXXX 5374
23 | 2024-07-02 | J235 | J236 | 63MM | 5 | DEHARI DIGAR | HAFIJ | 5172 2316 4344 | 9628157233
24 | 2024-07-02 | J235 | J233 | 63MM | 5 | DEHARI DIGAR | AJAY KUMAR | 4579 4174 1890
25 | 2024-07-02 | J264 | J265 | 63MM | 5 | DEHARI DIGAR | KESHAW PRASAD | 2295 5375 1876
26 | 2024-07-02 | J233 | J234 | 63MM | 8 | DEHARI DIGAR | SHIV SANKAR | 6251 6327 4103
27 | 2024-07-02 | J233 | J221 | 63MM | 8 | DEHARI DIGAR | DOODHNATH | 6163 2975 9046
28 | 2024-07-02 | J16 | J22 | 63MM | 12 | DEHARI DIGAR | MANGAL PRASAD | 3906 2491 6690
29 | 2024-08-02 | J16 | J22 | 63MM | 12 | DEHARI DIGAR | RAM FAKEER | 9182 9014 6836
30 | 2024-08-02 | J22 | J37 | 63MM | 6 | DEHARI DIGAR | NASIM UDDIN SHAIKH | 4643 8480 6264
31 | 2024-08-02 | J37 | J38 | 63MM | 6 | DEHARI DIGAR | DHANRAJI | 3351 4706 1500
32 | 2024-08-02 | J37 | J42 | 63MM | 5 | DEHARI DIGAR | IRFAN AHAMAD | 9813 5932 8883
33 | 2024-08-02 | J37 | J53A | 63MM | 5 | DEHARI DIGAR | SAYIDA | 8620 3157 3403
34 | 2024-08-02 | J53A | J53 | 63MM | 5 | DEHARI DIGAR | MO ANAS KHAN | 6974 7619 1315
35 | 2024-08-02 | J53A | J53 | 63MM | 5 | DEHARI DIGAR | SHAH ALAM | 2802 0831 4630
36 | 2024-08-02 | J53A | J53B | 63MM | 5 | DEHARI DIGAR | MO GULSHAD | 6993 3891 9826
37 | 2024-08-02 | J16 | J17 | 63MM | 8 | DEHARI DIGAR | BADAMA | 7338 9699 5693
38 | 2024-12-02 | J16 | J17 | 63MM | 8 | DEHARI DIGAR | SANGEETA | 4052 1343 1801
39 | 2024-12-02 | J264 | J262 | 63MM | 12 | DEHARI DIGAR | ASHA DEVI | 3735 5008 1965 | 7565059417
40 | 2024-12-02 | J248 | J250 | 63MM | 12 | DEHARI DIGAR | JAINUL ABDIN | 5753 1440 8326
41 | 2024-12-02 | J66 | J65 | 63MM | 6 | DEHARI DIGAR | HAKIM KHAN | 4877 9537 3464
42 | 2024-12-02 | J66 | J64 | 63MM | 6 | DEHARI DIGAR | MEERA DEVI | 6898 9649 5030
43 | 2024-12-02 | J79 | J258 | 63MM | 5 | DEHARI DIGAR | MO IBRAHIM | 9755 3635 9233
44 | 13/2/2024 | J258 | J259 | 63MM | 5 | DEHARI DIGAR | DUKHIRAM | 7479 6987 9263
45 | 13/2/2024 | J258 | J263 | 63MM | 5 | DEHARI DIGAR | RAM ASRE | 6613 4196 5037
46 | 13/2/2024 | J263 | J254 | 63MM | 5 | DEHARI DIGAR | FULPATTI | 2698 4768 0073
47 | 13/2/2024 | J263 | J254 | 63MM | 5 | DEHARI DIGAR | INDRAWATI | 7479 6987 9263
48 | 13/2/2024 | J254 | J216 | 63MM | 8 | DEHARI DIGAR | MOHSIN ALI | 6862 6686 0798
49 | 13/2/2024 | J203 | J204 | 63MM | 8 | DEHARI DIGAR | HAMID ALI | 6388 6246 9630
50 | 13/2/2024 | J203 | J204 | 63MM | 12 | DEHARI DIGAR | MO IBRAHIM | 3864 4418 5326
51 | 14/2/2024 | J207 | J209 | 63MM | 12 | DEHARI DIGAR | SAMS TABREZ | 5753 1440 8326
52 | 14/2/2024 | J207 | J208 | 63MM | 6 | DEHARI DIGAR | MO IJAHAR | 6225 7717 8059
53 | 14/2/2024 | J207 | J231 | 63MM | 6 | DEHARI DIGAR | AABUL HASAN | 6388 6226 9630
54 | 14/2/2024 | J207 | J231 | 63MM | 5 | DEHARI DIGAR | MO JAMEEL | 9755 3635 9233
55 | 14/2/2024 | J231 | J232 | 63MM | 5 | DEHARI DIGAR | AEMAN ALI | 2611 6720 1101
56 | 14/2/2024 | J238 | J231 | 63MM | 5 | DEHARI DIGAR | INJMAMUL | 3468 6238 7713
57 | 14/2/2024 | J238 | J237 | 63MM | 5 | DEHARI DIGAR | BHUVAR | 6898 9649 5030
58 | 14/2/2024 | J238 | J244 | 63MM | 5 | DEHARI DIGAR | VIMALA DEVI | 6613 4196 5037
59 | 15/2/2024 | J209 | J210A | 63MM | 8 | DEHARI DIGAR | MUKTAR ALI
60 | 15/2/2024 | J210A | J210B | 63MM | 8 | DEHARI DIGAR | JAKIR ALI | 6225 7717 8059
61 | 15/2/2024 | J210A | J210 | 63MM | 12 | DEHARI DIGAR | IBRAR AHMAD | 3864 4418 5326
62 | 15/2/2024 | J211 | J215 | 63MM | 12 | DEHARI DIGAR | VAJID ALI | 4877 9537 3464
63 | 15/2/2024 | J185 | J186 | 63MM | 6 | DEHARI DIGAR | ASHOK KUMAR | 2698 4768 0073
458

## dehri digar 10% fhtc
HYD+A1:H15RO TEST/ GAP CLOSING/ FHTC STRETCH/VALVE FITTING/COMMISIONING ACKNOWLEDGEMENT
Contractor Name;tanish project company
Block:mangraura |  |  | GP;dehri digar
Billing Month -sept |  |  | RAB No:
Approved for RAB Quantities : (Tick Whichever is Proposing)
Hydrotest
GAP Closing
| FHTC Stretch |  |  |  | √
Valve Fitting
Commisioning
S. No. | Pipe Dia | Scope Qty | Upto date Laying Quantity | This Bill Quantity for Above Tic Marked Item | Cumm upto This Bill Quantity of Above Tic Marked Item | Remarks
1 | 63 |  |  | 7403.7
2 | 75 |  |  | 909.5
3 | 90 |  |  | 312.6
4 | 110 |  |  | 207.1
5 | 125 |  |  | 212.6
6 | 140 |  |  | 1675.6
7 | 160 |  |  | 1066.2
8 | 180
9 | 200
63/368 63 connections are given by contractor remaining connections are not taken by public and pradhan also not given any letter
Sub-Contractor Site Engineer Block-incharge AGM PMX Incharge Project Incharge
|  |  |  | 7403.7 | 909.5 | 312.6 | 207.1 | 212.6 | 1675.6 | 1066.2

## brahupur 10% fhtc
HYD+A1:H15RO TEST/ GAP CLOSING/ FHTC STRETCH/VALVE FITTING/COMMISIONING ACKNOWLEDGEMENT
Contractor Name;tanish project company
Block:mangraura |  |  | GP;Brahupur
Billing Month -aug |  |  | RAB No:
Approved for RAB Quantities : (Tick Whichever is Proposing)
Hydrotest
GAP Closing
| FHTC Stretch |  |  |  | √
Valve Fitting
Commisioning
S. No. | Pipe Dia | Scope Qty | Upto date Laying Quantity | This Bill Quantity for Above Tic Marked Item | Cumm upto This Bill Quantity of Above Tic Marked Item | Remarks
1 | 63
2 | 75
3 | 90
4 | 110
5 | 125
6 | 140
7 | 160
8 | 180
9 | 200
451/859 459 connections are given by contractor remaining connections are not taken by public pradhan also not given any letter
Sub-Contractor Site Engineer Block-incharge AGM PMX Incharge Project Incharge

## aurangabad 10%fhtc
HYD+A1:H15RO TEST/ GAP CLOSING/ FHTC STRETCH/VALVE FITTING/COMMISIONING ACKNOWLEDGEMENT
Contractor Name;tanish project company
Block:mangraura |  |  | aurangabad
Billing Month -aug |  |  | RAB No:
Approved for RAB Quantities : (Tick Whichever is Proposing)
Hydrotest
GAP Closing
| FHTC Stretch |  |  |  | √
Valve Fitting
Commisioning
S. No. | Pipe Dia | Scope Qty | Upto date Laying Quantity | This Bill Quantity for Above Tic Marked Item | Cumm upto This Bill Quantity of Above Tic Marked Item | Remarks
1 | 63
2 | 75
3 | 90
4 | 110
5 | 125
6 | 140
7 | 160
8 | 180
9 | 200
172/568 only 172 connetions only given by contractor and remaining connections are not ready to take and pradhan also not given any letter
Sub-Contractor Site Engineer Block-incharge AGM PMX Incharge Project Incharge

## PURBHIKA AND RAIGARH
PUREBHIKA AND RAIGARH(RESTORATION)
Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | Dia of pipe | Pipe Length (M) AS PER SITE |  |  |  |  | SQM
1 | J60 | J66 | BRICK ROAD | 0.36 | 63 | 93 |  |  |  |  | 33.48
2 | J242 | J180 | BRICK ROAD | 0.36 | 63 | 53.4 |  |  |  |  | 19.224
3 | J242 | J167 | BRICK ROAD | 0.36 | 63 | 64.8 |  |  |  |  | 23.328
4 | J171 | J235 | INTERLOCKING | 0.36 | 63 | 39.8 |  |  |  |  | 14.328
5 | J218 | J208 | INTERLOCKING | 0.36 | 63 | 33.2 |  |  |  |  | 11.952
6 | J208 | J171 | INTERLOCKING | 0.36 | 63 | 33.2 |  |  |  |  | 11.952
7 | J306 | J305 | BRICK ROAD | 0.36 | 63 | 287.5 |  |  |  |  | 103.5
8 | J340 | J335 | BRICK ROAD | 0.36 | 63 | 88.9 |  |  |  |  | 32.004
9 | J340 | J311 | BRICK ROAD | 0.36 | 63 | 203 |  |  |  |  | 73.08
10 | J347 | J370 | BRICK ROAD | 0.36 | 63 | 29.9 |  |  |  |  | 10.764
11 | J370 | J365 | BRICK ROAD | 0.36 | 63 | 100.3 |  |  |  |  | 36.108
12 | J286 | J277 | BRICK ROAD | 0.36 | 63 | 27 |  |  |  |  | 9.72
13 | J277 | J273 | BRICK ROAD | 0.36 | 63 | 77.1 |  |  |  |  | 27.756
14 | J293 | J277 | BRICK ROAD | 0.36 | 63 | 82 |  |  |  |  | 29.52
15 | J196 | J303 | INTERLOCKING | 0.36 | 63 | 120.4 |  |  |  |  | 43.344
16 | J303 | J285 | INTERLOCKING | 0.36 | 63 | 117.1 |  |  |  |  | 42.156
17 | J299 | J293 | INTERLOCKING | 0.36 | 63 | 17.4 |  |  |  |  | 6.264
18 | J150 | 279 | B.T ROAD | 0.36 | 63 | 6 |  |  |  |  | 2.16
19 | J246 | J227 | B.T ROAD | 0.36 | 63 | 4 |  |  |  |  | 1.44
20 | j161 | j166 | brick road | 0.36 | 63 | 66.4 |  |  |  |  | 23.904
21 | j166 | j174 | brick road | 0.36 | 63 | 24.2 |  |  |  |  | 8.712
22 | j174 | j221 | brick road | 0.36 | 63 | 122.6 |  |  |  |  | 44.136
23 | j247 | j257 | b.t road | 0.36 | 63 | 5 |  |  |  |  | 1.8
24 | j253 | j248 | INTERLOCKING | 0.36 | 63 | 40 |  |  |  |  | 14.4
25 | j248 | j270 | INTERLOCKING | 0.36 | 63 | 34 |  |  |  |  | 12.24
26 | J270 | J278 | INTERLOCKING | 0.36 | 63 | 21.3 |  |  |  |  | 7.668
27 | J248 | J226 | BRICK ROAD | 0.36 | 63 | 81 |  |  |  |  | 29.16
28 | J33 | J11 | BRICK ROAD | 0.36 | 63 | 33.8 |  |  |  |  | 12.168
29 | J354 | J347 | BRICK ROAD | 0.36 | 63 | 29.8 |  |  |  |  | 10.728
30 | J347 | J371 | BRICK ROAD | 0.36 | 63 | 89.3 |  |  |  |  | 32.148
31 | J297 | J292 | B.T ROAD | 0.36 | 63 | 7 |  |  |  |  | 2.52
32 | J339 | J343 | BRICK ROAD | 0.37 | 75 | 18 |  |  |  |  | 6.66
33 | J343 | J333 | BRICK ROAD | 0.37 | 75 | 31 |  |  |  |  | 11.47
34 | J333 | J358 | BRICK ROAD | 0.37 | 75 | 82.4 |  |  |  |  | 30.488
35 | j221 | j227 | b.t road | 0.39 | 90 | 6.2 |  |  |  |  | 2.418
36 | j101 | j179 | brick road | 0.39 | 90 | 4.3 |  |  |  |  | 1.677
37 | J69 | J70 | B.T ROAD | 0.44 | 140 | 6.4 |  |  |  |  | 2.816
396
PUREBHIKA AND RAIGARD restoration
|  | Sl. No | Road Type | UNITS | WO/DPR Qty's | Qty Executed Up to Date | Qty Executed Billed up to Date | Qty Billed Up to Previous | This Bill(Executed) | Remarks
|  | 1 | BRICK ROAD | SQM |  |  | 609.735 |  | 20% remaining release
|  | 2 | INTERLOCKING | SQM |  |  | 164.3
|  | 3 | B.T. ROAD | SQM
Sub-Contractor Site Engineer (Sr.Eng/ DY.M-SMX ) (Dy.M-PMX ) AGM Project Incharge

## MADHURA RANI RESTORATION
MADHURA RANI GANJ AND SARAOULI(JMR) BLOCK-MANGRAURA
Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | Dia of pipe(MM) | Pipe Length (M) | SQM | REMARK
1 | J147 | J148 | BRICK ROAD | 0.36 | 63 | 33.6 | 12.096
2 | J3 | J10 | B.T ROAD | 0.36 | 63 | 45.7 | 16.452
3 | J91 | J91A | B.T ROAD | 0.36 | 63 | 27 | 9.72
4 | J624 | J595 | B.T ROAD | 0.36 | 63 | 3.3 | 1.188
5 | J587 | J639 | B.T ROAD | 0.36 | 63 | 2.5 | 0.9
6 | J616 | J537 | BRICK ROAD | 0.36 | 63 | 5.4 | 1.944
7 | j558 | j542 | BRICK ROAD | 0.36 | 63 | 76.3 | 27.468
8 | j601 | j530 | BRICK ROAD | 0.36 | 63 | 210.7 | 75.852
9 | j514 | j619 | BRICK ROAD | 0.36 | 63 | 323 | 116.28
10 | j414 | j407 | BRICK ROAD | 0.36 | 63 | 3.9 | 1.404
11 | j478 | j479a | BRICK ROAD | 0.36 | 63 | 12.2 | 4.392
12 | j479a | j479 | BRICK ROAD | 0.36 | 63 | 6.5 | 2.34
13 | j594 | j598 | BRICK ROAD | 0.36 | 63 | 3.3 | 1.188
14 | j526 | j530 | interlocking | 0.46 | 63 | 21.7 | 9.982
15 | j530 | j600 | interlocking | 0.46 | 63 | 181 | 83.26
16 | j600 | j601 | BRICK ROAD | 0.36 | 63 | 51.2 | 18.432
17 | j600 | j602 | BRICK ROAD | 0.36 | 63 | 53.2 | 19.152
18 | j602 | j616 | BRICK ROAD | 0.36 | 63 | 21.7 | 7.812
19 | j381 | j391 | B.T ROAD | 0.36 | 63 | 5 | 1.8
20 | j428 | j438 | BRICK ROAD | 0.36 | 63 | 95.5 | 34.38
21 | j438 | j443 | BRICK ROAD | 0.36 | 63 | 50.9 | 18.324
22 | j443 | j444 | BRICK ROAD | 0.36 | 63 | 2.3 | 0.828
23 | j438 | j429 | BRICK ROAD | 0.36 | 63 | 2.7 | 0.972
24 | j427a | j427b | BRICK ROAD | 0.36 | 63 | 37.1 | 13.356
25 | j427 | j428 | BRICK ROAD | 0.36 | 63 | 32.2 | 11.592
26 | j427a | j429 | BRICK ROAD | 0.36 | 63 | 8.1 | 2.916
27 | j429 | j430 | BRICK ROAD | 0.36 | 63 | 23.7 | 8.532
28 | j424 | j426 | BRICK ROAD | 0.36 | 63 | 53.6 | 19.296
29 | j542 | j491 | brick road | 0.36 | 63 | 100.7 | 36.252
30 | j380 | j399 | interlocking | 0.46 | 63 | 125.8 | 57.868
31 | j399 | j403 | interlocking | 0.46 | 63 | 25.2 | 11.592
32 | j403 | j411 | interlocking | 0.46 | 63 | 30.1 | 13.846
33 | j411 | j418 | interlocking | 0.46 | 63 | 57.2 | 26.312
34 | j380 | j399 | b.t road | 0.36 | 63 | 6.7 | 2.412
35 | j129 | j130 | brick road | 0.36 | 63 | 25.1 | 9.036
36 | j34 | j35 | b.t road | 0.36 | 63 | 5 | 1.8
37 | j34 | j35 | cc | 0.36 | 63 | 103.1 | 37.116
38 | j133 | j134 | cc | 0.36 | 63 | 113.2 | 40.752
39 | j134 | j136 | cc | 0.36 | 63 | 54 | 19.44
40 | j134 | j135 | cc | 0.36 | 63 | 24.8 | 8.928
41 | j133 | j138 | interlocking | 0.46 | 63 | 85.1 | 39.146
42 | j138 | j160 | cc | 0.36 | 63 | 47.1 | 16.956
43 | j138 | j139 | cc | 0.36 | 63 | 78.3 | 28.188
44 | j25 | j38 | b.t road | 0.36 | 63 | 4 | 1.44
45 | j25 | j38 | interlocking | 0.46 | 63 | 33.1 | 15.226
46 | j25 | j38 | cc | 0.36 | 63 | 93.5 | 33.66
47 | j39 | j38 | cc | 0.36 | 63 | 47.6 | 17.136
48 | j38 | j79 | cc | 0.36 | 63 | 80.8 | 29.088
49 | j27 | j27a | b.t road | 0.36 | 63 | 3 | 1.08
50 | j30 | j31 | cc | 0.36 | 63 | 73.1 | 26.316
51 | j126 | j129 | brick road | 0.41 | 110 | 30.2 | 12.382
52 | j2 | j3 | b.t road | 0.41 | 110 | 5 | 2.05
53 | j120 | j123 | brick road | 0.44 | 140 | 26.2 | 11.528
54 | j123 | j126 | brick road | 0.44 | 140 | 48.1 | 21.164
55 | j77 | j72 | b.t road | 0.44 | 140 | 206.2 | 90.728
56 | j24 | j23 | b.t road | 0.46 | 160 | 7.2 | 3.312
57 | j72 | j110 | b.t road | 0.46 | 160 | 4.6 | 2.116
58 | j115 | j120 | brick road | 0.46 | 160 | 338.3 | 155.618
59 | j310 | j309 | b.t road | 0.5 | 200 | 270.7 | 135.35
60 | j310 | j283 | b.t road | 0.5 | 200 | 119.7 | 59.85
61 | j283 | j228 | b.t road | 0.5 | 200 | 223.2 | 111.6
62 | j228 | j216 | b.t road | 0.5 | 200 | 248.5 | 124.25
63 | j216 | j170 | b.t road | 0.5 | 200 | 357.2 | 178.6
64 | j216 | j170 | b.t road | 0.5 | 200 | 76.8 | 38.4
65 | j170 | j169 | b.t road | 0.5 | 200 | 68.5 | 34.25
66 | j169 | j167 | b.t road | 0.5 | 200 | 191.2 | 95.6
67 | j169 | j167 | b.t road | 0.5 | 200 | 5 | 2.5
68 | j167 | j166 | b.t road | 0.5 | 200 | 25.1 | 12.55
69 | j166 | j159 | b.t road | 0.5 | 200 | 92.7 | 46.35
70 | j159 | j146 | b.t road | 0.5 | 200 | 119.5 | 59.75
71 | j159 | j141 | b.t road | 0.5 | 200 | 85.1 | 42.55
72 | j141 | j113 | b.t road | 0.5 | 200 | 133.5 | 66.75
73 | j113 | j27 | b.t road | 0.5 | 200 | 212.3 | 106.15
74 | j27 | j23 | b.t road | 0.5 | 200 | 61 | 30.5
75 | j27 | j23 | b.t road | 0.5 | 200 | 12.3 | 6.15
76 | j502 | j493 | brick road | 0.5 | 200 | 19.2 | 9.6
77 | j493 | j491 | brick road | 0.5 | 200 | 101 | 50.5
78 | j491 | j489 | brick road | 0.5 | 200 | 29.3 | 14.65
79 | j485 | j481 | brick road | 0.5 | 200 | 46.4 | 23.2
80 | j487 | j486 | b.t road | 0.5 | 200 | 65.8 | 32.9
81 | j486 | j482 | b.t road | 0.5 | 200 | 75.6 | 37.8
82 | j481 | j483 | b.t road | 0.5 | 200 | 57.3 | 28.65
83 | j495 | j487 | b.t road | 0.46 | 160 | 87.8 | 40.388
84 | j433 | j442 | brick road | 0.46 | 160 | 27.1 | 12.466
85 | j511 | j514 | interlocking | 0.46 | 140 | 152.8 | 70.288
86 | j447 | j442 | brick road | 0.44 | 140 | 52 | 22.88
87 | j74 | j75 | interlocking | 0.46 | 63 | 97 | 44.62
88 | j162 | j165 | b.t road | 0.36 | 63 | 298.7 | 107.532
89 | j45 | j133 | b.t road | 0.36 | 63 | 133 | 47.88
90 | j111 | j128 | b.t road | 0.36 | 63 | 238.4 | 85.824
91 | j128 | j130 | b.t road | 0.36 | 63 | 11.2 | 4.032
92 | j130 | j137 | b.t road | 0.36 | 63 | 44.5 | 16.02
93 | j137 | j142 | b.t road | 0.36 | 63 | 45.5 | 16.38
94 | j142 | j147 | b.t road | 0.36 | 63 | 22.3 | 8.028
95 | j381 | j382 | b.t road | 0.44 | 140 | 6.2 | 2.728
96 | j398 | j393 | brick road | 0.44 | 140 | 50.6 | 22.264
97 | j401 | j414 | brick road | 0.36 | 63 | 6.5 | 2.34
98 | j310 | j376 | b.t road | 0.5 | 200 | 6.9 | 3.45
99 | j587 | j639 | b.t road | 0.36 | 63 | 3.5 | 1.26
100 | j504 | j506 | b.t road | 0.36 | 63 | 7 | 2.52
101 | j536 | j538 | b.t road | 0.36 | 63 | 6.5 | 2.34
MADHURA RANI GANJ ROAD restoration
|  | Sl. No | Road Type | UNITS | WO/DPR Qty's | Qty Executed Up to Date | Qty Billed Up to Previous | This Bill(Executed) | Remarks
|  | 1 | BRICK ROAD | SQM |  |  | 802.4 | 20% remaining release
|  | 2 | INTERLOCKING | SQM |  |  | 372.14
|  | 3 | B.T. ROAD | SQM |  |  | 1723.88
|  | 4 | C.C ROAD | SQM |  |  | 257.58
Sub-Contractor Site Engineer (Sr.Eng/ DY.M-SMX ) (Dy.M-PMX ) AGM Project Incharge