## shivapur fhtc
G.P-SHIVPUR KHURD
SL.NO | START NODE | END NOD | dia of pipe | MDPE PIPE LENGHTH | HOUES HOLDAR NAME | FATHER /HUSBAND NAME | AADHAR NO | HOUSE HOLDER CONTACT NO | SITE ENGINEER SIGN | REMARK
1 | j52 | j39 | 63 | 5 | Shivam Tiwari | Lalta Prasad Tiwari | 494195367153 | 7394053405
2 | j39 | j35 | 63 | 5 | Ravi Kumar Tiwari | Badri Prasad Tiwari | 391772380397 | 8542055000
3 | j35 | j24 | 63 | 5 | Rekha Tiwari | Atul Kumar Tiwari | 615487274692 | 7408763656
4 | j24 | j28 | 63 | 5 | Chaman Prakash | Kedar Nath | 362709357243 | 6265996187
5 | j24 | j21 | 63 | 5 | Malti | Ram Swaroop | 966143690889 | 9838736288
6 | j21 | j15 | 63 | 5 | Hari ram | Dasu | 530342811383 | 9559717532
7 | J15 | J16 | 63 | 5 | Mangaruram | Dassu | 447811182902 | 3144060518
8 | J15 | J11 | 63 | 5 | Pramila Tiwari | Ram Ji Shukla | 771158965055 | 8299038459
9 | J15 | J11 | 63 | 5 | Sita | Bodhi | 243908927465 | 7380741350
10 | J15 | J11 | 63 | 5 | Ram Chandra Yadav | lalu ram | 637075841397 | 8368628766
11 | J15 | J11 | 63 | 5 | Vijay Kumar Yadav | Ram Chandra Yadav | 700959867184 | 8368628766
12 | J15 | J11 | 63 | 5 | Ashok Kumar Yadav | Ram Dular Yadav | 628989044361 | 9936914823
13 | J15 | J11 | 63 | 5 | Krishna Kumar | Rameshar | 941992278992 | 8009354280
14 | J4 | J5 | 63 | 5 | Asiya | Bachi | 315174105946 | 7084909396
15 | J4 | J5 | 63 | 5 | Mahrulnisha | Mohd Safik | 623257976372 | 8795651946
16 | J4 | J5 | 63 | 5 | Najo | Harunaliali | 614402541440 | 9822296090
17 | J4 | J5 | 63 | 5 | Shashi Tiwari | Chandrasekhar | 845621780155 | 8299192677
18 | J4 | J5 | 63 | 5 | Amar Kumar | Ram Charan | 406264222355 | 7897336491
19 | J4 | J5 | 63 | 5 | Bhuvararam | Bodhai | 243140320387 | 9839085315
20 | J3 | J4 | 63 | 5 | Nohari Ram | Indra | 969381862429 | 8081549605
21 | J3 | J4 | 63 | 5 | Ram Fer | Ram Jiyavan | 508710520114 | 9129221188
22 | J67(A) | J84 | 63 | 5 | Maliti Tiwari | Awadhraj Shukl | 640352749241 | 8009348627
23 | J67(A) | J84 | 63 | 5 | Kalu Ram | Ramlal | 422542699950 | 8881483922
24 | J67(A) | J79 | 63 | 5 | Rama Devi | Sita Ram | 378426684841 | 9839980313
25 | J67(A) | J67 | 63 | 5 | Kevla Devi | Somai | 610183923201 | 8090169157
26 | J67(A) | J67 | 63 | 5 | Pradeep Vanvasi | Abhay Raj Vanvasi | 648996545052 | 9727952903
27 | J67 | J82 | 63 | 5 | Shiv Kumar | Ramdev | 294702741353 | 9369813411
28 | J67 | J61 | 63 | 5 | Ramkaran | Sukhram | 420827169382 | 9161141318
29 | J46 | J61 | 63 | 5 | Arun Kumar | Bhola Nath | 955925168589 | 9794820050
30 | J46 | J61 | 63 | 5 | Ghisan | Gherrau | 262448156978 | 8756132724
31 | J61 | J45 | 63 | 5 | Ram Raj | Shukh Ram | 320660143982 | 9628923880
32 | J61 | J45 | 63 | 5 | Shobhnath Yadav | Bhola Nath | 571851060976 | 9082602092
33 | J45 | J40 | 63 | 5 | Chandan Kumar Yadav | Ram Awadh Yadav | 349657539542 | 6306332018
34 | J45 | J40 | 63 | 5 | Usha Devi | Ram Dayal | 400281916436 | 7394053405
35 | J40 | J41 | 63 | 5 | Pawan Kumar Yadav | Raghav Ram | 700242476612 | 8542055000
36 | J40 | J39 | 63 | 5 | Alok Kumar Tiwari | Raj Kumar Tiwari | 231541935364 | 7408763656
37 | J40 | J39 | 63 | 5 | Avdhesh Narayan Tiwari | GayaPrasad Tiwari | 825120192276 | 6265996187
38 | j45 | j53 | 63 | 5 | Rekha Tiwari | Ashok Kumar Tiwari | 837944903063 | 9838736288
39 | j45 | j53 | 63 | 5 | Neelam Tiwari | Surylal | 727040262408 | 9559717532
40 | j53 | j49 | 63 | 5 | Kiran Tiwari | Narendra Pathak | 384240239943 | 3144060518
41 | j53 | j49 | 63 | 5 | Jagdamba Prasad Tiwari | Gaya Prasad | 246938868760 | 8299038459
42 | j53 | j49 | 63 | 5 | Rakesh Kumar Tiwari | Gaya Prasad | 596110306199 | 7380741350
43 | j53 | j58 | 63 | 5 | Angura Devi | Mother Dina | 701950540928 | 8368628766
44 | j53 | j58 | 63 | 5 | Sunita Devi | sajanlal | 751620190402 | 8368628766
45 | J5A | J5B | 63 | 5 | Madhu | Achhelal | 226513526603 | 9558317344
46 | j58 | j58(1) | 63 | 6 | Rampatti | Amarnath | 821528526020 | 8009348627
47 | j58 | j58(1) | 63 | 6 | Antima Pal | Mohan Lal | 534011750776 | 8881483922
48 | j58(1) | j64a | 63 | 6 | Heera devi | Rajdev | 794876420609 | 9839980313
49 | j58(1) | j64a | 63 | 6 | Kalu Ram Verma | Ramaroshan | 412648924720 | 8090169157
50 | j64a | j64b | 63 | 6 | Santosh Kumar Pandey |  | 707821281626 | 7710823640
51 | j64a | j64 | 63 | 6 | Uma | Rakesh Kumar | 615669930592 | 9315117581
52 | j64 | j66 | 63 | 6 | Basanti | Ramprasad | 252365484406 | 9919594383
53 | j64 | j65 | 63 | 6 | Omprakash pandey | Rajmani | 758207475424 | 8009348627
54 | j64 | j65 | 63 | 6 | Surendra Verma | Sita Ram | 822492688993 | 8881483922
55 | j58(1) | j59 | 63 | 6 | Surajbali | kashiram | 847234197271 | 9839980313
56 | j58 | j60 | 63 | 6 | Pooja | Balvant | 658932868770 | 8090169157
57 | j58 | j60 | 63 | 6 | Sampatti Devi | Ram Awadh | 430052453574 | 9792688972
58 | j35 | j35(a) | 63 | 6 | Mahesh Narayan | Sukhai | 699085580667 | 9687634201
59 | j90 | j94 | 75 | 6 | Manisha | Pream Nath | 200979536105 | 9125435423
60 | j90 | j87 | 75 | 6 | Vonod Kumar | Jiya Lal | 534355139464 | 6392313283
61 | j87 | j76 | 75 | 6 | Rampadarath | Ramdev | 495585569992 | 8948772608
62 | j97 | j94 | 75 | 5 | Shyam Narayan Pathak | Kedar Nath pathak | 773380173116 | 8114040244
63 | j97 | j94 | 75 | 5 | Rama Shankar | Mata Prasad | 593534937493 | 9936716215
64 | j97 | j94 | 75 | 5 | Ashok Kumar Pathak | Ramyash Pathak | 574075864518 | 9648091303
65 | j76 | j43 | 75 | 5 | Somai Verma | Jagannath | 410473872917 | 8929593500
66 | j76 | j43 | 75 | 5 | Shiv Kali | Pappu | 441898927454 | 6359021585
67 | j76 | j43 | 75 | 5 | Sanjay Kumar Yadav | Ram Dular | 997810433961 | 9839975905
68 | j17 | j9 | 75 | 5 | Sumana | Ramesh | 827614136107 | 9696126049
69 | j17 | j9 | 75 | 5 | Ram Dular | Bhusai | 674581381680 | 6386950837
70 | j17 | j9 | 75 | 5 | Savitri Devi | Subhash Chandra | 822403288959 | 9454158793
71 | j9 | j43 | 75 | 5 | Sumitra | Jayram | 241907989554 | 9580774307
72 | j9 | j43 | 75 | 5 | laxmi Narayan Shukla | Ramabhilash Shukla | 244308874847 | 9452850558
73 | j9 | j9a | 75 | 5 | Dhanawati | Pappu | 496357567041 | 9451023950
74 | j11 | j9a | 75 | 5 | Dhanpatti | Dan Bahadur | 621504331654 | 7985260575
75 | j9(1) | j9(2) | 75 | 5 | Navneet Shukla | Vivek Shukla | 515234842595 | 9670632522
76 | j1 | 75(a) | 75 | 5 | Shrinath | Ramlal | 376521997014 | 9838578127
77 | j75a | J75 | 75 | 5 | Susheela | Jamuna Prasad | 756998132467 | 9795689491
78 | j75a | J75 | 75 | 5 | Santara Devi | Data Deen | 974372109432 | 8376968733
79 | j2 | j3 | 75 | 5 | Shri Ram Pal | Ram Kripal | 883282663192 | 8528226590
80 | J76 | J75 | 75 | 5 | Ram Sewak ptel | Ram Deen | 945641095683 | 8948772608
81 | J76 | J75 | 75 | 5 | Sunita | Dhani Ram | 640331353709 | 6392417833
82 | j1 | 75(a) | 75 | 5 | Mewa Lal | Guljar | 389351625126 | 9305351286
83 | j2 | 75(a) | 75 | 5 | Munna | Chote Lal | 494374244047 | 9328579891
84 | j3 | 75(a) | 75 | 5 | Deepak | Chhotelal | 942453081379 | 9328579891
85 | j9 | j2 | 90 | 5 | Ram Abhilakh Pal | Ram Bodh Pal | 637461534120 | 9792773028
86 | j9 | j2 | 90 | 5 | Ram Ashare Verma | Ram Khelawan | 737023979635 | 8376968733
87 | j9 | j2 | 90 | 5 | Shiv Kumar | Ram Chandra | 459670220185 | 7379983415
88 | j9 | j2 | 90 | 5 | Ram Karan Prajapati | Ghurahoo | 895445455275 | 9792773028
89 | j9 | j2 | 90 | 5 | Ranjeet Kumar Ojha | Dev Prasad Ojha | 780737766459 | 7572033705
90 | j9 | j2 | 90 | 5 | Shyam Narayan | Ramjas | LDR2674976 | 7233824031
91 | j9 | j2 | 90 | 5 | Ram Chandra | Satya Dev | 703670147127 | 9319328283
92 | j75a | J75 | 75 | 5 | Tej Bahadur | Jhiguri | 472299044571 | 7081633072
93 | j75a | J76 | 75 | 5 | Sunil Kumar Verma | Ram Achabair | 972582753822 | 9695255569
94 | j75a | J77 | 75 | 5 | Kusum Devi | Dinesh Kumar | 975915777738 | 9793447610
95 | j75a | J78 | 75 | 5 | Harikesh Verma | Gauri Shankar Verma | 529056282811 | 9794455354
96 | j75a | J79 | 75 | 5 | Bachchan Kumar | Jiya Lal | 237263498571 | 6392313283
97 | j2 | j2(a) | 110 | 5 | Pooja | Ramji | 531184133484 | 8264764610
98 | j2 | j2(a) | 110 | 5 | Jagannath Yadav | Ram Das Yadav | 890270337888 | 9838040164
99 | j2 | j2(a) | 110 | 5 | Rambaran Yadav | Devsaran | 446694908832 | 6307063171
100 | j2 | j2(a) | 110 | 5 | Rampyare | Deosharan | 388709390896 | 9769541749
101 | j2 | j2(a) | 110 | 5 | Saroja Devi | Pradeep Kumar | 391763506488 | 8756055715
102 | j2 | j2(a) | 110 | 5 | Kanchan Pal | Satish Kumar Pal | 821233194495 | 9839969715
103 | j2 | j2(a) | 110 | 5 | Amrawati | Shilendra Prasad Yadav | 288870943962 | 9198674443
104 | j2 | j2(a) | 110 | 5 | Jagannath Verma | Babulal | 839389525829 | 9565470059
105 | j2 | j2(a) | 110 | 5 | Jagdev Prasad | Ori Ram | 961355579889 | 8765414432
106 | j2 | j2(a) | 110 | 5 | Badri Prasad | Ram Das | 381732727095 | 7007317226
107 | j2 | j2(a) | 110 | 5 | Ratna Devi | Umashankar | 350701060349 | 9919729892
108 | j2(a) | j1 | 110 | 5 | Chhotelal | Bachi | 837346679991 | 9919908109
109 | OHT | j1 | 125 | 5 | Sangeeta | Mahesh | 511065982376 | 9935832578
110 | J9(A) | J9(b) | 63 | 5 | Abhay Raj | Bhulai Ram | 870376107043 | 8998614790
111 | J75(A) | J75(B) | 63 | 5 | Sita Devi | Mata Prasad | 868267502900 | 9695421215
112 | J75(A) | J75(B) | 63 | 5 | Kareena | Bhola Nath | 239637230893 | 8953794026
113 | J2(A) | J6 | 63 | 5 | Uttam Kumar Pandey | Pram Narayan | 470039951402 | 8574884338
114 | J6 | J8 | 63 | 5 | Kamlesh Devi | Late Jagdish | 805034532090 | 8081442114
115 | J6 | J8 | 63 | 5 | Rakesh Pal | Ram Tahal | 631562774948 | 8239323704
116 | J6 | J4 | 63 | 5 | Ruchi Yadav | Rajendra Yadav | 767341488647 | 7398087659
117 | J6 | J4 | 63 | 5 | Rekha Gupta | Shiv Shankar Gupta | 908836113382 | 9619082448
118 | J6 | J4 | 63 | 5 | Ram Asare | ShriRam | 802596045519 | 9621455449
119 | J6 | J4 | 63 | 5 | Sumna | Ramlavat | 655447711376 | 9580744920
120 | J6 | J4 | 63 | 5 | Ramkishan | Jagdamba Prasad | 400466982809 | 7800728943
121 | J6 | J4 | 63 | 5 | Ved Prakash Mishra | Ram Lakhan | 499367244779 | 9161025910
122 | J6 | J4 | 63 | 5 | Kulwant Prasad Tripathi | Ram Dev Tripathi | 668401506960 | 9792773028
123 | J6 | J4 | 63 | 8 | Nanhku Ram | Girdhari | 911193095988 | 8090402435
124 | J67(A) | J84 | 63 | 8 | Kalloo | Nohar | 867455216917 | 8874191075
125 | J67(A) | J84 | 63 | 8 | Nand Lal | Mendu Ram | 474929146385 | 6386268397
126 | J67(A) | J85 | 63 | 8 | Dinesh | Babulal Yadav | 768061591697 | 7754871923
127 | J67(A) | J80 | 63 | 5 | Rampatti | Amarnath | 821528526020 | 9125435423
128 | J67(A) | J81 | 63 | 5 | Bindu Yadav | Shesh Narayan Yadav | 805696349504 | 6386591384
129 | J67(A) | J82 | 63 | 5 | Ram Das Yadav | Ram Aadhar Yadav | 577232512745 | 9936532818
130 | J67(A) | J83 | 63 | 5 | Sheetla Prasad | RamNihor | 500020069557 | 9999263137
131 | J67(A) | J84 | 63 | 5 | Anil Kumari | Mukesh Kumar | 381953844057 | 9794746322
132 | J67(A) | J85 | 63 | 5 | Badki | Shrikrishna | 445019981685 | 9565092845
133 | J67(A) | J86 | 63 | 5 | Kalu Ram Verma | Ram Bharosh | 412648924720 | 9565449117
134 | J67(A) | J87 | 63 | 5 | Manjeet Kumar | Ganesh Prasad | 231169911396 | 7571971221
135 | J67(A) | J67 | 63 | 5 | Ram Avtar | Ram Bharosh | 367337738066 | 9717057064
136 | J67(A) | J67 | 63 | 5 | Ramesvar Prasad Yadav | Ram Kisor | 254273259246 | 9780923322
137 | J67(A) | J79 | 63 | 5 | Daya Ram | Nanu Ram | 815346693419 | 7291961738
138 | J67(A) | J80 | 63 | 5 | Sushama Verma | Mevalal | 648554040403 | 9794275153
139 | J67(A) | J81 | 63 | 5 | Sajan lal | Hari Ram | 484358963963 | 9455910846
140 | j43 | j46 | 75 | 5 | Bhajan Lal |  | 826650990335 | 8542003584
141 | j43 | j46 | 75 | 5 | Misrilal | Sukhai | 346980728204 | 9451023950
142 | j43 | j46 | 75 | 5 | Bimla Devi Verma | Dinesh Kumar Verma | 881327757752 | 8303417680
143 | j43 | j46 | 75 | 5 | Jashveer Yadav | Ram karan Yadav | 311686922314 | 9559992314
144 | j43 | j46 | 75 | 6 | Kalloo | Nohar | 867455216917 | 8874191075
145 | J67 | J82 | 63 | 6 | Mahendra | Prithvi Pal | 722603182043 | 8009271646
146 | J67 | J61 | 63 | 6 | Gurudin |  | 504321417697 | 9454977287
147 | J46 | J61 | 63 | 6 | Rekha | Sujeet Kumar Verma | 924779532718 | 9161304808
148 | J46 | J61 | 63 | 6 | Jokhu Ram | Chandika Prasad Yadav | 437687069901 | 7978998119
149 | J61 | J45 | 63 | 5 | Kanchan | Chhote lal | 503424939856 | 8933901812
150 | J61 | J45 | 63 | 5 | Shikha Tiwari | Vivek Tiwari | 479369081724 | 9792773028
151 | J45 | J40 | 63 | 5 | Yashoda Verma | Ram Varan | 283692933731 | 9792605480
152 | J45 | J40 | 63 | 5 | Ram Rati | Ram Khelawan | 260718510893 | 9721063483
153 | J40 | J41 | 63 | 5 | Shankuntala | Bhulan Pathak | 207090146679 | 8808462337
154 | J40 | J39 | 63 | 5 | Amrawati | Uday Pal | 351436173016 | 8009691455
155 | J40 | J39 | 63 | 5 | Narendra Kumar | Shiv Prasad | 270907637171 | 6392578978
156 | j45 | j53 | 63 | 5 | Akhilesh Kumar Shukla | Shyam Dutt Shukla | 706407382248 | 9260994553
157 | j52 | j39 | 63 | 5 | Kamlesh Kumar Pandey | Shitla Prasad Pandey | 343351509946 | 9450255094
158 | j39 | j35 | 63 | 5 | Sita |  | 598388493203 | 8795439054
159 | j35 | j24 | 63 | 8 | Shivram | Ganga | 403010157087 | 7039186311
160 | j24 | j28 | 63 | 8 | Nilam Kumari | SuryaLal | 727040262408 | 9792773028
161 | j24 | j21 | 63 | 5 | Ram Kishor | Ganga | 475445731047 | 9621942758
162 | j21 | j15 | 63 | 5 | Brijendra Kumar | Ramkhelawan | 823478720203 | 8960899443
163 | J15 | J16 | 63 | 5 | Sunil Kumar yadav | RmaShankar | 208202024848 | 8874996902
164 | J67 | J61 | 63 | 5 | Rajit Ram | Ramkripal | 973554005589 | 7379259207
165 | J46 | J61 | 63 | 5 | Prema | Heeralal | 512397155809 | 7054411362
166 | J46 | J61 | 63 | 5 | Kusum Devi | Devi Prasad | 950929842772 | 9219616929
167 | J61 | J45 | 63 | 5 | Anara | Sati Deen | 908460015628 | 6352498364
168 | J61 | J45 | 63 | 5 | Gita Verma | Ram Milan Verma | 448971644097 | 6390058663
879
421

## persanda fhtc
G.P-PERSANDA
SL.NO | DIA OF PITE(MM) | START NODE | END NOD | MDPE PIPE LENGHTH | HOUES HOLDAR NAME | FATHER /HUSBAND NAME | AADHAR NO | HOUSE HOLDER CONTACT NO | SITE ENGINEER SIGN | REMARK
1 | 63 | j36 | j35 | 5 | Manju Verma | Akhilesh Verma | 542851342379 | 7860939597
2 | 63 | j51 | j49 | 5 | Usha | Bhullar | 295832398518 | 8318859476
3 | 63 | j56A | J56B | 5 | Jagdamba Prasad Tiwari | Gaya Prasad | 246938868760 | 8735876811
4 | 63 | j62 | j65 | 7 | Santosh Tiwari |  | 330256352823 | 9335125310
5 | 63 | j62 | j66 | 5 | Saurabh Verma |  | 511431200211 | 9335322485
6 | 63 | j52 | j53 | 5 | Ram Sewak | Ram Pyare | 586596650022 | 9653344584
7 | 63 | j52 | j53 | 5 | Renu Yadav | Pradeep Kumar | 672159357835 | 8356850478
8 | 63 | j30 | j31 | 5 | Vijaya Devi | Ram Abhilash | 247830981019 | 7065874245
9 | 63 | J30 | J31 | 5 | Prabhawati | Ram Yash | 345267957940 | 9621942758
10 | 63 | J29A | J29 | 5 | Sanjay Kumar | Shiv Prasad | 969332194901 | 9151451560
11 | 63 | J41 | J48 | 5 | Ravi Kumar | Sanjeet Kumar | 893059437413 | 9327891474
12 | 63 | J30 | J29A | 5 | Angura Devi | Dina | 701950540928 | 9565649506
13 | 63 | J29A | J29B | 5 | Alok Kumar Tiwari | Raj Kumar Tiwari | 231541935384 | 9473545489
14 | 63 | J29A | J29B | 5 | Rajesh Kumar Tiwari | Gaya Prasad | 703765373690 | 8174007732
15 | 63 | J29 | J23 | 5 | Achchhe Lal | Bandhu Ram | 391896304119 | 9558317344
16 | 63 | J29 | J23 | 8 | Avdhesh Narayan Tiwari | Gaya Prasad Tiwari | 825120192276 | 7007898206
17 | 75 | J11 | J12 | 5 | Rakesh Kumar Tiwari | Gaya Prasad | 596110306199 | 7392076166
18 | 75 | J11 | J12 | 5 | Sajan lal | Ram Asre | 908647693973 | 8881468234
19 | 63 | J77 | J77A | 5 | Anant Ram | Mata Fer | 795416787862 | 9792773028
20 | 63 | J77A | J75A | 5 | Lila Devi | Chhedi | 263601508396 | 9792773028
21 | 63 | J75A | J75B | 5 | Ramhit Yadav | Ganga Ram | 226413532983 | 9621942758
22 | 63 | J75A | J70 | 5 | Dilip Kumar | Ram Lakhan | 237754352378 | 9120146254
23 | 63 | J70 | J71 | 5 | Santlal | Bhorai | 730039390268 | 9140885975
24 | 63 | J84A | J84B | 5 | Dwarika Prasad | Ram Bahadur | 805109336136 | 9936216894
25 | 63 | J90 | J91 | 5 | Dukhana Devi | Babu Lal | 970212467670 | 7388283219
26 | 63 | J90A | J92 | 5 | Narayan Dutta Tiwari | Ram Nath Tiwari | 441198747164 | 9792773028
27 | 110 | J37 | J35 | 5 | Sunita Tiwari |  | 549122399008 | 9792773028
28 | 110 | J37 | J35 | 5 | Ashadevi | Vinay Kumar | LDR3659695 | 9695672594
29 | 110 | J37 | J35 | 5 | Nisha Devi | Tirath Raj | 980883969100 | 8303361816
30 | 110 | J37 | J38 | 5 | Pawan Kumar Yadav | Raghav Ram | 700242476612 | 8054259550
155

## lauli fhtc
G.P-LAULI PHOKATKHAM
SL.NO | DATE | DIA OF PITE(MM) | START NODE | END NOD | MDPE PIPE LENGHTH | HOUES HOLDAR NAME | FATHER /HUSBAND NAME | AADHAR NO | HOUSE HOLDER CONTACT NO | REMARK
| 1 | 90 | J190 | J267 | 5 | Sarita | Ram Abhilash | 688948046092 | 7835863582
| 2 | 110 | J267 | J175 | 5 | Akhilesh Yadav |  | 812795266645 | 9580777029
| 3 | 90 | J175 | J265 | 8 | Usha | Mahendra | 305083809182 | 7800719588
| 4 | 90 | J267 | J136 | 6 | Ramraj | Shitla Prasad | 827252541661 | 9936881301
| 5 | 90 | J136 | J253 | 8 | Ramkhelawan | Shitla Prasad | 504011433508 | 9455930338
| 6 | 90 | J267 | J136 | 5 | Ram Bahadur | Babulal | 338555639289 | 9721063483
| 7 | 110 | J96 | J90 | 5 | Malti | Bhulai | 637233746667 | 8808462337
| 8 | 110 | J175 | J96 | 10 | Mata Prasad | Guru Deen | 739031358680 | 8009691455
| 9 | 110 | J175 | J96 | 6 | Vikash Kumar Sharma | Devi Sharma | 678810489155 | 6392578978
| 10 | 110 | J175 | J96 | 8 | Veena Singh | Maan Singh | 480791397332 | 9260994553
| 11 | 110 | J175 | J96 | 5 | Veena Singh | Maan Singh | 480791397332 | 9450255094
| 12 | 110 | J175 | J96 | 5 | Narendra Bahadur Singh | Hari Saran Singh | 717507410229 | 8795439054
| 13 | 75 | J190 | J197 | 8 | Narendra Bahadur Singh | Hari Saran Singh | 717507410229 | 7039186311
| 14 | 110 | J43 | J24 | 6 | Vikash Kumar Sharma | Devi Bheek Sharma | 678810489155 | 9580777029
| 15 | 140 | J24 | J17 | 8 | Satya Nam Maurya |  | 411959214332 | 9580777029
| 16 | 75 | J17 | J40 | 5 | Rita Devi | Rajendra Prasad Pandey | 781773515817 | 9433613232
| 17 | 140 | J55 | J24 | 5 | Chhaya tewari | Alok Tiwari | 284490703287 | 9651749605
| 18 | 140 | J55 | J24 | 8 | Vandana Pandey | Pradeep Kumar Tiwari | 487896549662 | 9936369105
| 19 | 140 | J55 | J24 | 6 | Nirmala | Lal Bahadur | 621824495098 | 9580777029
| 20 | 140 | J55 | J56 | 8 | Havaldar | Rampher | 698252997539 | 7081225077
| 21 | 140 | J56 | J67 | 5 | Arvind Kumar | Ram Tahal | 442934412466 | 9918972035
| 22 | 110 | J96 | J90 | 5 | Jagannath Verma | Babulal | 839389525829 | 9580777029
| 23 | 110 | J175 | J96 | 8 | Urmila | Tribhuvan | 534048981799 | 9956927954
| 24 | 110 | J175 | J96 | 6 | Lalmani | Parmeshwar Datt | 527811676571 | 9721050885
| 25 | 110 | J175 | J96 | 8 | Shyama Tiwari | Rakesh Kumar Tiwari | 790549693418 | 9918972035
| 26 | 110 | J175 | J96 | 5 | Shashant Tiwari | Rajendra Prasad Tiwari | 908352949398 | 9415381973
| 27 | 110 | J175 | J96 | 5 | Gokul | Holi Lal | 237900926311 | 9918972035
| 28 | 75 | J190 | J197 | 12 | Ram Avadh | Nohar | 305705441249 | 9918972035
| 29 | 75 | J190 | J197 | 6 | Manoj kumar | Hori Lal | 939633130725 | 9628455731
| 30 | 75 | J190 | J197 | 8 | Sanwari Devi | Shobhnath | 959171990432 | 9918972035
| 31 | 75 | J190 | J197 | 5 | Phoola Devi | Sadhu Ram | 561914434754 | 8795523240
| 32 | 75 | J190 | J197 | 5 | Ram avadh Pal | Dhaniram | 943033018054 | 9113073579
| 33 | 110 | J267 | J175 | 8 | Pream Lal Yadav | Ram Ujagir | 870699946061 | 9450346502
| 34 | 110 | J267 | J175 | 6 | Shailendra Kumar | Kamla Prasad | 878721708122 | 7379236796
| 35 | 110 | J267 | J175 | 8 | Geeta Devi | Shailendra Kumar | 959999871529 | 9839409411
| 36 | 110 | J267 | J175 | 5 | Urmila Devi | Vimal Kumar | 581387185016 | 8858551498
| 37 | 110 | J267 | J175 | 5 | Sury Kali | Ayodhya Prasad | 290402827598 | 9792418912
| 38 | 63 | J206 | J168 | 8 | Bharat Lal Vishwakarma | Bhagi Rathi | 801196891250 | 8849823053
| 39 | 63 | J168 | J178 | 6 | Bhola |  | 247035310201 | 9918240731
| 40 | 63 | J168 | J202 | 8 | Shailesh Patel | Ravishankar | 718383194606 | 9984903119
| 41 | 63 | J202 | J227 | 5 | Sanjay Kumar Yadav | Raja Ram Yadav | 767211461216 | 8423841192
| 42 | 63 | J202 | J233 | 5 | Amrawati Yadav | Brijlal Yadav | 229924826722 | 9517250825
| 43 | 63 | J208 | J183 | 8 | Manoj Yadav | Ram Hit Yadav | 713318280256 | 9454867380
| 44 | 63 | J61A | J61B | 6 | Manoj Kumar | Audhesh Narayan | 334404885956 | 9455131013
| 45 | 63 | J61B | J61C | 8 | Anil Kumar Chaturvedi | Chote Lal Chaturvedi | 218905564180 | 9984903736
| 46 | 63 | J53A | J53B | 5 | Pooja Devi | Chote Lal | 381546009687 | 9555279084
| 47 | 63 | J52A | J52B | 5 | Badri Prasad | Babu lal | 647089443365 | 8320972346
| 48 | 63 | J52B | J52C | 10 | Ramchandra | Rampher | 702605338012 | 9649806822
314

## reconsilation
shukla construction
s.no | description | units | ISSUED QTY | 1079 | 1089 | 1093 | 1100 | 7903 | 7909 | 7912 | 7917 | 7918 | 7922 | 7926 | 7927 | 7928 | 7943 | 7945 | 7946 | 7947 | 7950 | 12357 | 12364 | 12365 | 12377 | 12378 | 12381 | 12388 | 12395 | 12396 | 12397 | total | last billconsumed | this bill consumed |  | balance
1 | G.I PIPE | MTRS | 1 |  |  |  |  | 350 |  |  | 150 |  |  |  |  | 300 | 100 |  | 100 |  | 100 |  |  | 200 |  |  | 100 |  |  | 200 |  | 1600 | 1020 | 247 | 1267 | 333
2 | MDPE PIPE 20MM COIL-500MTRS | MTRS | 5 | 500 | 500 | 1000 | [9 empty] | 500 |  | 500 | 500 |  |  | 500 | 500 |  | 500 | 500 |  |  | 500 |  |  | 6000 | 5928 | 1348 | 7276 | -1276
3 | PPCLamps saddle-63*1/2" | nos | 1 | 100 | 50 | 100 | 200 |  | 100 |  |  |  | 100 |  | 150 |  | 100 | 100 | 100 |  |  | 80 | 60 |  | 80 |  |  | 100 | 50 | 60 |  | 1530 | 1020 | 147 | 1167 | 363
4 | PPCLamps saddle-75*1/2" | nos | [9 empty] | 25 | 25 |  | 25 | [6 empty] | 20 | 15 | [8 empty] | 110 |  | 45 | 45 | 65
5 | PPCLamps saddle-90*1/2" | nos | [20 empty] | 15 | [5 empty] | 10 |  |  | 25 |  | 12 | 12 | 13
6 | PPCLamps saddle-110*1/2" | nos | [20 empty] | 10 |  | 100 | [6 empty] | 110 |  | 35 | 35 | 75
7 | PPCLamps saddle-125*1/2" | nos | [11 empty] | 20 | [17 empty] | 20 |  | 1 | 1 | 19
8 | PPCLamps saddle-140*1/2" | nos | [11 empty] | 11 | [17 empty] | 11 |  | 7 | 7 | 4
9 | PPCLamps saddle-160*1/2" | nos | [29 empty] | 0 |  |  | 0 | 0
10 | PPCLamps saddle-200*1/2" | nos | [29 empty] | 0 |  |  | 0 | 0
11 | pp comp fm theard adapter-20mm*1/2" | nos | 1 | 100 | 50 | 100 | 200 |  | 100 |  |  | 100 | 100 |  | 200 |  | 100 | 100 | 100 |  |  | 100 | 100 |  | 100 | 100 |  | 100 | 40 | 60 |  | 1850 | 1020 | 247 | 1267 | 583
12 | pp comp fm theard elb off taken-20mm*1/2" | nos | 1 | 100 | 50 | 100 | 200 |  | 100 |  |  | 100 | 100 |  | 200 |  | 100 | 100 | 100 |  |  | 100 | 100 |  | 100 |  |  | 100 | 40 | 60 |  | 1750 | 1020 | 247 | 1267 | 483
13 | threaded fcv-1/2"(15nb) | nos | 1 | 100 | 50 | 100 | 200 |  | 100 |  | 7 | 100 | 100 |  | 200 |  | 100 | 100 | 100 |  |  | 100 | 100 |  |  |  |  | 100 | 40 | 60 |  | 1657 | 1020 | 247 | 1267 | 390
14 | GI elbow | nos | 2 |  |  |  | 700 | [7 empty] | 600 |  | 200 |  | 200 |  | 200 |  |  | 400 |  |  | 200 |  |  | 400 |  | 2900 | 2040 | 494 | 2534 | 366
15 | GI socket | nos | 1 |  |  |  | 350 | [7 empty] | 300 |  | 100 |  | 100 |  | 100 |  |  | 200 |  |  | 100 |  |  | 200 |  | 1450 | 1020 | 247 | 1267 | 183
16 | saddle g.i pipe-105mm(clamps) | nos | 2 | [28 empty] | 0 |  |  | 0 | 0
17 | 15mm nipple-0.3mm | nos | 1 |  |  |  | 350 | [7 empty] | 300 |  |  |  | 100 |  | 100 |  |  | 200 |  |  | 100 |  |  | 200 |  | 1350 | 1020 | 247 | 1267 | 83
18 | 15mm nipple-0.5mm | nos | 1 |  |  |  | 350 | [7 empty] | 300 |  |  |  | 100 |  | 100 |  |  | 200 |  |  | 100 |  |  | 200 |  | 1350 | 1020 | 247 | 1267 | 83
19 | bib cock ptmt(taps) | nos | 1 |  |  |  | 350 |  |  |  | 100 |  |  |  |  | 300 | 100 |  |  | 200 | 100 |  |  | 200 |  |  | 100 |  |  |  | 200 | 1650 | 1020 | 247 | 1267 | 383
20 | teflon tape | nos | 1 | [6 empty] | 16 |  |  |  | 50 |  | 100 |  |  |  | 50 |  |  |  | 50 |  | 50 | 35 |  |  |  | 50 | 401 | 350 | 51 | 401 | 0
21 | g.inails | nos | 4
1020

## KANSAPATTI RESTORATION
KANSAPATTI(RESTORATION)
Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | Dia of pipe | Pipe Length (M) AS PER SITE
1 | J74 | J75 | BRICK ROAD | 0.46 | 63 | 2.8
2 | J76 | J76A | BRICK ROAD | 0.46 | 75 | 3.1
3 | J76 | J79 | BRICK ROAD | 0.46 | 75 | 41.9
4 | J84 | J87 | BRICK ROAD | 0.46 | 75 | 2.6
5 | J89A | J89B | INTERLOCKING | 0.46 | 63 | 41
6 | J89B | J103 | INTERLOCKING | 0.46 | 63 | 67.6
7 | J89B | J89C | INTERLOCKING | 0.46 | 63 | 15.9
8 | J89C | J89E | INTERLOCKING | 0.46 | 63 | 13
9 | J89A | J115 | BRICK ROAD | 0.46 | 75 | 21.6
10 | J119 | J119 | BRICK ROAD | 0.46 | 63 | 77.6
11 | J116 | J85 | BRICK ROAD | 0.46 | 63 | 120.2
12 | J57 | J62 | BRICK ROAD | 0.46 | 63 | 50.7
13 | J51 | J48 | INTERLOCKING | 0.46 | 63 | 78.8
14 | J48 | J50 | INTERLOCKING | 0.46 | 63 | 73.1
15 | J48 | J45 | INTERLOCKING | 0.46 | 63 | 2.3
16 | J19 | J33 | BRICK ROAD | 0.46 | 63 | 208
17 | J69 | J70 | INTERLOCKING | 0.46 | 63 | 140.3
18 | J70 | J70B | INTERLOCKING | 0.46 | 63 | 212.5
19 | J99 | J94 | INTERLOCKING | 0.46 | 63 | 21.6
KANSAPATTI restoration
| Sl. No | Road Type | UNITS | WO/DPR Qty's | Qty Executed Up to Date | Qty Executed Billed up to Date | Qty Billed Up to Previous | This Bill(Executed) | Remarks
| 1 | BRICK ROAD | SQM | 495.16 | 243.11 | 243.11 |  | 20% remaining release
| 2 | INTERLOCKING | SQM | 0 | 306.406 | 306.406
| 3 | B.T. ROAD | SQM | 544.64 | 0 | 0
Sub-Contractor Site Engineer (Sr.Eng/ DY.M-SMX ) (Dy.M-PMX ) AGM Project Incharge

## shiva khurd rstoration
Shivpur khurd(RESTORATION)
| Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | Dia of pipe | Pipe Length (M) AS PER SITE
| 1 | J75(A) | J75(B) | BRICK ROAD | 0.363 | 63 | 2.6
| 2 | J6 | J8 | BRICK ROAD | 0.363 | 63 | 33.4
| 3 | J6 | J4 | BRICK ROAD | 0.363 | 63 | 15
| 4 | j76 | j43 | B.T. ROAD | 0.36 | 75 | 3.4
| 5 | J4 | J5 | BRICK ROAD | 0.363 | 63 | 143.1
| 6 | J3 | J4 | BRICK ROAD | 0.363 | 63 | 14.4
| 7 | j17 | j9 | B.T. ROAD | 0.36 | 75 | 3.8
| 8 | J67(A) | J84 | BRICK ROAD | 0.363 | 63 | 84.4
| 9 | J45 | J40 | BRICK ROAD | 0.363 | 63 | 3
| 10 | j45 | j53 | BRICK ROAD | 0.363 | 63 | 7.8
| 11 | j53 | j49 | BRICK ROAD | 0.363 | 63 | 5.8
| 12 | j53 | j58 | BRICK ROAD | 0.363 | 63 | 6.1
| 13 | j9 | j43 | B.T. ROAD | 0.36 | 75 | 3
| 14 | J76 | J75 | B.T. ROAD | 0.36 | 75 | 3.6
| 15 | j58 | j58(1) | BRICK ROAD | 0.363 | 63 | 3.8
| 16 | j58(1) | j64a | BRICK ROAD | 0.363 | 63 | 9.8
| 17 | j64 | j65 | BRICK ROAD | 0.363 | 63 | 11
| 18 | j58 | j60 | BRICK ROAD | 0.363 | 63 | 85.2
| 19 | j35a | j35b | BRICK ROAD | 0.363 | 63 | 1.9
| 20 | j30a | j30 | BRICK ROAD | 0.363 | 63 | 5.6
| 21 | j72 | j74 | BRICK ROAD | 0.363 | 63 | 45.7
| 22 | j68 | j69 | BRICK ROAD | 0.363 | 63 | 37
| 23 | j99 | j99a | BRICK ROAD | 0.363 | 63 | 3.3
| 24 | j99 | j99a | BRICK ROAD | 0.363 | 63 | 6.9
| 25 | j99a | j99b | BRICK ROAD | 0.363 | 63 | 2.2
| 26 | J67(A) | J67 | B.T. ROAD | 0.36 | 63 | 4.2
| 27 | J46 | J61 | B.T. ROAD | 0.36 | 63 | 4.2
| 28 | J40 | J39 | B.T. ROAD | 0.36 | 63 | 3
| 29 | j99(a) | j102 | BRICK ROAD | 0.363 | 63 | 19.1
| 30 | j102 | j106 | BRICK ROAD | 0.363 | 63 | 29.5
| 31 | j106 | j112 | BRICK ROAD | 0.363 | 63 | 88.2
| 32 | j106 | j110 | BRICK ROAD | 0.363 | 63 | 25.4
| 33 | j101 | j115 | BRICK ROAD | 0.363 | 63 | 136.6
| 34 | j97 | j99 | BRICK ROAD | 0.363 | 63 | 3
| 35 | j33 | j29 | BRICK ROAD | 0.363 | 63 | 20.6
| 36 | j33 | j30 | ccroad | 0.363 | 63 | 21
| 37 | j33 | j30 | BRICK ROAD | 0.363 | 63 | 19.8
| 38 | j73a | j73b | B.T. ROAD | 0.36 | 63 | 2.4
| 39 | j70 | j71 | B.T. ROAD | 0.36 | 63 | 3.2
| 40 | j21 | j26 | BRICK ROAD | 0.363 | 63 | 32.2
| 41 | j26 | j30 | BRICK ROAD | 0.363 | 63 | 30.5
| 42 | j26 | j17a | BRICK ROAD | 0.363 | 63 | 11.6
| 43 | j75a | J75 | BRICK ROAD | 0.375 | 75 | 5.1 |  |  | 3.2
3.4
3.8
3
SHIVAPUR KHURD restoration
| Sl. No | Road Type | UNITS | WO/DPR Qty's | Qty Executed Up to Date | Qty Executed Billed up to Date | Qty Billed Up to Previous | This Bill(Executed) | Remarks
| 1 | BRICK ROAD | SQM | 1200 | 341.856 | 341.856 | 341.856 | 20% remaining release
| 2 | INTERLOCKING | SQM | 0
| 3 | B.T. ROAD | SQM | 236.45 | 11.088 | 11.088 | 11.088
Sub-Contractor Site Engineer (Sr.Eng/ DY.M-SMX ) (Dy.M-PMX ) AGM Project Incharge

## malak restoration
Malak(RESTORATION)
| Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | Dia of pipe | Pipe Length (M) AS PER SITE
| 1 | j123 | j71 | brick road | 0.36 | 63 | 65.2
| 2 | j29 | j20 | brick road | 0.36 | 63 | 64.8
| 3 | j20 | j2 | brick road | 0.36 | 63 | 15.1
| 4 | j2 | j24 | brick road | 0.36 | 63 | 59.1
| 5 | j71 | j70 | brick road | 0.36 | 63 | 42.9
| 6 | j70 | j44 | brick road | 0.36 | 63 | 3
| 7 | j70 | j37 | brick road | 0.36 | 63 | 95.1
| 8 | j37 | j19 | brick road | 0.36 | 63 | 2.5
| 9 | j19 | j26 | brick road | 0.36 | 63 | 64.9
| 10 | j61 | j68 | brick road | 0.36 | 63 | 49
| 11 | j82 | j94 | brick road | 0.36 | 63 | 40
| 12 | j32 | j81 | brick road | 0.36 | 63 | 48
| 13 | j95 | j96 | brickroad | 0.36 | 63 | 66.4
| 14 | j96 | j133 | brick road | 0.36 | 63 | 100.1
| 15 | j96 | j82 | brick road | 0.36 | 63 | 49.5
| 16 | j48 | j57 | brick road | 0.36 | 63 | 33.1
| 17 | j57 | j77 | brick road | 0.36 | 63 | 23.7
| 18 | j27 | j11 | interlocking | 0.46 | 63 | 112.7
| 19 | j10 | j5 | brick road | 0.36 | 63 | 37.1
| 20 | j5 | j9 | brick road | 0.36 | 63 | 32
| 21 | j147 | j119 | interlocking | 0.46 | 63 | 23.7
| 22 | j116 | j116a | brick road | 0.36 | 63 | 165
| 23 | j27 | j21 | interlocking | 0.46 | 63 | 3.7
| 24 | j219 | j240 | brick road | 0.36 | 63 | 114.5
| 25 | j223 | j238 | brick road | 0.36 | 63 | 78
| 26 | j238 | j201 | interlocking | 0.46 | 63 | 17
| 27 | j201 | j217 | interlocking | 0.46 | 63 | 54.5
| 28 | j217 | j213 | interlocking | 0.46 | 63 | 96
| 29 | j217 | j220 | interlocking | 0.46 | 63 | 4.7
| 30 | j217 | j220 | brick road | 0.36 | 63 | 49.7
| 31 | j191 | j223 | brick road | 0.36 | 63 | 45.2
| 32 | j223a | j189 | brickroad | 0.36 | 63 | 35.5
| 33 | j227 | j225 | brick road | 0.36 | 63 | 29.8
| 34 | j225 | j224 | brickroad | 0.36 | 63 | 9
| 35 | j225 | j195 | brick road | 0.36 | 63 | 36.2
| 36 | j110 | j141 | interlocking | 0.46 | 63 | 52.6
| 37 | j100 | j163 | brick road | 0.36 | 63 | 69
| 38 | j143 | j149 | brick road | 0.36 | 63 | 26
| 39 | j153 | j160 | brick road | 0.36 | 63 | 8.3
| 40 | j160 | j169 | brick road | 0.36 | 63 | 92
| 41 | j169 | j125 | brick road | 0.36 | 63 | 56.5
| 42 | j169 | j125 | brick road | 0.36 | 63 | 15.8
| 43 | j131 | j135 | brick road | 0.36 | 63 | 27 |  |  |  | 2133.7 | 0.361
| 44 | j172 | j175 | brickroad | 0.36 | 63 | 46.1 |  |  |  |  | 770.2657
| 45 | J131A | J131B | brickroad | 0.36 | 63 | 15.9
| 46 | J125 | J142 | brickroad | 0.36 | 63 | 26.7
| 47 | j37 | j130 | brick road | 0.37 | 75 | 251.4
| 48 | j35 | j91 | interlocking | 0.46 | 90 | 232
| 49 | j86 | j104 | brick road | 0.39 | 90 | 44.6
MALAK restoration
|  | Sl. No | Road Type | UNITS | WO/DPR Qty's | Qty Executed Up to Date | Qty Executed Billed up to Date | Qty Billed Up to Previous | This Bill(Executed) | Remarks
|  | 1 | brick road | SQM | 1036.7 | 770.2657 | 770.2657 | 770.2657 | 20% remaining release
|  | 2 | interlocking | SQM | 0 | 274.574 | 274.574 | 274.574
|  | 3 | B.T. ROAD | SQM | 1404.9 | 0 | 0 | 0
Sub-Contractor Site Engineer (Sr.Eng/ DY.M-SMX ) (Dy.M-PMX ) AGM Project Incharge

## BHAIDPUR RoadDis. & Restoration
GOVERNMENT OF UTTAR PRADESH
STATE WATER & SANITATION MISSION ( SWSM )
Joint Measurement Report of JMR - Road Dismantling & Restoration
Name of the Work :- Survey , Design Preparation of DPR , Construction , Commissioning and O&M for 10 Years of Various Rural Water Supply Projects in the state of Uttar Pradesh as Per Request for Proposal for Division " Prayagraj "
Name of the Agency : POWER MECH PROJECTS LIMITED – BHOORATHNOM CONSTRUCTIONS COMPANY PRIVATE LIMITED (JV), Hyderabad.
Name OF Scheme |  | : BHAIDPUR
Block |  | : MANGRAURA
Total Scope |  | :
JMR No. |  | : 1
Date of JMR |  | :
Sr. No. | Start Node | End Node | Dia | Type OF Road | Dismantling Length | Dismantling Width | Dismantling Quantity | Restoration Length | Restoration Width | Restoration Quantity | Restoration Status | Remark
1 | J11 | J27 | 63 | INTERLOCKING | 73.1 | 0.46 | 33.626 | 73.1 | 0.46 | 33.626 | DONE
2 | J11 | J27 | 63 | INTERLOCKING | 3.2 | 0.46 | 1.472 | 3.2 | 0.46 | 1.472 | DONE
3 | J27 | J49 | 63 | INTERLOCKING | 43.2 | 0.46 | 19.872 | 43.2 | 0.46 | 19.872 | DONE
4 | J27 | J36 | 63 | INTERLOCKING | 140.9 | 0.46 | 64.814 | 140.9 | 0.46 | 64.814 | DONE
5 | J34 | J36 | 63 | BRICK ROAD | 1.8 | 0.363 | 0.6534 | 1.8 | 0.363 | 0.6534 | DONE
6 | J36 | J47 | 63 | BRICK ROAD | 60.1 | 0.363 | 21.8163 | 60.1 | 0.363 | 21.8163 | DONE
7 | J47 | J52 | 63 | BRICK ROAD | 33.4 | 0.363 | 12.1242 | 33.4 | 0.363 | 12.1242 | DONE
8 | J52 | J63 | 63 | BRICK ROAD | 7.4 | 0.363 | 2.6862 | 7.4 | 0.363 | 2.6862 | DONE
9 | J52 | J53 | 63 | BRICK ROAD | 2.4 | 0.363 | 0.8712 | 2.4 | 0.363 | 0.8712 | DONE
10 | J47 | J42 | 63 | BRICK ROAD | 100.6 | 0.363 | 36.5178 | 100.6 | 0.363 | 36.5178 | DONE
11 | J42 | J49 | 63 | BRICK ROAD | 58.7 | 0.363 | 21.3081 | 58.7 | 0.363 | 21.3081 | DONE
12 | J69 | J75 | 63 | INTERLOCKING | 47.8 | 0.46 | 21.988 | 47.8 | 0.46 | 21.988 | DONE
13 | J75 | J80 | 63 | BRICK ROAD | 20.7 | 0.363 | 7.5141 | 20.7 | 0.363 | 7.5141 | DONE
14 | J75 | J80 | 63 | INTERLOCKING | 40.1 | 0.46 | 18.446 | 40.1 | 0.46 | 18.446 | DONE
15 | J82 | J84 | 63 | BRICK ROAD | 63.5 | 0.363 | 23.0505 | 63.5 | 0.363 | 23.0505 | DONE
16 | J69 | J71 | 63 | INTERLOCKING | 20.1 | 0.46 | 9.246 | 20.1 | 0.46 | 9.246 | DONE
17 | J71 | J72 | 63 | BRICK ROAD | 13.4 | 0.363 | 4.8642 | 13.4 | 0.363 | 4.8642 | DONE
18 | J71 | J71A | 63 | INTERLOCKING | 146.1 | 0.46 | 67.206 | 146.1 | 0.46 | 67.206 | DONE
19 | J71A | J73 | 63 | BRICK ROAD | 22.2 | 0.363 | 8.0586 | 22.2 | 0.363 | 8.0586 | DONE
20 | J73 | J70 | 63 | BRICK ROAD | 31.2 | 0.363 | 11.3256 | 31.2 | 0.363 | 11.3256 | DONE
21 | J70 | J65 | 63 | BRICK ROAD | 74.8 | 0.363 | 27.1524 | 74.8 | 0.363 | 27.1524 | DONE
22 | J129A | J129 | 75 | C.C. | 157.7 | 0.375 | 59.1375 | 157.7 | 0.375 | 59.1375 | DONE
23 | J132 | J136 | 63 | C.C. | 95.5 | 0.363 | 34.6665 | 95.5 | 0.363 | 34.6665 | DONE
24 | J136 | 142A | 63 | C.C. | 25.7 | 0.363 | 9.3291 | 25.7 | 0.363 | 9.3291 | DONE
25 | J142A | J142 | 63 | C.C. | 74.1 | 0.363 | 26.8983 | 74.1 | 0.363 | 26.8983 | DONE
26 | J142A | J142 | 63 | INTERLOCKING | 75.1 | 0.46 | 34.546 | 75.1 | 0.46 | 34.546 | DONE
27 | J146 | J142 | 63 | INTERLOCKING | 43.7 | 0.46 | 20.102 | 43.7 | 0.46 | 20.102 | DONE
28 | J149 | J151 | 63 | BRICK ROAD | 36.8 | 0.363 | 13.3584 | 36.8 | 0.363 | 13.3584 | DONE
29 | J94 | J129A | 75 | C.C. | 3.8 | 0.375 | 1.425 | 3.8 | 0.375 | 1.425 | DONE
30 | J126 | J120 | 63 | BRICK ROAD | 397.3 | 0.363 | 144.2199 | 397.3 | 0.363 | 144.2199 | DONE
31 | J120 | J121 | 63 | BRICK ROAD | 20.3 | 0.363 | 7.3689 | 20.3 | 0.363 | 7.3689 | DONE
32 | J121 | J122 | 63 | BRICK ROAD | 174.9 | 0.363 | 63.4887 | 174.9 | 0.363 | 63.4887 | DONE
33 | J109 | J100 | 63 | C.C. | 78.4 | 0.363 | 28.4592 | 78.4 | 0.363 | 28.4592 | DONE
34 | J99 | J102A | 63 | C.C. | 115.4 | 0.363 | 41.8902 | 115.4 | 0.363 | 41.8902 | DONE
35 | J102A | J102 | 63 | C.C. | 54.8 | 0.363 | 19.8924 | 54.8 | 0.363 | 19.8924 | DONE
36 | J17 | J21A | 63 | BRICK ROAD | 122.5 | 0.363 | 44.4675 | 122.5 | 0.363 | 44.4675 | DONE
37 | J21B | J22 | 63 | BRICK ROAD | 24.9 | 0.363 | 9.0387 | 24.9 | 0.363 | 9.0387 | DONE
38 | J1 | J8 | 160 | BRICK ROAD | 102.8 | 0.46 | 47.288 | 102.8 | 0.46 | 47.288 | DONE
39 | J8 | J10 | 160 | BRICK ROAD | 143.1 | 0.46 | 65.826 | 143.1 | 0.46 | 65.826 | DONE
40 | J94 | J129A | 75 | C.C. | 164.9 | 0.375 | 61.8375 | 164.9 | 0.375 | 61.8375 | DONE
41 | J92 | J99 | 90 | C.C. | 43.1 | 0.39 | 16.809 | 43.1 | 0.39 | 16.809 | DONE
Total |  |  |  |  | 2959.5 |  | 1164.6614 | 2959.5 |  | 1164.6614
|  |  | Sl. No | Road Type | UNITS | WO/DPR Qty's | Qty Executed Up to Date | Qty Executed Billed up to Date | Qty Billed Up to Previous | This Bill(Executed) | Remarks
|  |  | 1 | BRICK ROAD | SQM | 360.46 | 572.99 | 572.99 | 572.99 | 20% remaining release
|  |  | 2 | INTERLOCKING | SQM | 0 | 291.318 | 291.318 | 291.318
|  |  | 3 | c.c road | SQM | 671.8 | 300.344 | 300.344 | 300.344
Sub-Contractor Site Engineer (Sr.Eng/ DY.M-SMX ) (Dy.M-PMX ) AGM Project Incharge

## persanda RESTORATION
persanda (RESTORATION)
| Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | Dia of pipe | Pipe Length (M) AS PER SITE |  |  |  | SQM
| 1 | j52 | j53 | B.T ROAD | 0.363 | 63 | 3 | 575.9J4:K28 | 1.063 |  | 1.089
| 2 | j30 | j31 | BRICK ROAD | 0.363 | 63 | 53.6 | 650.4 | 1.063 |  | 19.4568
| 3 | J29A | J29 | BRICK ROAD | 0.363 | 63 | 22.3 | 700.9 | 1.063 |  | 8.0949
| 4 | J30 | J29A | BRICK ROAD | 0.363 | 63 | 30.3 | 775.1 | 1.063 |  | 10.9989
| 5 | J29A | J29B | BRICK ROAD | 0.363 | 63 | 2.8 | 777.9 | 1.063 |  | 1.0164
| 6 | J29 | J23 | BRICK ROAD | 0.363 | 63 | 2.6 | 814.9 | 1.063 |  | 0.9438
| 7 | J13 | J19 | B.T ROAD | 0.363 | 63 | 7.3 | 1226.1 | 1.063 |  | 2.6499
| 8 | J32 | J30 | BRICK ROAD | 0.363 | 63 | 62.7 | 1692.3 | 1.063 |  | 22.7601
| 9 | J87 | J90A | BRICK ROAD | 0.39 | 90 | 78.9 | 1771.2 | 1.09 |  | 30.771
| 10 | J11 | J12 | B.T ROAD | 0.375 | 75 | 4.5 | 1838.9 | 1.075 |  | 1.6875
| 11 | J78 | J77 | BRICK ROAD | 0.363 | 63 | 3.5 | 1982.9 | 1.063 |  | 1.2705
| 12 | J92 | J92A | BRICK ROAD | 0.363 | 63 | 10.1 | 2769.3 | 1.063 |  | 3.6663
| 13 | J92 | J92B | BRICK ROAD | 0.363 | 63 | 38.1 | 2807.4 | 1.063 |  | 13.8303
| 14 | J69 | J72 | INTERLOCKING | 0.363 | 63 | 67.8 | 3261 | 1.063 |  | 24.6114
| 15 | J90A | J90 | BRICK ROAD | 0.375 | 75 | 55.6 | 3521.7 | 1.075 |  | 20.85
| 16 | J70 | J67 | C.C. | 0.39 | 90 | 200.1 | 4036.6 | 1.09 |  | 78.039
| 17 | J70 | J67 | BRICK ROAD | 0.39 | 90 | 41.8 | 4078.4 | 1.09 |  | 16.302
| 18 | J68 | J69 | B.T ROAD | 0.39 | 90 | 5.3 | 4300.8 | 1.09 |  | 2.067
| 19 | J37 | J35 | B.T ROAD | 0.41 | 110 | 4.3 | 4305.1 | 1.11 |  | 1.763
| 20 | J37 | J38 | B.T ROAD | 0.41 | 110 | 6.3 | 4339.1 | 1.11 |  | 2.583
| 21 | J20 | J13 | B.T ROAD | 0.425 | 125 | 6 | 5003.1 | 1.125 |  | 2.55
| 22 | J11 | J5 | BRICK ROAD | 0.425 | 125 | 45.9 | 5155.9 | 1.125 |  | 19.5075
| 23 | J82 | J85 | INTERLOCKING | 0.46 | 160 | 487.1 | 5913.7 | 1.16 |  | 224.066
| 24 | J82 | J85 | B.T ROAD | 0.46 | 160 | 6 | 5919.7 | 1.16 |  | 2.76
| 25 | J85 | J87 | B.T ROAD | 0.46 | 160 | 86.3 | 6006 | 1.16 |  | 39.698
| 26 | J85 | J87 | BRICK ROAD | 0.46 | 160 | 2.8 | 6008.8 | 1.16 |  | 1.288
| 27 | J67 | J26 | BRICK ROAD | 0.46 | 200 | 186.2 | 6208.8 | 1.2 |  | 85.652
| 28 | J26 | J27 | BRICK ROAD | 0.46 | 200 | 38.4 | 6247.2 | 1.2 |  | 17.664
| 29 | J17 | J14 | BRICK ROAD | 0.46 | 200 | 12.8 | 6260 | 1.2 |  | 5.888
| 30 | J14 | J78 | BRICK ROAD | 0.46 | 160 | 156.1 | 6416.1 | 1.16 |  | 71.806
| 31 | J68 | J82 | BT.ROAD | 0.46 | 160 | 5.4 | 6421.5 | 1.16 |  | 2.484
| 32 | J68 | J82 | BT.ROAD | 0.46 | 160 | 5.9 | 6427.4 | 1.16 |  | 2.714
| 33 | J68 | J82 | INTERLOCKING | 0.46 | 160 | 179.1 | 7040.6 | 1.16 |  | 82.386
| 34 | J3 | J78 | INTERLOCKING | 0.46 | 200 | 24.9 | 7065.5 | 1.2 |  | 11.454
| 35 | J3 | J78 | BRICK ROAD | 0.46 | 200 | 18.4 | 7083.9 | 1.2 |  | 8.464
PERSANDA restoration
|  | Sl. No | Road Type | UNITS | WO/DPR Qty's | Qty Executed Up to Date | Qty Executed Billed up to Date | Qty Billed Up to Previous | This Bill(Executed) | Remarks | Qty Billed Up to Previous | This Bill(Executed) | Remarks
|  | 1 | BRICK ROAD | SQM | 2176.5 | 360.23 | 360.23 |  |  |  | 360.23 | 20% remaining release
|  | 2 | INTERLOCKING | SQM | 0 | 342.51 | 342.51 |  |  |  | 342.51
|  | 3 | B.T. ROAD | SQM | 112.21 | 56.8474 | 56.8474 |  |  |  | 56.8474
|  | 4 | C.C ROAD | SQM | 0 | 78.039 | 78.039 |  |  |  | 78.039
Sub-Contractor Site Engineer (Sr.Eng/ DY.M-SMX ) (Dy.M-PMX ) AGM Project Incharge

## PUREMANIKANTA-1
PUREMANIKANTH(RESTORATION)
| Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | Dia of pipe | Pipe Length (M) AS PER SITE
| 1 | J41 | J54 | BRICK ROAD | 0.36 | 63 | 23.6
| 2 | J46 | J41 | BRICK ROAD | 0.36 | 63 | 101.5
| 3 | J41 | J80 | BRICK ROAD | 0.36 | 63 | 92.4
| 4 | J29D | J18 | INTERLOCKING | 0.46 | 63 | 14.1
| 5 | J29D | J70 | INTERLOCKING | 0.46 | 63 | 115.8
| 6 | J70 | J78 | BRICK ROAD | 0.36 | 63 | 42.1
| 7 | J70 | J76 | INTERLOCKING | 0.46 | 63 | 220.1
| 8 | J87 | J106 | BRICK ROAD | 0.36 | 63 | 9.7
| 9 | J87 | J138 | BRICK ROAD | 0.36 | 63 | 60.3
| 10 | J95 | J111 | C.C. ROAD | 0.36 | 63 | 102
| 11 | J95 | J98 | C.C. ROAD | 0.36 | 63 | 34.8
| 12 | J98 | J86 | BRICK ROAD | 0.36 | 63 | 44.5
| 13 | J98 | J87 | C.C. ROAD | 0.36 | 63 | 19.6
| 14 | J98 | J87 | BRICK ROAD | 0.36 | 63 | 22.3
| 15 | J106 | J97 | BRICK ROAD | 0.36 | 63 | 80.2
| 16 | J97 | J132 | C.C. ROAD | 0.36 | 63 | 92
| 17 | J132 | J143 | C.C. ROAD | 0.36 | 63 | 28.1
| 18 | J74A | J8 | BRICK ROAD | 0.36 | 125 | 35.1
| 19 | J28 | J25 | BRICK ROAD | 0.36 | 63 | 66.3
| 20 | J17 | J17A | BRICK ROAD | 0.36 | 63 | 22.3
| 21 | J17A | J116 | BRICK ROAD | 0.36 | 63 | 7.5
| 22 | J9 | J63 | BRICK ROAD | 0.36 | 63 | 26.1
| 23 | J115 | J104 | INTERLOCKING | 0.46 | 63 | 158.3
| 24 | J122 | J125 | BRICK ROAD | 0.36 | 63 | 180.1
| 25 | J63 | J79 | INTERLOCKING | 0.46 | 90 | 4.6
| 26 | J141 | J140 | BRICK ROAD | 0.36 | 63 | 10.1
| 27 | J141 | J140 | BRICK ROAD | 0.36 | 63 | 17.6
| 28 | J140 | J136 | BRICK ROAD | 0.36 | 63 | 4.1
| 29 | J134 | J128 | INTERLOCKING | 0.46 | 63 | 213.1
| 30 | J128 | J114 | BRICK ROAD | 0.36 | 63 | 5.6
| 31 | J79 | J79A | INTERLOCKING | 0.46 | 63 | 59.2
| 32 | J79A | J79B | INTERLOCKING | 0.46 | 63 | 2.8
| 33 | J79A | J49 | INTERLOCKING | 0.46 | 63 | 134.4
| 34 | J49 | J23 | BRICK ROAD | 0.36 | 63 | 53.1
| 35 | J49 | J24 | BRICK ROAD | 0.36 | 63 | 46.1
| 36 | J49 | J30 | INTERLOCKING | 0.46 | 63 | 16.1
| 37 | J30 | J55 | BRICK ROAD | 0.36 | 63 | 40
| 38 | J30 | J42 | INTERLOCKING | 0.46 | 63 | 25.6
| 39 | J42 | J61 | BRICK ROAD | 0.36 | 63 | 41.4
| 40 | J42 | J39 | INTERLOCKING | 0.46 | 63 | 43.3
| 41 | J39 | J50 | INTERLOCKING | 0.46 | 63 | 19.1
| 42 | J50 | J36 | INTERLOCKING | 0.46 | 75 | 31.9
| 43 | J36 | J73 | INTERLOCKING | 0.46 | 90 | 10.1
| 44 | J36 | J73 | BRICK ROAD | 0.36 | 90 | 8.4
| 45 | J56C | J56D | BRICK ROAD | 0.36 | 63 | 20.1
| 46 | J56D | J56 | BRICK ROAD | 0.36 | 125 | 24.2
| 47 | J56 | J5 | BRICK ROAD | 0.36 | 140 | 38.1
| 48 | J5 | J10 | BRICK ROAD | 0.36 | 63 | 18
| 49 | J5 | J5A | BRICK ROAD | 0.36 | 140 | 24.6
| 50 | J5A | J5B | BRICK ROAD | 0.36 | 63 | 2.1
| 51 | J5A | J2 | BRICK ROAD | 0.36 | 140 | 10
| 52 | 118 | 149 | BRICK ROAD | 0.36 | 63 | 180.2
| 53 | 118 | 112 | BRICK ROAD | 0.36 | 63 | 50.2
| 54 | 131 | 131A | INTERLOCKING | 0.46 | 63 | 96.2
| 1 | J72 | J60 | B.T. ROAD | 0.36 | 63 | 19
| 2 | J45 | J29 | B.T. ROAD | 0.36 | 63 | 100.1
| 3 | J70 | J76 | B.T. ROAD | 0.36 | 63 | 3.8
| 4 | J76 | J96 | B.T. ROAD | 0.36 | 75 | 99.1
| 5 | J29D | J29E | INTERLOCKING | 0.46 | 63 | 2.8
| 6 | J76 | J75 | B.T. ROAD | 0.36 | 90 | 178.5
| 7 | J74A | J74B | BRICK ROAD | 0.36 | 63 | 2.6
| 8 | J75 | J63 | B.T. ROAD | 0.36 | 90 | 101.1
| 9 | J75 | J63 | B.T. ROAD | 0.36 | 90 | 4
| 10 | J56D | J74 | BRICK ROAD | 0.36 | 125 | 13.8
| 11 | J96 | J106 | B.T. ROAD | 0.36 | 63 | 407.1
| 12 | J106 | J87 | B.T. ROAD | 0.36 | 63 | 39.4
| 13 | J80 | J72 | BRICK ROAD | 0.36 | 63 | 6.2
| 14 | J72 | J64 | INTERLOCKING | 0.46 | 63 | 5.2
| 15 | J106 | J97 | B.T. ROAD | 0.36 | 63 | 156.5
| 16 | J97 | J132 | B.T. ROAD | 0.36 | 63 | 22.8
| 17 | J132 | J143 | B.T. ROAD | 0.36 | 63 | 21.1
| 18 | J72 | J64 | BRICK ROAD | 0.36 | 63 | 6.2
| 19 | J29C | J29D | INTERLOCKING | 0.46 | 63 | 5.9
| 20 | J140 | J136 | BRICK ROAD | 0.36 | 63 | 2.7
| 21 | J25 | J13 | B.T. ROAD | 0.36 | 63 | 83.8
| 22 | J25 | J22 | B.T. ROAD | 0.36 | 63 | 12.3
| 23 | J22 | J34 | B.T. ROAD | 0.36 | 63 | 103.9
| 24 | J22 | J17 | B.T. ROAD | 0.36 | 63 | 33.5
| 25 | J17 | J57 | B.T. ROAD | 0.36 | 63 | 55.6
| 26 | J140 | J134 | BRICK ROAD | 0.36 | 63 | 20.8
| 27 | J134 | J135 | BRICK ROAD | 0.36 | 63 | 2.8
| 28 | J74 | J82 | BRICK ROAD | 0.36 | 63 | 1.5
| 29 | J96 | J115 | B.T. ROAD | 0.36 | 75 | 135.7
| 30 | J115 | J122 | B.T. ROAD | 0.36 | 63 | 96.6
| 31 | J122 | J125 | B.T. ROAD | 0.36 | 63 | 4.8
| 32 | J122 | J132 | B.T. ROAD | 0.36 | 63 | 56.1
| 33 | J74 | J74A | BRICK ROAD | 0.36 | 125 | 9.8
| 34 | J96 | J115 | B.T. ROAD | 0.36 | 90 | 5.8
| 35 | J115 | J122 | B.T. ROAD | 0.36 | 140 | 3.3
| 36 | J122 | J125 | B.T. ROAD | 0.36 | 63 | 151.2
| 37 | J122 | J132 | B.T. ROAD | 0.36 | 63 | 52
| 38 | J154 | 85 | INTERLOCKING | 0.46 | 63 | 14.3
| 39 | 85 | 94 | INTERLOCKING | 0.46 | 63 | 29
| 40 | 85 | 84 | INTERLOCKING | 0.46 | 63 | 98.2
PUREMANIKANTA restoration
| Sl. No | Road Type | UNITS | WO/DPR Qty's | Qty Executed Up to Date | Qty Executed Billed up to Date | Qty Billed Up to Previous | This Bill(Executed) | Remarks
| 1 | BRICK ROAD | SQM | 1478.5 | 530.748 | 530.748 | 530.748 | 20% remaining release
| 2 | INTERLOCKING | SQM | 0 | 607.246 | 607.246 | 607.246
| 3 | B.T. ROAD | SQM |  |  | 700.956 | 700.956
| 4 | C.C ROAD | SQM |  | 99.54 | 99.54 | 99.54
Sub-Contractor Site Engineer (Sr.Eng/ DY.M-SMX ) (Dy.M-PMX ) AGM Project Incharge

## LAULI RESTORATION
Lauli Pokhtakham(RESTORATION)
| Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | Dia of pipe | Pipe Length (M) AS PER SITE
| 1 | J296 | J296A | BRICK ROAD | 0.36 | 63 | 300
| 2 | J116A | J97 | INTERLOCKING | 0.46 | 63 | 57.1
| 3 | J97 | J71 | INTERLOCKING | 0.46 | 63 | 32.7
| 4 | J97 | J87 | INTERLOCKING | 0.46 | 63 | 40.8
| 5 | J87 | J89 | BRICK ROAD | 0.36 | 63 | 5.7
| 6 | J87 | J136A | BRICK ROAD | 0.36 | 63 | 30.1
| 7 | J136A | J85 | BRICK ROAD | 0.36 | 63 | 5
| 8 | J127 | J119 | BRICK ROAD | 0.36 | 63 | 247
| 9 | J126 | J118 | BRICK ROAD | 0.36 | 63 | 287.5
| 10 | J147 | J143A | BRICK ROAD | 0.36 | 63 | 10.8
| 11 | J143A | J143B | BRICK ROAD | 0.36 | 63 | 24
| 12 | J253 | J166 | BRICK ROAD | 0.36 | 63 | 435.5
| 13 | J265 | J157 | INTERLOCKING | 0.46 | 63 | 101.8
| 14 | J265 | J157 | BRICK ROAD | 0.36 | 63 | 40
| 15 | J289 | J295 | BRICK ROAD | 0.36 | 63 | 151.9
| 16 | J293 | J196 | BRICK ROAD | 0.36 | 63 | 223.1
| 17 | J196 | J152A | BRICK ROAD | 0.36 | 63 | 125.3
| 18 | J152A | J152 | BRICK ROAD | 0.36 | 63 | 9.7
| 19 | J196 | J187 | BRICK ROAD | 0.36 | 63 | 128.5
| 20 | J196 | J187 | BRICK ROAD | 0.36 | 63 | 62.5
| 21 | J261 | J271 | BRICK ROAD | 0.36 | 63 | 6.2
| 22 | J175 | J96 | BRICK ROAD | 0.36 | 110 | 30
| 23 | J295 | J170 | BRICK ROAD | 0.36 | 63 | 2.7
| 24 | J196 | J187 | BRICK ROAD | 0.36 | 63 | 2.3
| 25 | J289 | J295 | BRICK ROAD | 0.36 | 63 | 152.1
| 26 | J152A | J152 | BRICK ROAD | 0.36 | 63 | 9.8
| 27 | J196 | J187 | BRICK ROAD | 0.36 | 63 | 128.9
| 28 | J247 | J251 | BRICK ROAD | 0.36 | 63 | 52.9
| 29 | J262 | J273 | BRICK ROAD | 0.36 | 63 | 2.6
| 30 | J166 | J199 | BRICK ROAD | 0.36 | 63 | 131.2
| 31 | J199 | J201 | BRICK ROAD | 0.36 | 63 | 29.1
| 32 | J201 | J222A | BRICK ROAD | 0.36 | 63 | 62.7
| 33 | J222A | J222 | BRICK ROAD | 0.36 | 63 | 22.1
| 34 | J222 | J203 | BRICK ROAD | 0.36 | 63 | 47.2
| 35 | J222 | J186 | BRICK ROAD | 0.36 | 63 | 74.6
| 36 | J186 | J193 | BRICK ROAD | 0.36 | 63 | 7.8
| 37 | J193 | J210 | BRICK ROAD | 0.36 | 63 | 45.1
| 38 | J236 | J238 | BRICK ROAD | 0.36 | 63 | 2.6
| 39 | J240 | J257 | BRICK ROAD | 0.36 | 63 | 2.7
| 40 | J240 | J257 | BRICK ROAD | 0.36 | 63 | 6.4
| 41 | J224 | J224A | BRICK ROAD | 0.36 | 63 | 2.7
| 42 | J174 | J218 | INTERLOCKING | 0.46 | 63 | 24.8
| 43 | J218 | J195 | INTERLOCKING | 0.46 | 63 | 3
| 44 | J218 | J195 | BRICK ROAD | 0.36 | 63 | 2.8
| 45 | J18 | J6 | BRICK ROAD | 0.36 | 63 | 14
| 46 | J19 | J31 | BRICK ROAD | 0.36 | 63 | 32.8
| 47 | J11 | J15 | BRICK ROAD | 0.36 | 63 | 19.7
| 48 | J19 | J21 | BRICK ROAD | 0.36 | 63 | 3.8
| 49 | J5 | J70 | BRICK ROAD | 0.36 | 63 | 74.1
| 50 | J70(1) | J65(1) | BRICK ROAD | 0.36 | 63 | 2.5
| 51 | J49 | J55 | INTERLOCKING | 0.46 | 63 | 7.9
| 52 | J49 | J55 | BRICK ROAD | 0.36 | 63 | 11.2
| 53 | J49 | J55 | BRICK ROAD | 0.36 | 63 | 10.1
| 54 | J55 | J24 | INTERLOCKING | 0.46 | 140 | 4.2
| 55 | J56 | J50 | BRICK ROAD | 0.36 | 63 | 22.7
| 56 | J96 | J88 | BRICK ROAD | 0.36 | 63 | 109
| 57 | J88 | J94 | BRICK ROAD | 0.36 | 63 | 6.5
| 58 | J208 | J225 | BRICK ROAD | 0.36 | 63 | 6.1
| 59 | J180 | J186 | BRICK ROAD | 0.36 | 63 | 21.9 |  |  | 3454.4 | 0.36
| 60 | J180 | J186 | BRICK ROAD | 0.36 | 63 | 8.6 |  |  |  | 1243.584
| 61 | J206 | J168 | BRICK ROAD | 0.36 | 63 | 40.8
| 62 | J206 | J168 | BRICK ROAD | 0.36 | 63 | 82.2
| 63 | J293 | J296 | B.T. ROAD | 0.36 | 63 | 9
| 64 | J296A | J296B | BRICK ROAD | 0.36 | 63 | 10.8
| 65 | J100 | J108 | B.T. ROAD | 0.36 | 63 | 3.2
| 66 | J100 | J108 | B.T. ROAD | 0.36 | 63 | 3.2
| 67 | J197 | J222A | B.T. ROAD | 0.36 | 63 | 2.2
| 68 | J152A | J152B | BRICK ROAD | 0.36 | 63 | 3
| 69 | J97 | J71 | BRICK ROAD | 0.36 | 63 | 57
| 70 | J39A | J39B | BRICK ROAD | 0.36 | 63 | 2.8
| 71 | J46 | J18 | B.T. ROAD | 0.36 | 63 | 2.5
| 72 | J19 | J31 | B.T. ROAD | 0.36 | 63 | 3.6
| 73 | J21 | J25 | B.T. ROAD | 0.36 | 63 | 3.6
| 74 | J33 | J20 | B.T. ROAD | 0.36 | 63 | 2.4
| 75 | J180 | J169 | BRICK ROAD | 0.36 | 63 | 2.4
| 76 | J46 | J18 | BRICK ROAD | 0.36 | 63 | 1.3
| 77 | J56 | J50 | B.T. ROAD | 0.36 | 63 | 3.5
| 78 | J67 | J50 | B.T. ROAD | 0.36 | 63 | 3
LAULI restoration
| Sl. No | Road Type | UNITS | WO/DPR Qty's | Qty Executed Up to Date | Qty Executed Billed up to Date | Qty Billed Up to Previous | This Bill(Executed) | Remarks
| 1 | BRICK ROAD | SQM | 900.72 | 1243.584 | 1243.584 | 1243.584 | 20% remaining release
| 2 | INTERLOCKING | SQM | 0 | 125.258 | 125.258 | 125.258
| 3 | B.T. ROAD | SQM | 2183.8 | 13.032 | 13.032 | 13.032
Sub-Contractor Site Engineer (Sr.Eng/ DY.M-SMX ) (Dy.M-PMX ) AGM Project Incharge

## malak
HYDRO TEST/ GAP CLOSING/ FHTC STRETCH/VALVE FITTING/COMMISIONING ACKNOWLEDGEMENT
Contractor Name;shukla construction
Block:mangraura |  |  | GP;malak
Billing Month -aug |  |  | RAB No:
Approved for RAB Quantities : (Tick Whichever is Proposing)
Hydrotest
GAP Closing
| FHTC Stretch |  |  |  | √
Valve Fitting
Commisioning
S. No. | Pipe Dia | Scope Qty | Upto date Laying Quantity | This Bill Quantity for Above Tic Marked Item | Cumm upto This Bill Quantity of Above Tic Marked Item | Remarks
1 | 63 |  |  | 14319.7
2 | 75 |  |  | 811.8
3 | 90 |  |  | 999.9
4 | 110 |  |  | 480
5 | 125 |  |  | 537.1
6 | 140 |  |  | 564.3
7 | 160 |  |  | 42.7
8 | 180
9 | 200
NOTE;out of 562-234 connections done by contractor and balance connections are not ready to take connections NOTE;And pradhan aslo not given letter to the contractor
Sub-Contractor Site Engineer Block-incharge AGM PMX Incharge Project Incharge

## shivapur khurd
HYD+A1:H15RO TEST/ GAP CLOSING/ FHTC STRETCH/VALVE FITTING/COMMISIONING ACKNOWLEDGEMENT
Contractor Name;shukla construction
Block:mangraura |  |  | GP;shivapur khurd
Billing Month -aug |  |  | RAB No:
Approved for RAB Quantities : (Tick Whichever is Proposing)
Hydrotest
GAP Closing
| FHTC Stretch |  |  |  | √
Valve Fitting
Commisioning
S. No. | Pipe Dia | Scope Qty | Upto date Laying Quantity | This Bill Quantity for Above Tic Marked Item | Cumm upto This Bill Quantity of Above Tic Marked Item | Remarks
1 | 63 |  |  | 6020.7
2 | 75 |  |  | 2885.3
3 | 90 |  |  | 13.1
4 | 110 |  |  | 84.5
5 | 125 |  |  | 29.6
6 | 140
7 | 160
8 | 180
9 | 200
Note: out of 272-168 connections are done by contractor and balance are not ready to take connections NOTE:And pradhan aslo not given letter to the contractor
Sub-Contractor Site Engineer Block-incharge AGM PMX Incharge Project Incharge

## lauli
HYD+A1:H15RO TEST/ GAP CLOSING/ FHTC STRETCH/VALVE FITTING/COMMISIONING ACKNOWLEDGEMENT
Contractor Name;shukla construction
Block:mangraura |  |  | GP;lauli phokatkam
Billing Month -aug |  |  | RAB No:
Approved for RAB Quantities : (Tick Whichever is Proposing)
Hydrotest
GAP Closing
| FHTC Stretch |  |  |  | √
Valve Fitting
Commisioning
S. No. | Pipe Dia | Scope Qty | Upto date Laying Quantity | This Bill Quantity for Above Tic Marked Item | Cumm upto This Bill Quantity of Above Tic Marked Item | Remarks
1 | 63 |  |  | 21389.9
2 | 75 |  |  | 197.2
3 | 90 |  |  | 1055
4 | 110 |  |  | 611.7
5 | 125
6 | 140 |  |  | 367.1
7 | 160
8 | 180
9 | 200
Note: out of 619-196 connections are done by contractor and balance are not ready to take connections NOTE;And pradhan aslo not given letter to the contractor
Sub-Contractor Site Engineer Block-incharge AGM PMX Incharge Project Incharge

## BHAIDPUR HYDRO
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | bhaidpur | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | J12 | J10 | 160 | 129.1 | 5.5 | 3.3 | 1 | 4.3 | NO
2 | J12 | J10 | 160 | 4 | 5.5 | 3.3 | 1 | 4.3 | NO
3 | J10 | J11 | 160 | 122.1 | 5.5 | 3.3 | 1 | 4.3 | NO
4 | J10 | J11 | 160 | 3 | 5.5 | 3.3 | 1 | 4.3 | NO
5 | J60 | J91 | 140 | 377.4 | 5.5 | 3.3 | 1 | 4.3 | NO
6 | J60 | J91 | 140 | 5.6 | 5.5 | 3.3 | 1 | 4.3 | NO
7 | J60 | J91 | 140 | 159.2 | 5.5 | 3.3 | 1 | 4.3 | NO
8 | J7 | J5 | 63 | 88 | 5.5 | 3.3 | 1 | 4.3 | NO
9 | J3 | J4 | 63 | 86.6 | 5.5 | 3.3 | 1 | 4.3 | NO
10 | j93 | j95 | 63 | 33.6 | 5.5 | 3.3 | 1 | 4.3 | NO
11 | J93 | J105A | 63 | 95.6 | 5.5 | 3.3 | 1 | 4.3 | NO
12 | J105A | J105B | 63 | 97.1 | 5.5 | 3.3 | 1 | 4.3 | NO
13 | J129 | J130A | 63 | 24.9 | 5.5 | 3.3 | 1 | 4.3 | NO
14 | J130A | J130 | 63 | 15.7 | 5.5 | 3.3 | 1 | 4.3 | NO
15 | J130 | J132(1) | 63 | 12.9 | 5.5 | 3.3 | 1 | 4.3 | NO
16 | J132(1) | J132(2) | 63 | 38.8 | 5.5 | 3.3 | 1 | 4.3 | NO
17 | J132(1) | J132 | 63 | 36.6 | 5.5 | 3.3 | 1 | 4.3 | NO
18 | J136 | J137 | 63 | 31.3 | 5.5 | 3.3 | 1 | 4.3 | NO
19 | J8 | J9 | 63 | 166.8 | 5.5 | 3.3 | 1 | 4.3 | NO
20 | J94A | J94B | 63 | 46.1 | 5.5 | 3.3 | 1 | 4.3 | NO
21 | J13A | J13B | 63 | 37.7 | 5.5 | 3.3 | 1 | 4.3 | NO
22 | J25 | J26 | 63 | 14.1 | 5.5 | 3.3 | 1 | 4.3 | NO
23 | J39A | J40 | 63 | 67.2 | 5.5 | 3.3 | 1 | 4.3 | NO
24 | J39A | J40 | 63 | 11.2 | 5.5 | 3.3 | 1 | 4.3 | NO
25 | J44 | J55 | 63 | 241.2 | 5.5 | 3.3 | 1 | 4.3 | NO
26 | J57 | J62 | 63 | 3 | 5.5 | 3.3 | 1 | 4.3 | NO
27 | J57 | J62 | 63 | 166.1 | 5.5 | 3.3 | 1 | 4.3 | NO
28 | J57 | J63 | 63 | 19.7 | 5.5 | 3.3 | 1 | 4.3 | NO
29 | J63 | J77 | 63 | 57.4 | 5.5 | 3.3 | 1 | 4.3 | NO
30 | J77 | J78 | 63 | 48.8 | 5.5 | 3.3 | 1 | 4.3 | NO
31 | J77 | J84 | 63 | 59.8 | 5.5 | 3.3 | 1 | 4.3 | NO
32 | J84 | J84A | 63 | 2.7 | 5.5 | 3.3 | 1 | 4.3 | NO
33 | J84A | J85 | 63 | 155.8 | 5.5 | 3.3 | 1 | 4.3 | NO
34 | J84A | J88 | 63 | 470.2 | 5.5 | 3.3 | 1 | 4.3 | NO
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | bhaidpur | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | J1 | J8 | 160 | 102.8 | 5(kg/cm'2) | 3 | 1 | 4 | NO
2 | J8 | J10 | 160 | 143.1 | 5(kg/cm'2) | 3 | 1 | 4 | NO
3 | J10 | J60 | 160 | 157.8 | 5(kg/cm'2) | 3 | 1 | 4 | NO
4 | J17 | J12 | 125 | 118.7 | 5(kg/cm'2) | 3 | 1 | 4 | NO
5 | J12 | J28 | 125 | 3 | 5(kg/cm'2) | 3 | 1 | 4 | NO
6 | J12 | J28 | 125 | 1.7 | 5(kg/cm'2) | 3 | 1 | 4 | NO
7 | J11 | J13A | 110 | 68.2 | 5(kg/cm'2) | 3 | 1 | 4 | NO
8 | J13A | J25 | 110 | 45.1 | 5(kg/cm'2) | 3 | 1 | 4 | NO
9 | J25 | J34 | 110 | 93.5 | 5(kg/cm'2) | 3 | 1 | 4 | NO
10 | J34 | J39 | 110 | 63 | 5(kg/cm'2) | 3 | 1 | 4 | NO
11 | J94 | J116 | 75 | 63.2 | 5(kg/cm'2) | 3 | 1 | 4 | NO
12 | J129A | J129 | 75 | 157.7 | 5(kg/cm'2) | 3 | 1 | 4 | NO
13 | J129A | J129 | 75 | 13.4 | 5(kg/cm'2) | 3 | 1 | 4 | NO
14 | J68 | J65 | 63 | 74.1 | 5(kg/cm'2) | 3 | 1 | 4 | NO
15 | J68 | J65 | 63 | 5.2 | 5(kg/cm'2) | 3 | 1 | 4 | NO
16 | J68 | J65 | 63 | 141.8 | 5(kg/cm'2) | 3 | 1 | 4 | NO
17 | J65 | J17 | 63 | 98.9 | 5(kg/cm'2) | 3 | 1 | 4 | NO
18 | J17 | J21A | 63 | 11.2 | 5(kg/cm'2) | 3 | 1 | 4 | NO
19 | J17 | J21A | 63 | 122.5 | 5(kg/cm'2) | 3 | 1 | 4 | NO
20 | J21B | J22 | 63 | 109.8 | 5(kg/cm'2) | 3 | 1 | 4 | NO
21 | J21B | J22 | 63 | 24.9 | 5(kg/cm'2) | 3 | 1 | 4 | NO
22 | J21A | J21B | 63 | 19.8 | 5(kg/cm'2) | 3 | 1 | 4 | NO
23 | J11 | J27 | 63 | 73.1 | 5(kg/cm'2) | 3 | 1 | 4 | NO
24 | J11 | J27 | 63 | 3.2 | 5(kg/cm'2) | 3 | 1 | 4 | NO
25 | J27 | J49 | 63 | 43.2 | 5(kg/cm'2) | 3 | 1 | 4 | NO
26 | J27 | J49 | 63 | 6.9 | 5(kg/cm'2) | 3 | 1 | 4 | NO
27 | J27 | J36 | 63 | 140.9 | 5(kg/cm'2) | 3 | 1 | 4 | NO
28 | J34 | J36 | 63 | 108.1 | 5(kg/cm'2) | 3 | 1 | 4 | NO
29 | J34 | J36 | 63 | 1.8 | 5(kg/cm'2) | 3 | 1 | 4 | NO
30 | J36 | J47 | 63 | 60.1 | 5(kg/cm'2) | 3 | 1 | 4 | NO
31 | J47 | J52 | 63 | 33.4 | 5(kg/cm'2) | 3 | 1 | 4 | NO
32 | J52 | J63 | 63 | 7.4 | 5(kg/cm'2) | 3 | 1 | 4 | NO
33 | J52 | J63 | 63 | 49.6 | 5(kg/cm'2) | 3 | 1 | 4 | NO
34 | J52 | J53 | 63 | 2.4 | 5(kg/cm'2) | 3 | 1 | 4 | NO
35 | J52 | J53 | 63 | 62.8 | 5(kg/cm'2) | 3 | 1 | 4 | NO
36 | J53 | J53A | 63 | 11.4 | 5(kg/cm'2) | 3 | 1 | 4 | NO
37 | J53 | J53B | 63 | 15.5 | 5(kg/cm'2) | 3 | 1 | 4 | NO
38 | J47 | J42 | 63 | 100.6 | 5(kg/cm'2) | 3 | 1 | 4 | NO
39 | J42 | J49 | 63 | 58.7 | 5(kg/cm'2) | 3 | 1 | 4 | NO
40 | J49 | J49A | 63 | 11.3 | 5(kg/cm'2) | 3 | 1 | 4 | NO
41 | J28 | J49A | 63 | 21.6 | 5(kg/cm'2) | 3 | 1 | 4 | NO
42 | J28 | J28A | 63 | 43.3 | 5(kg/cm'2) | 3 | 1 | 4 | NO
43 | J28 | J12A | 63 | 114.9 | 5(kg/cm'2) | 3 | 1 | 4 | NO
44 | J12A | J12B | 63 | 42.1 | 5(kg/cm'2) | 3 | 1 | 4 | NO
45 | J12A | J12C | 63 | 30.1 | 5(kg/cm'2) | 3 | 1 | 4 | NO
46 | J12C | J43 | 63 | 28.9 | 5(kg/cm'2) | 3 | 1 | 4 | NO
47 | J12C | J28 | 63 | 25.4 | 5(kg/cm'2) | 3 | 1 | 4 | NO
48 | J49 | J59 | 63 | 112.2 | 5(kg/cm'2) | 3 | 1 | 4 | NO
49 | J59 | J75 | 63 | 25.5 | 5(kg/cm'2) | 3 | 1 | 4 | NO
50 | J59 | J14 | 63 | 40.6 | 5(kg/cm'2) | 3 | 1 | 4 | NO
51 | J14 | J14A | 63 | 20.2 | 5(kg/cm'2) | 3 | 1 | 4 | NO
52 | J14 | J50 | 63 | 80 | 5(kg/cm'2) | 3 | 1 | 4 | NO
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | bhaidpur | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | J5 | J3 | 125 | 104.9 | 6(KG/CM'2) | 4 | 1 | 5 | NO
2 | J3 | J1 | 125 | 63.6 | 6(KG/CM'2) | 4 | 1 | 5 | NO
3 | J91 | J94 | 125 | 3.8 | 6(KG/CM'2) | 4 | 1 | 5 | NO
4 | J91 | J94 | 125 | 157 | 6(KG/CM'2) | 4 | 1 | 5 | NO
5 | J91 | J92 | 125 | 67.6 | 6(KG/CM'2) | 4 | 1 | 5 | NO
6 | J92 | J93 | 125 | 89.1 | 6(KG/CM'2) | 4 | 1 | 5 | NO
7 | J39A | J44 | 90 | 139.1 | 6(KG/CM'2) | 4 | 1 | 5 | NO
8 | J39A | J44 | 90 | 3 | 6(KG/CM'2) | 4 | 1 | 5 | NO
9 | J39 | J57 | 90 | 115.9 | 6(KG/CM'2) | 4 | 1 | 5 | NO
10 | J59 | J64 | 63 | 59.8 | 6(KG/CM'2) | 4 | 1 | 5 | NO
11 | J64 | J64A | 63 | 18.2 | 6(KG/CM'2) | 4 | 1 | 5 | NO
12 | J64 | J64A | 63 | 31.5 | 6(KG/CM'2) | 4 | 1 | 5 | NO
13 | J64A | J37 | 63 | 65.6 | 6(KG/CM'2) | 4 | 1 | 5 | NO
14 | J37 | J33 | 63 | 39.8 | 6(KG/CM'2) | 4 | 1 | 5 | NO
15 | J33 | J32 | 63 | 16.8 | 6(KG/CM'2) | 4 | 1 | 5 | NO
16 | J33 | J23 | 63 | 26.7 | 6(KG/CM'2) | 4 | 1 | 5 | NO
17 | J64 | J69 | 63 | 27.4 | 6(KG/CM'2) | 4 | 1 | 5 | NO
18 | J69 | J75 | 63 | 47.8 | 6(KG/CM'2) | 4 | 1 | 5 | NO
19 | J75 | J59 | 63 | 63.5 | 6(KG/CM'2) | 4 | 1 | 5 | NO
20 | J75 | J80 | 63 | 20.7 | 6(KG/CM'2) | 4 | 1 | 5 | NO
21 | J75 | J80 | 63 | 40.1 | 6(KG/CM'2) | 4 | 1 | 5 | NO
22 | J75 | J80 | 63 | 3.2 | 6(KG/CM'2) | 4 | 1 | 5 | NO
23 | J80 | J80A | 63 | 27.1 | 6(KG/CM'2) | 4 | 1 | 5 | NO
24 | J80A | J81 | 63 | 14.5 | 6(KG/CM'2) | 4 | 1 | 5 | NO
25 | J80A | J80B | 63 | 26.2 | 6(KG/CM'2) | 4 | 1 | 5 | NO
26 | J80 | J82 | 63 | 34.9 | 6(KG/CM'2) | 4 | 1 | 5 | NO
27 | J82 | J83 | 63 | 51.5 | 6(KG/CM'2) | 4 | 1 | 5 | NO
28 | J82 | J84 | 63 | 63.5 | 6(KG/CM'2) | 4 | 1 | 5 | NO
29 | J69 | J71 | 63 | 20.1 | 6(KG/CM'2) | 4 | 1 | 5 | NO
30 | J71 | J72 | 63 | 13.4 | 6(KG/CM'2) | 4 | 1 | 5 | NO
31 | J71 | J72 | 63 | 50.1 | 6(KG/CM'2) | 4 | 1 | 5 | NO
32 | J71 | J71A | 63 | 146.1 | 6(KG/CM'2) | 4 | 1 | 5 | NO
33 | J71 | J71A | 63 | 47.2 | 6(KG/CM'2) | 4 | 1 | 5 | NO
34 | J71A | J71B | 63 | 23.2 | 6(KG/CM'2) | 4 | 1 | 5 | NO
35 | J71A | J73 | 63 | 13.7 | 6(KG/CM'2) | 4 | 1 | 5 | NO
36 | J71A | J73 | 63 | 22.2 | 6(KG/CM'2) | 4 | 1 | 5 | NO
37 | J73 | J72 | 63 | 64.8 | 6(KG/CM'2) | 4 | 1 | 5 | NO
38 | J72 | J72A | 63 | 24.6 | 6(KG/CM'2) | 4 | 1 | 5 | NO
39 | J72A | J72B | 63 | 17.9 | 6(KG/CM'2) | 4 | 1 | 5 | NO
40 | J72A | J70 | 63 | 72.4 | 6(KG/CM'2) | 4 | 1 | 5 | NO
41 | J73 | J70 | 63 | 31.2 | 6(KG/CM'2) | 4 | 1 | 5 | NO
42 | J70 | J65 | 63 | 3.5 | 6(KG/CM'2) | 4 | 1 | 5 | NO
43 | J70 | J65 | 63 | 74.8 | 6(KG/CM'2) | 4 | 1 | 5 | NO
44 | J132 | J136 | 63 | 22.9 | 6(KG/CM'2) | 4 | 1 | 5 | NO
45 | J132 | J136 | 63 | 95.5 | 6(KG/CM'2) | 4 | 1 | 5 | NO
46 | J136 | J136A | 63 | 60.1 | 6(KG/CM'2) | 4 | 1 | 5 | NO
47 | J136 | 142A | 63 | 25.7 | 6(KG/CM'2) | 4 | 1 | 5 | NO
48 | J142A | J142B | 63 | 31.4 | 6(KG/CM'2) | 4 | 1 | 5 | NO
49 | J142A | J142 | 63 | 74.1 | 6(KG/CM'2) | 4 | 1 | 5 | NO
50 | J142A | J142 | 63 | 75.1 | 6(KG/CM'2) | 4 | 1 | 5 | NO
51 | J146 | J142 | 63 | 43.7 | 6(KG/CM'2) | 4 | 1 | 5 | NO
52 | J129 | J135 | 63 | 272.8 | 6(KG/CM'2) | 4 | 1 | 5 | NO
53 | J135 | J138 | 63 | 176 | 6(KG/CM'2) | 4 | 1 | 5 | NO
54 | J138 | J139 | 63 | 6.5 | 6(KG/CM'2) | 4 | 1 | 5 | NO
55 | J138 | J139 | 63 | 48.2 | 6(KG/CM'2) | 4 | 1 | 5 | NO
56 | J138 | J146 | 63 | 158.6 | 6(KG/CM'2) | 4 | 1 | 5 | NO
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | bhaidpur | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | J92 | J99 | 90 | 98.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
2 | J92 | J99 | 90 | 88.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
3 | J92 | J99 | 90 | 43.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
4 | J39 | J39A | 90 | 5.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
5 | J94 | J129A | 75 | 84.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
6 | J94 | J129A | 75 | 3.8 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
7 | J94 | J129A | 75 | 80.7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
8 | J146 | J149 | 63 | 84.9 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
9 | J149 | J151 | 63 | 36.8 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
10 | J149 | J151 | 63 | 14.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
11 | J151 | J142 | 63 | 84.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
12 | J151 | J152 | 63 | 61.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
13 | J136 | J132 | 63 | 24.9 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
14 | J132 | J133 | 63 | 76.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
15 | J133 | J134 | 63 | 51.4 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
16 | J133 | J135 | 63 | 75.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
17 | J132 | J130 | 63 | 49.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
18 | J130 | J131 | 63 | 36.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
19 | J130 | J130A | 63 | 16.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
20 | J130A | J130B | 63 | 34.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
21 | J130A | J129 | 63 | 25.8 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
22 | J129A | J129B | 63 | 74.9 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
23 | J94 | J97A | 63 | 349.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
24 | J126 | J128 | 63 | 232.4 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
25 | J126 | J120 | 63 | 3.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
26 | J126 | J120 | 63 | 397.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
27 | J120 | J121 | 63 | 20.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
28 | J121 | J115 | 63 | 98.9 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
29 | J115 | J115A | 63 | 38 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
30 | J115A | J118 | 63 | 58.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
31 | J115A | J115B | 63 | 13.4 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
32 | J118 | J118A | 63 | 63.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
33 | J118 | J119 | 63 | 98.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
34 | J115 | J120 | 63 | 101.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
35 | J121 | J122 | 63 | 174.9 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
36 | J121 | J122 | 63 | 22.7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
37 | J109 | J100 | 63 | 78.4 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
38 | J100 | J101 | 63 | 51.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
39 | J100 | J99 | 63 | 66.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
40 | J99 | J102A | 63 | 115.4 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
41 | J102A | J102B | 63 | 65.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
42 | J102A | J102 | 63 | 5.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
43 | J102A | J102 | 63 | 54.8 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
44 | J102 | J103 | 63 | 57.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date

## BHAIDPUR LAK
HYD+A1:H15RO TEST/ GAP CLOSING/ FHTC STRETCH/VALVE FITTING/COMMISIONING ACKNOWLEDGEMENT
Contractor Name;shukla construction
Block:mangraura |  |  | GP;BHAIDPUR
Billing Month -aug |  |  | RAB No:
Approved for RAB Quantities : (Tick Whichever is Proposing)
| Hydrotest |  |  |  | √
GAP Closing
FHTC Stretch
Valve Fitting
Commisioning
S. No. | Pipe Dia | Scope Qty | Upto date Laying Quantity | This Bill Quantity for Above Tic Marked Item | Cumm upto This Bill Quantity of Above Tic Marked Item | Remarks
1 | 63 |  |  | 9419.1
2 | 75 |  |  | 403
3 | 90 |  |  | 492.7
4 | 110 |  |  | 269.8
5 | 125 |  |  | 609.4
6 | 140 |  |  | 540.2
7 | 160 |  |  | 303.7
8 | 180
9 | 200
Sub-Contractor Site Engineer Block-incharge AGM PMX Incharge Project Incharge