## madhura rani ganj
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd. | [7 empty] | 1
Contractor:- |  | Power Mech Project Ltd. | [7 empty] | 2
Block :- |  | Mangraura | [7 empty] | 3
GP :- |  | madhura rani ganj | [5 empty] | Date |  | 4
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation | 5
1 | j493 | j491 | 200 | 101 | 5.5 | 3.3 | 1 | 4.3 | no | 6
2 | j491 | j489 | 200 | 29.3 | 5.5 | 3.3 | 1 | 4.3 | no | 7
3 | j489 | j485 | 200 | 45 | 5.5 | 3.3 | 1 | 4.3 | no | 8
4 | j485 | j481 | 200 | 46.4 | 5.5 | 3.3 | 1 | 4.3 | no | 9
5 | j487 | j486 | 200 | 65.8 | 5.5 | 3.3 | 1 | 4.3 | no | 10
6 | j486 | j482 | 200 | 75.6 | 5.5 | 3.3 | 1 | 4.3 | no | 11
7 | j481 | j483 | 200 | 57.3 | 5.5 | 3.3 | 1 | 4.3 | no | 12
8 | j480 | j477 | 200 | 70.6 | 5.5 | 3.3 | 1 | 4.3 | no | 13
9 | j477 | j379 | 200 | 98.8 | 5.5 | 3.3 | 1 | 4.3 | no | 14
10 | j379 | j376 | 200 | 45.6 | 5.5 | 3.3 | 1 | 4.3 | no | 15
11 | j495 | j487 | 160 | 87.8 | 5.5 | 3.3 | 1 | 4.3 | no | 16
12 | j433 | j492 | 160 | 167.8 | 5.5 | 3.3 | 1 | 4.3 | no | 17
13 | j433 | j442 | 160 | 27.1 | 5.5 | 3.3 | 1 | 4.3 | no | 18
14 | j511 | j514 | 140 | 25.1 | 5.5 | 3.3 | 1 | 4.3 | no | 19
15 | j511 | j514 | 140 | 152.8 | 5.5 | 3.3 | 1 | 4.3 | no | 20
16 | j447 | j442 | 140 | 20 | 5.5 | 3.3 | 1 | 4.3 | no | 21
17 | j447 | j442 | 140 | 52 | 5.5 | 3.3 | 1 | 4.3 | no | 22
18 | j542 | j491 | 63 | 100.7 | 5.5 | 3.3 | 1 | 4.3 | no | 23
19 | j380 | j399 | 63 | 125.8 | 5.5 | 3.3 | 1 | 4.3 | no | 24
20 | j399 | j403 | 63 | 25.2 | 5.5 | 3.3 | 1 | 4.3 | no | 25
21 | j403 | j411 | 63 | 30.1 | 5.5 | 3.3 | 1 | 4.3 | no | 26
22 | j411 | j418 | 63 | 57.2 | 5.5 | 3.3 | 1 | 4.3 | no | 27
23 | j411 | j418 | 63 | 23.2 | 5.5 | 3.3 | 1 | 4.3 | no | 28
24 | j380 | j399 | 63 | 2 | 5.5 | 3.3 | 1 | 4.3 | no | 29
25 | j380 | j399 | 63 | 6.7 | 5.5 | 3.3 | 1 | 4.3 | no | 30
26 | j447a | j447b | 63 | 10.2 | 5.5 | 3.3 | 1 | 4.3 | no | 31
27 | j129 | j130 | 63 | 25.1 | 5.5 | 3.3 | 1 | 4.3 | no | 32
28 | j34 | j35 | 63 | 5 | 5.5 | 3.3 | 1 | 4.3 | no | 33
29 | j34 | j35 | 63 | 103.1 | 5.5 | 3.3 | 1 | 4.3 | no | 34
30 | j133 | j134 | 63 | 113.2 | 5.5 | 3.3 | 1 | 4.3 | no | 35
31 | j134 | j136 | 63 | 54 | 5.5 | 3.3 | 1 | 4.3 | no | 36
32 | j134 | j135 | 63 | 24.8 | 5.5 | 3.3 | 1 | 4.3 | no | 37
33 | j133 | j138 | 63 | 85.1 | 5.5 | 3.3 | 1 | 4.3 | no | 38
34 | j138 | j160 | 63 | 47.1 | 5.5 | 3.3 | 1 | 4.3 | no | 39
35 | j138 | j139 | 63 | 78.3 | 5.5 | 3.3 | 1 | 4.3 | no | 40
36 | j25 | j38 | 63 | 4 | 5.5 | 3.3 | 1 | 4.3 | no | 41
37 | j25 | j38 | 63 | 15.3 | 5.5 | 3.3 | 1 | 4.3 | no | 42
38 | j25 | j38 | 63 | 33.1 | 5.5 | 3.3 | 1 | 4.3 | no | 43
39 | j25 | j38 | 63 | 93.5 | 5.5 | 3.3 | 1 | 4.3 | no | 44
40 | j39 | j38 | 63 | 47.6 | 5.5 | 3.3 | 1 | 4.3 | no | 45
41 | j38 | j79 | 63 | 80.8 | 5.5 | 3.3 | 1 | 4.3 | no | 46
42 | j401 | j414 | 63 | 6.5 | 5.5 | 3.3 | 1 | 4.3 | no
43 | j587 | j639 | 63 | 3.5 | 5.5 | 3.3 | 1 | 4.3 | no
44 | j504 | j506 | 63 | 7 | 5.5 | 3.3 | 1 | 4.3 | no
45 | j536 | j538 | 63 | 6.5 | 5.5 | 3.3 | 1 | 4.3 | no
46 | j574 | j575 | 63 | 6.9 | 5.5 | 3.3 | 1 | 4.3 | no
47 | j7 | j7a | 63 | 302 | 5.5 | 3.3 | 1 | 4.3 | no
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT. |  | 47
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION |  | 48
NAME |  |  |  | NAME |  |  |  | NAME |  | 49
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date |  | 50
51
52
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh | [7 empty] | 53
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh | [7 empty] | 54
TPI:- |  | Medhaj Techno Concept Pvt. Ltd. | [7 empty] | 55
Contractor:- |  | Power Mech Project Ltd. | [7 empty] | 56
Block :- |  | Mangraura | [7 empty] | 57
GP :- |  | madhura rani ganj | [5 empty] | Date |  | 58
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation | 59
1 | j310 | j309 | 200 | 270.7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 60
2 | j310 | j283 | 200 | 119.7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 61
3 | j283 | j228 | 200 | 223.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 62
4 | j228 | j216 | 200 | 248.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 63
5 | j216 | j170 | 200 | 357.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 64
6 | j216 | j170 | 200 | 76.8 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 65
7 | j170 | j169 | 200 | 68.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 66
8 | j169 | j167 | 200 | 191.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 67
9 | j169 | j167 | 200 | 5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 68
10 | j167 | j166 | 200 | 25.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 69
11 | j166 | j159 | 200 | 92.7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 70
12 | j159 | j146 | 200 | 119.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 71
13 | j159 | j141 | 200 | 85.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 72
14 | j141 | j113 | 200 | 133.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 73
15 | j113 | j27 | 200 | 212.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 74
16 | j27 | j23 | 200 | 61 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 75
17 | j27 | j23 | 200 | 4.7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 76
18 | j27 | j23 | 200 | 12.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 77
19 | j502 | j493 | 200 | 19.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 78
20 | j310 | j376 | 200 | 6.9 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 79
21 | j381 | j382 | 140 | 6.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 80
22 | j381 | j382 | 140 | 29.7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 81
23 | j382 | j386 | 140 | 34.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 82
24 | j398 | j393 | 140 | 50.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 83
25 | j489 | j490 | 63 | 32 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 84
26 | j447a | j447b | 63 | 31 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 85
27 | j456 | j457 | 63 | 21.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 86
28 | j74 | j75 | 63 | 97 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 87
29 | j162 | j165 | 63 | 298.7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 88
30 | j45 | j133 | 63 | 133 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 89
31 | j111 | j128 | 63 | 238.4 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 90
32 | j128 | j130 | 63 | 11.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 91
33 | j130 | j137 | 63 | 44.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 92
34 | j137 | j142 | 63 | 45.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 93
35 | j142 | j147 | 63 | 22.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 94
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT. |  | 95
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION |  | 96
NAME |  |  |  | NAME |  |  |  | NAME |  | 97
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date |  | 98
99
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh | [7 empty] | 100
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh | [7 empty] | 101
TPI:- |  | Medhaj Techno Concept Pvt. Ltd. | [7 empty] | 102
Contractor:- |  | Power Mech Project Ltd. | [7 empty] | 103
Block :- |  | Mangraura | [7 empty] | 104
GP :- |  | madhura rani ganj | [5 empty] | Date |  | 105
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation | 106
1 | j442 | j448 | 160 | 167.5 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO | 107
2 | j49 | j47 | 160 | 215 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO | 108
3 | j47 | j45 | 160 | 701.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO | 109
4 | j47 | j45 | 160 | 3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO | 110
5 | j45 | j34 | 160 | 206 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO | 111
6 | j34 | j30 | 160 | 90 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO | 112
7 | j30 | j29 | 160 | 15 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO | 113
8 | j29 | j25 | 160 | 168 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO | 114
9 | j25 | j24 | 160 | 54.9 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO | 115
10 | j24 | j23 | 160 | 88.8 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO | 116
11 | j24 | j23 | 160 | 7.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO | 117
12 | j23 | j26 | 160 | 127.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO | 118
13 | j26 | j28 | 160 | 7.7 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO | 119
14 | j28 | j46 | 160 | 195.7 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO | 120
15 | j46 | j72 | 160 | 234.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO | 121
16 | j72 | j110 | 160 | 165.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO | 122
17 | j72 | j110 | 160 | 4.6 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO | 123
18 | j113 | j115 | 160 | 60 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO | 124
19 | j115 | j120 | 160 | 338.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO | 125
20 | j216 | j215 | 160 | 263.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO | 126
21 | j167 | j182 | 160 | 152.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO | 127
22 | j448 | j454 | 140 | 118.6 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 110 | 140
23 | j425 | j437 | 140 | 91.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 0 | 0 | #REF!
24 | j437 | j441 | 140 | 110.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
25 | j451 | j447 | 140 | 44.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
26 | j50 | j49 | 140 | 189.7 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
27 | j45 | j63 | 140 | 291.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
28 | j120 | j123 | 140 | 26.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
29 | j123 | j126 | 140 | 48.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
30 | j77 | j72 | 140 | 206.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
31 | j126 | j129 | 110 | 30.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
32 | j2 | j3 | 110 | 195.6 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
33 | j2 | j3 | 110 | 5 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
34 | j441 | j459 | 110 | 140.9 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
35 | j24 | j12 | 110 | 122.7 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
36 | j12 | j1 | 110 | 105.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
37 | j77 | j92 | 110 | 77.8 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
38 | j77 | j84 | 110 | 74.8 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
39 | j570 | j590 | 110 | 106.4 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
40 | j55 | j50 | 90 | 77.6 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
41 | j63 | j74 | 90 | 101.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
42 | j84 | j86 | 90 | 79.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
43 | j27 | j27a | 63 | 37.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
44 | j27 | j27a | 63 | 3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
45 | j30 | j31 | 63 | 73.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date

## madhura rani (ags)
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | madhura rani ganj and saraouli | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | j221 | j215 | 160 | 252 | 6 | 3 | 1 | 4 | no
2 | j309 | j273 | 160 | 7 | 6 | 3 | 1 | 4 | no
3 | j309 | j273 | 160 | 495.4 | 6 | 3 | 1 | 4 | no
4 | j273 | j243 | 160 | 3 | 6 | 3 | 1 | 4 | no
5 | j273 | j243 | 160 | 121 | 6 | 3 | 1 | 4 | no
6 | j273 | j243 | 160 | 3 | 6 | 3 | 1 | 4 | no
7 | j315 | j322 | 140 | 63 | 6 | 3 | 1 | 4 | no
8 | j315 | j322 | 140 | 20.1 | 6 | 3 | 1 | 4 | no
9 | j265 | j264 | 140 | 216 | 6 | 3 | 1 | 4 | no
10 | j264 | j252 | 140 | 79 | 6 | 3 | 1 | 4 | no
11 | j264 | j252 | 140 | 10.2 | 6 | 3 | 1 | 4 | no
12 | j341 | j354 | 63 | 101 | 6 | 3 | 1 | 4 | no
13 | j344 | j341 | 63 | 7.3 | 6 | 3 | 1 | 4 | no
14 | j337 | j337a | 63 | 15.5 | 6 | 3 | 1 | 4 | no
15 | j344 | j347 | 63 | 56.2 | 6 | 3 | 1 | 4 | no
16 | j341 | j366 | 63 | 197.1 | 6 | 3 | 1 | 4 | no
17 | j341 | j366 | 63 | 19.3 | 6 | 3 | 1 | 4 | no
18 | J341 | J366 | 63 | 173.2 | 6 | 3 | 1 | 4 | no
19 | J366 | J368 | 63 | 152.7 | 6 | 3 | 1 | 4 | no
20 | J368 | J369 | 63 | 54.8 | 6 | 3 | 1 | 4 | no
21 | J368 | J362 | 63 | 150 | 6 | 3 | 1 | 4 | no
22 | J366 | J355 | 63 | 3.2 | 6 | 3 | 1 | 4 | no
23 | J366 | J355 | 63 | 127.6 | 6 | 3 | 1 | 4 | no
24 | J355 | J360 | 63 | 125.5 | 6 | 3 | 1 | 4 | no
25 | J351 | J350 | 63 | 123 | 6 | 3 | 1 | 4 | no
26 | J322 | J336 | 63 | 240 | 6 | 3 | 1 | 4 | no
27 | J324 | j333 | 63 | 111.7 | 6 | 3 | 1 | 4 | no
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  | UTTAR PRADESH JAL NIGAM(RURAL)
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | madhura rani ganj and saraouli | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | j315 | j337 | 160 | 197.1 | 5.5 | 3.3 | 1 | 4.3 | no
2 | j309 | j315 | 160 | 320 | 5.5 | 3.3 | 1 | 4.3 | no
3 | j309 | j315 | 160 | 9.1 | 5.5 | 3.3 | 1 | 4.3 | no
4 | j309 | j315 | 160 | 400 | 5.5 | 3.3 | 1 | 4.3 | no
5 | j252 | j243 | 160 | 121.4 | 5.5 | 3.3 | 1 | 4.3 | no
6 | j243 | j231 | 160 | 144.4 | 5.5 | 3.3 | 1 | 4.3 | no
7 | j231 | j224 | 160 | 56.1 | 5.5 | 3.3 | 1 | 4.3 | no
8 | j252 | j243 | 160 | 121.4 | 5.5 | 3.3 | 1 | 4.3 | no
9 | j243 | j231 | 160 | 144.4 | 5.5 | 3.3 | 1 | 4.3 | no
10 | j231 | j224 | 160 | 56.1 | 5.5 | 3.3 | 1 | 4.3 | no
11 | j224 | j221 | 160 | 3.5 | 5.5 | 3.3 | 1 | 4.3 | no
12 | j224 | j221 | 160 | 164 | 5.5 | 3.3 | 1 | 4.3 | no
13 | j337 | j337a | 140 | 67.7 | 5.5 | 3.3 | 1 | 4.3 | no
14 | j337a(1) | j337a | 140 | 5.3 | 5.5 | 3.3 | 1 | 4.3 | no
15 | j337a(1) | j344 | 140 | 17.1 | 5.5 | 3.3 | 1 | 4.3 | no
16 | j344 | j341 | 140 | 24.3 | 5.5 | 3.3 | 1 | 4.3 | no
17 | j315 | j322 | 140 | 122.3 | 5.5 | 3.3 | 1 | 4.3 | no
18 | j315 | j322 | 140 | 4 | 5.5 | 3.3 | 1 | 4.3 | no
19 | j324 | j325 | 63 | 20.2 | 5.5 | 3.3 | 1 | 4.3 | no
20 | j324 | j322 | 63 | 38.8 | 5.5 | 3.3 | 1 | 4.3 | no
21 | j270 | j289 | 63 | 246 | 5.5 | 3.3 | 1 | 4.3 | no
22 | j289 | j306 | 63 | 291.1 | 5.5 | 3.3 | 1 | 4.3 | no
23 | j306 | j301 | 63 | 245.2 | 5.5 | 3.3 | 1 | 4.3 | no
24 | j306 | j301 | 63 | 3.1 | 5.5 | 3.3 | 1 | 4.3 | no
25 | j301 | j304 | 63 | 40.2 | 5.5 | 3.3 | 1 | 4.3 | no
26 | j304 | j305 | 63 | 61.1 | 5.5 | 3.3 | 1 | 4.3 | no
27 | j304 | j302a | 63 | 115.1 | 5.5 | 3.3 | 1 | 4.3 | no
28 | j304 | j302a | 63 | 4 | 5.5 | 3.3 | 1 | 4.3 | no
29 | j302a | j302b | 63 | 24.1 | 5.5 | 3.3 | 1 | 4.3 | no
30 | j302a | j302 | 63 | 15.6 | 5.5 | 3.3 | 1 | 4.3 | no
31 | j302 | j303 | 63 | 7.5 | 5.5 | 3.3 | 1 | 4.3 | no
32 | j302 | j303 | 63 | 32.1 | 5.5 | 3.3 | 1 | 4.3 | no
33 | j302 | j303 | 63 | 70.2 | 5.5 | 3.3 | 1 | 4.3 | no
34 | j302 | j299 | 63 | 8 | 5.5 | 3.3 | 1 | 4.3 | no
35 | j302 | j299 | 63 | 20 | 5.5 | 3.3 | 1 | 4.3 | no
36 | j302 | j299 | 63 | 3.2 | 5.5 | 3.3 | 1 | 4.3 | no
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  | UTTAR PRADESH JAL NIGAM(RURAL)
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | madhura rani ganj and saraouli | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | j265 | j270 | 110 | 65 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
2 | j299 | j300 | 63 | 75.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
3 | j299 | j297 | 63 | 40.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
4 | j297 | j298 | 63 | 36.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
5 | j298a | j298 | 63 | 14 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
6 | j298 | j298b | 63 | 22 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
7 | j297 | j295 | 63 | 93.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
8 | j295 | j293 | 63 | 104.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
9 | j293 | j288 | 63 | 55 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
10 | j293 | j288 | 63 | 11 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
11 | j293 | j290 | 63 | 10.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
12 | j290 | j286 | 63 | 15.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
13 | j286 | j285 | 63 | 88.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
14 | j295 | j294 | 63 | 171 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
15 | j265 | j266 | 63 | 340.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
16 | j266 | j267 | 63 | 61 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
17 | j267a | j267b | 63 | 12.9 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
18 | j266 | j268 | 63 | 29.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
19 | j265 | j264 | 63 | 216 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
20 | j264 | j262 | 63 | 219.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
21 | j262 | j263 | 63 | 35 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
22 | j262 | j256 | 63 | 50 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
23 | j256 | j255 | 63 | 3.8 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
24 | j256 | j255 | 63 | 6.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
25 | j255 | j260 | 63 | 118 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
26 | j255 | j249 | 63 | 64.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
27 | j249 | j253 | 63 | 17.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
28 | j249 | j253 | 63 | 15 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
29 | j249 | j244 | 63 | 13 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
30 | j244 | j250 | 63 | 116.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
31 | j244 | j231 | 63 | 58.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
32 | j244 | j231 | 63 | 25 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
33 | j244 | j231 | 63 | 94 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
34 | j252 | j250 | 63 | 81 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
35 | j250 | j244 | 63 | 51 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
36 | j250 | j251 | 63 | 49.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
37 | j250a | j250b | 63 | 57 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
38 | j224 | j225 | 63 | 53.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
39 | j225 | j226 | 63 | 146.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
40 | j225 | j227 | 63 | 3.4 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
41 | j225 | j227 | 63 | 56.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
42 | j221 | j222 | 63 | 67 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
43 | j216 | j220 | 63 | 321.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  | UTTAR PRADESH JAL NIGAM(RURAL)
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | madhura rani ganj and saraouli | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | j171 | j170 | 63 | 65.9 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
2 | j171 | j172 | 63 | 78.5 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
3 | j171 | j173 | 63 | 21.5 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
4 | j173 | j177 | 63 | 48.5 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
5 | j173 | j174 | 63 | 5.4 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
6 | j173 | j174 | 63 | 3.7 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
7 | j173 | j174 | 63 | 22.4 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
8 | j174 | j175 | 63 | 55.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
9 | j174 | j177 | 63 | 125.6 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
10 | j169 | j146 | 63 | 474 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
11 | j182 | j183 | 63 | 158.5 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
12 | j166 | j160 | 63 | 68.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
13 | j160 | j161 | 63 | 39 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
14 | j160 | j138 | 63 | 474.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
15 | j160 | j159 | 63 | 180 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
16 | j145 | j152 | 63 | 213 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
17 | j140 | j157 | 63 | 116 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
18 | j113 | j114 | 63 | 78 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
19 | j273 | j274 | 63 | 160 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
20 | j274 | j277 | 63 | 3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
21 | j274 | j277 | 63 | 206 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
22 | j274 | j275 | 63 | 32 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
23 | j275 | j276 | 63 | 3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
24 | j275 | j276 | 63 | 81.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
25 | j275 | j278 | 63 | 134.5 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
26 | j278a | j278b | 63 | 18.8 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
27 | j301 | j269 | 63 | 308.5 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
28 | j301 | j269 | 63 | 36.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
29 | j301 | j269 | 63 | 111.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  | UTTAR PRADESH JAL NIGAM(RURAL)
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | madhura rani ganj and saraouli | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | j296 | j245 | 63 | 248 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
2 | j245 | j246 | 63 | 8.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
3 | j246 | j247 | 63 | 45.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
4 | j246 | j246a | 63 | 6.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
5 | j246a | j246b | 63 | 29.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
6 | j246a | j246c | 63 | 4.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
7 | j246c | j246d | 63 | 24.7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
8 | j246 | j248 | 63 | 140.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
9 | j236 | j243 | 63 | 58 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
10 | j236 | j211 | 63 | 573.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
11 | j236 | j233 | 63 | 469.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
12 | j233 | j234 | 63 | 107 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
13 | j233 | j230 | 63 | 116 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
14 | j230 | j223 | 63 | 176.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
15 | j230 | j240 | 63 | 183.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
16 | j240 | j269 | 63 | 3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
17 | j240 | j269 | 63 | 247.4 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
18 | j306 | j313 | 63 | 3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
19 | j306 | j313 | 63 | 170.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
20 | j306 | j313 | 63 | 12 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
21 | j306 | j313 | 63 | 12 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
22 | j306 | j313 | 63 | 656 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  | UTTAR PRADESH JAL NIGAM(RURAL)
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | madhura rani ganj and saraouli | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | j296 | j245 | 63 | 248 | 5.5 | 3.3 | 1 | 4.3 | no
2 | j245 | j246 | 63 | 8.5 | 5.5 | 3.3 | 1 | 4.3 | no
3 | j246 | j247 | 63 | 45.1 | 5.5 | 3.3 | 1 | 4.3 | no
4 | j246 | j246a | 63 | 6.3 | 5.5 | 3.3 | 1 | 4.3 | no
5 | j246a | j246b | 63 | 29.2 | 5.5 | 3.3 | 1 | 4.3 | no
6 | j246a | j246c | 63 | 4.3 | 5.5 | 3.3 | 1 | 4.3 | no
7 | j246c | j246d | 63 | 24.7 | 5.5 | 3.3 | 1 | 4.3 | no
8 | j246 | j248 | 63 | 140.3 | 5.5 | 3.3 | 1 | 4.3 | no
9 | j236 | j243 | 63 | 58 | 5.5 | 3.3 | 1 | 4.3 | no
10 | j236 | j211 | 63 | 573.5 | 5.5 | 3.3 | 1 | 4.3 | no
11 | j236 | j233 | 63 | 469.1 | 5.5 | 3.3 | 1 | 4.3 | no
12 | j233 | j234 | 63 | 107 | 5.5 | 3.3 | 1 | 4.3 | no
13 | j233 | j230 | 63 | 116 | 5.5 | 3.3 | 1 | 4.3 | no
14 | j230 | j223 | 63 | 176.6 | 5.5 | 3.3 | 1 | 4.3 | no
15 | j230 | j240 | 63 | 183.1 | 5.5 | 3.3 | 1 | 4.3 | no
16 | j240 | j269 | 63 | 3 | 5.5 | 3.3 | 1 | 4.3 | no
17 | j240 | j269 | 63 | 247.4 | 5.5 | 3.3 | 1 | 4.3 | no
18 | j306 | j313 | 63 | 3 | 5.5 | 3.3 | 1 | 4.3 | no
19 | j306 | j313 | 63 | 170.1 | 5.5 | 3.3 | 1 | 4.3 | no
20 | j306 | j313 | 63 | 12 | 5.5 | 3.3 | 1 | 4.3 | no
21 | j306 | j313 | 63 | 12 | 5.5 | 3.3 | 1 | 4.3 | no
22 | j306 | j313 | 63 | 656 | 5.5 | 3.3 | 1 | 4.3 | no
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  | UTTAR PRADESH JAL NIGAM(RURAL)
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date

## MADHURA (new)
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | MADHURA RANI GANJ AND SARAOULI | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | j376 | j371 | 200 | 188.4 | 6 | 3 | 1 | 4 | no
2 | j376 | j371 | 200 | 14.3 | 6 | 3 | 1 | 4 | no
3 | j376 | j371 | 200 | 754 | 6 | 3 | 1 | 4 | no
4 | j371 | j316 | 200 | 503.7 | 6 | 3 | 1 | 4 | no
5 | J137 | J132 | 63 | 27 | 6 | 3 | 1 | 4 | no
6 | J142 | J143 | 63 | 86.1 | 6 | 3 | 1 | 4 | no
7 | J147 | J148 | 63 | 48.1 | 6 | 3 | 1 | 4 | no
8 | J147 | J148 | 63 | 33.6 | 6 | 3 | 1 | 4 | no
9 | J148A | J148 | 63 | 9.3 | 6 | 3 | 1 | 4 | no
10 | J148 | J148B | 63 | 53.2 | 6 | 3 | 1 | 4 | no
11 | J180 | J149 | 63 | 91.3 | 6 | 3 | 1 | 4 | no
12 | J147 | J187 | 63 | 146.1 | 6 | 3 | 1 | 4 | no
13 | J187 | J196 | 63 | 175.8 | 6 | 3 | 1 | 4 | no
14 | J196 | J197 | 63 | 37.1 | 6 | 3 | 1 | 4 | no
15 | J192 | J193 | 63 | 25 | 6 | 3 | 1 | 4 | no
16 | J192 | J187 | 63 | 24.7 | 6 | 3 | 1 | 4 | no
17 | J192 | J198 | 63 | 129.2 | 6 | 3 | 1 | 4 | no
18 | J198 | J196 | 63 | 34.5 | 6 | 3 | 1 | 4 | no
19 | J198 | J228 | 63 | 536.8 | 6 | 3 | 1 | 4 | no
20 | J3 | J10 | 63 | 45.7 | 6 | 3 | 1 | 4 | no
21 | J3 | J11 | 63 | 119.2 | 6 | 3 | 1 | 4 | no
22 | J27 | J26 | 63 | 85.5 | 6 | 3 | 1 | 4 | no
23 | J28 | 41 | 63 | 155 | 6 | 3 | 1 | 4 | no
24 | J91A | J91B | 63 | 18.6 | 6 | 3 | 1 | 4 | no
25 | J91 | J91A | 63 | 27 | 6 | 3 | 1 | 4 | no
26 | J91A | J90 | 63 | 18.1 | 6 | 3 | 1 | 4 | no
27 | J90 | J94 | 63 | 39.6 | 6 | 3 | 1 | 4 | no
28 | J90 | J86 | 63 | 31.8 | 6 | 3 | 1 | 4 | no
29 | J86 | J97 | 63 | 71 | 6 | 3 | 1 | 4 | no
30 | J97 | J94 | 63 | 42.7 | 6 | 3 | 1 | 4 | no
31 | J97 | J98 | 63 | 63.6 | 6 | 3 | 1 | 4 | no
32 | J98 | J99 | 63 | 20 | 6 | 3 | 1 | 4 | no
33 | J98 | J106 | 63 | 44.1 | 6 | 3 | 1 | 4 | no
34 | J100 | J101 | 63 | 45.7 | 6 | 3 | 1 | 4 | no
35 | J100 | J103 | 63 | 28.4 | 6 | 3 | 1 | 4 | no
36 | J103 | J105 | 63 | 35.3 | 6 | 3 | 1 | 4 | no
37 | J103 | J103A | 63 | 46.3 | 6 | 3 | 1 | 4 | no
38 | J84 | J100 | 63 | 64.7 | 6 | 3 | 1 | 4 | no
39 | J105 | J92 | 63 | 64.1 | 6 | 3 | 1 | 4 | no
40 | J128 | J76 | 63 | 59.4 | 6 | 3 | 1 | 4 | no
41 | J123 | J122 | 63 | 37.2 | 6 | 3 | 1 | 4 | no
42 | J61 | J49 | 63 | 318.2 | 6 | 3 | 1 | 4 | no
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | MADHURA RANI GANJ AND SARAOULI | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | j526 | j502 | 160 | 100.2 | 5.5 | 3.3 | 1 | 4.3 | no
2 | j381 | j391 | 160 | 16.1 | 5.5 | 3.3 | 1 | 4.3 | no
3 | j391 | j425 | 160 | 324.3 | 5.5 | 3.3 | 1 | 4.3 | no
4 | j431 | j428 | 160 | 18.3 | 5.5 | 3.3 | 1 | 4.3 | no
5 | j427a | j427 | 160 | 41.6 | 5.5 | 3.3 | 1 | 4.3 | no
6 | j409 | j406 | 160 | 205.2 | 5.5 | 3.3 | 1 | 4.3 | no
7 | j406 | j427 | 160 | 188.6 | 5.5 | 3.3 | 1 | 4.3 | no
8 | j406 | j401 | 160 | 12.1 | 5.5 | 3.3 | 1 | 4.3 | no
9 | j401 | j391 | 160 | 133.6 | 5.5 | 3.3 | 1 | 4.3 | no
10 | j495 | j505 | 160 | 105.3 | 5.5 | 3.3 | 1 | 4.3 | no
11 | j505 | j511 | 160 | 79.7 | 5.5 | 3.3 | 1 | 4.3 | no
12 | J47 | J48 | 63 | 72.4 | 5.5 | 3.3 | 1 | 4.3 | no
13 | J49 | J51 | 63 | 104 | 5.5 | 3.3 | 1 | 4.3 | no
14 | J51 | J52 | 63 | 19.6 | 5.5 | 3.3 | 1 | 4.3 | no
15 | J51 | J50 | 63 | 223 | 5.5 | 3.3 | 1 | 4.3 | no
16 | J55 | J58 | 63 | 190.2 | 5.5 | 3.3 | 1 | 4.3 | no
17 | J63 | J66 | 63 | 130.2 | 5.5 | 3.3 | 1 | 4.3 | no
18 | J32 | J33 | 63 | 37.1 | 5.5 | 3.3 | 1 | 4.3 | no
19 | J32 | J32A | 63 | 56.4 | 5.5 | 3.3 | 1 | 4.3 | no
20 | J32 | J32B | 63 | 21.3 | 5.5 | 3.3 | 1 | 4.3 | no
21 | J32A | J40 | 63 | 187.7 | 5.5 | 3.3 | 1 | 4.3 | no
22 | J29 | J21 | 63 | 187.3 | 5.5 | 3.3 | 1 | 4.3 | no
23 | J21 | J22 | 63 | 174.6 | 5.5 | 3.3 | 1 | 4.3 | no
24 | J21A | J21B | 63 | 32.1 | 5.5 | 3.3 | 1 | 4.3 | no
25 | J21A | J20 | 63 | 37.1 | 5.5 | 3.3 | 1 | 4.3 | no
26 | J20 | J19 | 63 | 46.3 | 5.5 | 3.3 | 1 | 4.3 | no
27 | J20 | J17 | 63 | 51.1 | 5.5 | 3.3 | 1 | 4.3 | no
28 | J17 | J19 | 63 | 10.6 | 5.5 | 3.3 | 1 | 4.3 | no
29 | J17 | J15 | 63 | 46.2 | 5.5 | 3.3 | 1 | 4.3 | no
30 | J15 | J15A | 63 | 27.3 | 5.5 | 3.3 | 1 | 4.3 | no
31 | J15 | J16 | 63 | 26.8 | 5.5 | 3.3 | 1 | 4.3 | no
32 | J13 | J14 | 63 | 39.2 | 5.5 | 3.3 | 1 | 4.3 | no
33 | J590 | J618 | 63 | 101.3 | 5.5 | 3.3 | 1 | 4.3 | no
34 | J618 | J628 | 63 | 29 | 5.5 | 3.3 | 1 | 4.3 | no
35 | J628 | J630 | 63 | 53.7 | 5.5 | 3.3 | 1 | 4.3 | no
36 | J618 | J627 | 63 | 194.7 | 5.5 | 3.3 | 1 | 4.3 | no
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | MADHURA RANI GANJ AND SARAOULI | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | j544 | j537 | 160 | 164 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
2 | j537 | j526 | 160 | 190 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
3 | j570 | j567 | 140 | 149 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
4 | j567 | j544 | 140 | 197.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
5 | j425 | j450 | 140 | 243.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
6 | j450 | j456 | 140 | 50.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
7 | j450 | j451 | 140 | 73 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
8 | j451 | j447 | 140 | 260 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
9 | j451 | j448 | 140 | 444 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
10 | J627 | J644 | 63 | 63.4 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
11 | J628 | J644 | 63 | 218.7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
12 | J576 | J627 | 63 | 214 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
13 | J644 | J658 | 63 | 469.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
14 | J658 | J657 | 63 | 153.4 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
15 | J657 | J624 | 63 | 388 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
16 | J624 | J620 | 63 | 185 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
17 | J624 | J595 | 63 | 3.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
18 | J624 | J595 | 63 | 113.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
19 | J595 | J596 | 63 | 74.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
20 | J595 | J587 | 63 | 47.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
21 | J587 | J525A | 63 | 36 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
22 | J525A | J525B | 63 | 29.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
23 | J525A | J511 | 63 | 162.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
24 | J511A | J511B | 63 | 41.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
25 | J587 | J639 | 63 | 2.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
26 | J587 | J639 | 63 | 421.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
27 | J639 | J638 | 63 | 2.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
28 | J638 | J657 | 63 | 237 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
29 | J658 | J648 | 63 | 218.4 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
30 | J648 | J638 | 63 | 142.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | MADHURA RANI GANJ AND SARAOULI | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | J648 | J640 | 63 | 51.4 | 5.5 | 3.3 | 1 | 4.3 | no
2 | J640 | J616 | 63 | 128 | 5.5 | 3.3 | 1 | 4.3 | no
3 | J616 | J617 | 63 | 38 | 5.5 | 3.3 | 1 | 4.3 | no
4 | J616 | J537 | 63 | 3.9 | 5.5 | 3.3 | 1 | 4.3 | no
5 | J616 | J537 | 63 | 5.4 | 5.5 | 3.3 | 1 | 4.3 | no
6 | J616 | J537 | 63 | 258.1 | 5.5 | 3.3 | 1 | 4.3 | no
7 | J544 | J545 | 63 | 103.1 | 5.5 | 3.3 | 1 | 4.3 | no
8 | J567 | J633 | 63 | 386.2 | 5.5 | 3.3 | 1 | 4.3 | no
9 | J633 | J640 | 63 | 73.4 | 5.5 | 3.3 | 1 | 4.3 | no
10 | J633 | J634 | 63 | 35.2 | 5.5 | 3.3 | 1 | 4.3 | no
11 | J639 | J601 | 63 | 163.7 | 5.5 | 3.3 | 1 | 4.3 | no
12 | J601 | J593 | 63 | 109.1 | 5.5 | 3.3 | 1 | 4.3 | no
13 | J593 | J568 | 63 | 90.7 | 5.5 | 3.3 | 1 | 4.3 | no
14 | J568 | J569 | 63 | 49.2 | 5.5 | 3.3 | 1 | 4.3 | no
15 | J568 | J562 | 63 | 52.1 | 5.5 | 3.3 | 1 | 4.3 | no
16 | J562 | J563 | 63 | 38.2 | 5.5 | 3.3 | 1 | 4.3 | no
17 | J562 | J557 | 63 | 20.6 | 5.5 | 3.3 | 1 | 4.3 | no
18 | J557 | J529 | 63 | 68.2 | 5.5 | 3.3 | 1 | 4.3 | no
19 | J557 | J543 | 63 | 120.2 | 5.5 | 3.3 | 1 | 4.3 | no
20 | J543 | J509 | 63 | 153.6 | 5.5 | 3.3 | 1 | 4.3 | no
21 | J509 | J529 | 63 | 51.3 | 5.5 | 3.3 | 1 | 4.3 | no
22 | J543 | J546 | 63 | 28.3 | 5.5 | 3.3 | 1 | 4.3 | no
23 | J546 | J552 | 63 | 89.3 | 5.5 | 3.3 | 1 | 4.3 | no
24 | J546 | J547 | 63 | 45.2 | 5.5 | 3.3 | 1 | 4.3 | no
25 | j546 | j558 | 63 | 94.1 | 5.5 | 3.3 | 1 | 4.3 | no
26 | j558 | j542 | 63 | 63.3 | 5.5 | 3.3 | 1 | 4.3 | no
27 | j558 | j542 | 63 | 76.3 | 5.5 | 3.3 | 1 | 4.3 | no
28 | j542 | j559 | 63 | 64.5 | 5.5 | 3.3 | 1 | 4.3 | no
29 | j559 | j558 | 63 | 90.6 | 5.5 | 3.3 | 1 | 4.3 | no
30 | j559 | j593 | 63 | 152.5 | 5.5 | 3.3 | 1 | 4.3 | no
31 | j601 | j530 | 63 | 5.8 | 5.5 | 3.3 | 1 | 4.3 | no
32 | j601 | j530 | 63 | 210.7 | 5.5 | 3.3 | 1 | 4.3 | no
33 | j504 | j506 | 63 | 225.7 | 5.5 | 3.3 | 1 | 4.3 | no
34 | j590a | j585 | 63 | 34.8 | 5.5 | 3.3 | 1 | 4.3 | no
35 | j585 | j574 | 63 | 52.3 | 5.5 | 3.3 | 1 | 4.3 | no
36 | j574 | j570a | 63 | 44.9 | 5.5 | 3.3 | 1 | 4.3 | no
37 | j570a | j570b | 63 | 18.1 | 5.5 | 3.3 | 1 | 4.3 | no
38 | j570a | j570c | 63 | 29.7 | 5.5 | 3.3 | 1 | 4.3 | no
39 | j578 | j575 | 63 | 51.6 | 5.5 | 3.3 | 1 | 4.3 | no
40 | j575 | j574 | 63 | 10.1 | 5.5 | 3.3 | 1 | 4.3 | no
41 | j575 | j580 | 63 | 29.7 | 5.5 | 3.3 | 1 | 4.3 | no
42 | j585 | j581 | 63 | 141.1 | 5.5 | 3.3 | 1 | 4.3 | no
43 | j379 | j502 | 63 | 292 | 5.5 | 3.3 | 1 | 4.3 | no
44 | j514 | j619 | 63 | 134.2 | 5.5 | 3.3 | 1 | 4.3 | no
45 | j514 | j619 | 63 | 323 | 5.5 | 3.3 | 1 | 4.3 | no
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | MADHURA RANI GANJ AND SARAOULI | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | j401 | j414 | 63 | 182 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
2 | j414 | j419 | 63 | 52.8 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
3 | j419 | j422 | 63 | 30 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
4 | j416 | j419 | 63 | 5.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
5 | j416 | j417 | 63 | 24 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
6 | j416 | j418 | 63 | 47 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
7 | j418 | j423 | 63 | 56 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
8 | j382 | j383 | 63 | 49.8 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
9 | j386 | j387 | 63 | 23.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
10 | j386 | j388 | 63 | 28.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
11 | j392 | j393 | 63 | 56.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
12 | j394 | j395 | 63 | 28.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
13 | j414 | j407 | 63 | 15 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
14 | j414 | j407 | 63 | 3.9 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
15 | j407 | j408 | 63 | 40 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
16 | j392 | j407 | 63 | 71.4 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
17 | j451 | j455a | 63 | 82.4 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
18 | j455a | j455b | 63 | 49 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
19 | j455a | j455c | 63 | 80 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
20 | j455c | j462 | 63 | 63.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
21 | j455c | j466 | 63 | 54.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
22 | j466 | j471 | 63 | 64 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
23 | j466 | j464 | 63 | 30.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
24 | j464 | j468 | 63 | 59.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
25 | j468 | j471 | 63 | 20.4 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
26 | j468 | j469 | 63 | 28 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
27 | j464 | j459 | 63 | 186 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
28 | j459 | j440 | 63 | 175 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
29 | j440 | j440a | 63 | 28.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
30 | j440a | j440b | 63 | 27.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
31 | j440a | j440c | 63 | 26.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
32 | j487 | j488 | 63 | 42.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
33 | j487 | j476 | 63 | 197 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
34 | j476 | j478 | 63 | 46.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
35 | j478 | j479a | 63 | 12.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
36 | j479a | j479 | 63 | 6.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
37 | j479a | j479 | 63 | 14.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
38 | j479a | j479b | 63 | 30.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
39 | j478 | j480 | 63 | 40.9 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
40 | j476 | j476a | 63 | 95.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | MADHURA RANI GANJ AND SARAOULI | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | j376 | j380 | 200 | 190.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
2 | j380 | j381 | 200 | 129.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
3 | j530 | j600 | 63 | 161.5 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
4 | j600 | j601 | 63 | 51.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
5 | j600 | j602 | 63 | 53.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
6 | j602 | j603 | 63 | 62.8 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
7 | j602 | j616 | 63 | 21.7 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
8 | j645 | j635 | 63 | 76.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
9 | j604 | j606 | 63 | 59.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
10 | j604 | j605 | 63 | 89.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
11 | j626 | j625 | 63 | 30.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
12 | j570 | j572 | 63 | 38 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
13 | j576a | j576b | 63 | 41.5 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
14 | j381 | j391 | 63 | 5 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
15 | j435 | j439 | 63 | 32.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
16 | j428 | j438 | 63 | 2.4 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
17 | j428 | j438 | 63 | 95.5 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
18 | j438 | j443 | 63 | 50.9 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
19 | j443 | j444 | 63 | 2.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
20 | j443 | j444 | 63 | 33.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
21 | j438 | j429 | 63 | 2.7 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
22 | j438 | j429 | 63 | 63.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
23 | j427a | j427b | 63 | 37.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
24 | j427 | j428 | 63 | 32.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
25 | j427a | j429 | 63 | 8.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
26 | j429 | j430 | 63 | 23.7 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
27 | j429 | j424 | 63 | 47.9 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
28 | j424 | j426 | 63 | 3.9 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
29 | j424 | j426 | 63 | 53.6 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
30 | j424 | j426 | 63 | 24 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
31 | j424 | j409 | 63 | 76.6 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
32 | j409 | j510 | 63 | 99.4 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
33 | j536 | j538 | 63 | 89.7 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
34 | j506 | j508 | 63 | 29.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
35 | j487 | j495 | 63 | 27 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
36 | j476a | j398 | 63 | 94.4 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
37 | j477 | j485 | 63 | 80.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
38 | j485 | j477 | 63 | 51.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
39 | j482 | j486 | 63 | 89.8 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
40 | j495 | j499 | 63 | 46.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
41 | j499 | j500 | 63 | 53.7 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
42 | j499 | j501 | 63 | 71.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
43 | j495 | j498 | 63 | 45.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
44 | j496 | j498 | 63 | 40.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
45 | j552a | j552b | 63 | 28.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
46 | j519 | j523 | 63 | 65.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
47 | j523 | j521 | 63 | 14 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
48 | j523 | j525 | 63 | 51.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
49 | j523 | j521 | 63 | 23.4 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
50 | j594 | j598 | 63 | 3.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
51 | j594 | j598 | 63 | 173 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
52 | j608 | j609 | 63 | 118 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
53 | j608 | j609 | 63 | 2.5 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
54 | j527 | j513 | 63 | 55.4 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
55 | j553 | j554 | 63 | 35.7 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
56 | j553a | j553b | 63 | 35.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
57 | j520 | j522 | 63 | 21 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
58 | j531a | j531b | 63 | 80.5 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
59 | j493 | j494 | 63 | 68.9 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
60 | j526 | j530 | 63 | 21.7 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
61 | j530 | j600 | 63 | 181 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | MADHURA RANI GANJ AND SARAOULI | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | OHT | j1(1) | 250 | 35 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
2 | j1(1) | j1 | 200 | 605 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
3 | j1(1) | j2 | 200 | 26 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
4 | j2 | j23 | 200 | 106 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
5 | j590 | j592 | 63 | 219 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
6 | j162 | j230 | 63 | 525 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
7 | j38 | j138 | 63 | 325.4 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
8 | j21 | j22 | 63 | 300 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
9 | j44 | j44(1) | 63 | 156.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
10 | j112 | j112(1) | 63 | 205.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date