## hydro test
| HYDROSTATIC TEST FOR PRESSURE PIPES | [11 empty] | HYDROSTATIC TEST FOR PRESSURE PIPES | [11 empty] | HYDROSTATIC TEST FOR PRESSURE PIPES | [11 empty] | HYDROSTATIC TEST FOR PRESSURE PIPES | [11 empty] | HYDROSTATIC TEST FOR PRESSURE PIPES | [11 empty] | HYDROSTATIC TEST FOR PRESSURE PIPES
Project:- |  | Rural water supply project Under JJM , Pratapgarh , Utter Pradesh | [9 empty] | Project:- |  | Rural water supply project Under JJM , Pratapgarh , Utter Pradesh | [9 empty] | Project:- |  | Rural water supply project Under JJM , Pratapgarh , Utter Pradesh | [9 empty] | Project:- |  | Rural water supply project Under JJM , Pratapgarh , Utter Pradesh | [9 empty] | Project:- |  | Rural water supply project Under JJM , Pratapgarh , Utter Pradesh | [9 empty] | Project:- |  | Rural water supply project Under JJM , Pratapgarh , Utter Pradesh
Client : - |  | State Water & Sanitation Mission Govt of Uttar Pradesh | [9 empty] | Client : - |  | State Water & Sanitation Mission Govt of Uttar Pradesh | [9 empty] | Client : - |  | State Water & Sanitation Mission Govt of Uttar Pradesh | [9 empty] | Client : - |  | State Water & Sanitation Mission Govt of Uttar Pradesh | [9 empty] | Client : - |  | State Water & Sanitation Mission Govt of Uttar Pradesh | [9 empty] | Client : - |  | State Water & Sanitation Mission Govt of Uttar Pradesh
TPI :- |  | Medhaj Techno Concept Pvt . Ltd. | [9 empty] | TPI :- |  | Medhaj Techno Concept Pvt . Ltd. | [9 empty] | TPI :- |  | Medhaj Techno Concept Pvt . Ltd. | [9 empty] | TPI :- |  | Medhaj Techno Concept Pvt . Ltd. | [9 empty] | TPI :- |  | Medhaj Techno Concept Pvt . Ltd. | [9 empty] | TPI :- |  | Medhaj Techno Concept Pvt . Ltd.
Contractor :- |  | Power Mech Project Ltd. | [9 empty] | Contractor :- |  | Power Mech Project Ltd. | [9 empty] | Contractor :- |  | Power Mech Project Ltd. | [9 empty] | Contractor :- |  | Power Mech Project Ltd. | [9 empty] | Contractor :- |  | Power Mech Project Ltd. | [9 empty] | Contractor :- |  | Power Mech Project Ltd.
Block: MANGRAURA GP: GEHRAULI | [11 empty] | Block: MANGRAURA GP: GEHRAULI | [11 empty] | Block: MANGRAURA GP: GEHRAULI | [11 empty] | Block: MANGRAURA GP: GEHRAULI | [11 empty] | Block: MANGRAURA GP: GEHRAULI | [11 empty] | Block: MANGRAURA GP: GEHRAULI
Dail Log Ref. …………………. | [5 empty] | Tested as per CPHEEO …………………….. | [5 empty] | Dail Log Ref. …………………. | [5 empty] | Tested as per CPHEEO …………………….. | [5 empty] | Dail Log Ref. …………………. | [5 empty] | Tested as per CPHEEO …………………….. | [5 empty] | Dail Log Ref. …………………. | [5 empty] | Tested as per CPHEEO …………………….. | [5 empty] | Dail Log Ref. …………………. | [5 empty] | Tested as per CPHEEO …………………….. | [5 empty] | Dail Log Ref. …………………. | [5 empty] | Tested as per CPHEEO ……………………..
Date 17-3-2023 | [5 empty] | Date of Testing …………………………………. | 2023-03-17 |  |  |  |  | Date | [5 empty] | Date of Testing …………………………………. | [5 empty] | Date | [5 empty] | Date of Testing …………………………………. | [5 empty] | Date | [5 empty] | Date of Testing …………………………………. | [5 empty] | Date | [5 empty] | Date of Testing …………………………………. | [5 empty] | Date | [5 empty] | Date of Testing ………………………………….
SL. No. | Material of Pipe | ID (MM) | Start Node | End Node | Length | Appliede test pressure (kg/cm'2) | Time in Hrs |  |  | Observation | Remark | SL. No. | Material of Pipe | ID (MM) | Start Node | End Node | Length | Appliede test pressure (kg/cm'2) | Time in Hrs |  |  | Observation | Remark | SL. No. | Material of Pipe | ID (MM) | Start Node | End Node | Length | Appliede test pressure (kg/cm'2) | Time in Hrs |  |  | Observation | Remark | SL. No. | Material of Pipe | ID (MM) | Start Node | End Node | Length | Appliede test pressure (kg/cm'2) | Time in Hrs |  |  | Observation | Remark | SL. No. | Material of Pipe | ID (MM) | Start Node | End Node | Length | Appliede test pressure (kg/cm'2) | Time in Hrs |  |  | Observation | Remark | SL. No. | Material of Pipe | ID (MM) | Start Node | End Node | Length | Appliede test pressure (kg/cm'2) | Time in Hrs |  |  | Observation | Remark
[7 empty] | Pressure rising time (Hrs) | Pressure Released time (Hrs) | Total Duration Hrs | [9 empty] | Pressure rising time (Hrs) | Pressure Released time (Hrs) | Total Duration Hrs | [9 empty] | Pressure rising time (Hrs) | Pressure Released time (Hrs) | Total Duration Hrs | [9 empty] | Pressure rising time (Hrs) | Pressure Released time (Hrs) | Total Duration Hrs | [9 empty] | Pressure rising time (Hrs) | Pressure Released time (Hrs) | Total Duration Hrs | [9 empty] | Pressure rising time (Hrs) | Pressure Released time (Hrs) | Total Duration Hrs
1 | HDPE | 126.3 | J2 | J51 | 522 | 6KG/CM2 | 17-03-2023(09:30AM) | 17-03-2023(12:30PM) | 3:00 |  |  | 1 | HDPE | 140 | j33 | j72 | 227.8 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 1 | HDPE | 63 | j29(1) | j29(2) | 362 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 1 | HDPE | 63 | j9 | j20 | 96.4 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 1 | HDPE | 63 | J99 | J59 | 43.8 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO |  | 1 | HDPE | 63 | J144 | J148 | 45.4 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO
2 | HDPE | 126.3 | J51 | J33 | 423 | 6KG/CM2 | 17-03-2023(09:30AM) | 17-03-2023(12:30PM) | 3:00 |  |  | 2 | HDPE | 140 | j72 | j74 | 68 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 2 | HDPE | 63 | j155 | j115 | 305.2 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 2 | HDPE | 63 | j9 | j20 | 10.3 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 2 | HDPE | 63 | J99 | J59 | 17 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO |  | 2 | HDPE | 63 | J148 | J145 | 101.2 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO
3 | [11 empty] | 3 | HDPE | 140 | j74 | j94 | 34.5 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 3 | HDPE | 63 | j166 | j162 | 133.1 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 3 | HDPE | 63 | j20 | j26 | 56 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 3 | HDPE | 63 | J103 | J70 | 25.8 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO |  | 3 | HDPE | 63 | J145 | J53 | 31.6 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO
|  | POWER MECH |  |  |  | MEDHAJ |  |  | JAL NIGAM U.P. |  |  | 4 | HDPE | 125 | j72 | j88 | 88 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 4 | HDPE | 63 | j162 | j155 | 211.3 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 4 | HDPE | 63 | j26 | j28 | 20 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 4 | HDPE | 63 | J103 | J70 | 4.4 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO |  | 4 | HDPE | 63 | J145 | J40 | 121.1 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO
Name: | [11 empty] | 5 | HDPE | 125 | j88 | j84 | 94.3 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 5 | HDPE | 63 | j162 | j155 | 7.5 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 5 | HDPE | 63 | j26 | j21 | 12.6 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 5 | HDPE | 63 | J70 | J141 | 109.5 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO |  | 5 | HDPE | 63 | J40 | J22 | 34 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO
Signature: | [11 empty] | 6 | HDPE | 63 | j122 | j104 | 733.7 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 6 | HDPE | 63 | j155 | j44 | 106.3 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 6 | HDPE | 63 | j21 | j54 | 93 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 6 | HDPE | 63 | J112 | J70 | 24 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO |  | 6 | HDPE | 63 | J22 | J125 | 22.8 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO
[12 empty] | 7 | HDPE | 63 | j122 | j39 | 116 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 7 | HDPE | 63 | j44 | j124 | 132.8 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 7 | HDPE | 63 | j54 | j159 | 100.2 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 7 | HDPE | 63 | J136 | J105 | 32 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO |  | 7 | HDPE | 63 | J22 | J20 | 55.4 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO
[12 empty] | 8 | HDPE | 63 | j122 | j39 | 3.5 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 8 | HDPE | 63 | j124 | j30 | 61.4 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 8 | HDPE | 63 | j54 | j159 | 12.8 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 8 | HDPE | 63 | J135 | J131 | 35.4 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO |  | 8 | HDPE | 63 | J21 | J138 | 38.9 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO
[12 empty] | 9 | HDPE | 63 | j104 | j64 | 33.4 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 9 | HDPE | 63 | j124 | j128 | 31.9 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 9 | HDPE | 63 | j159 | j123 | 21.7 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 9 | HDPE | 63 | J84 | J60 | 2.3 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO |  | 9 | HDPE | 63 | J138 | J153 | 36.7 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO
[12 empty] | 10 | HDPE | 63 | j64 | j151 | 65.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 10 | HDPE | 63 | j128 | j45 | 61.4 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 10 | HDPE | 63 | j123 | j82 | 78 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 10 | HDPE | 63 | J84 | J60 | 232.7 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO |  | 10 | HDPE | 63 | J114 | J138 | 19.2 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO
[12 empty] | 11 | HDPE | 63 | j151 | j158 | 49 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 11 | HDPE | 63 | j128 | j81 | 100.6 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 11 | HDPE | 63 | j149 | j163 | 28 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 11 | HDPE | 63 | J84 | J60 | 131.4 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO |  | 11 | HDPE | 63 | J148 | J125 | 71.6 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO
[12 empty] | 12 | HDPE | 63 | j151 | j13 | 168.3 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 12 | HDPE | 63 | j56 | j10 | 112.2 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 12 | HDPE | 63 | j163 | j140 | 27.4 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 12 | HDPE | 110 | J84 | J101 | 67.7 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO |  | 12 | HDPE | 63 | J159 | J139 | 61.7 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO
[12 empty] | 13 | HDPE | 63 | j151 | j13 | 3.5 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 13 | HDPE | 63 | j44 | j27 | 74.6 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 13 | HDPE | 63 | j163 | j140 | 33.7 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 13 | HDPE | 63 | J101 | J134 | 30.4 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO |  | 13 | HDPE | 63 | J118 | J90 | 55.3 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO
[12 empty] | 14 | HDPE | 63 | j13 | j18 | 40.5 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 14 | HDPE | 63 | j27 | j15 | 51.1 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 14 | HDPE | 63 | j140 | j123 | 39 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 14 | HDPE | 110 | J101 | J111 | 519.2 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO |  | 14 | HDPE | 63 | J102 | J46 | 38.7 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO
[12 empty] | 15 | HDPE | 63 | j13 | j16 | 46.4 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 15 | HDPE | 63 | j162 | j146 | 170.9 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 15 | HDPE | 63 | j140 | j89 | 86 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 15 | HDPE | 63 | J111 | J108 | 38.2 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO |  | 15 | HDPE | 63 | J165 | J167 | 275 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO
[12 empty] | 16 | HDPE | 63 | j16 | j64 | 68 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 16 | HDPE | 63 | j146 | j64 | 123 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 16 | HDPE | 63 | j89 | j41 | 56.8 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 16 | HDPE | 63 | J108 | J117 | 82.5 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO |  |  |  | POWER MECH |  |  |  | MEDHAJ |  |  | JAL NIGAM U.P.
[12 empty] | 17 | HDPE | 63 | j16 | j64 | 3.5 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 17 | HDPE | 63 | j164 | j133 | 81 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 17 | HDPE | 63 | j89 | j41 | 18.2 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 17 | HDPE | 63 | J117 | J36 | 56.8 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO |  | Name:
[12 empty] | 18 | HDPE | 63 | j16 | j11 | 104.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 18 | HDPE | 63 | j133 | j167 | 177 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 18 | HDPE | 63 | j89 | j94 | 61.2 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 18 | HDPE | 63 | J117 | J120 | 87.2 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO |  | Signature:
[12 empty] | 19 | HDPE | 63 | j104 | j42 | 72.7 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 19 | HDPE | 63 | j146 | j142 | 71.7 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 19 | HDPE | 63 | j74 | j113 | 38.9 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 19 | HDPE | 63 | J120 | J129 | 14.2 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO
[12 empty] | 20 | HDPE | 63 | j104 | j42 | 26.6 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 20 | HDPE | 63 | j142 | j137 | 126.5 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 20 | HDPE | 63 | j113 | j163a | 90 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 20 | HDPE | 63 | J120 | J67 | 27 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO
[12 empty] | 21 | HDPE | 63 | j167 | j166 | 86 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 21 | HDPE | 63 | j142 | j82 | 269.4 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 21 | HDPE | 63 | j113 | j163a | 8.2 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 21 | HDPE | 63 | J90 | J69 | 3 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO
[12 empty] | 22 | HDPE | 63 | j167 | j166 | 3.5 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 22 | HDPE | 63 | j133 | j143 | 90 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 22 | HDPE | 63 | j163a | j163 | 21.6 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 22 | HDPE | 63 | J90 | J69 | 22 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO
[12 empty] | 23 | HDPE | 63 | j166 | j126 | 335 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 23 | HDPE | 63 | j164 | j160 | 72.1 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 23 | HDPE | 63 | j113 | j86 | 102.6 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 23 | HDPE | 63 | J90 | J90A | 3.3 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO
[12 empty] | 24 | HDPE | 63 | j126 | j34 | 142.7 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 24 | HDPE | 63 | j160 | j154 | 77.2 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 24 | HDPE | 63 | j86 | j92 | 18.1 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 24 | HDPE | 63 | J90A | J132 | 121 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO
[12 empty] | 25 | HDPE | 63 | j34 | j24 | 27.8 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  |  | POWER MECH |  |  |  | MEDHAJ |  |  | JAL NIGAM U.P. |  |  | 25 | HDPE | 63 | j98 | j86 | 13.5 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 25 | HDPE | 63 | J132A | J132B | 20.6 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO
[12 empty] | 26 | HDPE | 63 | j34 | j24 | 3.5 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | Name: | [11 empty] | 26 | HDPE | 63 | j90 | j98 | 29 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 26 | HDPE | 63 | J132 | J149 | 26.5 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO
[12 empty] | 27 | HDPE | 63 | j126 | j55 | 53.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | Signature: | [11 empty] | 27 | HDPE | 63 | j2(b) | j5 | 44 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 27 | HDPE | 63 | J149 | J163 | 29 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO
[12 empty] | 28 | HDPE | 63 | j55 | j115 | 52.4 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO | [13 empty] | 28 | HDPE | 63 | j5 | j4 | 77 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 28 | HDPE | 63 | J149 | J107 | 45.7 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO
[12 empty] | 29 | HDPE | 63 | j115 | j29 | 67.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO | [13 empty] | 29 | HDPE | 63 | j5 | j5(1) | 8.3 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 29 | HDPE | 63 | J149 | J107 | 9.8 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO
[12 empty] | 30 | HDPE | 63 | j29 | j55 | 74 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO | [13 empty] | 30 | HDPE | 63 | j5(1) | j8 | 35.3 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 30 | HDPE | 63 | J98 | J87 | 3 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO
[12 empty] | 31 | HDPE | 63 | j34 | j29(1) | 100 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO | [13 empty] | 31 | HDPE | 63 | j5 | j2 | 37.3 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 31 | HDPE | 63 | J98 | J87 | 35.2 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO
[14 empty] | POWER MECH |  |  |  | MEDHAJ |  |  | JAL NIGAM U.P. | [14 empty] | 32 | HDPE | 160 | j2(a) | j2(b) | 192 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 32 | HDPE | 140 | J94 | J78 | 133.5 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO
[12 empty] | Name: | [23 empty] | 33 | HDPE | 63 | j76 | j100 | 55.5 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 33 | HDPE | 125 | J78 | J76A | 100 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO
[12 empty] | Signature: | [23 empty] | 34 | HDPE | 63 | j76 | j100 | 3.5 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 34 | HDPE | 110 | J76A | J76 | 49 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO
[36 empty] | 35 | HDPE | 63 | j73 | j71 | 60.6 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 35 | HDPE | 90 | J76 | J93 | 86 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO
[36 empty] | 36 | HDPE | 63 | j73 | j57 | 81.5 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 36 | HDPE | 110 | J33 | J65 | 216.9 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO
[36 empty] | 37 | HDPE | 63 | j57 | j79 | 37.4 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 37 | HDPE | 63 | J65 | J63 | 27.8 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO
[36 empty] | 38 | HDPE | 63 | j57 | j47 | 47.6 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 38 | HDPE | 90 | J65 | J118 | 136.6 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO
[36 empty] | 39 | HDPE | 63 | j108 | j73 | 147 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 39 | HDPE | 63 | J118 | J160 | 202.5 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO
[36 empty] | 40 | HDPE | 90 | J93 | j122 | 214 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 40 | HDPE | 63 | J82 | J144 | 56.9 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO
[36 empty] | 41 | HDPE | 63 | J129 | J66 | 373.4 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  |  |  | POWER MECH |  |  |  | MEDHAJ |  |  | JAL NIGAM U.P.
[36 empty] | 42 | HDPE | 63 | J129 | J66 | 3 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | Name:
[36 empty] | 43 | HDPE | 63 | J129 | J135 | 27.4 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | Signature:
[36 empty] | 44 | HDPE | 63 | J135 | J136 | 12 | 5.5KG/CM2 | 3 | 1 | 4 | NO
[36 empty] | 45 | HDPE | 63 | J136 | J103 | 34 | 5.5KG/CM2 | 3 | 1 | 4 | NO
[36 empty] | 46 | HDPE | 63 | J103 | J99 | 23.2 | 5.5KG/CM2 | 3 | 1 | 4 | NO
[36 empty] | 47 | HDPE | 63 | J99 | J150 | 40.3 | 5.5KG/CM2 | 3 | 1 | 4 | NO
[38 empty] | POWER MECH |  |  |  | MEDHAJ |  |  | JAL NIGAM U.P.
Name:
Signature: