## AMUWAHI
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | AMUWAHI | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | J1 | J2 | 110 | 384.4 | 6 | 3 | 1 | 4 | no
2 | J2 | J5 | 63 | 97.9 | 6 | 3 | 1 | 4 | no
3 | J5 | J4 | 63 | 3.1 | 6 | 3 | 1 | 4 | no
4 | J5 | J4 | 63 | 26.2 | 6 | 3 | 1 | 4 | no
5 | J8 | J7 | 63 | 113.4 | 6 | 3 | 1 | 4 | no
6 | J7 | J2 | 63 | 6.6 | 6 | 3 | 1 | 4 | no
7 | J7 | J2 | 63 | 8.6 | 6 | 3 | 1 | 4 | no
8 | J7 | J2 | 63 | 110.9 | 6 | 3 | 1 | 4 | no
9 | J7 | J12 | 63 | 206.4 | 6 | 3 | 1 | 4 | no
10 | J7 | J14 | 63 | 442.4 | 6 | 3 | 1 | 4 | no
11 | J14 | J15 | 63 | 43 | 6 | 3 | 1 | 4 | no
12 | J14 | J16 | 63 | 76.5 | 6 | 3 | 1 | 4 | no
13 | J14 | J16 | 63 | 3.8 | 6 | 3 | 1 | 4 | no
14 | J16 | J17 | 63 | 5.8 | 6 | 3 | 1 | 4 | no
15 | J16 | J17 | 63 | 137.3 | 6 | 3 | 1 | 4 | no
16 | J16 | J17 | 63 | 5.9 | 6 | 3 | 1 | 4 | no
17 | J16 | J17 | 63 | 34.8 | 6 | 3 | 1 | 4 | no
18 | J16 | J18 | 63 | 255.3 | 6 | 3 | 1 | 4 | no
19 | J5 | J21 | 63 | 287.1 | 6 | 3 | 1 | 4 | no
20 | J21 | J20 | 63 | 3.2 | 6 | 3 | 1 | 4 | no
21 | J21 | J20 | 63 | 37.8 | 6 | 3 | 1 | 4 | no
22 | J21 | J23 | 63 | 181.4 | 6 | 3 | 1 | 4 | no
23 | J21 | J23 | 63 | 4.6 | 6 | 3 | 1 | 4 | no
24 | J23 | J24 | 63 | 53.1 | 6 | 3 | 1 | 4 | no
25 | J23 | J26 | 63 | 45.2 | 6 | 3 | 1 | 4 | no
26 | J23 | J26 | 63 | 21.9 | 6 | 3 | 1 | 4 | no
27 | J26 | J27 | 63 | 4.9 | 6 | 3 | 1 | 4 | no
28 | J5 | J6 | 63 | 84.9 | 6 | 3 | 1 | 4 | no
29 | J26 | J27 | 63 | 52 | 6 | 3 | 1 | 4 | no
30 | J26 | J40 | 63 | 48.9 | 6 | 3 | 1 | 4 | no
31 | J26 | J40 | 63 | 15.8 | 6 | 3 | 1 | 4 | no
32 | J40 | J41 | 63 | 98.7 | 6 | 3 | 1 | 4 | no
33 | J40 | J52 | 63 | 12.9 | 6 | 3 | 1 | 4 | no
34 | J40 | J52 | 63 | 17.4 | 6 | 3 | 1 | 4 | no
35 | J40 | J52 | 63 | 8.6 | 6 | 3 | 1 | 4 | no
36 | J40 | J52 | 63 | 4.9 | 6 | 3 | 1 | 4 | no
37 | J52 | J53 | 63 | 44.3 | 6 | 3 | 1 | 4 | no
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | AMUWAHI | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | J52 | J52A | 63 | 15.2 | 5.5 | 3.3 | 1 | 4.3 | no
2 | J52A | J52B | 63 | 61.6 | 5.5 | 3.3 | 1 | 4.3 | no
3 | J52A | J73 | 63 | 22.9 | 5.5 | 3.3 | 1 | 4.3 | no
4 | J52A | J73 | 63 | 73 | 5.5 | 3.3 | 1 | 4.3 | no
5 | J52A | J73 | 63 | 3.7 | 5.5 | 3.3 | 1 | 4.3 | no
6 | J73 | J74 | 63 | 96.3 | 5.5 | 3.3 | 1 | 4.3 | no
7 | J73 | J77 | 63 | 137 | 5.5 | 3.3 | 1 | 4.3 | no
8 | J77 | J79 | 63 | 217.4 | 5.5 | 3.3 | 1 | 4.3 | no
9 | J99 | J104 | 63 | 429.7 | 5.5 | 3.3 | 1 | 4.3 | no
10 | J99 | J104 | 63 | 79.5 | 5.5 | 3.3 | 1 | 4.3 | no
11 | J104 | J103 | 63 | 216.6 | 5.5 | 3.3 | 1 | 4.3 | no
12 | J103 | J99 | 63 | 277.1 | 5.5 | 3.3 | 1 | 4.3 | no
13 | J77 | J80 | 63 | 136.4 | 5.5 | 3.3 | 1 | 4.3 | no
14 | J80 | J89 | 63 | 120.4 | 5.5 | 3.3 | 1 | 4.3 | no
15 | J90 | J103 | 63 | 240 | 5.5 | 3.3 | 1 | 4.3 | no
16 | J104 | J122 | 63 | 4.5 | 5.5 | 3.3 | 1 | 4.3 | no
17 | J104 | J122 | 63 | 212.6 | 5.5 | 3.3 | 1 | 4.3 | no
18 | J122 | J123 | 63 | 81 | 5.5 | 3.3 | 1 | 4.3 | no
19 | J122 | J126 | 63 | 219.5 | 5.5 | 3.3 | 1 | 4.3 | no
20 | J122 | J126 | 63 | 147.9 | 5.5 | 3.3 | 1 | 4.3 | no
21 | J126 | J127 | 63 | 136.2 | 5.5 | 3.3 | 1 | 4.3 | no
22 | J126 | J120 | 63 | 345 | 5.5 | 3.3 | 1 | 4.3 | no
23 | J120 | J121 | 63 | 73 | 5.5 | 3.3 | 1 | 4.3 | no
24 | J120 | J105 | 63 | 151.6 | 5.5 | 3.3 | 1 | 4.3 | no
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | AMUWAHI | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | J25 | J3 | 110 | 242.8 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
2 | J3 | J1 | 110 | 85.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
3 | J28 | J23 | 90 | 34.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
4 | J28 | J23 | 90 | 4.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
5 | J25 | J29 | 90 | 60.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
6 | J29 | J38 | 90 | 60 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
7 | J49 | J61 | 75 | 4 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
8 | J49 | J61 | 75 | 34.7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
9 | J45 | J34 | 75 | 56.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
10 | J45 | J34 | 75 | 91.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
11 | J38 | J71 | 75 | 164.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
12 | j90 | j89 | 63 | 22.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
13 | j90 | j91 | 63 | 108.8 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
14 | j91 | j98 | 63 | 152.8 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
15 | j98 | j105 | 63 | 265.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
16 | j98 | j105 | 63 | 5.7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
17 | j116 | j117 | 63 | 25.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
18 | j105 | j114 | 63 | 265.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
19 | j114 | j113 | 63 | 3.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
20 | j114 | j113 | 63 | 291.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
21 | j114 | j113 | 63 | 67.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
22 | J113 | J115 | 63 | 75.7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
23 | J113 | J111 | 63 | 97.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
24 | J111 | J110 | 63 | 24.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
25 | J111 | J108 | 63 | 43.7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
26 | J108 | J109 | 63 | 78.9 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
27 | J108 | J106 | 63 | 22.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
28 | J108 | J106 | 63 | 17.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
29 | J106 | J107 | 63 | 14.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
30 | J106 | J101 | 63 | 143.7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
31 | J106 | J107 | 63 | 23.8 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
32 | J106 | J101 | 63 | 23.4 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
33 | J106 | J101 | 63 | 106.7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
34 | J101 | J100 | 63 | 17.7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
35 | J101 | J100 | 63 | 64.7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
36 | J101 | J100 | 63 | 11.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
37 | J101 | J100 | 63 | 27.7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | AMUWAHI | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | J34 | J28 | 90 | 79 | 5.5 | 3.3 | 1 | 4.3 | no
2 | J34 | J28 | 90 | 3.1 | 5.5 | 3.3 | 1 | 4.3 | no
3 | J45 | J49 | 75 | 38.6 | 5.5 | 3.3 | 1 | 4.3 | no
4 | J45 | J49 | 75 | 41.1 | 5.5 | 3.3 | 1 | 4.3 | no
5 | J101 | J100 | 63 | 18.4 | 5.5 | 3.3 | 1 | 4.3 | no
6 | J100 | J105 | 63 | 235.3 | 5.5 | 3.3 | 1 | 4.3 | no
7 | J101 | J92 | 63 | 93.5 | 5.5 | 3.3 | 1 | 4.3 | no
8 | J92 | J93 | 63 | 228.7 | 5.5 | 3.3 | 1 | 4.3 | no
9 | J92 | J72A | 63 | 110.4 | 5.5 | 3.3 | 1 | 4.3 | no
10 | J92 | J72A | 63 | 129.2 | 5.5 | 3.3 | 1 | 4.3 | no
11 | J72A | J72B | 63 | 35.7 | 5.5 | 3.3 | 1 | 4.3 | no
12 | J72A | J72B | 63 | 49.4 | 5.5 | 3.3 | 1 | 4.3 | no
13 | J72A | J100 | 63 | 92.5 | 5.5 | 3.3 | 1 | 4.3 | no
14 | J100 | J72 | 63 | 263.1 | 5.5 | 3.3 | 1 | 4.3 | no
15 | J72A | J64 | 63 | 18 | 5.5 | 3.3 | 1 | 4.3 | no
16 | J64 | J65 | 63 | 15.5 | 5.5 | 3.3 | 1 | 4.3 | no
17 | J65 | J66 | 63 | 13.6 | 5.5 | 3.3 | 1 | 4.3 | no
18 | J65 | J66 | 63 | 11.6 | 5.5 | 3.3 | 1 | 4.3 | no
19 | J65 | J67 | 63 | 46.4 | 5.5 | 3.3 | 1 | 4.3 | no
20 | J67 | J68 | 63 | 26.9 | 5.5 | 3.3 | 1 | 4.3 | no
21 | J67 | J68 | 63 | 21.4 | 5.5 | 3.3 | 1 | 4.3 | no
22 | J67 | J70 | 63 | 39.7 | 5.5 | 3.3 | 1 | 4.3 | no
23 | J67 | J70 | 63 | 58.2 | 5.5 | 3.3 | 1 | 4.3 | no
24 | J64 | J61 | 63 | 42.4 | 5.5 | 3.3 | 1 | 4.3 | no
25 | J61 | J59 | 63 | 53.7 | 5.5 | 3.3 | 1 | 4.3 | no
26 | J59 | J60 | 63 | 47.6 | 5.5 | 3.3 | 1 | 4.3 | no
27 | J59 | J57 | 63 | 118.5 | 5.5 | 3.3 | 1 | 4.3 | no
28 | J57 | J58 | 63 | 127.6 | 5.5 | 3.3 | 1 | 4.3 | no
29 | J57 | J55 | 63 | 286 | 5.5 | 3.3 | 1 | 4.3 | no
30 | J55 | J56 | 63 | 229.3 | 5.5 | 3.3 | 1 | 4.3 | no
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | AMUWAHI | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | J55 | J44 | 63 | 178.3 | 5.5 | 3.3 | 1 | 4.3 | no
2 | J44 | J45 | 63 | 148.4 | 5.5 | 3.3 | 1 | 4.3 | no
3 | J44 | J45 | 63 | 142 | 5.5 | 3.3 | 1 | 4.3 | no
4 | J49 | J37 | 63 | 10.4 | 5.5 | 3.3 | 1 | 4.3 | no
5 | J49 | J61 | 63 | 75.7 | 5.5 | 3.3 | 1 | 4.3 | no
6 | J49 | J61 | 63 | 3.2 | 5.5 | 3.3 | 1 | 4.3 | no
7 | J34 | J49 | 63 | 35.3 | 5.5 | 3.3 | 1 | 4.3 | no
8 | J28 | J35 | 63 | 58.2 | 5.5 | 3.3 | 1 | 4.3 | no
9 | J35 | J36 | 63 | 4 | 5.5 | 3.3 | 1 | 4.3 | no
10 | J35 | J36 | 63 | 69 | 5.5 | 3.3 | 1 | 4.3 | no
11 | J35 | J44A | 63 | 75.7 | 5.5 | 3.3 | 1 | 4.3 | no
12 | J44A | J44 | 63 | 83.2 | 5.5 | 3.3 | 1 | 4.3 | no
13 | J71 | J84 | 63 | 155.8 | 5.5 | 3.3 | 1 | 4.3 | no
14 | J84 | 87 | 63 | 50.1 | 5.5 | 3.3 | 1 | 4.3 | no
15 | J87 | 91 | 63 | 108.1 | 5.5 | 3.3 | 1 | 4.3 | no
16 | J87 | 91 | 63 | 4.5 | 5.5 | 3.3 | 1 | 4.3 | no
17 | J90 | J90A | 63 | 4 | 5.5 | 3.3 | 1 | 4.3 | no
18 | J90 | J90A | 63 | 51 | 5.5 | 3.3 | 1 | 4.3 | no
19 | J86 | J85 | 63 | 52.4 | 5.5 | 3.3 | 1 | 4.3 | no
20 | J86 | J85 | 63 | 2.8 | 5.5 | 3.3 | 1 | 4.3 | no
21 | J85 | J89 | 63 | 30.3 | 5.5 | 3.3 | 1 | 4.3 | no
22 | J83 | J85 | 63 | 32.6 | 5.5 | 3.3 | 1 | 4.3 | no
23 | J83 | J78 | 63 | 57.3 | 5.5 | 3.3 | 1 | 4.3 | no
24 | J83 | J78 | 63 | 2.2 | 5.5 | 3.3 | 1 | 4.3 | no
25 | J83 | J78 | 63 | 46.9 | 5.5 | 3.3 | 1 | 4.3 | no
26 | J83 | J78 | 63 | 138.5 | 5.5 | 3.3 | 1 | 4.3 | no
27 | J78 | J71 | 63 | 234.5 | 5.5 | 3.3 | 1 | 4.3 | no
28 | J29 | J30 | 63 | 4.8 | 5.5 | 3.3 | 1 | 4.3 | no
29 | J29 | J30 | 63 | 9 | 5.5 | 3.3 | 1 | 4.3 | no
30 | J30 | J32 | 63 | 107 | 5.5 | 3.3 | 1 | 4.3 | no
31 | J32 | J33 | 63 | 16.6 | 5.5 | 3.3 | 1 | 4.3 | no
32 | J31 | J32 | 63 | 8.4 | 5.5 | 3.3 | 1 | 4.3 | no
33 | J30 | J37 | 63 | 44.6 | 5.5 | 3.3 | 1 | 4.3 | no
34 | J3 | J10 | 63 | 82.5 | 5.5 | 3.3 | 1 | 4.3 | no
35 | J3 | J10 | 63 | 24.3 | 5.5 | 3.3 | 1 | 4.3 | no
36 | J3 | J10 | 63 | 31 | 5.5 | 3.3 | 1 | 4.3 | no
37 | J87 | J88 | 63 | 49.5 | 5.5 | 3.3 | 1 | 4.3 | no
38 | J84 | J94 | 63 | 4 | 5.5 | 3.3 | 1 | 4.3 | no
39 | J84 | J94 | 63 | 151.7 | 5.5 | 3.3 | 1 | 4.3 | no
40 | J94 | J95 | 63 | 39.9 | 5.5 | 3.3 | 1 | 4.3 | no
41 | J95 | J96 | 63 | 10 | 5.5 | 3.3 | 1 | 4.3 | no
42 | J95 | J97 | 63 | 173 | 5.5 | 3.3 | 1 | 4.3 | no
43 | J97 | J94 | 63 | 75.3 | 5.5 | 3.3 | 1 | 4.3 | no
44 | J97 | J98 | 63 | 60.6 | 5.5 | 3.3 | 1 | 4.3 | no
45 | J97 | J98 | 63 | 4 | 5.5 | 3.3 | 1 | 4.3 | no
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date