## aurangabad (2)
GOVERNMENT OF UTTAR PRADESH
STATE WATER & SANITATION MISSION ( SWSM )
Joint Measurement Report of Pipe Line
Name of the Work :- Survey , Design Preparation of DPR , Construction , Commissioning and O&M for 10 Years of Various Rural Water Supply Projects in the state of Uttar Pradesh as Per Request for Proposal for Division " Prayagraj "
Name of the Agency : POWER MECH PROJECTS LIMITED – BHOORATHNOM CONSTRUCTIONS COMPANY PRIVATE LIMITED (JV), Hyderabad.
Name OF Scheme |  | :AURANGABAD
Block |  | : Mangraura
Total Scope |  | :
JMR No. |  | : 1
Date of JMR |  | :ROAD RESTORATION
Sr. No. | Start Node | End Node | Dia | Pipe Length (as per Drawing) | Pipe Length (as per Site) | Width | Depth | Quantity | Type OF Road | Dismantling Length | Dismantling Width | Dismantling Quantity | Restoration Length | Restoration Width | Restoration Quantity | Restoration Status | Remark
1 | 137 | 128 | 75 |  | 11.7 | 0.375 | 1.07 |  | interlocking | 11.7 | 0.46 | 5.382 | 11.7 | 0.46 | 5.382
2 | 128 | 135 | 63 | 206 | 121.9 | 0.36 | 1.06 |  | interlocking | 121.9 | 0.46 | 56.074 | 121.9 | 0.46 | 56.074
3 | 135a | 135b | 63 |  | 6 | 0.36 | 1.06 |  | interlocking | 6 | 0.46 | 2.76 | 6 | 0.46 | 2.76
4 | 130 | 126 | 63 | 247 | 50.2 | 0.36 | 1.06 |  | brick road | 50.2 | 0.36 | 18.072 | 50.2 | 0.36 | 18.072
5 | 128 | 126 | 75 | 133 | 20 | 0.375 | 1.07 |  | interlocking | 20 | 0.46 | 9.2 | 20 | 0.46 | 9.2
6 | 128 | 126 | 75 |  | 19.7 | 0.375 | 1.07 |  | culvert
7 | 126 | 56 | 75 |  | 128.5 | 0.375 | 1.07 |  | b.t road | 128.5 | 0.375 | 48.1875 | 128.5 | 0.375 | 48.1875
8 | 126 | 56 | 75 |  | 7 | 0.375 | 1.07 |  | b.t road crossing | 7 | 0.375 | 2.625 | 7 | 0.375 | 2.625
9 | 56 | 122 | 160 |  | 56.9 | 0.46 | 1.16 |  | interlocking | 56.9 | 0.46 | 26.174 | 56.9 | 0.46 | 26.174
10 | 56 | 122 | 160 |  | 4.2 | 0.46 | 1.16 |  | brick road | 4.2 | 0.46 | 1.932 | 4.2 | 0.46 | 1.932
11 | 122 | 124 | 160 | 129 | 6 | 0.46 | 1.16 |  | b.t road crossing | 6 | 0.46 | 2.76 | 6 | 0.46 | 2.76
12 | 143 | 145 | 160 |  | 5.9 | 0.46 | 1.16 |  | b.t crossing | 5.9 | 0.46 | 2.714 | 5.9 | 0.46 | 2.714
13 | 145 | 144 | 75 |  | 9.8 | 0.375 | 1.07 |  | b.t crossing | 9.8 | 0.375 | 3.675 | 9.8 | 0.375 | 3.675
14 | 144 | 149 | 140 |  | 63.2 | 0.44 | 1.14 |  | interlocking | 63.2 | 0.46 | 29.072 | 63.2 | 0.46 | 29.072
15 | 149 | 154 | 140 | 351 | 6 | 0.44 | 1.14 |  | b.t crossing | 6 | 0.44 | 2.64 | 6 | 0.44 | 2.64
16 | 149 | 154 | 140 |  | 152.1 | 0.44 | 1.14 |  | brick road | 152.1 | 0.44 | 66.924 | 152.1 | 0.44 | 66.924
17 | 149 | 154 | 140 |  | 14.7 | 0.44 | 1.14 |  | brick road | 14.7 | 0.44 | 6.468 | 14.7 | 0.44 | 6.468
18 | 154 | 164 | 110 | 232 | 91.6 | 0.41 | 1.1 |  | brick road | 91.6 | 0.41 | 37.556 | 91.6 | 0.41 | 37.556
19 | 164 | 166 | 160 |  | 31 | 0.46 | 1.14 |  | brick road | 31 | 0.46 | 14.26 | 31 | 0.46 | 14.26
20 | 172 | 166 | 160 | 129 | 128.7 | 0.46 | 1.14 |  | brick road | 128.7 | 0.46 | 59.202 | 128.7 | 0.46 | 59.202
21 | 154 | 160 | 63 |  | 92.2 | 0.36 | 1.06 |  | brick road | 92.2 | 0.36 | 33.192 | 92.2 | 0.36 | 33.192
#REF! | 144 | 122 | 140 |  | 6.8 | 0.44 | 1.14 |  | culvert
22 | 144 | 122 | 140 |  | 192 | 0.44 | 1.14 |  | interlocking | 192 | 0.46 | 88.32 | 192 | 0.46 | 88.32
23 | 144 | 122 | 140 |  | 8 | 0.44 | 1.14 |  | culvert
23 | 224 | 228 | 90 | 55 | 53.2 | 0.39 | 1.09 |  | brick road | 53.2 | 0.39 | 20.748 | 53.2 | 0.39 | 20.748
24 | 228 | 231 | 90 | 10 | 10.8 | 0.39 | 1.09 |  | brick road | 10.8 | 0.39 | 4.212 | 10.8 | 0.39 | 4.212
25 | 228 | 225 | 63 | 98 | 3.1 | 0.36 | 1.06 |  | brick road | 3.1 | 0.36 | 1.116 | 3.1 | 0.36 | 1.116
26 | 225 | 228 | 90 | 47 | 5.6 | 0.39 | 1.09 |  | b.t road crossing | 5.6 | 0.39 | 2.184 | 5.6 | 0.39 | 2.184
27 | 230 | 236 | 90 | 259 | 177.4 | 0.39 | 1.09 |  | brick road | 177.4 | 0.39 | 69.186 | 177.4 | 0.39 | 69.186
28 | 223 | 193 | 90 |  | 7 | 0.39 | 1.09 |  | b.t crossing | 7 | 0.39 | 2.73 | 7 | 0.39 | 2.73 |  |  | 203.2
29 | 193 | 195 | 140 | 93 | 7.4 | 0.44 | 1.14 |  | culvert | [8 empty] | 89.6
30 | 181 | 187 | 140 | 113 | 44.7 | 0.44 | 1.14 |  | interlockng | 44.7 | 0.46 | 20.562 | 44.7 | 0.46 | 20.562
31 | 187 | 193 | 140 |  | 5 | 0.44 | 1.14 |  | b.t crossing | 5 | 0.44 | 2.2 | 5 | 0.44 | 2.2
32 | 181 | 179 | 160 | 55 | 29.7 | 0.46 | 1.16 |  | interlocking | 29.7 | 0.46 | 13.662 | 29.7 | 0.46 | 13.662
33 | 181 | 179 | 160 |  | 55.3 | 0.46 | 1.16 |  | cc road | 55.3 | 0.46 | 25.438 | 55.3 | 0.46 | 25.438
34 | 179 | 178 | 160 | 148 | 151.5 | 0.46 | 1.16 |  | cc road | 151.5 | 0.46 | 69.69 | 151.5 | 0.46 | 69.69
35 | 178 | 206 | 160 | 361 | 373.2 | 0.46 | 1.16 |  | cc road | 373.2 | 0.46 | 171.672 | 373.2 | 0.46 | 171.672
36 | 206 | 213 | 160 | 130 | 184.5 | 0.46 | 1.16 |  | b.t road | 184.5 | 0.46 | 84.87 | 184.5 | 0.46 | 84.87
37 | 213 | 218 | 140 | 179 | 31 | 0.44 | 1.14 |  | b.t road | 31 | 0.44 | 13.64 | 31 | 0.44 | 13.64
38 | 172 | 178 | 160 | 424 | 423.2 | 0.46 | 1.16 |  | cc road | 423.2 | 0.46 | 194.672 | 423.2 | 0.46 | 194.672
39 | 198 | 199 | 140 | 138 | 141.5 | 0.44 | 1.14 |  | brick road | 141.5 | 0.44 | 62.26 | 141.5 | 0.44 | 62.26
40 | 199 | 207 | 75 | 148 | 29 | 0.375 | 1.07 |  | brick road | 29 | 0.375 | 10.875 | 29 | 0.375 | 10.875
41 | 199 | 207 | 75 |  | 5 | 0.375 | 1.07 |  | interlocking | 5 | 0.46 | 2.3 | 5 | 0.46 | 2.3
42 | 199 | 207 | 75 |  | 41 | 0.375 | 1.07 |  | brick road | 41 | 0.375 | 15.375 | 41 | 0.375 | 15.375
43 | 22 | 38 | 160 |  | 5 | 0.46 | 1.16 |  | b.t crossing | 5 | 0.46 | 2.3 | 5 | 0.46 | 2.3
44 | 1 | 3 | 63 |  | 82.2 | 0.36 | 1.06 |  | brick road | 82.2 | 0.36 | 29.592 | 82.2 | 0.36 | 29.592
45 | 23 | 27 | 200 | 152 | 158.8 | 0.46 | 1.2 |  | b.t road | 158.8 | 0.46 | 73.048 | 158.8 | 0.46 | 73.048
46 | 27 | 30 | 63 | 322 | 5 | 0.36 | 1.06 |  | b.t crossing | 5 | 0.36 | 1.8 | 5 | 0.36 | 1.8
47 | 27 | 37 | 200 | 168 | 172.3 | 0.46 | 1.2 |  | b.t road | 172.3 | 0.46 | 79.258 | 172.3 | 0.46 | 79.258
48 | 37 | 42 | 200 | 472 | 481.1 | 0.46 | 1.2 |  | b.t road | 481.1 | 0.46 | 221.306 | 481.1 | 0.46 | 221.306
49 | 42 | 43 | 200 | 14 | 98 | 0.46 | 1.2 |  | interlocking | 98 | 0.46 | 45.08 | 98 | 0.46 | 45.08
50 | 41 | 122 | 140 | 453 | 472 | 0.44 | 1.14 |  | brick road | 472 | 0.44 | 207.68 | 472 | 0.44 | 207.68
51 | 42 | 48 | 140 | 203 | 211.8 | 0.44 | 1.14 |  | b.t road | 211.8 | 0.44 | 93.192 | 211.8 | 0.44 | 93.192
52 | 48 | 57 | 140 | 136 | 110.5 | 0.44 | 1.14 |  | b.t road | 110.5 | 0.44 | 48.62 | 110.5 | 0.44 | 48.62
53 | 48 | 57 | 140 |  | 25.6 | 0.44 | 1.14 |  | interlocking | 25.6 | 0.46 | 11.776 | 25.6 | 0.46 | 11.776
54 | 57 | 58 | 63 | 115 | 55.8 | 0.36 | 1.06 |  | brick road | 55.8 | 0.36 | 20.088 | 55.8 | 0.36 | 20.088
55 | 82 | 71 | 75 | 69 | 62 | 0.375 | 1.07 |  | brick road | 62 | 0.375 | 23.25 | 62 | 0.375 | 23.25
56 | 57 | 62 | 140 | 142 | 139.1 | 0.44 | 1.07 |  | interlocking | 139.1 | 0.46 | 63.986 | 139.1 | 0.46 | 63.986
57 | 62 | 92 | 140 | 213 | 220 | 0.44 | 1.14 |  | b.t road | 220 | 0.44 | 96.8 | 220 | 0.44 | 96.8
58 | 95 | 96 | 63 | 48 | 5 | 0.36 | 1.06 |  | b.t crossing | 5 | 0.36 | 1.8 | 5 | 0.36 | 1.8
59 | 92 | 101 | 110 | 138 | 142.2 | 0.41 | 1.1 |  | brick road | 142.2 | 0.41 | 58.302 | 142.2 | 0.41 | 58.302
60 | 104 | 106 | 110 | 116 | 119.6 | 0.41 | 1.1 |  | brick road | 119.6 | 0.41 | 49.036 | 119.6 | 0.41 | 49.036
61 | 116 | 119 | 63 | 35 | 3 | 0.36 | 1.06 |  | brick road | 3 | 0.36 | 1.08 | 3 | 0.36 | 1.08
62 | 108 | 109 | 75 | 45 | 48 | 0.375 | 1.07 |  | brick road | 48 | 0.375 | 18 | 48 | 0.375 | 18
#REF! | 108 | 103 | 75 |  | 6 | 0.375 | 1.07 |  | culvert
63 | 173 | 174 | 63 | 83 | 107.5 | 0.36 | 1.06 |  | interlocking | 107.5 | 0.46 | 49.45 | 107.5 | 0.46 | 49.45
64 | 59 | 61 | 140 | 40 | 75.1 | 0.44 | 1.14 |  | interlocking | 75.1 | 0.46 | 34.546 | 75.1 | 0.46 | 34.546
[5 empty] | 5818.8 | [6 empty] | 2534.5715 |  |  | 2534.5715
Representative PMPL - BRCCPL (JV) Pratapgarh | [6 empty] | Representative Medhaj Techno Concept Pvt Ltd (TPI) Pratapgarh |  |  |  |  | Representative UP Jal Nigam (Rural) Pratapgarh

## persanda
persanda (RESTORATION)
Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | Dia of pipe | Pipe Length (M) AS PER SITE
1 | j52 | j53 | B.T ROAD | 0.363 | 63 | 3 | 575.9J4:K28 | 1.063
2 | j30 | j31 | BRICK ROAD | 0.363 | 63 | 53.6 | 650.4 | 1.063
3 | J29A | J29 | BRICK ROAD | 0.363 | 63 | 22.3 | 700.9 | 1.063
4 | J30 | J29A | BRICK ROAD | 0.363 | 63 | 30.3 | 775.1 | 1.063
5 | J29A | J29B | BRICK ROAD | 0.363 | 63 | 2.8 | 777.9 | 1.063
6 | J29 | J23 | BRICK ROAD | 0.363 | 63 | 2.6 | 814.9 | 1.063
7 | J13 | J19 | B.T ROAD | 0.363 | 63 | 7.3 | 1226.1 | 1.063
8 | J32 | J30 | BRICK ROAD | 0.363 | 63 | 62.7 | 1692.3 | 1.063
9 | J87 | J90A | BRICK ROAD | 0.39 | 90 | 78.9 | 1771.2 | 1.09
10 | J11 | J12 | B.T ROAD | 0.375 | 75 | 4.5 | 1838.9 | 1.075
11 | J78 | J77 | BRICK ROAD | 0.363 | 63 | 3.5 | 1982.9 | 1.063
12 | J92 | J92A | BRICK ROAD | 0.363 | 63 | 10.1 | 2769.3 | 1.063
13 | J92 | J92B | BRICK ROAD | 0.363 | 63 | 38.1 | 2807.4 | 1.063
14 | J69 | J72 | INTERLOCKING | 0.363 | 63 | 67.8 | 3261 | 1.063
15 | J90A | J90 | BRICK ROAD | 0.375 | 75 | 55.6 | 3521.7 | 1.075
16 | J70 | J67 | C.C. | 0.39 | 90 | 200.1 | 4036.6 | 1.09
17 | J70 | J67 | BRICK ROAD | 0.39 | 90 | 41.8 | 4078.4 | 1.09
18 | J68 | J69 | B.T ROAD | 0.39 | 90 | 5.3 | 4300.8 | 1.09
19 | J37 | J35 | B.T ROAD | 0.41 | 110 | 4.3 | 4305.1 | 1.11
20 | J37 | J38 | B.T ROAD | 0.41 | 110 | 6.3 | 4339.1 | 1.11
21 | J20 | J13 | B.T ROAD | 0.425 | 125 | 6 | 5003.1 | 1.125
22 | J11 | J5 | BRICK ROAD | 0.425 | 125 | 45.9 | 5155.9 | 1.125
23 | J82 | J85 | INTERLOCKING | 0.46 | 160 | 487.1 | 5913.7 | 1.16
24 | J82 | J85 | B.T ROAD | 0.46 | 160 | 6 | 5919.7 | 1.16
25 | J85 | J87 | B.T ROAD | 0.46 | 160 | 86.3 | 6006 | 1.16
26 | J85 | J87 | BRICK ROAD | 0.46 | 160 | 2.8 | 6008.8 | 1.16
27 | J67 | J26 | BRICK ROAD | 0.46 | 200 | 186.2 | 6208.8 | 1.2
28 | J26 | J27 | BRICK ROAD | 0.46 | 200 | 38.4 | 6247.2 | 1.2
29 | J17 | J14 | BRICK ROAD | 0.46 | 200 | 12.8 | 6260 | 1.2
30 | J14 | J78 | BRICK ROAD | 0.46 | 160 | 156.1 | 6416.1 | 1.16
31 | J68 | J82 | BT.ROAD | 0.46 | 160 | 5.4 | 6421.5 | 1.16
32 | J68 | J82 | BT.ROAD | 0.46 | 160 | 5.9 | 6427.4 | 1.16
33 | J68 | J82 | INTERLOCKING | 0.46 | 160 | 179.1 | 7040.6 | 1.16
34 | J3 | J78 | INTERLOCKING | 0.46 | 200 | 24.9 | 7065.5 | 1.2
35 | J3 | J78 | BRICK ROAD | 0.46 | 200 | 18.4 | 7083.9 | 1.2

## ATTARASAND AGS
ATTARSAND AND PARASPUR(RESTORATION)
Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | Dia of pipe | Pipe Length (M) | [5 empty] | CUMMULATIVE | RESTORATION
[7 empty] | 75mm | 90mm | 110mm | 160mm | 200mm
1 | j735 | j708 | brick road | 0.39 | 63 | 98 | [5 empty] | #REF! | 98
2 | j97 | j274 | brick road | 0.39 | 75 | 36 | [5 empty] | #REF! | 36
3 | j274 | j378 | brick road | 0.39 | 75 | 55 | [5 empty] | #REF! | 55
4 | j694 | j700 | brick road | 0.39 | 75 | 41.1 | [5 empty] | #REF! | 41.1
5 | j700 | j301 | brick road | 0.39 | 75 | 16 | [5 empty] | #REF! | 16
6 | j700 | j604 | brick road | 0.39 | 75 | 35.6 | [5 empty] | #REF! | 35.6
7 | j604 | j505 | brick road | 0.39 | 75 | 64 | [5 empty] | #REF! | 64
8 | J58 | J92 | INTERLOCKING | 0.39 | 90 | 100.2 | [5 empty] | #REF! | 100
9 | j170 | j252 | brick road | 0.39 | 90 | 47 | [5 empty] | #REF! | 47
10 | j252 | j735 | brick road | 0.39 | 90 | 190.2 | [5 empty] | #REF! | 270
11 | j735 | j252 | brick road | 0.39 | 90 | 153 | [5 empty] | #REF! | 153
12 | j725 | j340 | brick road | 0.39 | 90 | 74 | [5 empty] | #REF! | 74
13 | j474 | j499 | brick road | 0.44 | 110 | 39 | [5 empty] | #REF! | 39
14 | j158 | j170 | brick road | 0.44 | 110 | 10 | [5 empty] | #REF! | 10
15 | j505 | j488 | brick road | 0.44 | 110 | 40 | [5 empty] | #REF! | 40
16 | J99 | J75 | INTERLOCKING | 0.44 | 160 | 255.85 | [5 empty] | #REF! | 256
17 | j505 | j373 | brick road | 0.44 | 160 | 47 | [5 empty] | #REF! | 47
18 | j373 | j474 | brick road | 0.44 | 160 | 50 | [5 empty] | #REF! | 50
19 | j373 | j723 | brick road | 0.44 | 200 | 68 | [5 empty] | #REF! | 68
MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT. |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  |  | SIGN.with date |  |  |  | SIGN.with date
#REF!

## PURBHIKA AND RAIGARH
PUREBHIKA AND RAIGARH(RESTORATION)
Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | Dia of pipe | Pipe Length (M) AS PER SITE
1 | J60 | J66 | BRICK ROAD | 0.36 | 63 | 93
2 | J242 | J180 | BRICK ROAD | 0.36 | 63 | 53.4
3 | J242 | J167 | BRICK ROAD | 0.36 | 63 | 64.8
4 | J171 | J235 | INTERLOCKING | 0.36 | 63 | 39.8
5 | J218 | J208 | INTERLOCKING | 0.36 | 63 | 33.2
6 | J208 | J171 | INTERLOCKING | 0.36 | 63 | 33.2
7 | J306 | J305 | BRICK ROAD | 0.36 | 63 | 287.5
8 | J340 | J335 | BRICK ROAD | 0.36 | 63 | 88.9
9 | J340 | J311 | BRICK ROAD | 0.36 | 63 | 203
10 | J347 | J370 | BRICK ROAD | 0.36 | 63 | 29.9
11 | J370 | J365 | BRICK ROAD | 0.36 | 63 | 100.3
12 | J286 | J277 | BRICK ROAD | 0.36 | 63 | 27
13 | J277 | J273 | BRICK ROAD | 0.36 | 63 | 77.1
14 | J293 | J277 | BRICK ROAD | 0.36 | 63 | 82
15 | J196 | J303 | INTERLOCKING | 0.36 | 63 | 120.4
16 | J303 | J285 | INTERLOCKING | 0.36 | 63 | 117.1
17 | J299 | J293 | INTERLOCKING | 0.36 | 63 | 17.4
18 | J150 | 279 | B.T ROAD | 0.36 | 63 | 6
19 | J246 | J227 | B.T ROAD | 0.36 | 63 | 4
20 | j161 | j166 | brick road | 0.36 | 63 | 66.4
21 | j166 | j174 | brick road | 0.36 | 63 | 24.2
22 | j174 | j221 | brick road | 0.36 | 63 | 122.6
23 | j247 | j257 | b.t road | 0.36 | 63 | 5
24 | j253 | j248 | INTERLOCKING | 0.36 | 63 | 40
25 | j248 | j270 | INTERLOCKING | 0.36 | 63 | 34
26 | J270 | J278 | INTERLOCKING | 0.36 | 63 | 21.3
27 | J248 | J226 | BRICK ROAD | 0.36 | 63 | 81
28 | J33 | J11 | BRICK ROAD | 0.36 | 63 | 33.8
29 | J354 | J347 | BRICK ROAD | 0.36 | 63 | 29.8
30 | J347 | J371 | BRICK ROAD | 0.36 | 63 | 89.3
31 | J297 | J292 | B.T ROAD | 0.36 | 63 | 7
32 | J339 | J343 | BRICK ROAD | 0.37 | 75 | 18
33 | J343 | J333 | BRICK ROAD | 0.37 | 75 | 31
34 | J333 | J358 | BRICK ROAD | 0.37 | 75 | 82.4
35 | j221 | j227 | b.t road | 0.39 | 90 | 6.2
36 | j101 | j179 | brick road | 0.39 | 90 | 4.3
37 | J69 | J70 | B.T ROAD | 0.44 | 140 | 6.4
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  | SIGN.with date | 877
396

## Kansapatti
KANSAPATTI(RESTORATION)
Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | Dia of pipe | Pipe Length (M) AS PER SITE
1 | J4 | J132 | B.T. ROAD | 0.46 | 63 | 5
2 | J5 | J6 | B.T. ROAD | 0.46 | 63 | 4
3 | J5 | J8 | B.T. ROAD | 0.46 | 140 | 4.7
4 | J16 | J13 | B.T. ROAD | 0.46 | 63 | 4.7
5 | J14 | J12 | B.T. ROAD | 0.46 | 63 | 6
6 | J74 | J75 | BRICK ROAD | 0.46 | 63 | 2.8
7 | J76 | J76A | BRICK ROAD | 0.46 | 75 | 3.1
8 | J76 | J79 | BRICK ROAD | 0.46 | 75 | 42.4
9 | J84 | J87 | BRICK ROAD | 0.46 | 75 | 2.6
10 | J84 | J89 | B.T. ROAD | 0.46 | 75 | 3.2
11 | J89A | J89B | INTERLOCKING | 0.46 | 63 | 41
12 | J89B | J103 | INTERLOCKING | 0.46 | 63 | 67.6
13 | J89B | J89 | INTERLOCKING | 0.46 | 63 | 15.9
14 | J89C | J89E | INTERLOCKING | 0.46 | 63 | 13
15 | J89A | J115 | B.T. ROAD | 0.46 | 75 | 4
16 | J89A | J115 | BRICK ROAD | 0.46 | 75 | 21.6
17 | J89A | J115 | B.T. ROAD | 0.46 | 75 | 41
18 | J119 | J119 | BRICK ROAD | 0.46 | 63 | 77.6
19 | J116 | J85 | BRICK ROAD | 0.46 | 63 | 121.2
20 | J116 | J85 | B.T. ROAD | 0.46 | 63 | 3.4
21 | J115A | J115 | B.T. ROAD | 0.46 | 90 | 20
22 | J57 | J62 | BRICK ROAD | 0.46 | 63 | 50.7
23 | J51 | J48 | B.T. ROAD | 0.46 | 63 | 3.4
24 | J51 | J48 | INTERLOCKING | 0.46 | 63 | 78.8
25 | J48 | J50 | INTERLOCKING | 0.46 | 63 | 73.1
26 | J48 | J45 | INTERLOCKING | 0.46 | 63 | 2.3
27 | J19 | J33 | BRICK ROAD | 0.46 | 63 | 208
22 | J70 | J70B | INTERLOCKING | 0.46 | 63 | 212.5
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  | SIGN.with date
KANSAPATTI(RESTORATION)
Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | Dia of pipe | Pipe Length (M) AS PER SITE
1 | J74 | J75 | BRICK ROAD | 0.46 | 63 | 2.8
2 | J76 | J76A | BRICK ROAD | 0.46 | 75 | 3.1
3 | J76 | J79 | BRICK ROAD | 0.46 | 75 | 41.9
4 | J84 | J87 | BRICK ROAD | 0.46 | 75 | 2.6
5 | J89A | J89B | INTERLOCKING | 0.46 | 63 | 41
6 | J89B | J103 | INTERLOCKING | 0.46 | 63 | 67.6
7 | J89B | J89C | INTERLOCKING | 0.46 | 63 | 15.9
8 | J89C | J89E | INTERLOCKING | 0.46 | 63 | 13
9 | J89A | J115 | BRICK ROAD | 0.46 | 75 | 21.6
10 | J119 | J119 | BRICK ROAD | 0.46 | 63 | 77.6
11 | J116 | J85 | BRICK ROAD | 0.46 | 63 | 120.2
12 | J57 | J62 | BRICK ROAD | 0.46 | 63 | 50.7
13 | J51 | J48 | INTERLOCKING | 0.46 | 63 | 78.8
14 | J48 | J50 | INTERLOCKING | 0.46 | 63 | 73.1
15 | J48 | J45 | INTERLOCKING | 0.46 | 63 | 2.3
16 | J19 | J33 | BRICK ROAD | 0.46 | 63 | 208
17 | J69 | J70 | INTERLOCKING | 0.46 | 63 | 140.3
18 | J70 | J70B | INTERLOCKING | 0.46 | 63 | 212.5
19 | J99 | J94 | INTERLOCKING | 0.46 | 63 | 21.6
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  | SIGN.with date

## Dharouli(lauli)
DHAROULI(RESTORATION)
Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | Dia of pipe | Pipe Length (M) AS PER SITE
1 | J184 | 183 | BOE | 0.41 | 63 | 63.4 |  | 25.994
2 | 184 | 228 | BOE | 0.41 | 63 | 20.5 |  | 8.405
3 | 228 | 225 | BOE | 0.41 | 63 | 21 |  | 8.61
4 | 228 | 246 | BOE | 0.41 | 63 | 40.8 |  | 16.728
5 | 246 | 242 | BOE | 0.41 | 63 | 43 |  | 17.63
6 | 242 | 226 | BOE | 0.41 | 63 | 96.1 |  | 39.401
7 | 242 | 179 | BOE | 0.41 | 63 | 81 |  | 33.21
8 | 178 | 152 | BOE | 0.41 | 63 | 28 |  | 11.48
9 | 152 | 167 | BOE | 0.41 | 63 | 25 |  | 10.25
10 | 170 | 127 | BOE | 0.41 | 63 | 31 |  | 12.71
11 | 125 | 124 | BOE | 0.41 | 63 | 63 |  | 25.83
12 | 150 | 192 | BOE | 0.41 | 63 | 20.2 |  | 8.282
13 | 157 | 138 | B.T | 0.36 | 63 | 5 |  | 1.8
14 | 187 | 182 | B.T | 0.36 | 63 | 7.2 |  | 2.592
15 | 182 | 168 | BOE | 0.41 | 63 | 48.7 |  | 19.967
16 | 166 | 168 | BOE | 0.41 | 63 | 46.3 |  | 18.983
17 | 186 | 151 | BOE | 0.41 | 63 | 32 |  | 13.12
18 | 165 | 201 | BOE | 0.41 | 63 | 60 |  | 24.6
19 | 201 | 131 | INTERLOCKING | 0.46 | 63 | 87.5 |  | 40.25
20 | 131 | 140 | BOE | 0.41 | 63 | 75 |  | 30.75
21 | 140 | 223 | BOE | 0.41 | 63 | 86 |  | 35.26
22 | 140 | 148 | BOE | 0.41 | 63 | 63 |  | 25.83
23 | 148 | 162 | BOE | 0.41 | 63 | 12 |  | 4.92
24 | 131 | 143 | INTERLOCKING | 0.46 | 63 | 74.6 |  | 34.316
25 | 143 | 149 | INTERLOCKING | 0.46 | 63 | 78.8 |  | 36.248
26 | 169 | 230 | BOE | 0.41 | 63 | 40 |  | 16.4
27 | 202 | 240 | BOE | 0.41 | 63 | 77.3 |  | 31.693
28 | 213 | 209 | B.T | 0.36 | 63 | 5 |  | 1.8
29 | 213 | 209 | BOE | 0.41 | 63 | 97.7 |  | 40.057
30 | 213 | 187 | B.T | 0.36 | 63 | 3 |  | 1.08
31 | 233 | 208 | B.T | 0.36 | 63 | 5 |  | 1.8
32 | 179 | 184 | BOE | 0.41 | 63 | 16.7 |  | 6.847
33 | 238 | 237 | B.T | 0.36 | 63 | 3 |  | 1.08
34 | 238 | 237 | BOE | 0.41 | 63 | 127 |  | 52.07
35 | 237 | 231 | BOE | 0.41 | 63 | 130 |  | 53.3
36 | 214 | 236 | B.T | 0.36 | 63 | 3 |  | 1.08
37 | J165 | J161 | INTERLOCKING | 0.46 | 63 | 21 |  | 9.66
38 | J165 | J161 | BOE | 0.41 | 63 | 10 |  | 4.1
39 | J161 | J201 | INTERLOCKING | 0.46 | 63 | 30.3 |  | 13.938
40 | 204 | 179 | INTERLOCKING | 0.46 | 90 | 55 |  | 25.3
41 | 178 | 199 | BOE | 0.41 | 110 | 11 |  | 4.51
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  | SIGN.with date
Lauli Pokhtakham(RESTORATION)
Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | Dia of pipe | Pipe Length (M) AS PER SITE
1 | J296 | J296A | BRICK ROAD | 0.36 | 63 | 300
2 | J116A | J97 | INTERLOCKING | 0.46 | 63 | 57.1
3 | J97 | J71 | INTERLOCKING | 0.46 | 63 | 32.7
4 | J97 | J87 | INTERLOCKING | 0.46 | 63 | 40.8
5 | J87 | J89 | BRICK ROAD | 0.36 | 63 | 5.7
6 | J87 | J136A | BRICK ROAD | 0.36 | 63 | 30.1
7 | J136A | J85 | BRICK ROAD | 0.36 | 63 | 5
8 | J127 | J119 | BRICK ROAD | 0.36 | 63 | 247
9 | J126 | J118 | BRICK ROAD | 0.36 | 63 | 287.5
10 | J147 | J143A | BRICK ROAD | 0.36 | 63 | 10.8
11 | J143A | J143B | BRICK ROAD | 0.36 | 63 | 24
12 | J253 | J166 | BRICK ROAD | 0.36 | 63 | 435.5
13 | J265 | J157 | INTERLOCKING | 0.46 | 63 | 101.8
14 | J265 | J157 | BRICK ROAD | 0.36 | 63 | 40
15 | J289 | J295 | BRICK ROAD | 0.36 | 63 | 151.9
16 | J293 | J196 | BRICK ROAD | 0.36 | 63 | 223.1
17 | J196 | J152A | BRICK ROAD | 0.36 | 63 | 125.3
18 | J152A | J152 | BRICK ROAD | 0.36 | 63 | 9.7
19 | J196 | J187 | BRICK ROAD | 0.36 | 63 | 128.5
20 | J196 | J187 | BRICK ROAD | 0.36 | 63 | 62.5
21 | J261 | J271 | BRICK ROAD | 0.36 | 63 | 6.2
22 | J175 | J96 | BRICK ROAD | 0.36 | 110 | 30
23 | J295 | J170 | BRICK ROAD | 0.36 | 63 | 2.7
24 | J196 | J187 | BRICK ROAD | 0.36 | 63 | 2.3
25 | J289 | J295 | BRICK ROAD | 0.36 | 63 | 152.1
26 | J152A | J152 | BRICK ROAD | 0.36 | 63 | 9.8
27 | J196 | J187 | BRICK ROAD | 0.36 | 63 | 128.9
28 | J247 | J251 | BRICK ROAD | 0.36 | 63 | 52.9
29 | J262 | J273 | BRICK ROAD | 0.36 | 63 | 2.6
30 | J166 | J199 | BRICK ROAD | 0.36 | 63 | 131.2
31 | J199 | J201 | BRICK ROAD | 0.36 | 63 | 29.1
32 | J201 | J222A | BRICK ROAD | 0.36 | 63 | 62.7
33 | J222A | J222 | BRICK ROAD | 0.36 | 63 | 22.1
34 | J222 | J203 | BRICK ROAD | 0.36 | 63 | 47.2
35 | J222 | J186 | BRICK ROAD | 0.36 | 63 | 74.6
36 | J186 | J193 | BRICK ROAD | 0.36 | 63 | 7.8
37 | J193 | J210 | BRICK ROAD | 0.36 | 63 | 45.1
38 | J236 | J238 | BRICK ROAD | 0.36 | 63 | 2.6
39 | J240 | J257 | BRICK ROAD | 0.36 | 63 | 2.7
40 | J240 | J257 | BRICK ROAD | 0.36 | 63 | 6.4
41 | J224 | J224A | BRICK ROAD | 0.36 | 63 | 2.7
42 | J174 | J218 | INTERLOCKING | 0.46 | 63 | 24.8
43 | J218 | J195 | INTERLOCKING | 0.46 | 63 | 3
44 | J218 | J195 | BRICK ROAD | 0.36 | 63 | 2.8
45 | J18 | J6 | BRICK ROAD | 0.36 | 63 | 14
46 | J19 | J31 | BRICK ROAD | 0.36 | 63 | 32.8
47 | J11 | J15 | BRICK ROAD | 0.36 | 63 | 19.7
48 | J19 | J21 | BRICK ROAD | 0.36 | 63 | 3.8
49 | J5 | J70 | BRICK ROAD | 0.36 | 63 | 74.1
50 | J70(1) | J65(1) | BRICK ROAD | 0.36 | 63 | 2.5
51 | J49 | J55 | INTERLOCKING | 0.46 | 63 | 7.9
52 | J49 | J55 | BRICK ROAD | 0.36 | 63 | 11.2
53 | J49 | J55 | BRICK ROAD | 0.36 | 63 | 10.1
54 | J55 | J24 | INTERLOCKING | 0.46 | 140 | 4.2
55 | J56 | J50 | BRICK ROAD | 0.36 | 63 | 22.7
56 | J96 | J88 | BRICK ROAD | 0.36 | 63 | 109
57 | J88 | J94 | BRICK ROAD | 0.36 | 63 | 6.5
58 | J208 | J225 | BRICK ROAD | 0.36 | 63 | 6.1
59 | J180 | J186 | BRICK ROAD | 0.36 | 63 | 21.9
60 | J180 | J186 | BRICK ROAD | 0.36 | 63 | 8.6
61 | J206 | J168 | BRICK ROAD | 0.36 | 63 | 40.8
62 | J206 | J168 | BRICK ROAD | 0.36 | 63 | 82.2
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  | SIGN.with date
Lauli Pokhtakham(RESTORATION)
Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | Dia of pipe | Pipe Length (M) AS PER SITE
1 | J293 | J296 | B.T. ROAD | 0.36 | 63 | 9 |  |  | 9 | J293 | J296
2 | J296A | J296B | BRICK ROAD | 0.36 | 63 | 10.8 |  |  | 3.2 | J100 | J108
3 | J100 | J108 | B.T. ROAD | 0.36 | 63 | 3.2 |  |  | 3.2 | J100 | J108
4 | J100 | J108 | B.T. ROAD | 0.36 | 63 | 3.2 |  |  | 2.2 | J197 | J222A
5 | J197 | J222A | B.T. ROAD | 0.36 | 63 | 2.2 |  |  | 2.5 | J46 | J18
6 | J152A | J152B | BRICK ROAD | 0.36 | 63 | 3 |  |  | 3.6 | J19 | J31
7 | J97 | J71 | BRICK ROAD | 0.36 | 63 | 57 |  |  | 3.6 | J21 | J25
8 | J39A | J39B | BRICK ROAD | 0.36 | 63 | 2.8 |  |  | 2.4 | J33 | J20
9 | J46 | J18 | B.T. ROAD | 0.36 | 63 | 2.5 |  |  | 3.5 | J56 | J50
10 | J19 | J31 | B.T. ROAD | 0.36 | 63 | 3.6 |  |  | 3 | J67 | J50
11 | J21 | J25 | B.T. ROAD | 0.36 | 63 | 3.6
12 | J33 | J20 | B.T. ROAD | 0.36 | 63 | 2.4
13 | J180 | J169 | BRICK ROAD | 0.36 | 63 | 2.4
14 | J46 | J18 | BRICK ROAD | 0.36 | 63 | 1.3
15 | J56 | J50 | B.T. ROAD | 0.36 | 63 | 3.5
16 | J67 | J50 | B.T. ROAD | 0.36 | 63 | 3
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  | SIGN.with date

## Choumari
CHOUMARI(RESTORATION)
Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | Dia of pipe | Pipe Length (M) AS PER SITE
1 | J71 | J78 | BRICK ROAD | 0.36 | 63 | 3.1
2 | J74 | J73 | BRICK ROAD | 0.36 | 63 | 3
3 | J72 | J81 | BRICK ROAD | 0.36 | 63 | 51.4
4 | J23 | J31 | BRICK ROAD | 0.36 | 63 | 21.8
5 | J56 | J31 | BRICK ROAD | 0.36 | 63 | 29
6 | J156A | J156B | INTERLOCKING | 0.46 | 63 | 58.9
7 | J126 | J125 | BRICK ROAD | 0.36 | 63 | 14.5
8 | J126 | J125 | INTERLOCKING | 0.46 | 63 | 7.6
9 | J132A | J132B | BRICK ROAD | 0.36 | 63 | 3.6
10 | J132B | J132C | INTERLOCKING | 0.46 | 63 | 4.5
11 | J132A | J132G | INTERLOCKING | 0.46 | 63 | 3
12 | J128 | J131 | BRICK ROAD | 0.36 | 63 | 4.2
13 | J128 | J123 | BRICK ROAD | 0.36 | 63 | 3
14 | J118 | J127 | BRICK ROAD | 0.36 | 63 | 55.3
15 | J118 | J127 | BRICK ROAD | 0.36 | 63 | 75.6
16 | J118 | J127 | BRICK ROAD | 0.36 | 63 | 3
17 | J114 | J112 | BRICK ROAD | 0.36 | 63 | 49.1
18 | J114 | J111 | BRICK ROAD | 0.36 | 63 | 4.2
19 | J130 | J122 | BRICK ROAD | 0.36 | 75 | 3.8
20 | J104 | J103 | BRICK ROAD | 0.36 | 75 | 6.6
21 | J91 | J88 | INTERLOCKING | 0.46 | 160 | 5.9
22 | J91 | J88 | BRICK ROAD | 0.46 | 160 | 5.6
23 | J80 | J79 | BRICK ROAD | 0.46 | 160 | 10
24 | J56 | J39 | BRICK ROAD | 0.46 | 160 | 5.7
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  | SIGN.with date

## Barasarai
BARASARAI(JMR RESTORATION) | [7 empty] | CUMMULATIVE | Remark
Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | Dia of pipe | Pipe Length (M) | As per dpr
1 | J4 | J5 | B.T ROAD | 0.36 | 63 | 3.2 | 12 | 3.2 |  | 3.2
2 | J22 | J21 | BRICK ROAD | 0.36 | 63 | 14 |  | #REF! |  | 14
3 | J23 | J39 | BRICK ROAD | 0.36 | 63 | 23.8 | 22 | #REF! |  | 23.8
4 | J52 | J68 | BRICK ROAD | 0.36 | 63 | 55.4 |  | #REF! |  | 55.4
5 | J38 | J37 | BRICK ROAD | 0.36 | 63 | 22.1 | 25 | #REF! |  | 22.1
6 | J38 | J43 | BRICK ROAD | 0.36 | 63 | 47.5 | 45 | #REF! |  | 47.5
7 | J43 | J44 | BRICK ROAD | 0.36 | 63 | 39.9 | 44 | #REF! |  | 39.9
8 | J68 | J69 | BRICK ROAD | 0.36 | 63 | 18.4 | 11 | #REF! |  | 18.4
9 | J73 | J74 | BRICK ROAD | 0.36 | 63 | 123.5 | 124 | #REF! |  | 123.5
10 | J76 | J75 | BRICK ROAD | 0.36 | 63 | 68.2 | 42 | #REF! |  | 68.2
11 | J89 | J90 | BRICK ROAD | 0.36 | 63 | 8.4 | 165 | #REF! |  | 8.4
12 | J80 | J86 | BRICK ROAD | 0.36 | 63 | 16 |  | #REF! |  | 16
13 | J86 | J81 | BRICK ROAD | 0.36 | 63 | 96.3 | 97 | #REF! |  | 96.3
14 | J32 | J33 | BRICK ROAD | 0.36 | 63 | 34.2 | 21 | #REF! |  | 34.2
15 | J32 | J30 | BRICK ROAD | 0.36 | 63 | 73.5 | 65 | #REF! |  | 73.5
16 | J133 | J140 | B.T ROAD | 0.36 | 63 | 3 |  | #REF! |  | 3
17 | J54 | J57 | B.T ROAD | 0.36 | 63 | 3 | 134 | #REF! |  | 3
18 | J57 | J61 | B.T ROAD | 0.36 | 63 | 3 |  | #REF! |  | 3
19 | J62 | J63 | B.T ROAD | 0.36 | 63 | 3 |  | #REF! |  | 3
20 | J213 | J217 | BRICK ROAD | 0.36 | 63 | 30 |  | #REF! |  | 30
21 | J217 | J226 | BRICK ROAD | 0.36 | 63 | 28 | 80 | #REF! |  | 28
22 | J210 | J210A | BRICK ROAD | 0.36 | 63 | 70 |  | #REF! |  | 70
23 | J210A | J212 | BRICK ROAD | 0.36 | 63 | 27.5 |  | #REF! |  | 27.5
24 | J216 | J215 | B.T ROAD | 0.36 | 63 | 3 | 32 | #REF! |  | 3
25 | J216 | J215 | BRICK ROAD | 0.36 | 63 | 32 |  | #REF! |  | 32
26 | J218 | J223 | B.T ROAD | 0.36 | 63 | 3 | 66 | #REF! |  | 3
27 | J223 | J224 | B.T ROAD | 0.36 | 63 | 3 | 20 | #REF! |  | 3
28 | J223 | J224 | BRICK ROAD | 0.36 | 63 | 21 |  | #REF! |  | 21
29 | J233 | J233A | B.T ROAD | 0.36 | 63 | 3 |  | #REF! |  | 3
30 | J234 | J251 | INTERLOCKING | 0.36 | 63 | 107.3 | 176 | #REF! |  | 107.3
31 | J251 | J254 | INTERLOCKING | 0.36 | 63 | 1.5 | 11 | #REF! |  | 1.5
32 | J254 | J255 | BRICK ROAD | 0.36 | 63 | 32.1 | 85 | #REF! |  | 32.1
33 | J251 | J252 | INTERLOCKING | 0.36 | 63 | 17.8 | 18 | #REF! |  | 17.8
34 | J252 | J253 | INTERLOCKING | 0.36 | 63 | 4 | 25 | #REF! |  | 4
35 | J252 | J249 | INTERLOCKING | 0.36 | 63 | 29 | 185 | #REF! |  | 29
36 | J249 | J232 | BRICK ROAD | 0.36 | 63 | 23 |  | #REF! |  | 23
37 | J114 | J117 | INTERLOCKING | 0.36 | 63 | 16.7 | 90 | #REF! |  | 16.7
38 | J177 | J185 | BRICK ROAD | 0.36 | 63 | 227 |  | #REF! |  | 227
39 | J91 | J98 | BRICK ROAD | 0.36 | 63 | 190.8 | 198 | #REF! |  |  | 90.8
40 | J10 | J22 | BRICK ROAD | 0.37 | 75 | 88 | 158 | #REF! |  | 88
41 | J217 | J209 | BRICK ROAD | 0.37 | 75 | 62.2 | 59 | #REF! |  | 62.2
42 | J198 | J201 | INTERLOCKING | 0.39 | 90 | 5 |  | #REF! |  | 5
43 | J201 | J204 | B.T ROAD | 0.39 | 90 | 5 |  | #REF! |  | 5
44 | J204 | J197 | B.T ROAD | 0.39 | 90 | 3 |  | #REF! |  | 3
45 | J69 | J73 | BRICK ROAD | 0.41 | 110 | 50.9 | 48 | #REF! |  | 50.9
46 | J73 | J76 | BRICK ROAD | 0.41 | 110 | 16.7 |  | #REF! |  | 16.7
47 | J81 | J89 | BRICK ROAD | 0.41 | 110 | 20 | 42 | #REF! |  | 20
48 | J89 | J92 | B.T ROAD | 0.41 | 110 | 3 |  | #REF! |  | 3
49 | J89 | J92 | BRICK ROAD | 0.41 | 110 | 10 |  | #REF! |  | 15
50 | J127 | J96 | B.T ROAD | 0.41 | 110 | 6 |  | #REF! |  | 6
51 | J192 | J196 | B.T ROAD | 0.41 | 110 | 8 | 195 | #REF! |  | 8
52 | J115 | J124 | BRICK ROAD | 0.41 | 110 | 31 | 30 | #REF!
53 | J113 | J115 | BRICK ROAD | 0.42 | 125 | 87.9 | 88 | #REF!
54 | J4 | J10 | B.T ROAD | 0.44 | 140 | 3 |  | #REF! |  | 3
MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  |  | DESIGNATION
NAME |  |  |  |  | NAME
SIGN.with date |  |  |  |  | SIGN.with date
[11 empty] | POWER MECH PROJECT LIMITED -BRCPCL(JV). | MEDHAJ CONSULTANCY (THIRD PARTY INS.)
[11 empty] | DESIGNATION | DESIGNATION | DESIGNATION
[11 empty] | NAME | NAME | NAME
[11 empty] | SIGN.with date | SIGN.with date | SIGN.with date

## PADAMPUR
PADAMPUR(JMR)
Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | Dia of pipe | Pipe Length (M) | REMARKS
1 | J75 | J81 | B.T ROAD | 0.36 | 63 | 8.2
2 | J97 | J105 | B.T ROAD | 0.36 | 63 | 3.4
3 | J115 | J83 | B.T ROAD | 0.36 | 63 | 3
4 | J113 | J129 | BRICK ROAD | 0.46 | 63 | 2.6
5 | J135 | J140A | INTERLOCKING | 0.46 | 63 | 3.1
6 | J81 | J88 | B.T ROAD | 0.36 | 63 | 3.6
7 | J22 | J32 | B.T ROAD | 0.36 | 63 | 4
8 | J14 | J27 | cc road | 0.46 | 63 | 88.8
9 | J27 | J35 | cc road | 0.46 | 63 | 50.7
10 | J32 | J28 | B.T ROAD | 0.36 | 63 | 3
11 | j35 | j36 | interlocking | 0.46 | 63 | 92
12 | J5 | J42 | cc road | 0.46 | 63 | 114.6
13 | J42 | J34 | cc road | 0.46 | 63 | 21.9
14 | J64 | J52 | B.T ROAD | 0.36 | 63 | 5
15 | j131 | j143 | brick road | 0.46 | 63 | 2.6
16 | j149 | j120 | BRICK ROAD | 0.46 | 63 | 116.3
17 | J8 | J27 | cc road | 0.46 | 63 | 58.8
18 | j8 | j26 | cc road | 0.46 | 63 | 46.8
19 | j8 | j26 | cc road | 0.46 | 63 | 5.4
20 | j26 | j25 | cc road | 0.46 | 63 | 21.1
21 | j26 | j36 | cc road | 0.46 | 63 | 3
22 | J9 | J30 | cc road | 0.46 | 63 | 4.1
23 | J9 | J30 | cc road | 0.46 | 63 | 63.4
24 | J30 | J27 | cc road | 0.46 | 63 | 75.1
25 | J30 | J6 | cc road | 0.46 | 63 | 40.2
26 | j117 | j113 | BRICK ROAD | 0.46 | 63 | 50.1
27 | j110 | j128 | INTERLOCKING | 0.46 | 63 | 3.2
28 | J147 | J118 | INTERLOCKING | 0.46 | 75 | 8.6
29 | J118 | J92 | B.T ROAD | 0.38 | 75 | 4.6
30 | J80 | J84 | B.T ROAD | 0.39 | 90 | 6.6
31 | J84 | J89 | B.T ROAD | 0.39 | 90 | 3
32 | J9 | J12 | cc road | 0.46 | 160 | 4.4
MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  |  | DESIGNATION
NAME |  |  |  |  | NAME
SIGN.with date |  |  |  |  | SIGN.with date

## Malak
Malak(RESTORATION)
Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | Dia of pipe | Pipe Length (M) AS PER SITE
1 | j123 | j71 | brick road | 0.36 | 63 | 65.2
2 | j29 | j20 | brick road | 0.36 | 63 | 64.8
3 | j20 | j2 | brick road | 0.36 | 63 | 15.1
4 | j2 | j24 | brick road | 0.36 | 63 | 59.1
5 | j71 | j70 | brick road | 0.36 | 63 | 42.9
6 | j70 | j44 | brick road | 0.36 | 63 | 3
7 | j70 | j37 | brick road | 0.36 | 63 | 95.1
8 | j37 | j19 | brick road | 0.36 | 63 | 2.5
9 | j19 | j26 | brick road | 0.36 | 63 | 64.9
10 | j61 | j68 | brick road | 0.36 | 63 | 49
11 | j82 | j94 | brick road | 0.36 | 63 | 40
12 | j32 | j81 | brick road | 0.36 | 63 | 48
13 | j95 | j96 | brickroad | 0.36 | 63 | 66.4
14 | j96 | j133 | brick road | 0.36 | 63 | 100.1
15 | j96 | j82 | brick road | 0.36 | 63 | 49.5
16 | j48 | j57 | brick road | 0.36 | 63 | 33.1
17 | j57 | j77 | brick road | 0.36 | 63 | 23.7
18 | j27 | j11 | interlocking | 0.46 | 63 | 112.7
19 | j10 | j5 | brick road | 0.36 | 63 | 37.1
20 | j5 | j9 | brick road | 0.36 | 63 | 32
21 | j147 | j119 | interlocking | 0.46 | 63 | 23.7
22 | j116 | j116a | brick road | 0.36 | 63 | 165
23 | j27 | j21 | interlocking | 0.46 | 63 | 3.7
24 | j219 | j240 | brick road | 0.36 | 63 | 114.5
25 | j223 | j238 | brick road | 0.36 | 63 | 78
26 | j238 | j201 | interlocking | 0.46 | 63 | 17
27 | j201 | j217 | interlocking | 0.46 | 63 | 54.5
28 | j217 | j213 | interlocking | 0.46 | 63 | 96
29 | j217 | j220 | interlocking | 0.46 | 63 | 4.7
30 | j217 | j220 | brick road | 0.36 | 63 | 49.7
31 | j191 | j223 | brick road | 0.36 | 63 | 45.2
32 | j223a | j189 | brickroad | 0.36 | 63 | 35.5
33 | j227 | j225 | brick road | 0.36 | 63 | 29.8
34 | j225 | j224 | brickroad | 0.36 | 63 | 9
35 | j225 | j195 | brick road | 0.36 | 63 | 36.2
36 | j110 | j141 | interlocking | 0.46 | 63 | 52.6
37 | j100 | j163 | brick road | 0.36 | 63 | 69
38 | j143 | j149 | brick road | 0.36 | 63 | 26
39 | j153 | j160 | brick road | 0.36 | 63 | 8.3
40 | j160 | j169 | brick road | 0.36 | 63 | 92
41 | j169 | j125 | brick road | 0.36 | 63 | 56.5
42 | j169 | j125 | brick road | 0.36 | 63 | 15.8
43 | j131 | j135 | brick road | 0.36 | 63 | 27
44 | j172 | j175 | brickroad | 0.36 | 63 | 46.1
45 | J131A | J131B | brickroad | 0.36 | 63 | 15.9
46 | J125 | J142 | brickroad | 0.36 | 63 | 26.7
47 | j37 | j130 | brick road | 0.37 | 75 | 251.4
48 | j35 | j91 | interlocking | 0.46 | 90 | 232
49 | j86 | j104 | brick road | 0.39 | 90 | 44.6
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  | SIGN.with date

## shivpur khurd
Shivpur khurd(RESTORATION)
Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | Dia of pipe | Pipe Length (M) AS PER SITE
1 | J75(A) | J75(B) | BRICK ROAD | 0.363 | 63 | 2.6
2 | J6 | J8 | BRICK ROAD | 0.363 | 63 | 33.4
3 | J6 | J4 | BRICK ROAD | 0.363 | 63 | 15
4 | j76 | j43 | B.T. ROAD | 0.36 | 75 | 3.4
5 | J4 | J5 | BRICK ROAD | 0.363 | 63 | 143.1
6 | J3 | J4 | BRICK ROAD | 0.363 | 63 | 14.4
7 | j17 | j9 | B.T. ROAD | 0.36 | 75 | 3.8
8 | J67(A) | J84 | BRICK ROAD | 0.363 | 63 | 84.4
9 | J45 | J40 | BRICK ROAD | 0.363 | 63 | 3
10 | j45 | j53 | BRICK ROAD | 0.363 | 63 | 7.8
11 | j53 | j49 | BRICK ROAD | 0.363 | 63 | 5.8
12 | j53 | j58 | BRICK ROAD | 0.363 | 63 | 6.1
13 | j9 | j43 | B.T. ROAD | 0.36 | 75 | 3
14 | J76 | J75 | B.T. ROAD | 0.36 | 75 | 3.6
15 | j58 | j58(1) | BRICK ROAD | 0.363 | 63 | 3.8
16 | j58(1) | j64a | BRICK ROAD | 0.363 | 63 | 9.8
17 | j64 | j65 | BRICK ROAD | 0.363 | 63 | 11
18 | j58 | j60 | BRICK ROAD | 0.363 | 63 | 85.2
19 | j35a | j35b | BRICK ROAD | 0.363 | 63 | 1.9
20 | j30a | j30 | BRICK ROAD | 0.363 | 63 | 5.6
21 | j72 | j74 | BRICK ROAD | 0.363 | 63 | 45.7
22 | j68 | j69 | BRICK ROAD | 0.363 | 63 | 37
23 | j99 | j99a | BRICK ROAD | 0.363 | 63 | 3.3
24 | j99 | j99a | BRICK ROAD | 0.363 | 63 | 6.9
25 | j99a | j99b | BRICK ROAD | 0.363 | 63 | 2.2
26 | J67(A) | J67 | B.T. ROAD | 0.36 | 63 | 4.2
27 | J46 | J61 | B.T. ROAD | 0.36 | 63 | 4.2
28 | J40 | J39 | B.T. ROAD | 0.36 | 63 | 3
29 | j99(a) | j102 | BRICK ROAD | 0.363 | 63 | 19.1
30 | j102 | j106 | BRICK ROAD | 0.363 | 63 | 29.5
31 | j106 | j112 | BRICK ROAD | 0.363 | 63 | 88.2
32 | j106 | j110 | BRICK ROAD | 0.363 | 63 | 25.4
33 | j101 | j115 | BRICK ROAD | 0.363 | 63 | 136.6
34 | j97 | j99 | BRICK ROAD | 0.363 | 63 | 3
35 | j33 | j29 | BRICK ROAD | 0.363 | 63 | 20.6
36 | j33 | j30 | ccroad | 0.363 | 63 | 21
37 | j33 | j30 | BRICK ROAD | 0.363 | 63 | 19.8
38 | j73a | j73b | B.T. ROAD | 0.36 | 63 | 2.4
39 | j70 | j71 | B.T. ROAD | 0.36 | 63 | 3.2
40 | j21 | j26 | BRICK ROAD | 0.363 | 63 | 32.2
41 | j26 | j30 | BRICK ROAD | 0.363 | 63 | 30.5
42 | j26 | j17a | BRICK ROAD | 0.363 | 63 | 11.6
43 | j75a | J75 | BRICK ROAD | 0.375 | 75 | 5.1 |  | 3.2
3.4
3.8
3
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  | SIGN.with date

## Puremanikanth
PUREMANIKANTH(RESTORATION)
ATTARSAND AND PRASPUR(ROAD RESTORATION) | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | Dia of pipe | Pipe Length (M) AS PER SITE
1 | J41 | J54 | BRICK ROAD | 0.36 | 63 | 23.6
2 | J46 | J41 | B.T ROAD | 0.36 | 63 | 101.5
3 | J41 | J80 | B.T ROAD | 0.36 | 63 | 92.4
4 | J29D | J18 | B.T ROAD | 0.46 | 63 | 14.1
5 | J29D | J70 | B.T ROAD | 0.46 | 63 | 115.8
6 | J70 | J78 | B.T ROAD | 0.36 | 63 | 42.1
7 | J70 | J76 | B.T ROAD | 0.46 | 63 | 220.1
8 | J87 | J106 | B.T ROAD | 0.36 | 63 | 9.7
9 | J87 | J138 | B.T ROAD | 0.36 | 63 | 60.3
10 | J95 | J111 | B.T ROAD | 0.36 | 63 | 102
11 | J95 | J98 | B.T ROAD | 0.36 | 63 | 34.8
12 | J98 | J86 | BRICK ROAD | 0.36 | 63 | 44.5
13 | J98 | J87 | C.C. ROAD | 0.36 | 63 | 19.6
14 | J98 | J87 | BRICK ROAD | 0.36 | 63 | 22.3
15 | J106 | J97 | BRICK ROAD | 0.36 | 63 | 80.2
16 | J97 | J132 | C.C. ROAD | 0.36 | 63 | 92
17 | J132 | J143 | C.C. ROAD | 0.36 | 63 | 28.1
18 | J74A | J8 | BRICK ROAD | 0.36 | 125 | 35.1
19 | J28 | J25 | BRICK ROAD | 0.36 | 63 | 66.3
20 | J17 | J17A | BRICK ROAD | 0.36 | 63 | 22.3
21 | J17A | J116 | BRICK ROAD | 0.36 | 63 | 7.5
22 | J9 | J63 | BRICK ROAD | 0.36 | 63 | 26.1
23 | J115 | J104 | INTERLOCKING | 0.46 | 63 | 158.3
24 | J122 | J125 | BRICK ROAD | 0.36 | 63 | 180.1
25 | J63 | J79 | INTERLOCKING | 0.46 | 90 | 4.6
26 | J141 | J140 | BRICK ROAD | 0.36 | 63 | 10.1
27 | J141 | J140 | BRICK ROAD | 0.36 | 63 | 17.6
28 | J140 | J136 | BRICK ROAD | 0.36 | 63 | 4.1
29 | J134 | J128 | INTERLOCKING | 0.46 | 63 | 213.1
30 | J128 | J114 | BRICK ROAD | 0.36 | 63 | 5.6
31 | J79 | J79A | INTERLOCKING | 0.46 | 63 | 59.2
32 | J79A | J79B | INTERLOCKING | 0.46 | 63 | 2.8
33 | J79A | J49 | INTERLOCKING | 0.46 | 63 | 134.4
34 | J49 | J23 | BRICK ROAD | 0.36 | 63 | 53.1
35 | J49 | J24 | BRICK ROAD | 0.36 | 63 | 46.1
36 | J49 | J30 | INTERLOCKING | 0.46 | 63 | 16.1
37 | J30 | J55 | BRICK ROAD | 0.36 | 63 | 40
38 | J30 | J42 | INTERLOCKING | 0.46 | 63 | 25.6
39 | J42 | J61 | BRICK ROAD | 0.36 | 63 | 41.4
40 | J42 | J39 | INTERLOCKING | 0.46 | 63 | 43.3
41 | J39 | J50 | INTERLOCKING | 0.46 | 63 | 19.1
42 | J50 | J36 | INTERLOCKING | 0.46 | 75 | 31.9
43 | J36 | J73 | INTERLOCKING | 0.46 | 90 | 10.1
44 | J36 | J73 | BRICK ROAD | 0.36 | 90 | 8.4
45 | J56C | J56D | BRICK ROAD | 0.36 | 63 | 20.1
46 | J56D | J56 | BRICK ROAD | 0.36 | 125 | 24.2
47 | J56 | J5 | BRICK ROAD | 0.36 | 140 | 38.1
48 | J5 | J10 | BRICK ROAD | 0.36 | 63 | 18
49 | J5 | J5A | BRICK ROAD | 0.36 | 140 | 24.6
50 | J5A | J5B | BRICK ROAD | 0.36 | 63 | 2.1
51 | J5A | J2 | BRICK ROAD | 0.36 | 140 | 10
52 | j118 | j149 | BRICK ROAD | 0.36 | 63 | 180.2
53 | j118 | j112 | BRICK ROAD | 0.36 | 63 | 50.2
54 | j131 | j131a | INTERLOCKING | 0.46 | 63 | 96.2
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  | SIGN.with date
PUREMANIKANTH(RESTORATION)
Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | Dia of pipe | Pipe Length (M) AS PER SITE
1 | J72 | J60 | B.T. ROAD | 0.36 | 63 | 3.2
2 | J45 | J29 | B.T. ROAD | 0.36 | 63 | 100.1
3 | J70 | J76 | B.T. ROAD | 0.36 | 63 | 3.8
4 | J76 | J96 | B.T. ROAD | 0.36 | 75 | 99.1
5 | J29D | J29E | INTERLOCKING | 0.46 | 63 | 2.8
6 | J76 | J75 | B.T. ROAD | 0.36 | 90 | 178.5
7 | J74A | J74B | BRICK ROAD | 0.36 | 63 | 2.6
8 | J75 | J63 | B.T. ROAD | 0.36 | 90 | 101.1
9 | J75 | J63 | B.T. ROAD | 0.36 | 90 | 4
10 | J56D | J74 | BRICK ROAD | 0.36 | 125 | 13.8
11 | J96 | J106 | B.T. ROAD | 0.36 | 63 | 407.1
12 | J106 | J87 | B.T. ROAD | 0.36 | 63 | 39.4
13 | J80 | J72 | BRICK ROAD | 0.36 | 63 | 6.2
14 | J72 | J64 | INTERLOCKING | 0.46 | 63 | 5.2
15 | J106 | J97 | B.T. ROAD | 0.36 | 63 | 156.5
16 | J97 | J132 | B.T. ROAD | 0.36 | 63 | 22.8
17 | J132 | J143 | B.T. ROAD | 0.36 | 63 | 21.1
18 | J72 | J64 | BRICK ROAD | 0.36 | 63 | 6.2
19 | J29C | J29D | INTERLOCKING | 0.46 | 63 | 5.9
20 | J140 | J136 | BRICK ROAD | 0.36 | 63 | 2.7
21 | J25 | J13 | B.T. ROAD | 0.36 | 63 | 83.8
22 | J25 | J22 | B.T. ROAD | 0.36 | 63 | 12.3
23 | J22 | J34 | B.T. ROAD | 0.36 | 63 | 103.9
24 | J22 | J17 | B.T. ROAD | 0.36 | 63 | 33.5
25 | J17 | J57 | B.T. ROAD | 0.36 | 63 | 55.6
26 | J140 | J134 | BRICK ROAD | 0.36 | 63 | 20.8
27 | J134 | J135 | BRICK ROAD | 0.36 | 63 | 2.8
28 | J74 | J82 | BRICK ROAD | 0.36 | 63 | 1.5
29 | J96 | J115 | B.T. ROAD | 0.36 | 75 | 135.7
30 | J115 | J122 | B.T. ROAD | 0.36 | 63 | 96.6
31 | J122 | J125 | B.T. ROAD | 0.36 | 63 | 4.8
32 | J122 | J132 | B.T. ROAD | 0.36 | 63 | 56.1
33 | J74 | J74A | BRICK ROAD | 0.36 | 125 | 9.8
34 | J96 | J115 | B.T. ROAD | 0.36 | 90 | 5.8
35 | J115 | J122 | B.T. ROAD | 0.36 | 140 | 3.3
36 | J122 | J125 | B.T. ROAD | 0.36 | 63 | 151.2
37 | J122 | J132 | B.T. ROAD | 0.36 | 63 | 52
38 | j154 | j85 | INTERLOCKING | 0.46 | 63 | 14.3
39 | j85 | j94 | INTERLOCKING | 0.46 | 63 | 29
40 | j85 | j84 | INTERLOCKING | 0.46 | 63 | 98.2
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  | SIGN.with date

## Sheet2
ATTARSAND AND PRASPUR(ROAD RESTORATION)
Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | Dia of pipe | Pipe Length (M) AS PER SITE
1 | J23 | J61 | B.T ROAD |  | 110 | 129.3
2 | J61 | J43 | B.T ROAD |  | 110 | 58.6
3 | J43 | 68 | B.T ROAD |  | 110 | 94
4 | J68 | J57 | B.T ROAD |  | 110 | 30.6
5 | J57 | J30 | B.T ROAD |  | 110 | 87.3
6 | J30 | J79 | B.T ROAD |  | 110 | 6.5
7 | J79 | J35 | B.T ROAD |  | 110 | 49.2
8 | J35 | J28 | B.T ROAD |  | 110 | 49.5
9 | J26 | J5 | B.T ROAD |  | 63 | 161.2
10 | J29 | J228 | B.T ROAD |  | 140 | 865.6
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  | SIGN.with date