## SARAI JAMMUVARI
| HYDROSTATIC TEST FOR PRESSURE PIPES | [11 empty] | HYDROSTATIC TEST FOR PRESSURE PIPES | [11 empty] | HYDROSTATIC TEST FOR PRESSURE PIPES
Project:- |  | Rural water supply project Under JJM , Pratapgarh , Utter Pradesh | [9 empty] | Project:- |  | Rural water supply project Under JJM , Pratapgarh , Utter Pradesh | [9 empty] | Project:- |  | Rural water supply project Under JJM , Pratapgarh , Utter Pradesh
Client : - |  | State Water & Sanitation Mission Govt of Uttar Pradesh | [9 empty] | Client : - |  | State Water & Sanitation Mission Govt of Uttar Pradesh | [9 empty] | Client : - |  | State Water & Sanitation Mission Govt of Uttar Pradesh
TPI :- |  | Medhaj Techno Concept Pvt . Ltd. | [9 empty] | TPI :- |  | Medhaj Techno Concept Pvt . Ltd. | [9 empty] | TPI :- |  | Medhaj Techno Concept Pvt . Ltd.
Contractor :- |  | Power Mech Project Ltd. | [9 empty] | Contractor :- |  | Power Mech Project Ltd. | [9 empty] | Contractor :- |  | Power Mech Project Ltd.
Block: MANGRAURA, G.P-SARAI JAMMUVARI | [11 empty] | Block: MANGRAURA, G.P-SARAI JAMMUVARI | [17 empty] | Block: MANGRAURA, G.P-SARAI JAMMUVARI
Dail Log Ref. …………………. | 2023-05-20 |  |  |  |  | Tested as per CPHEEO …………………….. | 2023-05-20 |  |  |  |  | Dail Log Ref. …………………. | 2023-05-25 |  |  |  |  | Tested as per CPHEEO …………………….. | 2023-05-25 |  |  |  |  | Dail Log Ref. …………………. | [5 empty] | Tested as per CPHEEO ……………………..
Date | [5 empty] | Date of Testing | [5 empty] | Date | [5 empty] | Date of Testing | [5 empty] | Date | [5 empty] | Date of Testing
SL. No. | Material of Pipe | ID (MM) | Start Node | End Node | Length | Applied test pressure (kg/cm'2) | Time in Hrs |  |  | Observation | Remark | SL. No. | Material of Pipe | ID (MM) | Start Node | End Node | Length | Applied test pressure (kg/cm'2) | Time in Hrs |  |  | Observation | Remark | SL. No. | Material of Pipe | ID (MM) | Start Node | End Node | Length | Applied test pressure (kg/cm'2) | Time in Hrs |  |  | Observation | Remark
[7 empty] | Pressure rising time (Hrs) | Pressure Released time (Hrs) | Total Duration Hrs | [9 empty] | Pressure rising time (Hrs) | Pressure Released time (Hrs) | Total Duration Hrs | [9 empty] | Pressure rising time (Hrs) | Pressure Released time (Hrs) | Total Duration Hrs
1 | HDPE | 81.1 | J18 | J17 | 71.1 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 1 | HDPE | 126.3 | J4 | J281 | 117.8 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 1 | HDPE | 56.7 | j215 | j269 | 48 | 6KG/CM2 | 3 | 1 | 4 | NO
2 | HDPE | 99.3 | J17 | J19 | 382.4 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 2 | HDPE | 126.3 | J281 | J8 | 26.3 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 2 | HDPE | 56.7 | j276 | j263 | 91 | 6KG/CM2 | 3 | 1 | 4 | NO
3 | HDPE | 56.7 | J18 | J9 | 660.2 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 3 | HDPE | 81.1 | J8 | J46 | 93.2 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 3 | HDPE | 144.4 | j150 | j259 | 62 | 6KG/CM2 | 3 | 1 | 4 | NO
4 | HDPE | 56.7 | J17 | J39 | 201.4 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 4 | HDPE | 67.4 | J46 | J34 | 105.6 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 4 | HDPE | 144.4 | j259 | j248 | 18 | 6KG/CM2 | 3 | 1 | 4 | NO
5 | HDPE | 99.3 | J19 | J10 | 48 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 5 | HDPE | 144.4 | J8 | J9 | 141.3 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 5 | HDPE | 144.4 | j248 | j264 | 202 | 6KG/CM2 | 3 | 1 | 4 | NO
6 | HDPE | 99.3 | J10 | J109 | 467.2 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 6 | HDPE | 144.4 | J9 | J70 | 322.4 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 6 | HDPE | 144.4 | j264 | j272 | 44 | 6KG/CM2 | 3 | 1 | 4 | NO
7 | HDPE | 67.4 | J109 | J98 | 134 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 7 | HDPE | 126.3 | J9 | J13 | 106.9 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 7 | HDPE | 144.4 | j272 | j276 | 38 | 6KG/CM2 | 3 | 1 | 4 | NO
8 | HDPE | 67.4 | J98 | J116 | 270 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 8 | HDPE | 144.4 | J72 | J89 | 12 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 8 | HDPE | 144.4 | j264 | j260 | 47 | 6KG/CM2 | 3 | 1 | 4 | NO
9 | HDPE | 56.7 | J45 | J25 | 49 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 9 | HDPE | 126.3 | J72 | J92 | 580.2 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 9 | HDPE | 126.3 | j260 | j261 | 180 | 6KG/CM2 | 3 | 1 | 4 | NO
10 | HDPE | 67.4 | J45 | J116 | 123 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 10 | HDPE | 67.4 | J92 | J51 | 290.7 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 10 | HDPE | 126.3 | j260 | j258 | 15 | 6KG/CM2 | 3 | 1 | 4 | NO
11 | HDPE | 67.4 | J45 | J20 | 190 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 11 | HDPE | 56.7 | J51 | J201 | 235.3 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 11 | HDPE | 99.3 | j38 | j540 | 100 | 6KG/CM2 | 3 | 1 | 4 | NO
12 | HDPE | 56.7 | J20 | J31 | 40 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 12 | HDPE | 126.3 | J51 | J101 | 582.9 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 12 | HDPE | 99.3 | j40 | j74 | 150 | 6KG/CM2 | 3 | 1 | 4 | NO
13 | HDPE | 67.4 | J22 | J1 | 209 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 13 | HDPE | 56.7 | J101 | J258 | 358.2 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 13 | HDPE | 67.4 | j46 | j26 | 15 | 6KG/CM2 | 3 | 1 | 4 | NO
14 | HDPE | 56.7 | J1 | J6 | 61 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 14 | HDPE | 126.3 | J101 | J2 | 381.6 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 14 | HDPE | 99.3 | j40 | j74 | 30 | 6KG/CM2 | 3 | 1 | 4 | NO
15 | HDPE | 99.3 | J1 | J10 | 315 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 15 | HDPE | 56.7 | J258 | J280 | 221.9 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 15 | HDPE | 56.7 | j44 | j76 | 200 | 6KG/CM2 | 3 | 1 | 4 | NO
16 | HDPE | 81.1 | J109 | J107 | 257.2 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 16 | HDPE | 67.4 | J92 | J33 | 220.3 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 16 | HDPE | 56.7 | j76 | j93 | 40 | 6KG/CM2 | 3 | 1 | 4 | NO
17 | HDPE | 56.7 | J163 | J103 | 184.3 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 17 | HDPE | 81.1 | J33 | J27 | 62.1 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 17 | HDPE | 56.7 | j76 | j84 | 1677 | 6KG/CM2 | 3 | 1 | 4 | NO
18 | HDPE | 56.7 | J163 | J134 | 78.5 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 18 | HDPE | 67.4 | J33 | J42 | 177.9 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 18 | HDPE | 56.7 | j91 | j106 | 230 | 6KG/CM2 | 3 | 1 | 4 | NO
19 | HDPE | 56.7 | J134 | J142 | 142 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 19 | HDPE | 67.4 | J42 | J27 | 89.8 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 19 | HDPE | 126.3 | j173 | j212 | 156 | 6KG/CM2 | 3 | 1 | 4 | NO
20 | HDPE | 99.3 | J19 | J21 | 51.3 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 20 | HDPE | 99.3 | J27 | J21 | 226.2 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 20 | HDPE | 126.3 | j173 | j212 | 120 | 6KG/CM2 | 3 | 1 | 4 | NO
|  | POWER MECH |  |  |  | MEDHAJ |  |  | JAL NIGAM U.P. |  |  | 21 | HDPE | 67.4 | J26 | J34 | 117.7 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 21 | HDPE | 126.3 | j58 | j43 | 200 | 6KG/CM2 | 3 | 1 | 4 | NO
Name: |  | K.ANWESH KUMAR REDDY | [11 empty] | POWER MECH |  |  |  | MEDHAJ |  |  | JAL NIGAM U.P. |  |  |  |  | POWER MECH |  |  |  | MEDHAJ |  |  | JAL NIGAM U.P.
Designation: |  | SR.ENGINEER | [9 empty] | Name: |  | K.ANWESH KUMAR REDDY | [9 empty] | Name: |  | K.ANWESH KUMAR REDDY
Signature: | [11 empty] | Designation: |  | SR.ENGINEER | [9 empty] | Designation: |  | SR.ENGINEER
Date: | [11 empty] | Signature: | [11 empty] | Signature:
[12 empty] | Date: | [11 empty] | Date: