## mandah & bhoji
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | mandah and bhoji | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | j56 | j41 | 110 | 508.6 | 6 | 3 | 1 | 4 | no
2 | j56 | j79 | 90 | 67.1 | 6 | 3 | 1 | 4 | no
3 | j79 | j85 | 90 | 30.1 | 6 | 3 | 1 | 4 | no
4 | j85 | j93 | 90 | 167.7 | 6 | 3 | 1 | 4 | no
5 | j179 | j169 | 63 | 72.5 | 6 | 3 | 1 | 4 | no
6 | j169 | j170 | 63 | 45.4 | 6 | 3 | 1 | 4 | no
7 | j169 | j167 | 63 | 8.8 | 6 | 3 | 1 | 4 | no
8 | j167 | j168 | 63 | 32.2 | 6 | 3 | 1 | 4 | no
9 | j167 | j165 | 63 | 44.2 | 6 | 3 | 1 | 4 | no
10 | j165 | j166 | 63 | 35.7 | 6 | 3 | 1 | 4 | no
11 | j179 | j199 | 63 | 82.7 | 6 | 3 | 1 | 4 | no
12 | j199 | j203 | 63 | 9.7 | 6 | 3 | 1 | 4 | no
13 | j203 | j206 | 63 | 38.7 | 6 | 3 | 1 | 4 | no
14 | j203 | j206 | 63 | 13.6 | 6 | 3 | 1 | 4 | no
15 | j203 | j206 | 63 | 43.1 | 6 | 3 | 1 | 4 | no
16 | j200 | j200a | 63 | 2 | 6 | 3 | 1 | 4 | no
17 | j200a | j200b | 63 | 33 | 6 | 3 | 1 | 4 | no
18 | j202 | j197 | 63 | 22.4 | 6 | 3 | 1 | 4 | no
19 | j197 | j191 | 63 | 46.5 | 6 | 3 | 1 | 4 | no
20 | j191 | j192 | 63 | 50.8 | 6 | 3 | 1 | 4 | no
21 | j191 | j187 | 63 | 25.4 | 6 | 3 | 1 | 4 | no
22 | j191 | j187 | 63 | 31.1 | 6 | 3 | 1 | 4 | no
23 | j187 | j180 | 63 | 29.2 | 6 | 3 | 1 | 4 | no
24 | j180 | j178 | 63 | 49.9 | 6 | 3 | 1 | 4 | no
25 | j180 | j178 | 63 | 5.8 | 6 | 3 | 1 | 4 | no
26 | j178 | j182 | 63 | 19.3 | 6 | 3 | 1 | 4 | no
27 | j182 | j183 | 63 | 10.3 | 6 | 3 | 1 | 4 | no
28 | j178 | j173 | 63 | 24 | 6 | 3 | 1 | 4 | no
29 | j178 | j173 | 63 | 2 | 6 | 3 | 1 | 4 | no
30 | j173 | j176 | 63 | 64.4 | 6 | 3 | 1 | 4 | no
31 | j173 | j159 | 63 | 126.1 | 6 | 3 | 1 | 4 | no
32 | j159 | j158 | 63 | 49.9 | 6 | 3 | 1 | 4 | no
33 | j158 | j158(1) | 63 | 3.8 | 6 | 3 | 1 | 4 | no
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | mandah and bhoji | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | j158 | j171 | 63 | 111.5 | 5.5 | 3.3 | 1 | 4.3 | no
2 | j171 | j172 | 63 | 20.7 | 5.5 | 3.3 | 1 | 4.3 | no
3 | j177 | j171 | 63 | 46.3 | 5.5 | 3.3 | 1 | 4.3 | no
4 | j158 | j157 | 63 | 125.6 | 5.5 | 3.3 | 1 | 4.3 | no
5 | j157 | j151 | 63 | 7 | 5.5 | 3.3 | 1 | 4.3 | no
6 | j157 | j210 | 63 | 188 | 5.5 | 3.3 | 1 | 4.3 | no
7 | j157 | j101 | 75 | 174.7 | 5.5 | 3.3 | 1 | 4.3 | no
8 | j101 | j101(1) | 75 | 9 | 5.5 | 3.3 | 1 | 4.3 | no
9 | j101 | j108 | 75 | 8.2 | 5.5 | 3.3 | 1 | 4.3 | no
10 | j101 | j108 | 75 | 125 | 5.5 | 3.3 | 1 | 4.3 | no
11 | j108 | j158 | 63 | 198 | 5.5 | 3.3 | 1 | 4.3 | no
12 | j158 | j158(1) | 63 | 6.5 | 5.5 | 3.3 | 1 | 4.3 | no
13 | j108 | j102 | 63 | 53 | 5.5 | 3.3 | 1 | 4.3 | no
14 | j102 | j103 | 63 | 59 | 5.5 | 3.3 | 1 | 4.3 | no
15 | j102 | j103 | 63 | 3 | 5.5 | 3.3 | 1 | 4.3 | no
16 | j102 | j98 | 63 | 80.3 | 5.5 | 3.3 | 1 | 4.3 | no
17 | j98 | j82 | 63 | 2.5 | 5.5 | 3.3 | 1 | 4.3 | no
18 | j98 | j82 | 63 | 124.3 | 5.5 | 3.3 | 1 | 4.3 | no
19 | j98 | j165 | 63 | 421.1 | 5.5 | 3.3 | 1 | 4.3 | no
20 | j101 | j134 | 63 | 542.4 | 5.5 | 3.3 | 1 | 4.3 | no
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | mandah and bhoji | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | j134 | j134(1) | 63 | 7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
2 | j134 | j141 | 63 | 95.8 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
3 | j141 | j141(1) | 63 | 3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
4 | j141 | j145 | 63 | 75.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
5 | j145 | j144 | 63 | 62.4 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
6 | j144 | j146 | 63 | 71 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
7 | j144 | j142 | 63 | 71.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
8 | j142 | j143 | 63 | 74.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
9 | j142 | j140 | 63 | 50.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
10 | j140 | j137 | 63 | 87.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
11 | j141 | j153 | 63 | 138.7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
12 | j153 | j154 | 63 | 61.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
13 | j153 | j155 | 63 | 141.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
14 | j134 | j99 | 63 | 196.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
15 | j99 | j132 | 63 | 3.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
16 | j99 | j132 | 63 | 89.9 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
17 | j132 | j135 | 63 | 67.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
18 | j99 | j93 | 63 | 168.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
19 | j93 | j94 | 63 | 107.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
20 | j93 | j94 | 63 | 3.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
21 | j94 | j95 | 63 | 76.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
22 | j95 | j96 | 63 | 53.7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
23 | j94 | j113 | 63 | 344.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
24 | j113 | j124 | 63 | 249 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
25 | j124 | j125 | 63 | 31.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
26 | 130 | 127 | 63 | 276.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | mandah and bhoji | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | 127 | 121 | 63 | 24.6 | 5.5KG/CM2 | 3 | 1 | 4 | NO
2 | j121a | j121b | 63 | 13.9 | 5.5KG/CM2 | 3 | 1 | 4 | NO
3 | j121a | j117 | 63 | 23.2 | 5.5KG/CM2 | 3 | 1 | 4 | NO
4 | j117 | j118 | 63 | 34.8 | 5.5KG/CM2 | 3 | 1 | 4 | NO
5 | j117 | j104 | 63 | 16.3 | 5.5KG/CM2 | 3 | 1 | 4 | NO
6 | j117 | j109 | 63 | 74.4 | 5.5KG/CM2 | 3 | 1 | 4 | NO
7 | j117 | j109 | 63 | 29.1 | 5.5KG/CM2 | 3 | 1 | 4 | NO
8 | j109 | j116 | 63 | 37 | 5.5KG/CM2 | 3 | 1 | 4 | NO
9 | j116 | j123 | 63 | 125.1 | 5.5KG/CM2 | 3 | 1 | 4 | NO
10 | j109 | j100 | 63 | 21.9 | 5.5KG/CM2 | 3 | 1 | 4 | NO
11 | j100 | j104 | 63 | 23.7 | 5.5KG/CM2 | 3 | 1 | 4 | NO
12 | j105 | j105 | 63 | 72.4 | 5.5KG/CM2 | 3 | 1 | 4 | NO
13 | j104 | j106 | 63 | 17.9 | 5.5KG/CM2 | 3 | 1 | 4 | NO
14 | j106 | j110 | 63 | 57.6 | 5.5KG/CM2 | 3 | 1 | 4 | NO
15 | j100 | j89 | 63 | 101.8 | 5.5KG/CM2 | 3 | 1 | 4 | NO
16 | j89 | j83 | 63 | 22.5 | 5.5KG/CM2 | 3 | 1 | 4 | NO
17 | j83 | j56 | 63 | 76.5 | 5.5KG/CM2 | 3 | 1 | 4 | NO
18 | j56 | j56(1) | 63 | 5.7 | 5.5KG/CM2 | 3 | 1 | 4 | NO
19 | j122 | j119 | 63 | 121 | 5.5KG/CM2 | 3 | 1 | 4 | NO
20 | j119a | j119b | 63 | 63 | 5.5KG/CM2 | 3 | 1 | 4 | NO
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | mandah and bhoji | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | j8 | j4 | 160 | 122 | 5.5KG/CM2 | 3 | 1 | 4 | NO
2 | j4 | j1 | 160 | 34 | 5.5KG/CM2 | 3 | 1 | 4 | NO
3 | j25 | j8 | 140 | 5.6 | 5.5KG/CM2 | 3 | 1 | 4 | NO
4 | j25 | j8 | 140 | 612.9 | 5.5KG/CM2 | 3 | 1 | 4 | NO
5 | j56 | j41 | 110 | 508.6 | 5.5KG/CM2 | 3 | 1 | 4 | NO
6 | j101 | j61 | 90 | 280.4 | 5.5KG/CM2 | 3 | 1 | 4 | NO
7 | j61 | j47 | 110 | 183.6 | 5.5KG/CM2 | 3 | 1 | 4 | NO
8 | j47 | j47(1) | 63 | 7.1 | 5.5KG/CM2 | 3 | 1 | 4 | NO
9 | j50 | j48 | 63 | 70.4 | 5.5KG/CM2 | 3 | 1 | 4 | NO
10 | j48 | j49 | 63 | 7.4 | 5.5KG/CM2 | 3 | 1 | 4 | NO
11 | j48 | j49 | 63 | 54.9 | 5.5KG/CM2 | 3 | 1 | 4 | NO
12 | j48 | j47 | 63 | 57 | 5.5KG/CM2 | 3 | 1 | 4 | NO
13 | j47 | j25 | 110 | 272.2 | 5.5KG/CM2 | 3 | 1 | 4 | NO
14 | j25 | j41 | 110 | 440 | 5.5KG/CM2 | 3 | 1 | 4 | NO
15 | j41 | j41(1) | 110 | 9 | 5.5KG/CM2 | 3 | 1 | 4 | NO
16 | j41 | j40 | 63 | 23 | 5.5KG/CM2 | 3 | 1 | 4 | NO
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | mandah and bhoji | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | j4 | j5 | 63 | 139.4 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
2 | j5a | j5b | 63 | 55.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
3 | j8 | j9 | 63 | 149.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
4 | j9 | j2 | 63 | 67.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
5 | j2 | j3 | 63 | 50.9 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
6 | j2 | j1 | 110 | 152.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
7 | j14 | j16 | 63 | 20.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
8 | j16 | j18 | 63 | 322.4 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
9 | j18 | j18(1) | 63 | 4.9 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
10 | j18 | j20 | 63 | 355 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
11 | j20 | j22 | 63 | 359 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
12 | j22 | j23 | 63 | 51.4 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
13 | j23 | j28 | 63 | 380 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
14 | j28 | j29 | 63 | 129.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
15 | j28 | j31 | 63 | 134.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
16 | j31 | j32 | 63 | 65.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
17 | j32 | j33 | 63 | 39.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
18 | j32 | j34 | 63 | 275.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
19 | j34 | j42 | 63 | 262.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
20 | j42 | j44 | 63 | 92 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
21 | j34 | j35 | 63 | 132 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
22 | j35 | j37 | 63 | 10 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
23 | j35 | j65 | 63 | 45 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
24 | j37 | j38 | 63 | 39 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
25 | j37 | j39 | 63 | 81 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
26 | j31 | j30 | 63 | 146 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  | SIGN.with date