## SARAI JAMMUVARI
Sarai jammuvari JMR COMPLETED | [9 empty] | REMARKS
Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | Dia of pipe | Pipe Length (M) |  |  | CUMMULATIVE
1 | j18 | j9 |  |  | 63 | 660.6 |  |  | 660.6
2 | j17 | j39 |  |  | 63 | 201.4 |  |  | 862 |  |  |  | 63 | 2232.2
3 | j45 | j25 |  |  | 63 | 49 |  |  | 911 |  |  |  | 75 | 1928.3
4 | j20 | j31 |  |  | 63 | 40 |  |  | 951 |  |  |  | 90 | 483.6
5 | j1 | j6 |  |  | 63 | 61 |  |  | 1012 |  |  |  | 110 | 1263.9
6 | j163 | j103 |  |  | 63 | 184.3 |  |  | 1196.3 |  |  |  | 140 | 0
7 | j163 | j134 |  |  | 63 | 78.5 |  |  | 1274.8 |  |  |  | 160 | 0
8 | j134 | j142 |  |  | 63 | 142 |  |  | 1416.8
9 | j51 | j201 |  |  | 63 | 235.3 |  |  | 1652.1
10 | j101 | j258 |  |  | 63 | 358.2 |  |  | 2010.3
11 | J258 | J280 |  |  | 63 | 221.9 |  |  | 2232.2
12 | J20 | J1 |  |  | 75 | 205.5 |  |  | 2437.7
13 | J20 | J1 | B.T | 0.39 | 75 | 3.5 |  |  | 2441.2
14 | J33 | J42 |  |  | 75 | 177.9 |  |  | 2619.1
15 | J42 | J27 |  |  | 75 | 89.8 |  |  | 2708.9
16 | J92 | J33 |  |  | 75 | 220.3 |  |  | 2929.2
17 | j109 | j98 |  |  | 75 | 134 |  |  | 3063.2
18 | j98 | j116 |  |  | 75 | 270 |  |  | 3333.2
19 | j45 | j116 |  |  | 75 | 123 |  |  | 3456.2
20 | j45 | j20 |  |  | 75 | 190 |  |  | 3646.2
21 | j46 | j34 |  |  | 75 | 105.6 |  |  | 3751.8 | ROUTE CHANGE
22 | j26 | j54 |  |  | 75 | 117 |  |  | 3868.8
23 | j92 | j51 |  |  | 75 | 291.7 |  |  | 4160.5
24 | j18 | j17 |  |  | 90 | 71.1 |  |  | 4231.6
25 | j109 | j107 |  |  | 90 | 257.2 |  |  | 4488.8
26 | j8 | j46 |  |  | 90 | 93.2 |  |  | 4582
27 | J33 | J27 |  |  | 90 | 62.1 |  |  | 4644.1
28 | j17 | j19 |  |  | 110 | 377.9 |  |  | 5022
29 | j17 | j19 | BRICK ROAD | 0.44 | 110 | 4.5 |  |  | 5026.5
30 | j19 | j10 |  |  | 110 | 43 |  |  | 5069.5
31 | j19 | j10 | B.T | 0.44 | 110 | 5 |  |  | 5074.5
32 | j10 | j109 |  |  | 110 | 463.7 |  |  | 5538.2
33 | j10 | j109 | B.T | 0.44 | 110 | 3.5 |  |  | 5541.7
34 | j1 | j10 |  |  | 110 | 315 |  |  | 5856.7
35 | j19 | j21 |  |  | 110 | 51.3 |  |  | 5908
36 | J27 | J21 |  |  | 110 | 226.2 |  |  | 6134.2
37 | j4 | j281 |  |  | 140 | 117.8 |  |  | 6252
38 | j281 | j8 |  |  | 140 | 26.3 |  |  | 6278.3
39 | j70 | j92 |  |  | 140 | 580.2 |  |  | 6858.5
40 | j57 | j101 |  |  | 140 | 582.9 |  |  | 7441.4
41 | j101 | j2 |  |  | 140 | 380.6 |  |  | 7822
42 | J9 | j13 |  |  | 140 | 106.9 |  |  | 7928.9
43 | j8 | j9 |  |  | 160 | 141.3 |  |  | 8070.2 | [5 empty] | 20262.6
44 | j9 | j70 |  |  | 160 | 322.4 |  |  | 8392.6
45 | j90 | j89 |  |  | 160 | 12 |  |  | 8404.6
63 | 75 | 90 | 110 | 140 | 160
2232.2 | 1928.3 | 483.6 | 1490.1 | 1794.7 | 475.7 | 8404.6
2595 | 2479 | 905 | 1570 | 1944 | 1122 | 10615
48204.15
|  | Sarai jammuvari | [9 empty] | REMARKS
|  | Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | Dia of pipe | Pipe Length (M) |  |  | CUMMULATIVE
|  | 1 | j18 | j9 |  |  | 63 | 660.6 |  |  | 660.6
|  | 2 | j17 | j39 |  |  | 63 | 201.4 |  |  | 862
|  | 3 | j45 | j25 |  |  | 63 | 49 |  |  | 911
|  | 4 | j20 | j31 |  |  | 63 | 40 |  |  | 951
|  | 5 | j1 | j6 |  |  | 63 | 61 |  |  | 1012
|  | 6 | j163 | j103 |  |  | 63 | 184.3 |  |  | 1196.3
|  | 7 | j163 | j134 |  |  | 63 | 78.5 |  |  | 1274.8
|  | 8 | j134 | j142 |  |  | 63 | 142 |  |  | 1416.8
|  | 9 | j51 | j201 |  |  | 63 | 235.3 |  |  | 1652.1
|  | 10 | j101 | j258 |  |  | 63 | 358.2 |  |  | 2010.3
|  | 11 | J258 | J280 |  |  | 63 | 221.9 |  |  | 2232.2
|  | 12 | J275 | J269 |  |  | 63 | 48 |  |  | 2280.2
|  | 13 | J276 | J263 |  |  | 63 | 91 |  |  | 2371.2
|  | 14 | J44 | J76 |  |  | 63 | 200 |  |  | 2571.2
|  | 15 | J76 | J93 |  |  | 63 | 40 |  |  | 2611.2
|  | 16 | J76 | J84 |  |  | 63 | 167 |  |  | 2778.2
|  | 17 | J91 | J106 |  |  | 63 | 230 |  |  | 3008.2
|  | 18 | J20 | J1 |  |  | 75 | 205.5 |  |  | 3213.7
|  | 19 | J20 | J1 | B.T | 0.39 | 75 | 3.5 |  |  | 3217.2
|  | 20 | J33 | J42 |  |  | 75 | 177.9 |  |  | 3395.1
|  | 21 | J42 | J27 |  |  | 75 | 89.8 |  |  | 3484.9
|  | 22 | J92 | J33 |  |  | 75 | 220.3 |  |  | 3705.2
|  | 23 | j109 | j98 |  |  | 75 | 134 |  |  | 3839.2
|  | 24 | j98 | j116 |  |  | 75 | 270 |  |  | 4109.2
|  | 25 | j45 | j116 |  |  | 75 | 123 |  |  | 4232.2
|  | 26 | j45 | j20 |  |  | 75 | 190 |  |  | 4422.2
|  | 27 | j46 | j34 |  |  | 75 | 105.6 |  |  | 4527.8
|  | 28 | j26 | j54 |  |  | 75 | 117 |  |  | 4644.8
|  | 29 | j92 | j51 |  |  | 75 | 291.7 |  |  | 4936.5
|  | 30 | j18 | j17 |  |  | 90 | 71.1 |  |  | 5007.6
|  | 31 | j109 | j107 |  |  | 90 | 257.2 |  |  | 5264.8
|  | 32 | j8 | j46 |  |  | 90 | 93.2 |  |  | 5358
|  | 33 | J33 | J27 |  |  | 90 | 62.1 |  |  | 5420.1
|  | 34 | j17 | j19 |  |  | 110 | 377.9 |  |  | 5798
|  | 35 | j17 | j19 | BRICK ROAD | 0.44 | 110 | 4.5 |  |  | 5802.5
|  | 36 | j19 | j10 |  |  | 110 | 43 |  |  | 5845.5
|  | 37 | j19 | j10 | B.T | 0.44 | 110 | 5 |  |  | 5850.5
|  | 38 | j10 | j109 |  |  | 110 | 463.7 |  |  | 6314.2
|  | 39 | j10 | j109 | B.T | 0.44 | 110 | 3.5 |  |  | 6317.7
|  | 40 | j1 | j10 |  |  | 110 | 315 |  |  | 6632.7
|  | 41 | j19 | j21 |  |  | 110 | 51.3 |  |  | 6684
|  | 42 | J27 | J21 |  |  | 110 | 226.2 |  |  | 6910.2
|  | 43 | J38 | J40 |  |  | 110 | 100 |  |  | 7010.2
|  | 44 | J40 | J74 |  |  | 110 | 150 |  |  | 7160.2
|  | 45 | j4 | j281 |  |  | 140 | 117.8 |  |  | 7278
|  | 46 | j281 | j8 |  |  | 140 | 26.3 |  |  | 7304.3
|  | 47 | j70 | j92 |  |  | 140 | 580.2 |  |  | 7884.5
|  | 48 | j57 | j101 |  |  | 140 | 582.9 |  |  | 8467.4
|  | 49 | j101 | j2 |  |  | 140 | 380.6 |  |  | 8848
|  | 50 | J9 | j13 |  |  | 140 | 106.9 |  |  | 8954.9
|  | 51 | J260 | J261 |  |  | 140 | 180 |  |  | 9134.9
|  | 52 | J260 | J258 |  |  | 140 | 15 |  |  | 9149.9
|  | 53 | J172 | J212 |  |  | 140 | 156 |  |  | 9305.9
|  | 54 | J173 | J212 |  |  | 140 | 120 |  |  | 9425.9
|  | 55 | J58 | J43 |  |  | 140 | 200 |  |  | 9625.9
|  | 56 | j8 | j9 |  |  | 160 | 141.3 |  |  | 9767.2
|  | 57 | j9 | j70 |  |  | 160 | 322.4 |  |  | 10089.6
|  | 58 | j90 | j89 |  |  | 160 | 12 |  |  | 10101.6
|  | 59 | J150 | J259 |  |  | 160 | 62 |  |  | 10163.6
|  | 60 | J259 | J248 |  |  | 160 | 18 |  |  | 10181.6
|  | 61 | J248 | J264 |  |  | 160 | 202 |  |  | 10383.6
|  | 62 | J264 | J272 |  |  | 160 | 44 |  |  | 10427.6
|  | 63 | J272 | J276 |  |  | 160 | 38 |  |  | 10465.6
|  | 64 | J264 | J260 |  |  | 160 | 47 |  |  | 10512.6
|  |  |  | 63 | 75 | 90 | 110 | 140 | 160
|  |  |  | 3008.2 | 1928.3 | 483.6 | 1740.1 | 2465.7 | 886.7 |  | 10512.6
|  |  |  | 4654 | 3234 | 1867 | 2197 | 3213 | 872 |  | 16037

## SARAY JAMMUVARI (KAYTHI)
Block |  | Mangraura
GP |  | SARAY JAMMUVARI
Total Length (M) |  | 10015
FHTC (No's)
Agency Name |  | KHAYATHI ENTERPRISES
Sl.No | Date | Start Node | End Node | Type of Road | DI/HDPE | Pipe Length (M) | [7 empty] | Cumulative Length (M) | LHS/RHS | Distance from Road C/L | Site Engineer Sign | Remarks
[6 empty] | 63mm | 75mm | 90mm | 110mm | 125mm | 140mm | 160mm | DI 250mm
1 | 2023-02-17 | J17 | J19 | KC ROAD | HDPE |  |  |  | 380 |  |  |  |  | 380 | RHS | 2.2 | K.ANWESH
2 | 2023-02-18 | J17 | J39 | KC ROAD | HDPE | 200 | [7 empty] | 580 | LHS | 1.5 | K.ANWESH
3 | 2023-02-18 | J1 | J10 | KC ROAD | HDPE |  |  |  | 200 |  |  |  |  | 780 | RHS | 2.2 | K.ANWESH
4 | 2023-02-18 | J17 | J18 | KC ROAD | HDPE |  |  | 60 | [5 empty] | 840 | RHS | 2.2 | K.ANWESH
5 | 2023-02-19 | J1 | J6 | KC ROAD | HDPE | 60 | [7 empty] | 900 | RHS | 2.2 | K.ANWESH
6 | 2023-02-19 | J1 | J10 | KC ROAD | HDPE |  |  |  | 100 |  |  |  |  | 1000 | RHS | 2.2 | K.ANWESH
7 | 2023-02-19 | J28 | J27 | KC ROAD | HDPE |  |  |  | 241 |  |  |  |  | 1241 | RHS | 2.2 | K.ANWESH
8 | 2023-02-20 | J1 | J20 | KC ROAD | HDPE |  | 202 | [6 empty] | 1443 | LHS | 1.2 | K.ANWESH
9 | 2023-02-20 | J20 | J45 | KC ROAD | HDPE |  | 187 | [6 empty] | 1630 | LHS | 1.2 | K.ANWESH
10 | 2023-02-20 | J20 | J31 | KC ROAD | HDPE | 38 | [7 empty] | 1668 | LHS | 1 | K.ANWESH
11 | 2023-02-22 | J45 | J25 | KC ROAD | HDPE | 48 | [7 empty] | 1716 | LHS | 1.2 | K.ANWESH
12 | 2023-02-22 | J10 | J109 | KC ROAD | HDPE |  |  |  | 454 |  |  |  |  | 2170 | LHS | 1.2 | K.ANWESH
13 | 2023-02-22 | J109 | J107 | KC ROAD | HDPE |  |  | 252 | [5 empty] | 2422 | LHS | 1.2 | K.ANWESH
14 | 2023-02-23 | J45 | J116 | KC ROAD | HDPE |  | 160 | [6 empty] | 2582 | LHS | 1.2 | shashiranjan
15 | 2023-02-24 | j134 | j142 | KC ROAD | HDPE | 90 | [7 empty] | 2672 | LHS | 1.2 | shashiranjan
16 | 2023-02-24 | j134 | j163 | KC ROAD | HDPE | 77 | [7 empty] | 2749 | LHS | 1.2 | shashiranjan
17 | 2023-02-24 | j163 | j103 | KC ROAD | HDPE | 183 | [7 empty] | 2932 | LHS | 1.2 | shashiranjan
18 | 2023-02-24 | j134 | j107 | KC ROAD | HDPE |  | 80 | [6 empty] | 3012 | LHS | 1.2 | shashiranjan
19 | 2023-02-25 | j109 | j98 | KC ROAD | HDPE |  | 132 | [6 empty] | 3144 | LHS | 1.2 | shashiranjan
20 | 2023-02-25 | j198 | j116 | KC ROAD | HDPE |  | 198 | [6 empty] | 3342 | LHS | 1.2 | shashiranjan
21 | 2023-02-27 | j27 | j33 | KC ROAD | HDPE |  | 51 | [6 empty] | 3393 | LHS | 1.2 | shashiranjan
22 | 2023-02-27 | j33 | j92 | KC ROAD | HDPE |  | 219 | [6 empty] | 3612 | LHS | 1.2 | shashiranjan
23 | 2023-02-27 | j27 | j42 | KC ROAD | HDPE |  | 89 | [6 empty] | 3701 | LHS | 1.2 | shashiranjan
24 | 2023-02-27 | j33 | j42 | KC ROAD | HDPE |  | 169 | [6 empty] | 3870 | LHS | 1.2 | shashiranjan
25 | 2023-02-28 | j92 | j72 | KC ROAD | HDPE | [5 empty] | 200 |  |  | 4070 | LHS | 1 | shashiranjan
26 | 2023-02-28 | j92 | j51 | KC ROAD | HDPE |  | 150 | [6 empty] | 4220 | RHS | 1 | shashiranjan
27 | 2023-02-28 | j27 | j39 | KC ROAD | HDPE |  | 10 | [6 empty] | 4230 | RHS | 1 | shashiranjan
28 | 2023-03-01 | j92 | j70 | KC ROAD | HDPE | [5 empty] | 360 |  |  | 4590 | LHS | 1 | shashiranjan
29 | 2023-03-01 | j92 | j51 | KC ROAD | HDPE |  | 100 | [6 empty] | 4690 | RHS | 1 | shashiranjan
30 | 2023-03-02 | j51 | j101 | KC ROAD | HDPE | [5 empty] | 432 |  |  | 5122 | LHS | 2 | shashiranjan
31 | 2023-03-03 | J51 | J101 | KC ROAD | HDPE | 130 | [7 empty] | 5252 | LHS | 2 | shashiranjan
32 | 2023-03-03 | J51 | J201 | KC ROAD | HDPE | 220 | [7 empty] | 5472 | LHS | 2 | shashiranjan
33 | 2023-03-04 | J28 | J281 | KC ROAD | HDPE |  |  | 56 | [5 empty] | 5528 | LHS | 2 | shashiranjan
34 | 2023-03-16 | j101 | j155 | KC ROAD | HDPE | [5 empty] | 150 |  |  | 5678 | LHS | 2 | shashiranjan
35 | 2023-03-17 | j101 | j155 | KC ROAD | HDPE | [5 empty] | 100 |  |  | 5778 | LHS | 2 | shashiranjan
36 | 2023-03-18 | j101 | j155 | KC ROAD | HDPE | [5 empty] | 150 |  |  | 5928 | LHS | 2 | shashiranjan
37 | 2023-03-19 | j19 | j281 | KC ROAD | HDPE | [5 empty] | 120 |  |  | 6048 | LHS | 2 | shashiranjan
38 | 2023-03-20 | j19 | j281 | KC ROAD | HDPE | [5 empty] | 12 |  |  | 6060 | LHS | 2 | shashiranjan
39 | 2023-03-20 | j281 | j46 | KC ROAD | HDPE |  |  | 90 | [5 empty] | 6150 | LHS | 2 | shashiranjan
40 | 2023-03-20 | j7 | j8 | KC ROAD | HDPE | [6 empty] | 84 |  | 6234 | LHS | 2 | shashiranjan | 140*140*90
41 | 2023-03-21 | j9 | j8 | KC ROAD | HDPE | 300 | [7 empty] | 6534 | LHS | 1 | shashiranjan
42 | 2023-03-23 | J101 | J258 | KC ROAD | HDPE | 110 | [7 empty] | 6644 | LHS | 1 | shashiranjan | 140*140*63
43 | 2023-03-23 | J101 | J155 | KC ROAD | HDPE | [5 empty] | 36 |  |  | 6680 | LHS | 1 | shashiranjan
44 | 2023-03-24 | J101 | J258 | KC ROAD | HDPE | 200 | [7 empty] | 6880 | LHS | 1 | shashiranjan
45 | 2023-04-15 | j8 | j9 | KC ROAD | HDPE | [6 empty] | 24 |  | 6904 | LHS | 2 | shashiranjan
46 | 2023-04-15 | j9 | j170 | KC ROAD | HDPE | [6 empty] | 318 |  | 7222 | LHS | 2 | shashiranjan
47 | 2023-04-17 | j8 | j9 | KC ROAD | HDPE | [6 empty] | 25 |  | 7247 | LHS | 2 | shashiranjan
48 | 2023-04-17 | j9 | j22 | KC ROAD | HDPE | 130 | [7 empty] | 7377 | LHS | 2 | shashiranjan
49 | 2023-04-19 | J10 | J19 | KC ROAD | HDPE |  |  |  | 45 |  |  |  |  | 7422 | LHS | 2 | shashiranjan
50 | 2023-04-19 | J19 | J28 | KC ROAD | HDPE |  |  |  | 20 |  |  |  |  | 7442 | LHS | 2 | shashiranjan
51 | 2023-04-19 | J17 | J19 | KC ROAD | HDPE |  |  |  | 30 |  |  |  |  | 7472 | LHS | 2 | shashiranjan
52 | 2023-04-20 | j109 | j98 | KC ROAD | HDPE |  | 110 | [6 empty] | 7582 | LHS | 2 | shashiranjan
53 | 2023-04-20 | j107 | j109 | KC ROAD | HDPE |  |  | 10 | [5 empty] | 7592 | LHS | 2 | shashiranjan
54 | 2023-04-22 | J9 | J13 | KC ROAD | HDPE | [5 empty] | 108 |  |  | 7700 | LHS | 2 | shashiranjan
55 | 2023-04-22 | J9 | J218 | KC ROAD | HDPE | 218 | [7 empty] | 7918 | LHS | 2 | shashiranjan
56 | 2023-04-25 | J101 | J258 | KC ROAD | HDPE | 45 | [7 empty] | 7963 | LHS | 2 | shashiranjan
57 | 2023-04-25 | J260 | J28 | KC ROAD | HDPE | 218 | [7 empty] | 8181 | LHS | 2 | shashiranjan
58 | 2023-04-25 | j270 | j279 | KC ROAD | HDPE | 75 | [7 empty] | 8256 | LHS | 2 | shashiranjan
59 | 2023-04-25 | j270 | j274 | KC ROAD | HDPE | 66 | [7 empty] | 8322 | LHS | 2 | shashiranjan
60 | 2023-04-26 | J276 | J263 | KC ROAD | HDPE | 91 | [7 empty] | 8413 | LHS | 2 | shashiranjan
61 | 2023-04-26 | J275 | J269 | KC ROAD | HDPE | 48 | [7 empty] | 8461 | LHS | 2 | shashiranjan
62 | 2023-04-27 | j155 | j272 | KC ROAD | HDPE | [6 empty] | 200 |  | 8661 | LHS | 2 | shashiranjan
63 | 2023-04-28 | j272 | j264 | KC ROAD | HDPE | [6 empty] | 44 |  | 8705 | LHS | 2 | shashiranjan
64 | 2023-04-28 | j264 | j260 | KC ROAD | HDPE | [6 empty] | 47 |  | 8752 | LHS | 2 | shashiranjan
65 | 2023-04-28 | j264 | j272a | KC ROAD | HDPE | [6 empty] | 14 |  | 8766 | LHS | 2 | shashiranjan
66 | 2023-04-29 | j272 | j264 | KC ROAD | HDPE | [6 empty] | 44 |  | 8810 | LHS | 2 | shashiranjan
67 | 2023-04-29 | j264 | j260 | KC ROAD | HDPE | [6 empty] | 47 |  | 8857 | LHS | 2 | shashiranjan
68 | 2023-04-29 | j264 | j272(a) | KC ROAD | HDPE | [6 empty] | 14 |  | 8871 | LHS | 2 | shashiranjan
69 | 2023-05-03 | J150 | J264 | KC ROAD | HDPE | [6 empty] | 125 |  | 8996 | LHS | 2 | shashiranjan
70 | 2023-05-03 | J264 | J276 | KC ROAD | HDPE | [6 empty] | 48 |  | 9044 | LHS | 2 | shashiranjan
71 | 2023-05-03 | J260 | J267 | KC ROAD | HDPE | [5 empty] | 12 |  |  | 9056 | LHS | 2 | shashiranjan
72 | 2023-05-03 | J46 | J54 | KC ROAD | HDPE |  |  |  | 90 |  |  |  |  | 9146 | LHS | 2 | shashiranjan
73 | 2023-05-04 | J260 | J267 | KC ROAD | HDPE | [5 empty] | 180 |  |  | 9326 | LHS | 2 | shashiranjan
74 | 2023-05-06 | J260 | J267 | KC ROAD | HDPE |  |  |  | 100 |  |  |  |  | 9426 | LHS | 2 | shashiranjan
75 | 2023-05-06 | J40 | J74 | KC ROAD | HDPE |  |  |  | 150 |  |  |  |  | 9576 | LHS | 2 | shashiranjan
76 | 2023-05-06 | J46 | J26 | KC ROAD | HDPE |  | 15 | [6 empty] | 9591 | LHS | 2 | shashiranjan
77 | 2023-05-07 | j40 | j74 | KC ROAD | HDPE |  |  |  | 30 |  |  |  |  | 9621 | LHS | 2 | shashiranjan
78 | 2023-05-07 | j44 | j76 | KC ROAD | HDPE | 200 | [7 empty] | 9821 | LHS | 2 | shashiranjan
79 | 2023-05-07 | j76 | j93 | KC ROAD | HDPE | 40 | [7 empty] | 9861 | LHS | 2 | shashiranjan
80 | 2023-05-08 | j76 | j84 | KC ROAD | HDPE | 167 | [7 empty] | 10028 | LHS | 2 | shashiranjan
81 | 2023-05-08 | j91 | j106 | KC ROAD | HDPE | 230 | [7 empty] | 10258 | LHS | 2 | shashiranjan
82 | 2023-05-10 | j46 | j34 | KC ROAD | HDPE |  | 100 | [6 empty] | 10358 | LHS | 2 | shashiranjan
83 | 2023-05-12 | j176 | j212 | KC ROAD | HDPE | [5 empty] | 156 |  |  | 10514 | LHS | 2 | shashiranjan
84 | 2023-05-14 | j173 | j212 | KC ROAD | HDPE | [5 empty] | 120 |  |  | 10634 | LHS | 2 | shashiranjan
85 | 2023-05-14 | j230 | j251 | KC ROAD | HDPE | 240 | [7 empty] | 10874 | LHS | 2 | shashiranjan
86 | 2023-05-18 | J38 | J43 | KC ROAD | HDPE | [5 empty] | 200 |  |  | 11074 | LHS | 2 | shashiranjan
[6 empty] | 63mm | 75mm | 90mm | 110mm | 125mm | 140mm | 160mm | DI 250mm
[6 empty] | 3424 | 1972 | 468 | 1840 | 0 | 2336 | 1034 | 0 | 11074
[6 empty] | 4654 | 3234 | 1867 | 2197 |  | 3213 | 872 |  | 16037
[14 empty] | 11162 | 4576 | 6586 | 63 | 3424 | 1152 | 4576
[14 empty] | 4969 | 2302 | 2667 | 75 | 1972 | 330 | 2302
[14 empty] | 3526 | 806 | 2720 | 90 | 468 | 338 | 806
[14 empty] | 2490 | 1840 | 650 | 110 | 1840 |  | 1840
[14 empty] | 4516 | 2959 | 1557 | 140 | 2336 | 623 | 2959
[14 empty] | 3477 | 2211 | 1266 | 160 | 1034 | 1577 | 2611
15094

## SARAY JAMMUVARI(ajadi)
Block |  | Mangraura
GP |  | SARAY JAMMUVARI
Total Length (M) |  | 20125
FHTC (No's)
Agency Name |  | Ajadi enterprises
Sl.No | Date | Start Node | End Node | Type of Road | DI/HDPE | Pipe Length (M) | [7 empty] | Cumulative Length (M) | LHS/RHS | Distance from Road C/L | Site Engineer Sign | Remarks
[6 empty] | 63mm | 75mm | 90mm | 110mm | 125mm | 140mm | 160mm | DI 250mm
1 | 2023-02-23 | j49 | j62 | KC ROAD | HDPE | 315 | [7 empty] | 315 | LHS | 1.2 | SHASHIRANJAN
2 | 2023-02-23 | j145 | j169 | KC ROAD | HDPE | 98 | [7 empty] | 413 | LHS | 1 | SHASHIRANJAN
3 | 2023-02-23 | j170 | j177 | KC ROAD | HDPE | 34 | [7 empty] | 447 | LHS | 1 | SHASHIRANJAN
4 | 2023-02-24 | j184 | j228 | KC ROAD | HDPE | 110 | [7 empty] | 557 | LHS | 1.2 | SHASHIRANJAN
5 | 2023-02-24 | j169 | j228 | KC ROAD | HDPE | 67 | [7 empty] | 624 | LHS | 1.2 | SHASHIRANJAN
6 | 2023-02-27 | j228 | j191 | KC ROAD | HDPE | 30 | [7 empty] | 654 | LHS | 1.2 | SHASHIRANJAN
7 | 2023-02-27 | j177 | j219 | KC ROAD | HDPE | 23 | [7 empty] | 677 | LHS | 1.2 | SHASHIRANJAN
8 | 2023-02-27 | j182 | j220 | KC ROAD | HDPE | 34 | [7 empty] | 711 | LHS | 1.2 | SHASHIRANJAN
9 | 2023-02-27 | j182 | j189 | KC ROAD | HDPE |  |  | 73 | [5 empty] | 784 | LHS | 1.2 | SHASHIRANJAN
10 | 2023-02-28 | j64 | j220 | KC ROAD | HDPE | 50 | [7 empty] | 834 | LHS | 1.2 | SHASHIRANJAN
11 | 2023-02-28 | j189 | j172 | KC ROAD | HDPE |  |  | 70 | [5 empty] | 904 | LHS | 1.2 | SHASHIRANJAN
12 | 2023-02-28 | j172 | j154 | KC ROAD | HDPE |  |  | 28 | [5 empty] | 932 | LHS | 1.2 | SHASHIRANJAN
13 | 2023-03-01 | j173 | j155 | KC ROAD | HDPE |  | 90 | [6 empty] | 1022 | RHS | 1.2 | SHASHIRANJAN
14 | 2023-03-02 | j120 | j165 | KC ROAD | HDPE |  | 98 | [6 empty] | 1120 | LHS | 1.2 | SHASHIRANJAN
15 | 2023-03-02 | j165 | j167 | KC ROAD | HDPE |  | 102 | [6 empty] | 1222 | LHS | 1.2 | SHASHIRANJAN
16 | 2023-03-03 | j182 | j181 | KC ROAD | HDPE | 25 | [7 empty] | 1247 | LHS | 1.2 | SHASHIRANJAN
17 | 2023-03-03 | j204 | j188 | KC ROAD | HDPE | 20 | [7 empty] | 1267 | LHS | 1.2 | SHASHIRANJAN
18 | 2023-03-03 | j204 | j178 | KC ROAD | HDPE | 13 | [7 empty] | 1280 | LHS | 1.2 | SHASHIRANJAN
19 | 2023-03-03 | j178 | j192 | KC ROAD | HDPE | 27 | [7 empty] | 1307 | LHS | 1.2 | SHASHIRANJAN
20 | 2023-03-03 | j120 | j185 | KC ROAD | HDPE |  | 40 | [6 empty] | 1347 | LHS | 1.2 | SHASHIRANJAN
21 | 2023-03-06 | j145 | j113 | KC ROAD | HDPE | [6 empty] | 177 |  | 1524 | LHS | 1.2 | SHASHIRANJAN
22 | 2023-03-06 | j113 | j108 | KC ROAD | HDPE | [6 empty] | 52 |  | 1576 | LHS | 1.2 | SHASHIRANJAN
23 | 2023-03-06 | j108 | j161 | KC ROAD | HDPE | [6 empty] | 71 |  | 1647 | LHS | 1.2 | SHASHIRANJAN
24 | 2023-03-11 | J108 | J161 | KC ROAD | HDPE | [6 empty] | 99 |  | 1746 | CENTER | 0 | SHASHIRANJAN
25 | 2023-03-11 | J161 | J147 | KC ROAD | HDPE | [6 empty] | 11 |  | 1757 | CENTER | 0 | SHASHIRANJAN
26 | 2023-03-11 | J147 | J133 | KC ROAD | HDPE | [6 empty] | 76 |  | 1833 | CENTER | 0 | SHASHIRANJAN
27 | 2023-03-14 | j133 | j110 | KC ROAD | HDPE | [6 empty] | 77 |  | 1910 | CENTER | 0 | SHASHIRANJAN
28 | 2023-03-14 | j110 | j155 | KC ROAD | HDPE | [6 empty] | 100 |  | 2010 | CENTER | 0 | SHASHIRANJAN
29 | 2023-03-16 | j110 | j155 | KC ROAD | HDPE | [6 empty] | 55 |  | 2065 | CENTER | 0 | SHASHIRANJAN
30 | 2023-03-16 | j155 | j102 | KC ROAD | HDPE | [6 empty] | 49 |  | 2114 | CENTER | 0 | SHASHIRANJAN
31 | 2023-03-17 | j110 | j136 | KC ROAD | HDPE | [6 empty] | 200 |  | 2314 | CENTER | 0 | SHASHIRANJAN
32 | 2023-03-18 | j110 | j136 | KC ROAD | HDPE | [6 empty] | 610 |  | 2924 | CENTER | 0 | SHASHIRANJAN
33 | 2023-03-23 | j62 | J160 | KC ROAD | HDPE | [5 empty] | 59 |  |  | 2983 | LHS | 1.2 | SHASHIRANJAN
34 | 2023-03-23 | j160 | J257 | KC ROAD | HDPE | [5 empty] | 178 |  |  | 3161 | LHS | 1.2 | SHASHIRANJAN
35 | 2023-03-23 | j62 | J145 | KC ROAD | HDPE | [5 empty] | 129 |  |  | 3290 | LHS | 1.2 | SHASHIRANJAN
36 | 2023-03-24 | j6 | J168 | KC ROAD | HDPE | 43 | [7 empty] | 3333 | LHS | 1 | SHASHIRANJAN
37 | 2023-03-24 | j169 | J191 | KC ROAD | HDPE | 34 | [7 empty] | 3367 | LHS | 1 | SHASHIRANJAN
38 | 2023-03-24 | j191 | J229 | KC ROAD | HDPE | 34 | [7 empty] | 3401 | LHS | 1 | SHASHIRANJAN
39 | 2023-03-24 | j191 | J177 | KC ROAD | HDPE | 12 | [7 empty] | 3413 | LHS | 1 | SHASHIRANJAN
40 | 2023-03-24 | j177 | J219 | KC ROAD | HDPE | 23 | [7 empty] | 3436 | LHS | 1 | SHASHIRANJAN
41 | 2023-03-24 | j177 | J171 | KC ROAD | HDPE | 59 | [7 empty] | 3495 | LHS | 1 | SHASHIRANJAN
42 | 2023-03-24 | j154 | J244 | KC ROAD | HDPE | 51 | [7 empty] | 3546 | LHS | 1 | SHASHIRANJAN
43 | 2023-03-24 | j185 | J193 | KC ROAD | HDPE | 50 | [7 empty] | 3596 | LHS | 1 | SHASHIRANJAN
44 | 2023-04-01 | j89 | j99 | KC ROAD | HDPE | [5 empty] | 147 |  |  | 3743 | LHS | 1 | SHASHIRANJAN
45 | 2023-04-01 | j99 | j102 | KC ROAD | HDPE | [5 empty] | 37 |  |  | 3780 | LHS | 1 | SHASHIRANJAN
46 | 2023-04-01 | j102 | j94 | KC ROAD | HDPE | [5 empty] | 17 |  |  | 3797 | LHS | 1 | SHASHIRANJAN
47 | 2023-04-01 | j94 | j96 | KC ROAD | HDPE | [5 empty] | 56 |  |  | 3853 | LHS | 1 | SHASHIRANJAN
48 | 2023-04-17 | j12 | j35 | KC ROAD | HDPE |  |  | 167 | [5 empty] | 4020 | LHS | 1 | SHASHIRANJAN
[6 empty] | 63mm | 75mm | 90mm | 110mm | 125mm | 140mm | 160mm
[6 empty] | 1152 | 330 | 338 | 0 | 0 | 623 | 1577 |  | 4020
[6 empty] | 8570 | 2490 | 2621 | 920 |  | 2569 | 2955 |  | 20125
13224
5724
4488
3117
6168
3827