## mandah & bhoji
GOVERNMENT OF UTTAR PRADESH
STATE WATER & SANITATION MISSION ( SWSM )
Joint Measurement Report of Pipe Line
Name of the Work :- Survey , Design Preparation of DPR , Construction , Commissioning and O&M for 10 Years of Various Rural Water Supply Projects in the state of Uttar Pradesh as Per Request for Proposal for Division " Prayagraj "
Name of the Agency : POWER MECH PROJECTS LIMITED – BHOORATHNOM CONSTRUCTIONS COMPANY PRIVATE LIMITED (JV), Hyderabad.
Name OF Scheme |  | :mandah & bhoji
Block |  | : Mangraura
Total Scope |  | :
JMR No. |  | : 1
Date of JMR |  | :
Sr. No. | Start Node | End Node | Dia | Pipe Length (as per Drawing) | Pipe Length (as per Site) | Width | Depth | Quantity | Type OF Road | Dismantling Length | Dismantling Width | Dismantling Quantity | Restoration Length | Restoration Width | Restoration Quantity | Restoration Status | Remark
1 | j179 | j169 | 63 | 65 | 72.5 | 0.363 | 1.063
2 | j169 | j170 | 63 | 52 | 45.4 | 0.363 | 1.063
3 | j169 | j167 | 63 | 20 | 8.8 | 0.363 | 1.063
4 | j167 | j168 | 63 | 53 | 32.2 | 0.363 | 1.063
5 | j167 | j165 | 63 | 37 | 44.2 | 0.363 | 1.063
6 | j165 | j166 | 63 | 32 | 35.7 | 0.363 | 1.063
7 | j179 | j199 | 63 | 83 | 82.7 | 0.363 | 1.063
8 | j199 | j203 | 63 | 11 | 9.7 | 0.363 | 1.063
9 | j203 | j206 | 63 | 225 | 38.7 | 0.363 | 1.063
10 | j203 | j206 | 63 |  | 13.6 | 0.363 | 1.063 |  | i.l | 13.6 | 0.363 | 4.9368 | =
11 | j203 | j206 | 63 |  | 43.1 | 0.363 | 1.063
12 | j200 | j200a | 63 |  | 2 | 0.363 | 1.063 |  | c.c road crossing | 2 | 0.363 | 0.726
13 | j200a | j200b | 63 |  | 33 | 0.363 | 1.063
14 | j202 | j197 | 63 |  | 22.4 | 0.363 | 1.063 |  | i.l | 22.4 | 0.363 | 8.1312
15 | j197 | j191 | 63 | 46 | 46.5 | 0.363 | 1.063 |  | i.l | 46.5 | 0.363 | 16.8795
16 | j191 | j192 | 63 | 17 | 50.8 | 0.363 | 1.063
17 | j191 | j187 | 63 | 37 | 25.4 | 0.363 | 1.063 |  | i.l | 25.4 | 0.363 | 9.2202
18 | j191 | j187 | 63 |  | 31.1 | 0.363 | 1.063 |  | brick road | 31.1 | 0.363 | 11.2893
19 | j187 | j180 | 63 |  | 29.2 | 0.363 | 1.063 |  | brick road | 29.2 | 0.363 | 10.5996
20 | j180 | j178 | 63 | 46 | 49.9 | 0.363 | 1.063
21 | j180 | j178 | 63 |  | 5.8 | 0.363 | 1.063 |  | b.t road crossing | 5.8 | 0.363 | 2.1054
22 | j178 | j182 | 63 |  | 19.3 | 0.363 | 1.063
23 | j182 | j183 | 63 | 13 | 10.3 | 0.363 | 1.063
24 | j178 | j173 | 63 | 21 | 24 | 0.363 | 1.063
25 | j178 | j173 | 63 |  | 2 | 0.363 | 1.063 |  | b.t road crossing | 2 | 0.363 | 0.726
26 | j173 | j176 | 63 |  | 64.4 | 0.363 | 1.063
27 | j173 | j159 | 63 | 128 | 126.1 | 0.363 | 1.063
28 | j159 | j158 | 63 | 46 | 49.9 | 0.363 | 1.063
29 | j158 | j158(1) | 63 |  | 3.8 | 0.363 | 1.063 |  | brick road | 3.8 | 0.363 | 1.3794
30 | j158 | j171 | 63 | 121 | 111.5 | 0.363 | 1.063
31 | j171 | j172 | 63 | 28 | 20.7 | 0.363 | 1.063
32 | j177 | j171 | 63 | 37 | 46.3 | 0.363 | 1.063
33 | j158 | j157 | 63 | 130 | 125.6 | 0.363 | 1.063
34 | j157 | j151 | 63 |  | 7 | 0.363 | 1.063
35 | j157 | j210 | 63 | 194 | 188 | 0.363 | 1.063
36 | j157 | j101 | 75 | 180 | 174.7 | 0.375 | 1.075
37 | j101 | j101(1) | 75 |  | 9 | 0.375 | 1.075 |  | b.t road crossing | 9 | 0.375 | 3.375
38 | j101 | j108 | 75 |  | 8.2 | 0.375 | 1.075 |  | b.t road crossing | 8.2 | 0.375 | 3.075
39 | j101 | j108 | 75 | 125 | 125 | 0.375 | 1.075
40 | j108 | j158 | 63 | 198 | 198 | 0.363 | 1.063
41 | j158 | j158(1) | 63 |  | 6.5 | 0.363 | 1.063 |  | b.t road crossing | 6.5 | 0.363 | 2.3595
42 | j108 | j102 | 63 | 51 | 53 | 0.363 | 1.063
43 | j102 | j103 | 63 | 98 | 59 | 0.363 | 1.063
44 | j102 | j103 | 63 |  | 3 | 0.363 | 1.063 |  | b.t road crossing | 3 | 0.363 | 1.089
45 | j102 | j98 | 63 | 76 | 80.3 | 0.363 | 1.063
46 | j98 | j82 | 63 |  | 2.5 | 0.363 | 1.063
47 | j98 | j82 | 63 | 118 | 124.3 | 0.363 | 1.063 |  | brick road crossing | 124.3 | 0.363 | 45.1209
48 | j98 | j165 | 63 | 429 | 421.1 | 0.363 | 1.063
49 | j101 | j134 | 63 | 556 | 542.4 | 0.363 | 1.063
50 | j134 | j134(1) | 63 |  | 7 | 0.363 | 1.063 |  | i.l | 7 | 0.363 | 2.541
51 | j134 | j141 | 63 | 87 | 95.8 | 0.363 | 1.063
52 | j141 | j141(1) | 63 |  | 3 | 0.363 | 1.063 |  | Brick crossing | 3 | 0.363 | 1.089
53 | j141 | j145 | 63 | 78 | 75.1 | 0.363 | 1.063
54 | j145 | j144 | 63 | 56 | 62.4 | 0.363 | 1.063
55 | j144 | j146 | 63 | 23 | 71 | 0.363 | 1.063
56 | j144 | j142 | 63 | 81 | 71.5 | 0.363 | 1.063
57 | j142 | j143 | 63 | 74 | 74.3 | 0.363 | 1.063
58 | j142 | j140 | 63 | 50 | 50.3 | 0.363 | 1.063
59 | j140 | j137 | 63 | 88 | 87.3 | 0.363 | 1.063
60 | j141 | j153 | 63 | 143 | 138.7 | 0.363 | 1.063
61 | j153 | j154 | 63 | 28 | 61.1 | 0.363 | 1.063
62 | j153 | j155 | 63 | 139 | 141.6 | 0.363 | 1.063
63 | j134 | j99 | 63 | 192 | 196.3 | 0.363 | 1.063
64 | j99 | j132 | 63 |  | 3.6 | 0.363 | 1.063 |  | i.l road crossing | 3.6 | 0.363 | 1.3068
65 | j99 | j132 | 63 | 94 | 89.9 | 0.363 | 1.063
66 | j132 | j135 | 63 | 64 | 67.3 | 0.363 | 1.063
67 | j99 | j93 | 63 | 170 | 168.6 | 0.363 | 1.063
68 | j93 | j94 | 63 | 114 | 107.2 | 0.363 | 1.063
69 | j93 | j94 | 63 |  | 3.2 | 0.363 | 1.063 |  | i.l road crossing | 3.2 | 0.363 | 1.1616
70 | j94 | j95 | 63 | 108 | 76.1 | 0.363 | 1.063
71 | j95 | j96 | 63 | 16 | 53.7 | 0.363 | 1.063
72 | j94 | j113 | 63 | 340 | 344.5 | 0.363 | 1.063
73 | j113 | j124 | 63 | 258 | 249 | 0.363 | 1.063
74 | j124 | j125 | 63 |  | 31.5 | 0.363 | 1.063
75 | 130 | 127 | 63 | 166 | 276.1 | 0.363 | 1.063
76 | 127 | 121 | 63 |  | 24.6 | 0.363 | 1.063 |  | brick road | 24.6 | 0.363 | 8.9298
77 | j121a | j121b | 63 |  | 13.9 | 0.363 | 1.063
78 | j121a | j117 | 63 | 20 | 23.2 | 0.363 | 1.063
79 | j117 | j118 | 63 | 37 | 34.8 | 0.363 | 1.063
80 | j117 | j104 | 63 | 118 | 16.3 | 0.363 | 1.063 |  | brick road | 16.3 | 0.363 | 5.9169
81 | j117 | j109 | 63 |  | 74.4 | 0.363 | 1.063
82 | j117 | j109 | 63 |  | 29.1 | 0.363 | 1.063 |  | brick road | 29.1 | 0.363 | 10.5633
83 | j109 | j116 | 63 | 38 | 37 | 0.363 | 1.063 |  | brick road | 37 | 0.363 | 13.431
84 | j116 | j123 | 63 | 118 | 125.1 | 0.363 | 1.063
85 | j109 | j100 | 63 | 27 | 21.9 | 0.363 | 1.063
86 | j100 | j104 | 63 | 24 | 23.7 | 0.363 | 1.063
87 | j105 | j105 | 63 | 89 | 72.4 | 0.363 | 1.063
88 | j104 | j106 | 63 | 17 | 17.9 | 0.363 | 1.063 |  | brick road | 17.9 | 0.363 | 6.4977
89 | j106 | j110 | 63 |  | 57.6 | 0.363 | 1.063
90 | j110 | j114 | 63 |  |  | 0.363 | 1.063
91 | j100 | j89 | 63 | 90 | 101.8 | 0.363 | 1.063
92 | j89 | j83 | 63 | 30 | 22.5 | 0.363 | 1.063
93 | j83 | j56 | 63 | 79 | 76.5 | 0.363 | 1.063
94 | j56 | j56(1) | 63 |  | 5.7 | 0.363 | 1.063 |  | b.t road crossing | 5.7 | 0.363 | 2.0691
95 | j56 | j79 | 90 | 56 | 67.1 | 0.39 | 1.09
96 | j79 | j85 | 90 | 44 | 30.1 | 0.39 | 1.09
97 | j85 | j93 | 90 | 170 | 167.7 | 0.39 | 1.09
98 | j122 | j119 | 63 | 126 | 121 | 0.363 | 1.063
99 | j119a | j119b | 63 |  | 63 | 0.363 | 1.063
100 | j56 | j41 | 110 | 512 | 508.6 | 0.41 | 1.11
101 | j101 | j61 | 90 |  | 280.4 | 0.39 | 1.09
102 | j61 | j47 | 110 |  | 183.6 | 0.41 | 1.11
103 | j47 | j47(1) | 63 |  | 7.1 | 0.363 | 1.063 |  | b.t road crossing | 7.1 | 0.363 | 2.5773
104 | j50 | j48 | 63 | 98 | 70.4 | 0.363 | 1.063 |  | b.t | 70.4 | 0.363 | 25.5552
105 | j48 | j49 | 63 |  | 7.4 | 0.363 | 1.063
106 | j48 | j49 | 63 | 58 | 54.9 | 0.363 | 1.063
107 | j48 | j47 | 63 | 60 | 57 | 0.363 | 1.063
108 | j47 | j25 | 110 | 264 | 272.2 | 0.41 | 1.11
109 | j25 | j41 | 110 | 445 | 440 | 0.41 | 1.11
110 | j41 | j41(1) | 110 |  | 9 | 0.41 | 1.11 |  | b.t crossing | 9 | 0.41 | 3.69
111 | j41 | j40 | 63 | 13 | 23 | 0.363 | 1.063
112 | j25 | j8 | 140 |  | 5.6 | 0.44 | 1.14 |  | b.t road crossing | 5.6 | 0.44 | 2.464
113 | j25 | j8 | 140 | 608 | 612.9 | 0.44 | 1.14
114 | j8 | j4 | 160 | 125 | 122 | 0.46 | 1.16 |  | brick road | 122 | 0.46 | 56.12
115 | j4 | j1 | 160 | 24 | 34 | 0.46 | 1.16
116 | j4 | j5 | 63 |  | 139.4 | 0.363 | 1.063
117 | j5a | j5b | 63 |  | 55.3 | 0.363 | 1.063
118 | j8 | j9 | 63 |  | 149.2 | 0.363 | 1.063
119 | j9 | j2 | 63 |  | 67.3 | 0.363 | 1.063 |  | brick road | 67.3 | 0.363 | 24.4299
120 | j2 | j3 | 63 |  | 50.9 | 0.363 | 1.063
121 | j2 | j1 | 110 |  | 152.1 | 0.41 | 1.11
122 | j14 | j16 | 63 |  | 20.3 | 0.363 | 1.063 |  | brick road | 20.3 | 0.363 | 7.3689
123 | j16 | j18 | 63 | 316 | 322.4 | 0.363 | 1.063
124 | j18 | j18(1) | 63 |  | 4.9 | 0.363 | 1.063
125 | j18 | j20 | 63 | 325 | 355 | 0.363 | 1.063
126 | j20 | j22 | 63 | 369 | 359 | 0.363 | 1.063
127 | j22 | j23 | 63 | 49 | 51.4 | 0.363 | 1.063
128 | j23 | j28 | 63 | 391 | 380 | 0.363 | 1.063
129 | j28 | j29 | 63 | 25 | 129.1 | 0.363 | 1.063
130 | j28 | j31 | 63 | 31 | 134.1 | 0.363 | 1.063
131 | j31 | j32 | 63 |  | 65.1 | 0.363 | 1.063
132 | j32 | j33 | 63 |  | 39.6 | 0.363 | 1.063
133 | j32 | j34 | 63 |  | 275.1 | 0.363 | 1.063
134 | j34 | j42 | 63 |  | 262.3 | 0.363 | 1.063
135 | j42 | j44 | 63 |  | 92 | 0.363 | 1.063
136 | j34 | j35 | 63 |  | 132 | 0.363 | 1.063
137 | j35 | j37 | 63 |  | 10 | 0.363 | 1.063
138 | j35 | j65 | 63 |  | 45 | 0.363 | 1.063
139 | j37 | j38 | 63 |  | 39 | 0.363 | 1.063
140 | j37 | j39 | 63 |  | 81 | 0.363 | 1.063
141 | j31 | j30 | 63 |  | 146 | 0.363 | 1.063
13407.6
296.7243
|  |  | 63 | 75 | 90 | 110 | 140 | 160
|  |  | 10205.4 | 316.9 | 545.3 | 1565.5 | 618.5 | 156

## RESTORATION
GOVERNMENT OF UTTAR PRADESH
STATE WATER & SANITATION MISSION ( SWSM )
Joint Measurement Report of Pipe Line
Name of the Work :- Survey , Design Preparation of DPR , Construction , Commissioning and O&M for 10 Years of Various Rural Water Supply Projects in the state of Uttar Pradesh as Per Request for Proposal for Division " Prayagraj "
Name of the Agency : POWER MECH PROJECTS LIMITED – BHOORATHNOM CONSTRUCTIONS COMPANY PRIVATE LIMITED (JV), Hyderabad.
Name OF Scheme |  | :mandah & bhoji
Block |  | : Mangraura
Total Scope |  | :
JMR No. |  | : 1
Date of JMR |  | :
Sr. No. | Start Node | End Node | Dia | Pipe Length (as per Drawing) | Pipe Length (as per Site) | Width | Depth | Quantity | Type OF Road | Dismantling Length | Dismantling Width | Dismantling Quantity | Restoration Length | Restoration Width | Restoration Quantity | Restoration Status | Remark
1 | j203 | j206 | 63 | 13.6 | 0.363 | 1.063 |  | i.l | 13.6 | 0.363 | 4.9368
2 | j200 | j200a | 63 | 2 | 0.363 | 1.063 |  | c.c road crossing | 2 | 0.363 | 0.726
3 | j202 | j197 | 63 | 22.4 | 0.363 | 1.063 |  | i.l | 22.4 | 0.363 | 8.1312
4 | j197 | j191 | 63 | 46.5 | 0.363 | 1.063 |  | i.l | 46.5 | 0.363 | 16.8795
5 | j191 | j187 | 63 | 25.4 | 0.363 | 1.063 |  | i.l | 25.4 | 0.363 | 9.2202
6 | j191 | j187 | 63 | 31.1 | 0.363 | 1.063 |  | brick road | 31.1 | 0.363 | 11.2893
7 | j187 | j180 | 63 | 29.2 | 0.363 | 1.063 |  | brick road | 29.2 | 0.363 | 10.5996
8 | j180 | j178 | 63 | 5.8 | 0.363 | 1.063 |  | b.t road crossing | 5.8 | 0.363 | 2.1054
9 | j178 | j173 | 63 | 2 | 0.363 | 1.063 |  | b.t road crossing | 2 | 0.363 | 0.726
10 | j158 | j158(1) | 63 | 3.8 | 0.363 | 1.063 |  | brick road | 3.8 | 0.363 | 1.3794
11 | j101 | j101(1) | 75 | 9 | 0.375 | 1.075 |  | b.t road crossing | 9 | 0.375 | 3.375
12 | j101 | j108 | 75 | 8.2 | 0.375 | 1.075 |  | b.t road crossing | 8.2 | 0.375 | 3.075
13 | j158 | j158(1) | 63 | 6.5 | 0.363 | 1.063 |  | b.t road crossing | 6.5 | 0.363 | 2.3595
14 | j102 | j103 | 63 | 3 | 0.363 | 1.063 |  | b.t road crossing | 3 | 0.363 | 1.089
15 | j98 | j82 | 63 | 124.3 | 0.363 | 1.063 |  | brick road crossing | 124.3 | 0.363 | 45.1209
16 | j134 | j134(1) | 63 | 7 | 0.363 | 1.063 |  | i.l | 7 | 0.363 | 2.541
17 | j141 | j141(1) | 63 | 3 | 0.363 | 1.063 |  | Brick crossing | 3 | 0.363 | 1.089
18 | j99 | j132 | 63 | 3.6 | 0.363 | 1.063 |  | i.l road crossing | 3.6 | 0.363 | 1.3068
19 | j93 | j94 | 63 | 3.2 | 0.363 | 1.063 |  | i.l road crossing | 3.2 | 0.363 | 1.1616
20 | 127 | 121 | 63 | 24.6 | 0.363 | 1.063 |  | brick road | 24.6 | 0.363 | 8.9298
21 | j117 | j104 | 63 | 16.3 | 0.363 | 1.063 |  | brick road | 16.3 | 0.363 | 5.9169
22 | j117 | j109 | 63 | 29.1 | 0.363 | 1.063 |  | brick road | 29.1 | 0.363 | 10.5633
23 | j109 | j116 | 63 | 37 | 0.363 | 1.063 |  | brick road | 37 | 0.363 | 13.431
24 | j104 | j106 | 63 | 17.9 | 0.363 | 1.063 |  | brick road | 17.9 | 0.363 | 6.4977
25 | j56 | j56(1) | 63 | 5.7 | 0.363 | 1.063 |  | b.t road crossing | 5.7 | 0.363 | 2.0691
26 | j47 | j47(1) | 63 | 7.1 | 0.363 | 1.063 |  | b.t road crossing | 7.1 | 0.363 | 2.5773
27 | j50 | j48 | 63 | 70.4 | 0.363 | 1.063 |  | b.t | 70.4 | 0.363 | 25.5552
28 | j41 | j41(1) | 110 | 9 | 0.41 | 1.11 |  | b.t crossing | 9 | 0.41 | 3.69
29 | j25 | j8 | 140 | 5.6 | 0.44 | 1.14 |  | b.t road crossing | 5.6 | 0.44 | 2.464
30 | j8 | j4 | 160 | 122 | 0.46 | 1.16 |  | brick road | 122 | 0.46 | 56.12
31 | j9 | j2 | 63 | 67.3 | 0.363 | 1.063 |  | brick road | 67.3 | 0.363 | 24.4299
32 | j14 | j16 | 63 | 20.3 | 0.363 | 1.063 |  | brick road | 20.3 | 0.363 | 7.3689