## SAKRA 2
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | SAKRA | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | J14 | J31 | 140 | 105 | 6 | 3 | 1 | 4 | no
2 | J31 | J106 | 140 | 18 | 6 | 3 | 1 | 4 | no
3 | J106 | J74A | 140 | 42 | 6 | 3 | 1 | 4 | no
4 | J74A | J74 | 140 | 7 | 6 | 3 | 1 | 4 | no
5 | J74 | J58 | 140 | 78 | 6 | 3 | 1 | 4 | no
6 | J58 | J48 | 140 | 88 | 6 | 3 | 1 | 4 | no
7 | J48 | J5 | 140 | 18 | 6 | 3 | 1 | 4 | no
8 | J5 | J85 | 140 | 77 | 6 | 3 | 1 | 4 | no
9 | J29 | J227 | 140 | 515 | 6 | 3 | 1 | 4 | no
10 | J227 | J228 | 140 | 260 | 6 | 3 | 1 | 4 | no
11 | J228 | J188 | 140 | 641 | 6 | 3 | 1 | 4 | no
12 | J77 | J47 | 140 | 92 | 6 | 3 | 1 | 4 | no
13 | J47 | J45 | 140 | 261 | 6 | 3 | 1 | 4 | no
14 | J45 | J102 | 140 | 64 | 6 | 3 | 1 | 4 | no
15 | 102 | 137 | 140 | 140 | 6 | 3 | 1 | 4 | no
16 | 137 | 67 | 140 | 28 | 6 | 3 | 1 | 4 | no
17 | 67 | 24 | 140 | 196 | 6 | 3 | 1 | 4 | no
18 | 24 | 38 | 140 | 288 | 6 | 3 | 1 | 4 | no
19 | 38 | 167 | 140 | 484 | 6 | 3 | 1 | 4 | no
20 | J130 | J74 | 110 | 68 | 6 | 3 | 1 | 4 | no
21 | J74 | J69/A | 110 | 44 | 6 | 3 | 1 | 4 | no
22 | J130 | J129 | 110 | 11 | 6 | 3 | 1 | 4 | no
23 | J129 | J82 | 110 | 83 | 6 | 3 | 1 | 4 | no
24 | J82 | J66 | 110 | 176 | 6 | 3 | 1 | 4 | no
25 | J66 | J83 | 110 | 57 | 6 | 3 | 1 | 4 | no
26 | J83 | J101 | 110 | 31 | 6 | 3 | 1 | 4 | no
27 | J101 | J96 | 110 | 37 | 6 | 3 | 1 | 4 | no
28 | J101 | J96 | 110 | 29 | 6 | 3 | 1 | 4 | no
29 | J96 | J109 | 110 | 47 | 6 | 3 | 1 | 4 | no
30 | J109 | J1 | 110 | 73 | 6 | 3 | 1 | 4 | no
31 | J109 | J1 | 110 | 3 | 6 | 3 | 1 | 4 | no
32 | J1 | J23 | 110 | 109 | 6 | 3 | 1 | 4 | no
33 | J23 | J51 | 110 | 170 | 6 | 3 | 1 | 4 | no
34 | J23 | J51 | 110 | 3 | 6 | 3 | 1 | 4 | no
35 | J51 | J61 | 110 | 53 | 6 | 3 | 1 | 4 | no
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | SAKRA | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | J32 | J13 | 90 | 48 | 5.5 | 3.3 | 1 | 4.3 | no
2 | J13 | J9 | 90 | 163 | 5.5 | 3.3 | 1 | 4.3 | no
3 | J13 | J9 | 90 | 5 | 5.5 | 3.3 | 1 | 4.3 | no
4 | J9 | J49 | 90 | 7 | 5.5 | 3.3 | 1 | 4.3 | no
5 | J49 | J46 | 90 | 7 | 5.5 | 3.3 | 1 | 4.3 | no
6 | J49 | J2 | 90 | 107 | 5.5 | 3.3 | 1 | 4.3 | no
7 | J2 | J4 | 90 | 402 | 5.5 | 3.3 | 1 | 4.3 | no
8 | J72 | J81 | 90 | 50 | 5.5 | 3.3 | 1 | 4.3 | no
9 | J48 | J150 | 90 | 167 | 5.5 | 3.3 | 1 | 4.3 | no
10 | J9 | J12 | 75 | 257 | 5.5 | 3.3 | 1 | 4.3 | no
11 | J46 | J19 | 75 | 202 | 5.5 | 3.3 | 1 | 4.3 | no
12 | J2 | J129 | 75 | 98 | 5.5 | 3.3 | 1 | 4.3 | no
13 | J6 | J59 | 63 | 197 | 5.5 | 3.3 | 1 | 4.3 | no
14 | J59 | J172 | 63 | 40 | 5.5 | 3.3 | 1 | 4.3 | no
15 | J59 | J172 | 63 | 3 | 5.5 | 3.3 | 1 | 4.3 | no
16 | J59 | J7 | 63 | 250 | 5.5 | 3.3 | 1 | 4.3 | no
17 | J7 | J114 | 63 | 72 | 5.5 | 3.3 | 1 | 4.3 | no
18 | J7 | J114 | 63 | 3 | 5.5 | 3.3 | 1 | 4.3 | no
19 | J32 | J111 | 63 | 54 | 5.5 | 3.3 | 1 | 4.3 | no
20 | J32 | J111 | 63 | 45 | 5.5 | 3.3 | 1 | 4.3 | no
21 | J13 | J78 | 63 | 106 | 5.5 | 3.3 | 1 | 4.3 | no
22 | J13 | J78 | 63 | 23 | 5.5 | 3.3 | 1 | 4.3 | no
23 | J78 | J171 | 63 | 44 | 5.5 | 3.3 | 1 | 4.3 | no
24 | J78 | J171 | 63 | 3 | 5.5 | 3.3 | 1 | 4.3 | no
25 | J12 | J42 | 63 | 101 | 5.5 | 3.3 | 1 | 4.3 | no
26 | J42 | J178 | 63 | 44 | 5.5 | 3.3 | 1 | 4.3 | no
27 | J42 | J132 | 63 | 74 | 5.5 | 3.3 | 1 | 4.3 | no
28 | J49 | J125 | 63 | 90 | 5.5 | 3.3 | 1 | 4.3 | no
29 | J19 | J182 | 63 | 36 | 5.5 | 3.3 | 1 | 4.3 | no
30 | J19 | J146 | 63 | 65 | 5.5 | 3.3 | 1 | 4.3 | no
31 | J74 | J150 | 63 | 64 | 5.5 | 3.3 | 1 | 4.3 | no
32 | J74 | J150 | 63 | 10 | 5.5 | 3.3 | 1 | 4.3 | no
33 | J82 | J162 | 63 | 50 | 5.5 | 3.3 | 1 | 4.3 | no
34 | J66 | J168 | 63 | 138 | 5.5 | 3.3 | 1 | 4.3 | no
35 | J101 | J203 | 63 | 33 | 5.5 | 3.3 | 1 | 4.3 | no
36 | J96 | J123 | 63 | 3 | 5.5 | 3.3 | 1 | 4.3 | no
37 | J96 | J123 | 63 | 39 | 5.5 | 3.3 | 1 | 4.3 | no
38 | J109 | J170 | 63 | 46 | 5.5 | 3.3 | 1 | 4.3 | no
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | SAKRA | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | 20 | 18 | 90 | 179 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
2 | 18 | 139 | 90 | 23 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
3 | 113 | 65 | 90 | 88 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
4 | 65 | 27 | 90 | 121 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
5 | 20 | 40 | 90 | 314 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
6 | 40 | 144 | 90 | 59 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
7 | 18 | J97,J107,J140 | 90 | 115 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
8 | 18 | J97,J107,J140 | 90 | 145 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
9 | J61 | J68 | 90 | 155 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
10 | J61 | J68 | 90 | 11 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
11 | J79 | J3 | 90 | 88 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
12 | J79 | J3 | 90 | 50 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
13 | J93 | J28 | 90 | 20 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
14 | J93 | J28 | 90 | 58 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
15 | J7 | J32 | 90 | 94 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
16 | 100 | 102 | 75 | 29 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
17 | 100 | 175 | 75 | 41 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
18 | 67 | 137 | 75 | 120 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
19 | 38 | 202 | 75 | 45 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
20 | 144 | 54 | 75 | 106 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
21 | 185 | 103 | 75 | 86 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
22 | 103 | 140 | 75 | 39 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
23 | 140 | 118 | 75 | 54 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
24 | 103 | 110 | 75 | 75 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
25 | 217 | J157,J117 | 75 | 48 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
26 | 117 | 65 | 75 | 79 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
27 | 117 | 65 | 75 | 50 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
28 | J1 | J76 | 63 | 49 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
29 | J76 | J116 | 63 | 40 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
30 | J1 | J10 | 63 | 420 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
31 | J23 | J37 | 63 | 104 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
32 | J83 | J71 | 63 | 78 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
33 | J66 | J71 | 63 | 17 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
34 | J71 | J94 | 63 | 50 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
35 | J94 | J11 | 63 | 66 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
36 | J94 | J11 | 63 | 14 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
37 | J11 | J22,J72 | 63 | 135 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
38 | J11 | J22,J72 | 63 | 34 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
39 | J72 | J199 | 63 | 13 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
40 | J57 | J138 | 63 | 71 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
41 | J3 | J39 | 63 | 254 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh | [7 empty] | 32.5
TPI:- |  | Medhaj Techno Concept Pvt. Ltd. | [7 empty] | 16.3
Contractor:- |  | Power Mech Project Ltd. | [7 empty] | 13
Block :- |  | Mangraura | [7 empty] | 23
GP :- |  | SAKRA | [5 empty] | Date |  | 11.3
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | J14 | J44 | 75 | 66 | 5.5KG/CM2 | 3 | 1 | 4 | NO
2 | J14 | J44 | 75 | 29 | 5.5KG/CM2 | 3 | 1 | 4 | NO
3 | J44 | J130 | 75 | 66 | 5.5KG/CM2 | 3 | 1 | 4 | NO
4 | J11 | J29 | 75 | 233 | 5.5KG/CM2 | 3 | 1 | 4 | NO
5 | J3 | J33 | 75 | 5 | 5.5KG/CM2 | 3 | 1 | 4 | NO
6 | J3 | J33 | 75 | 151 | 5.5KG/CM2 | 3 | 1 | 4 | NO
7 | J3 | J33 | 75 | 54 | 5.5KG/CM2 | 3 | 1 | 4 | NO
8 | J33 | J89 | 75 | 44 | 5.5KG/CM2 | 3 | 1 | 4 | NO
9 | J93 | J33 | 75 | 15 | 5.5KG/CM2 | 3 | 1 | 4 | NO
10 | J26 | J32 | 75 | 47 | 5.5KG/CM2 | 3 | 1 | 4 | NO
11 | J89 | J16,J152 | 75 | 100 | 5.5KG/CM2 | 3 | 1 | 4 | NO
12 | J77 | J98 | 75 | 125 | 5.5KG/CM2 | 3 | 1 | 4 | NO
13 | J98 | J165 | 75 | 87 | 5.5KG/CM2 | 3 | 1 | 4 | NO
14 | J47 | J163 | 75 | 47 | 5.5KG/CM2 | 3 | 1 | 4 | NO
15 | J163 | J17 | 75 | 195 | 5.5KG/CM2 | 3 | 1 | 4 | NO
16 | J45 | J127 | 75 | 68 | 5.5KG/CM2 | 3 | 1 | 4 | NO
17 | J127 | J75 | 75 | 40 | 5.5KG/CM2 | 3 | 1 | 4 | NO
18 | J75 | J175 | 75 | 62 | 5.5KG/CM2 | 3 | 1 | 4 | NO
19 | J75 | J104 | 75 | 25 | 5.5KG/CM2 | 3 | 1 | 4 | NO
20 | J75 | J104 | 75 | 60 | 5.5KG/CM2 | 3 | 1 | 4 | NO
21 | J102 | J100 | 75 | 32 | 5.5KG/CM2 | 3 | 1 | 4 | NO
22 | 137 | 100 | 75 | 72 | 5.5KG/CM2 | 3 | 1 | 4 | NO
23 | J93 | J186 | 63 | 36 | 5.5KG/CM2 | 3 | 1 | 4 | NO
24 | J93 | J186 | 63 | 3 | 5.5KG/CM2 | 3 | 1 | 4 | NO
25 | J52 | J193 | 63 | 23 | 5.5KG/CM2 | 3 | 1 | 4 | NO
26 | J52 | J60 | 63 | 240 | 5.5KG/CM2 | 3 | 1 | 4 | NO
27 | J26 | J63 | 63 | 168 | 5.5KG/CM2 | 3 | 1 | 4 | NO
28 | J74 | J174 | 63 | 30 | 5.5KG/CM2 | 3 | 1 | 4 | NO
29 | J58 | J180 | 63 | 27 | 5.5KG/CM2 | 3 | 1 | 4 | NO
30 | J5 | J8 | 63 | 166 | 5.5KG/CM2 | 3 | 1 | 4 | NO
31 | J5 | J8 | 63 | 177 | 5.5KG/CM2 | 3 | 1 | 4 | NO
32 | J98 | J201 | 63 | 21 | 5.5KG/CM2 | 3 | 1 | 4 | NO
33 | J163 | J187 | 63 | 58 | 5.5KG/CM2 | 3 | 1 | 4 | NO
34 | J17 | J159 | 63 | 57 | 5.5KG/CM2 | 3 | 1 | 4 | NO
35 | J159 | J159A | 63 | 66 | 5.5KG/CM2 | 3 | 1 | 4 | NO
36 | J104 | J56 | 63 | 102 | 5.5KG/CM2 | 3 | 1 | 4 | NO
37 | J104 | J56 | 63 | 22 | 5.5KG/CM2 | 3 | 1 | 4 | NO
38 | J56 | J220 | 63 | 76 | 5.5KG/CM2 | 3 | 1 | 4 | NO
39 | 24 | 192 | 63 | 200 | 5.5KG/CM2 | 3 | 1 | 4 | NO
40 | 24 | 192 | 63 | 200 | 5.5KG/CM2 | 3 | 1 | 4 | NO
41 | 27 | 84 | 63 | 280 | 5.5KG/CM2 | 3 | 1 | 4 | NO
42 | 54 | 112 | 63 | 198 | 5.5KG/CM2 | 3 | 1 | 4 | NO
43 | 54 | 160 | 63 | 97 | 5.5KG/CM2 | 3 | 1 | 4 | NO
44 | 160 | 207 | 63 | 44 | 5.5KG/CM2 | 3 | 1 | 4 | NO
45 | 160 | 185 | 63 | 97 | 5.5KG/CM2 | 3 | 1 | 4 | NO
46 | 110 | 226 | 63 | 119 | 5.5KG/CM2 | 3 | 1 | 4 | NO
47 | 110 | 217 | 63 | 58 | 5.5KG/CM2 | 3 | 1 | 4 | NO
48 | 117 | 169 | 63 | 86 | 5.5KG/CM2 | 3 | 1 | 4 | NO
49 | 117 | 169 | 63 | 2 | 5.5KG/CM2 | 3 | 1 | 4 | NO
50 | 18 | J139,J191 | 63 | 47 | 5.5KG/CM2 | 3 | 1 | 4 | NO
51 | 18 | J139,J191 | 63 | 42 | 5.5KG/CM2 | 3 | 1 | 4 | NO
52 | 18 | 95 | 63 | 40 | 5.5KG/CM2 | 3 | 1 | 4 | NO
53 | 18 | 95 | 63 | 150 | 5.5KG/CM2 | 3 | 1 | 4 | NO
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date