## brahupur
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | barahupur | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | j7 | j1 | 200 | 1502.2 | 6 | 3 | 1 | 4 | no
2 | j7 | j1 | 200 | 7.8 | 6 | 3 | 1 | 4 | no
3 | j111 | j112 | 63 | 215 | 6 | 3 | 1 | 4 | no
4 | j143 | j53 | 63 | 5 | 6 | 3 | 1 | 4 | no
5 | j93 | 92 | 63 | 7 | 6 | 3 | 1 | 4 | no
6 | j111 | j240 | 63 | 83.3 | 6 | 3 | 1 | 4 | no
7 | j186 | j141 | 63 | 65 | 6 | 3 | 1 | 4 | no
8 | j186 | j179 | 63 | 26.8 | 6 | 3 | 1 | 4 | no
9 | j232 | j179 | 63 | 53 | 6 | 3 | 1 | 4 | no
10 | j179 | j163 | 63 | 76.2 | 6 | 3 | 1 | 4 | no
11 | j179 | j163 | 63 | 5 | 6 | 3 | 1 | 4 | no
12 | j93 | j117 | 63 | 5 | 6 | 3 | 1 | 4 | no
13 | j93 | j163 | 63 | 7 | 6 | 3 | 1 | 4 | no
14 | j50 | j51 | 63 | 208.3 | 6 | 3 | 1 | 4 | no
15 | j5 | j4 | 63 | 94.6 | 6 | 3 | 1 | 4 | no
16 | j8 | j9 | 63 | 6 | 6 | 3 | 1 | 4 | no
17 | j8 | j9 | 63 | 76 | 6 | 3 | 1 | 4 | no
18 | j79 | j7 | 63 | 815.3 | 6 | 3 | 1 | 4 | no
19 | j79 | j35 | 63 | 46.3 | 6 | 3 | 1 | 4 | no
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | barahupur | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | j41 | j7 | 160 | 625 | 5.5 | 3 | 1 | 4 | no
2 | j167 | j229 | 140 | 231.3 | 5.5 | 3 | 1 | 4 | no
3 | j229 | j216 | 140 | 10 | 5.5 | 3 | 1 | 4 | no
4 | j216 | j41 | 140 | 338 | 5.5 | 3 | 1 | 4 | no
5 | j41 | j50 | 125 | 129.7 | 5.5 | 3 | 1 | 4 | no
6 | j50 | j111 | 125 | 111.8 | 5.5 | 3 | 1 | 4 | no
7 | j47 | j254 | 63 | 112.3 | 5.5 | 3 | 1 | 4 | no
8 | j24 | j254 | 63 | 161 | 5.5 | 3 | 1 | 4 | no
9 | j32 | j65 | 63 | 25 | 5.5 | 3 | 1 | 4 | no
10 | j65 | j54 | 63 | 30 | 5.5 | 3 | 1 | 4 | no
11 | j65 | j151 | 63 | 23.4 | 5.5 | 3 | 1 | 4 | no
12 | j256 | j267 | 63 | 104.3 | 5.5 | 3 | 1 | 4 | no
13 | j267 | j187 | 63 | 53.2 | 5.5 | 3 | 1 | 4 | no
14 | j267 | j315 | 63 | 123.2 | 5.5 | 3 | 1 | 4 | no
15 | j315 | j271 | 63 | 40 | 5.5 | 3 | 1 | 4 | no
16 | j315 | j271 | 63 | 11.1 | 5.5 | 3 | 1 | 4 | no
17 | j315 | j321 | 63 | 186.8 | 5.5 | 3 | 1 | 4 | no
18 | j216 | j265 | 63 | 315.6 | 5.5 | 3 | 1 | 4 | no
19 | j55 | j119 | 63 | 21.1 | 5.5 | 3 | 1 | 4 | no
20 | j88 | j66 | 63 | 30.2 | 5.5 | 3 | 1 | 4 | no
21 | j58 | j88 | 63 | 27.2 | 5.5 | 3 | 1 | 4 | no
22 | j55 | j56 | 63 | 20.5 | 5.5 | 3 | 1 | 4 | no
23 | j88 | j72 | 63 | 24.7 | 5.5 | 3 | 1 | 4 | no
24 | j72 | j84 | 63 | 54.5 | 5.5 | 3 | 1 | 4 | no
25 | j27 | j84 | 63 | 48.5 | 5.5 | 3 | 1 | 4 | no
26 | j27 | j45 | 63 | 46.8 | 5.5 | 3 | 1 | 4 | no
27 | j45 | j64 | 63 | 41.5 | 5.5 | 3 | 1 | 4 | no
28 | j45 | j155 | 63 | 62.6 | 5.5 | 3 | 1 | 4 | no
29 | j45 | j155 | 63 | 34 | 5.5 | 3 | 1 | 4 | no
30 | j155 | j254 | 63 | 26 | 5.5 | 3 | 1 | 4 | no
31 | j254 | j45 | 63 | 71.3 | 5.5 | 3 | 1 | 4 | no
32 | j254 | j151 | 63 | 19 | 5.5 | 3 | 1 | 4 | no
33 | j151 | j72 | 63 | 80.2 | 5.5 | 3 | 1 | 4 | no
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | barahupur | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | j155 | j207 | 63 | 198.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
2 | j155 | j207 | 63 | 38.7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
3 | j306 | j215 | 63 | 65.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
4 | j306 | j324 | 63 | 7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
5 | j324 | j206 | 63 | 55 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
6 | j206 | j142 | 63 | 106 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
7 | j206 | j184 | 63 | 85.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
8 | j184 | j120 | 63 | 50 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
9 | j184 | j319 | 63 | 79 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
10 | j292 | j300 | 63 | 41 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
11 | j309 | j309a | 63 | 51 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
12 | j322 | j309 | 63 | 91.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
13 | j322a | j285 | 63 | 103 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
14 | j324 | j233 | 63 | 113.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
15 | j233 | j339 | 63 | 65.4 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
16 | j233 | j259 | 63 | 368.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
17 | j233 | j259 | 63 | 7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
18 | j259 | j102 | 110 | 311.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
19 | j246 | j102 | 63 | 413.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
20 | j246 | j102 | 63 | 10 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
21 | j80 | j339 | 63 | 307.7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
22 | j259 | j216 | 125 | 211 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | barahupur | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | j306 | j259 | 63 | 803.2 | 5.5 | 3.3 | 1 | 4.3 | no
2 | j207 | j204 | 63 | 72.3 | 5.5 | 3.3 | 1 | 4.3 | no
3 | j198 | j107 | 63 | 133 | 5.5 | 3.3 | 1 | 4.3 | no
4 | j107 | j132 | 63 | 102.3 | 5.5 | 3.3 | 1 | 4.3 | no
5 | j132 | j60 | 63 | 23.2 | 5.5 | 3.3 | 1 | 4.3 | no
6 | j107 | j305 | 63 | 76.5 | 5.5 | 3.3 | 1 | 4.3 | no
7 | j279 | j152 | 63 | 37.2 | 5.5 | 3.3 | 1 | 4.3 | no
8 | j355 | j20 | 63 | 157.2 | 5.5 | 3.3 | 1 | 4.3 | no
9 | j86 | j162 | 63 | 98.2 | 5.5 | 3.3 | 1 | 4.3 | no
10 | j162 | j42 | 63 | 82.3 | 5.5 | 3.3 | 1 | 4.3 | no
11 | j42 | j40 | 63 | 78 | 5.5 | 3.3 | 1 | 4.3 | no
12 | j42 | j61 | 63 | 73.2 | 5.5 | 3.3 | 1 | 4.3 | no
13 | j162 | j109 | 63 | 45 | 5.5 | 3.3 | 1 | 4.3 | no
14 | j145 | j146 | 63 | 69.3 | 5.5 | 3.3 | 1 | 4.3 | no
15 | j224 | j274 | 63 | 125.1 | 5.5 | 3.3 | 1 | 4.3 | no
16 | j224 | j274 | 63 | 5 | 5.5 | 3.3 | 1 | 4.3 | no
17 | j274 | j326 | 63 | 148.8 | 5.5 | 3.3 | 1 | 4.3 | no
18 | j274 | j291 | 63 | 248.6 | 5.5 | 3.3 | 1 | 4.3 | no
19 | j291 | j347 | 63 | 15 | 5.5 | 3.3 | 1 | 4.3 | no
20 | j347 | j190 | 63 | 162.3 | 5.5 | 3.3 | 1 | 4.3 | no
21 | j228 | j338 | 63 | 65 | 5.5 | 3.3 | 1 | 4.3 | no
22 | j346 | j330 | 63 | 47.7 | 5.5 | 3.3 | 1 | 4.3 | no
23 | j327 | j323 | 63 | 30.3 | 5.5 | 3.3 | 1 | 4.3 | no
24 | j327 | j323 | 63 | 46.4 | 5.5 | 3.3 | 1 | 4.3 | no
25 | j291 | j327 | 63 | 51 | 5.5 | 3.3 | 1 | 4.3 | no
26 | j327 | j349 | 63 | 33.3 | 5.5 | 3.3 | 1 | 4.3 | no
27 | j327a | j327b | 63 | 35 | 5.5 | 3.3 | 1 | 4.3 | no
28 | j349 | j225 | 63 | 29 | 5.5 | 3.3 | 1 | 4.3 | no
29 | j225 | j223 | 63 | 16 | 5.5 | 3.3 | 1 | 4.3 | no
30 | j225 | j262 | 63 | 21.3 | 5.5 | 3.3 | 1 | 4.3 | no
31 | j225 | j218 | 63 | 46.6 | 5.5 | 3.3 | 1 | 4.3 | no
32 | j220 | j349 | 63 | 56.3 | 5.5 | 3.3 | 1 | 4.3 | no
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | barahupur | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | j122 | j73 | 63 | 75 | 6 | 3 | 1 | 4 | no
2 | j278 | j345 | 63 | 30.1 | 6 | 3 | 1 | 4 | no
3 | j345 | j157 | 63 | 65 | 6 | 3 | 1 | 4 | no
4 | j345 | j194 | 63 | 44.2 | 6 | 3 | 1 | 4 | no
5 | j304 | j283 | 63 | 15 | 6 | 3 | 1 | 4 | no
6 | j350 | j318 | 63 | 34.3 | 6 | 3 | 1 | 4 | no
7 | j296 | j350 | 63 | 30.1 | 6 | 3 | 1 | 4 | no
8 | j356 | j314 | 63 | 30.3 | 6 | 3 | 1 | 4 | no
9 | j314 | j258 | 63 | 15.2 | 6 | 3 | 1 | 4 | no
10 | j314 | j258 | 63 | 45.5 | 6 | 3 | 1 | 4 | no
11 | j202 | j129 | 63 | 31.1 | 6 | 3 | 1 | 4 | no
12 | j314 | j296 | 63 | 41 | 6 | 3 | 1 | 4 | no
13 | j350 | j147 | 63 | 31.1 | 6 | 3 | 1 | 4 | no
14 | j350 | j147 | 63 | 18 | 6 | 3 | 1 | 4 | no
15 | j109 | j255 | 63 | 50 | 6 | 3 | 1 | 4 | no
16 | j255 | j59 | 63 | 54.3 | 6 | 3 | 1 | 4 | no
17 | j123 | j255 | 63 | 51 | 6 | 3 | 1 | 4 | no
18 | j255 | j357 | 63 | 23.5 | 6 | 3 | 1 | 4 | no
19 | j208 | j342 | 63 | 65.3 | 6 | 3 | 1 | 4 | no
20 | j235 | j266 | 63 | 278.3 | 6 | 3 | 1 | 4 | no
21 | j266 | j189 | 63 | 51.3 | 6 | 3 | 1 | 4 | no
22 | j266 | j234 | 63 | 48.1 | 6 | 3 | 1 | 4 | no
23 | j235 | j266 | 63 | 7 | 6 | 3 | 1 | 4 | no
24 | j266 | j189 | 63 | 5 | 6 | 3 | 1 | 4 | no
25 | j321 | j19 | 63 | 753.3 | 6 | 3 | 1 | 4 | no
26 | j19 | j21 | 90 | 60.3 | 6 | 3 | 1 | 4 | no
27 | j19 | j49 | 75 | 120 | 6 | 3 | 1 | 4 | no
28 | j66 | j55 | 63 | 26 | 6 | 3 | 1 | 4 | no
29 | j49 | j66 | 75 | 30 | 6 | 3 | 1 | 4 | no
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | barahupur | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | j270 | j277 | 63 | 30.1 | 5.5 | 3.5 | 1 | 4.5 | no
2 | j220 | j234 | 63 | 41 | 5.5 | 3.5 | 1 | 4.5 | no
3 | j234 | j224 | 63 | 118.3 | 5.5 | 3.5 | 1 | 4.5 | no
4 | j234 | j224 | 63 | 5 | 5.5 | 3.5 | 1 | 4.5 | no
5 | j6 | j159 | 63 | 1113.3 | 5.5 | 3.5 | 1 | 4.5 | no
6 | j159 | j115 | 63 | 489.6 | 5.5 | 3.5 | 1 | 4.5 | no
7 | j115 | j101 | 63 | 123.3 | 5.5 | 3.5 | 1 | 4.5 | no
8 | j115 | j93 | 63 | 150.8 | 5.5 | 3.5 | 1 | 4.5 | no
9 | j93 | j103 | 63 | 130.7 | 5.5 | 3.5 | 1 | 4.5 | no
10 | j93 | j144 | 63 | 37 | 5.5 | 3.5 | 1 | 4.5 | no
11 | j144 | j90 | 63 | 35.3 | 5.5 | 3.5 | 1 | 4.5 | no
12 | j143 | j165 | 63 | 10 | 5.5 | 3.5 | 1 | 4.5 | no
13 | j165 | j158 | 63 | 68 | 5.5 | 3.5 | 1 | 4.5 | no
14 | j155 | j207 | 63 | 51.5 | 5.5 | 3.5 | 1 | 4.5 | no
15 | j212 | j126 | 63 | 394.9 | 5.5 | 3.5 | 1 | 4.5 | no
16 | j126 | j56 | 63 | 170 | 5.5 | 3.5 | 1 | 4.5 | no
17 | j126 | j134 | 63 | 193 | 5.5 | 3.5 | 1 | 4.5 | no
18 | j311 | j134 | 63 | 648.3 | 5.5 | 3.5 | 1 | 4.5 | no
19 | j134 | j211 | 63 | 332.2 | 5.5 | 3.5 | 1 | 4.5 | no
20 | j161 | j161a | 63 | 61.3 | 5.5 | 3.5 | 1 | 4.5 | no
21 | j276 | j306 | 63 | 78 | 5.5 | 3.5 | 1 | 4.5 | no
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | barahupur | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | j326 | j264 | 63 | 48 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
2 | j326 | j287 | 63 | 52 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
3 | j287 | j286 | 63 | 29 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
4 | j286 | j282 | 63 | 50 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
5 | j182 | j159 | 63 | 69 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
6 | j159 | j173 | 63 | 89 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
7 | j167 | j158 | 63 | 43 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
8 | j321 | j365 | 63 | 200 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
9 | j315 | j315a | 63 | 50 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
10 | j134 | j134a | 63 | 50 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
11 | j117 | j118 | 63 | 37 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
12 | j117 | j121 | 63 | 20 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
13 | j121 | j127 | 63 | 28 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
14 | j128 | j130 | 63 | 30 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
15 | j229 | j197 | 125 | 48 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
16 | j264 | j209 | 63 | 29 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
17 | j209 | j289 | 63 | 22 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
18 | j209 | j169 | 63 | 22 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
19 | j205 | j181 | 63 | 119 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
20 | j181 | j202 | 63 | 72 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
21 | j181 | j181a | 63 | 198 | 5KG/CM22 | 3.5 | 1 | 4.5 | NO
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date

## brahupur hydro2
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | barahupur | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | j205 | j202 | 63 | 3.5 | 6 | 3 | 1 | 4 | no
2 | j205 | j202 | 63 | 89.1 | 6 | 3 | 1 | 4 | no
3 | j205 | j202 | 63 | 105.3 | 6 | 3 | 1 | 4 | no
4 | j234 | j220 | 63 | 61.1 | 6 | 3 | 1 | 4 | no
5 | j220 | j218 | 63 | 27 | 6 | 3 | 1 | 4 | no
6 | j218 | j200 | 63 | 83.3 | 6 | 3 | 1 | 4 | no
7 | j291 | j263 | 63 | 51.1 | 6 | 3 | 1 | 4 | no
8 | j326 | 286 | 63 | 96.3 | 6 | 3 | 1 | 4 | no
9 | j286 | j282 | 63 | 35 | 6 | 3 | 1 | 4 | no
10 | j286 | j293 | 63 | 36.1 | 6 | 3 | 1 | 4 | no
11 | j326 | j169 | 63 | 98.1 | 6 | 3 | 1 | 4 | no
12 | j224 | j273 | 63 | 70.2 | 6 | 3 | 1 | 4 | no
13 | j175 | j273 | 63 | 77.1 | 6 | 3 | 1 | 4 | no
14 | j224 | j273 | 63 | 7 | 6 | 3 | 1 | 4 | no
15 | j273 | j247 | 63 | 56 | 6 | 3 | 1 | 4 | no
16 | j247 | j303 | 63 | 30.9 | 6 | 3 | 1 | 4 | no
17 | j247 | j294 | 63 | 9.6 | 6 | 3 | 1 | 4 | no
18 | j246 | j294 | 63 | 246.3 | 6 | 3 | 1 | 4 | no
19 | j259 | j102 | 110 | 53.4 | 6 | 3 | 1 | 4 | no
20 | j246 | j294 | 63 | 5 | 6 | 3 | 1 | 4 | no
21 | j248 | j171 | 110 | 89.1 | 6 | 3 | 1 | 4 | no
22 | j109 | j145 | 63 | 110.7 | 6 | 3 | 1 | 4 | no
23 | j194 | j122 | 63 | 29.3 | 6 | 3 | 1 | 4 | no
24 | j122 | j170 | 63 | 11.2 | 6 | 3 | 1 | 4 | no
25 | j122 | j170 | 63 | 21.7 | 6 | 3 | 1 | 4 | no
26 | j170 | j296 | 63 | 62.2 | 6 | 3 | 1 | 4 | no
27 | j296 | j145 | 63 | 19.3 | 6 | 3 | 1 | 4 | no
28 | j229 | j197 | 140 | 39.1 | 6 | 3 | 1 | 4 | no
29 | j177 | j168 | 63 | 55.3 | 6 | 3 | 1 | 4 | no
30 | j138 | j48 | 63 | 56.3 | 6 | 3 | 1 | 4 | no
31 | j159 | j173 | 63 | 66.8 | 6 | 3 | 1 | 4 | no
32 | j235 | j158 | 63 | 290.3 | 6 | 3 | 1 | 4 | no
33 | j158 | j167 | 63 | 4.7 | 6 | 3 | 1 | 4 | no
34 | j158 | j167 | 63 | 46 | 6 | 3 | 1 | 4 | no
35 | j7a | j7b | 200 | 38.3 | 6 | 3 | 1 | 4 | no
36 | j138 | j48 | 63 | 4 | 6 | 3 | 1 | 4 | no
37 | j92 | j329 | 63 | 157 | 6 | 3 | 1 | 4 | no
38 | j271(1) | j271(2) | 63 | 270 | 6 | 3 | 1 | 4 | no
39 | j155 | j155(1) | 63 | 105 | 6 | 3 | 1 | 4 | no
40 | j265 | j284 | 63 | 46 | 6 | 3 | 1 | 4 | no
41 | j265 | j280 | 63 | 49 | 6 | 3 | 1 | 4 | no
42 | j265 | j314 | 63 | 19 | 6 | 3 | 1 | 4 | no
43 | j102 | j80 | 63 | 130.2 | 6 | 3 | 1 | 4 | no
44 | j307 | j308 | 63 | 68.5 | 6 | 3 | 1 | 4 | no
45 | j6(1) | j6(2) | 63 | 383.2 | 6 | 3 | 1 | 4 | no
46 | j20 | j20(1) | 63 | 275.3 | 6 | 3 | 1 | 4 | no
47 | j246 | j351 | 63 | 219.3 | 6 | 3 | 1 | 4 | no
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date