## brahapur
GOVERNMENT OF UTTAR PRADESH
STATE WATER & SANITATION MISSION ( SWSM )
Joint Measurement Report of Pipe Line
Name of the Work :- Survey , Design Preparation of DPR , Construction , Commissioning and O&M for 10 Years of Various Rural Water Supply Projects in the state of Uttar Pradesh as Per Request for Proposal for Division " Prayagraj "
Name of the Agency : POWER MECH PROJECTS LIMITED – BHOORATHNOM CONSTRUCTIONS COMPANY PRIVATE LIMITED (JV), Hyderabad.
Name OF Scheme |  | :brahapur
Block |  | : Mangraura
Total Scope |  | :
JMR No. |  | : 1
Date of JMR |  | :
Sr. No. | Start Node | End Node | Dia | Pipe Length (as per Drawing) | Pipe Length (as per Site) | Width | Depth | Quantity | Type OF Road | Dismantling Length | Dismantling Width | Dismantling Quantity | Restoration Length | Restoration Width | Restoration Quantity | Restoration Status | Remark
1 | j167 | j229 | 140 | 225 | 231.3 | 0.44 | 1.14
2 | j229 | j216 | 140 | 20 | 10 | 0.44 | 1.14
3 | j216 | j41 | 140 |  | 338 | 0.44 | 1.14
4 | j41 | j50 | 125 |  | 129.7 | 0.42 | 1.12 |  | b.t
5 | j50 | j111 | 125 |  | 111.8 | 0.42 | 1.12
6 | j41 | j7 | 160 |  | 625 | 0.46 | 1.16
7 | j7 | j1 | 200 | 1418 | 1502.2 | 0.5 | 1.2 |  | b.t
8 | j7 | j1 | 200 |  | 7.8 | 0.5 | 1.2 |  | b.t crossing | 7.8 | 0.5 | 3.9 | 7.8 | 0.5 | 3.9
9 | j6 | j159 | 63 |  | 1113.3 | 0.36 | 1.06
10 | j159 | j115 | 63 |  | 489.6 | 0.36 | 1.06 |  | b.t
11 | j115 | j101 | 63 |  | 123.3 | 0.36 | 1.06
12 | j115 | j93 | 63 |  | 150.8 | 0.36 | 1.06
13 | j93 | j103 | 63 |  | 130.7 | 0.36 | 1.06
14 | j93 | j144 | 63 |  | 37 | 0.36 | 1.06
15 | j144 | j90 | 63 |  | 35.3 | 0.36 | 1.06
16 | j143 | j165 | 63 |  | 10 | 0.36 | 1.06 |  | b.t
17 | j165 | j158 | 63 |  | 68 | 0.36 | 1.06 |  | b.t
18 | j111 | j112 | 63 |  | 215 | 0.36 | 1.06
19 | j143 | j53 | 63 |  | 5 | 0.36 | 1.06 |  | b.t crossing | 5 | 0.36 | 1.8 | 5 | 0.36 | 1.8
20 | j93 | 92 | 63 |  | 7 | 0.46 | 1.06 |  | interlocking | 7 | 0.46 | 3.22 | 7 | 0.46 | 3.22
21 | j111 | j240 | 63 |  | 83.3 | 0.36 | 1.06 |  | brick road | 83.3 | 0.36 | 29.988 | 83.3 | 0.36 | 29.988
22 | j186 | j141 | 63 |  | 65 | 0.36 | 1.06
23 | j186 | j179 | 63 |  | 26.8 | 0.36 | 1.06
24 | j232 | j179 | 63 | 39 | 53 | 0.36 | 1.06
25 | j179 | j163 | 63 |  | 76.2 | 0.36 | 1.06
26 | j179 | j163 | 63 |  | 5 | 0.36 | 1.06 |  | b.t crossing | 5 | 0.36 | 1.8 | 5 | 0.36 | 1.8
27 | j93 | j117 | 63 |  | 5 | 0.36 | 1.06 |  | b.t crossing | 5 | 0.36 | 1.8 | 5 | 0.36 | 1.8
28 | j93 | j163 | 63 |  | 7 | 0.36 | 1.06 |  | b.t crossing | 7 | 0.36 | 2.52 | 7 | 0.36 | 2.52
29 | j50 | j51 | 63 |  | 208.3 | 0.36 | 1.06
30 | j5 | j4 | 63 |  | 94.6 | 0.36 | 1.06
31 | j8 | j9 | 63 |  | 6 | 0.36 | 1.06 |  | b.t crossing | 6 | 0.36 | 2.16 | 6 | 0.36 | 2.16
32 | j8 | j9 | 63 |  | 76 | 0.36 | 1.06 |  | brick road | 76 | 0.36 | 27.36 | 76 | 0.36 | 27.36
33 | j79 | j7 | 63 |  | 815.3 | 0.36 | 1.06
34 | j79 | j35 | 63 |  | 46.3 | 0.36 | 1.06
35 | j47 | j254 | 63 |  | 112.3 | 0.36 | 1.06
36 | j24 | j254 | 63 |  | 161 | 0.36 | 1.06 |  | brick road | 161 | 0.36 | 57.96 | 161 | 0.36 | 57.96
37 | j32 | j65 | 63 |  | 25 | 0.46 | 1.06 |  | interlocking | 25 | 0.46 | 11.5 | 25 | 0.46 | 11.5
38 | j65 | j54 | 63 |  | 30 | 0.36 | 1.06
39 | j65 | j151 | 63 |  | 23.4 | 0.36 | 1.06
40 | j256 | j267 | 63 |  | 104.3 | 0.36 | 1.06
41 | j267 | j187 | 63 |  | 53.2 | 0.36 | 1.06
42 | j267 | j315 | 63 |  | 123.2 | 0.36 | 1.06
43 | j315 | j271 | 63 |  | 40 | 0.36 | 1.06
44 | j315 | j271 | 63 |  | 11.1 | 0.36 | 1.06
45 | j315 | j321 | 63 |  | 186.8 | 0.36 | 1.06
46 | j216 | j265 | 63 |  | 315.6 | 0.36 | 1.06
47 | j321 | j19 | 63 |  | 753.3 | 0.36 | 1.06
48 | j19 | j21 | 90 |  | 60.3 | 0.39 | 1.09
49 | j19 | j49 | 75 |  | 120 | 0.46 | 1.07 |  | interlocking | 120 | 0.46 | 55.2 | 120 | 0.46 | 55.2
50 | j66 | j55 | 63 |  | 26 | 0.36 | 1.06
51 | j49 | j66 | 75 |  | 30 | 0.37 | 1.07
52 | j55 | j119 | 63 |  | 21.1 | 0.36 | 1.06
53 | j88 | j66 | 63 |  | 30.2 | 0.46 | 1.06 |  | interlocking | 30.2 | 0.46 | 13.892 | 30.2 | 0.46 | 13.892
54 | j58 | j88 | 63 |  | 27.2 | 0.36 | 1.06
55 | j55 | j56 | 63 |  | 20.5 | 0.46 | 1.06 |  | interlocking | 20.5 | 0.46 | 9.43 | 20.5 | 0.46 | 9.43
56 | j88 | j72 | 63 |  | 24.7 | 0.46 | 1.06 |  | interlocking | 24.7 | 0.46 | 11.362 | 24.7 | 0.46 | 11.362
57 | j72 | j84 | 63 |  | 54.5 | 0.36 | 1.06
58 | j27 | j84 | 63 |  | 48.5 | 0.36 | 1.06
59 | j27 | j45 | 63 |  | 46.8 | 0.36 | 1.06
60 | j45 | j64 | 63 |  | 41.5 | 0.36 | 1.06
61 | j45 | j155 | 63 |  | 62.6 | 0.36 | 1.06
62 | j45 | j155 | 63 |  | 34 | 0.36 | 1.06 |  | brick road | 34 | 0.36 | 12.24 | 34 | 0.36 | 12.24
63 | j155 | j254 | 63 |  | 26 | 0.36 | 1.06
64 | j254 | j45 | 63 |  | 71.3 | 0.36 | 1.06 |  | brick road | 71.3 | 0.36 | 25.668 | 71.3 | 0.36 | 25.668 |  |  | 407
65 | j254 | j151 | 63 |  | 19 | 0.36 | 1.06 |  | brick road | 19 | 0.36 | 6.84 | 19 | 0.36 | 6.84
66 | j151 | j72 | 63 |  | 80.2 | 0.46 | 1.06 |  | interlocking | 80.2 | 0.46 | 36.892 | 80.2 | 0.46 | 36.892
67 | j254 | j207 | 63 |  | 198.3 | 0.36 | 1.06 |  | brick road | 198.3 | 0.36 | 71.388 | 198.3 | 0.36 | 71.388
68 | j254 | j207 | 63 |  | 38.7 | 0.46 | 1.06 |  | interlocking | 38.7 | 0.46 | 17.802 | 38.7 | 0.46 | 17.802
69 | j254 | j207 | 63 |  | 51.5 | 0.36 | 1.06
70 | j212 | j126 | 63 |  | 394.9 | 0.36 | 1.06 |  | brick road | 394.9 | 0.36 | 142.164 | 394.9 | 0.36 | 142.164
71 | j126 | j56 | 63 |  | 170 | 0.36 | 1.06 |  | brick road | 170 | 0.36 | 61.2 | 170 | 0.36 | 61.2
72 | j126 | j134 | 63 |  | 193 | 0.36 | 1.06 |  | brick road | 193 | 0.36 | 69.48 | 193 | 0.36 | 69.48
73 | j311 | j134 | 63 |  | 648.3 | 0.36 | 1.06
74 | j134 | j211 | 63 |  | 332.2 | 0.36 | 1.06 |  | brick road | 332.2 | 0.36 | 119.592 | 332.2 | 0.36 | 119.592
75 | j161 | j161a | 63 |  | 61.3 | 0.36 | 1.06
76 | j276 | j306 | 63 | 106 | 78 | 0.36 | 1.06
77 | j306 | j215 | 63 | 49 | 65.5 | 0.36 | 1.06
78 | j306 | j324 | 63 |  | 7 | 0.46 | 1.06 |  | interlocking | 7 | 0.46 | 3.22 | 7 | 0.46 | 3.22
79 | j324 | j206 | 63 | 65 | 55 | 0.36 | 1.06
80 | j206 | j142 | 63 | 45 | 106 | 0.36 | 1.06
81 | j206 | j184 | 63 | 88 | 85.1 | 0.36 | 1.06
82 | j184 | j120 | 63 | 26 | 50 | 0.36 | 1.06
83 | j184 | j319 | 63 | 38 | 79 | 0.36 | 1.06
84 | j292 | j300 | 63 |  | 41 | 0.36 | 1.06
85 | j309 | j309a | 63 |  | 51 | 0.46 | 1.06 |  | interlocking | 51 | 0.46 | 23.46 | 51 | 0.46 | 23.46
86 | j322 | j309 | 63 |  | 91.3 | 0.36 | 1.06
87 | j322a | j285 | 63 |  | 103 | 0.36 | 1.06
88 | j324 | j233 | 63 | 112 | 113.3 | 0.36 | 1.06
89 | j233 | j339 | 63 | 104 | 65.4 | 0.36 | 1.06
90 | j233 | j259 | 63 |  | 368.3 | 0.36 | 1.06
91 | j233 | j259 | 63 |  | 7 | 0.36 | 1.06 |  | b.t crossing | 7 | 0.36 | 2.52 | 7 | 0.36 | 2.52
92 | j259 | j102 | 110 | 356 | 311.1 | 0.41 | 1.1
93 | j246 | j102 | 63 |  | 413.1 | 0.36 | 1.06
94 | j246 | j102 | 63 |  | 10 | 0.36 | 1.06 |  | culvert
95 | j80 | j339 | 63 |  | 307.7 | 0.36 | 1.06
96 | j259 | j216 | 125 |  | 211 | 0.42 | 1.12
97 | j306 | j259 | 63 |  | 803.2 | 0.36 | 1.06
98 | j207 | j204 | 63 | 79 | 72.3 | 0.36 | 1.06
99 | j198 | j107 | 63 | 121 | 133 | 0.36 | 1.06 |  | brick road | 133 | 0.36 | 47.88 | 133 | 0.36 | 47.88
100 | j107 | j132 | 63 | 64 | 102.3 | 0.36 | 1.06
101 | j132 | j60 | 63 |  | 23.2 | 0.36 | 1.06
102 | j107 | j305 | 63 |  | 76.5 | 0.36 | 1.06
103 | j279 | j152 | 63 |  | 37.2 | 0.36 | 1.06
104 | j355 | j20 | 63 |  | 157.2 | 0.36 | 1.06
105 | j86 | j162 | 63 | 105 | 98.2 | 0.36 | 1.06
106 | j162 | j42 | 63 |  | 82.3 | 0.36 | 1.06
107 | j42 | j40 | 63 |  | 78 | 0.36 | 1.06
108 | j42 | j61 | 63 |  | 73.2 | 0.36 | 1.06
109 | j162 | j109 | 63 |  | 45 | 0.36 | 1.06
110 | j145 | j146 | 63 |  | 69.3 | 0.36 | 1.06
111 | j224 | j274 | 63 | 126 | 125.1 | 0.36 | 1.06
112 | j224 | j274 | 63 |  | 5 | 0.36 | 1.06 |  | b.t crossing | 5 | 0.36 | 1.8 | 5 | 0.36 | 1.8
113 | j274 | j326 | 63 | 167 | 148.8 | 0.36 | 1.06 |  | brick road | 148.8 | 0.36 | 53.568 | 148.8 | 0.36 | 53.568
114 | j274 | j291 | 63 |  | 248.6 | 0.36 | 1.06
115 | j291 | j347 | 63 |  | 15 | 0.36 | 1.06 |  | brick road | 15 | 0.36 | 5.4 | 15 | 0.36 | 5.4
116 | j347 | j190 | 63 |  | 162.3 | 0.36 | 1.06
117 | j228 | j338 | 63 |  | 65 | 0.36 | 1.06
118 | j346 | j330 | 63 |  | 47.7 | 0.36 | 1.06
119 | j327 | j323 | 63 |  | 30.3 | 0.36 | 1.06
120 | j327 | j323 | 63 |  | 46.4 | 0.36 | 1.06
121 | j291 | j327 | 63 |  | 51 | 0.36 | 1.06 |  | brick road | 51 | 0.36 | 18.36 | 51 | 0.36 | 18.36
122 | j327 | j349 | 63 |  | 33.3 | 0.36 | 1.06 |  | brick road | 33.3 | 0.36 | 11.988 | 33.3 | 0.36 | 11.988
123 | j327a | j327b | 63 |  | 35 | 0.36 | 1.06
124 | j349 | j225 | 63 |  | 29 | 0.36 | 1.06 |  | brick road | 29 | 0.36 | 10.44 | 29 | 0.36 | 10.44
125 | j225 | j223 | 63 |  | 16 | 0.36 | 1.06
126 | j225 | j262 | 63 |  | 21.3 | 0.36 | 1.06 |  | brick road | 21.3 | 0.36 | 7.668 | 21.3 | 0.36 | 7.668
127 | j225 | j218 | 63 |  | 46.6 | 0.36 | 1.06 |  | brick road | 46.6 | 0.36 | 16.776 | 46.6 | 0.36 | 16.776
128 | j220 | j349 | 63 |  | 56.3 | 0.36 | 1.06 |  | brick road | 56.3 | 0.36 | 20.268 | 56.3 | 0.36 | 20.268
129 | j270 | j277 | 63 |  | 30.1 | 0.36 | 1.06
130 | j220 | j234 | 63 |  | 41 | 0.36 | 1.06
131 | j234 | j224 | 63 |  | 118.3 | 0.36 | 1.06
132 | j234 | j224 | 63 |  | 5 | 0.36 | 1.06 |  | b.t crossing | 5 | 0.36 | 1.8 | 5 | 0.36 | 1.8
133 | j122 | j73 | 63 |  | 75 | 0.36 | 1.06
134 | j278 | j345 | 63 |  | 30.1 | 0.36 | 1.06
135 | j345 | j157 | 63 |  | 65 | 0.36 | 1.06 |  | brick road | 65 | 0.36 | 23.4 | 65 | 0.36 | 23.4
136 | j345 | j194 | 63 |  | 44.2 | 0.36 | 1.06 |  | brick road | 44.2 | 0.36 | 15.912 | 44.2 | 0.36 | 15.912
137 | j304 | j283 | 63 |  | 15 | 0.36 | 1.06 |  | brick road | 15 | 0.36 | 5.4 | 15 | 0.36 | 5.4
138 | j350 | j318 | 63 |  | 34.3 | 0.36 | 1.06 |  | brick road | 34.3 | 0.36 | 12.348 | 34.3 | 0.36 | 12.348
139 | j296 | j350 | 63 |  | 30.1 | 0.36 | 1.06 |  | brick road | 30.1 | 0.36 | 10.836 | 30.1 | 0.36 | 10.836
140 | j356 | j314 | 63 |  | 30.3 | 0.36 | 1.06 |  | brick road | 30.3 | 0.36 | 10.908 | 30.3 | 0.36 | 10.908
141 | j314 | j258 | 63 |  | 15.2 | 0.36 | 1.06 |  | brick road | 15.2 | 0.36 | 5.472 | 15.2 | 0.36 | 5.472
142 | j314 | j258 | 63 |  | 45.5 | 0.36 | 1.06
143 | j202 | j129 | 63 |  | 31.1 | 0.36 | 1.06
144 | j314 | j296 | 63 |  | 41 | 0.36 | 1.06
145 | j350 | j147 | 63 |  | 31.1 | 0.36 | 1.06 |  | brick road | 31.1 | 0.36 | 11.196 | 31.1 | 0.36 | 11.196
146 | j350 | j147 | 63 |  | 18 | 0.36 | 1.06 |  | brick road | 18 | 0.36 | 6.48 | 18 | 0.36 | 6.48
147 | j109 | j255 | 63 |  | 50 | 0.36 | 1.06
148 | j255 | j59 | 63 |  | 54.3 | 0.36 | 1.06
149 | j123 | j255 | 63 |  | 51 | 0.36 | 1.06 |  | brick road | 51 | 0.36 | 18.36 | 51 | 0.36 | 18.36
150 | j255 | j357 | 63 |  | 23.5 | 0.36 | 1.06 |  |  | 23.5 | 0.36 | 8.46 | 23.5 | 0.36 | 8.46
151 | j208 | j342 | 63 |  | 65.3 | 0.36 | 1.06
152 | j235 | j266 | 63 |  | 278.3 | 0.36 | 1.06
153 | j266 | j189 | 63 |  | 51.3 | 0.36 | 1.06
154 | j266 | j234 | 63 |  | 48.1 | 0.36 | 1.06
155 | j235 | j266 | 63 |  | 7 | 0.36 | 1.06 |  | b.t crossing | 7 | 0.36 | 2.52 | 7 | 0.36 | 2.52
156 | j266 | j189 | 63 |  | 5 | 0.36 | 1.06 |  | b.t crossing | 5 | 0.36 | 1.8 | 5 | 0.36 | 1.8
157 | j326 | j264 | 63 |  | 48 | 0.36 | 1.06
158 | j326 | j287 | 63 |  | 52 | 0.36 | 1.06
159 | j287 | j286 | 63 |  | 29 | 0.36 | 1.06
160 | j286 | j282 | 63 |  | 50 | 0.36 | 1.06
161 | j182 | j159 | 63 |  | 69 | 0.36 | 1.06
162 | j159 | j173 | 63 |  | 89 | 0.36 | 1.06
163 | j167 | j158 | 63 |  | 43 | 0.36 | 1.06 |  | brickroad | 43 | 0.36 | 15.48 | 43 | 0.36 | 15.48
164 | j321 | j365 | 63 |  | 200 | 0.36 | 1.06
165 | j315 | j315a | 63 |  | 50 | 0.36 | 1.06
166 | j134 | j134a | 63 |  | 50 | 0.36 | 1.06
167 | j117 | j118 | 63 |  | 37 | 0.36 | 1.06 |  | brick road | 37 | 0.36 | 13.32 | 37 | 0.36 | 13.32
168 | j117 | j121 | 63 |  | 20 | 0.36 | 1.06
169 | j121 | j127 | 63 |  | 28 | 0.36 | 1.06
170 | j128 | j130 | 63 |  | 30 | 0.36 | 1.06
171 | j229 | j197 | 125 |  | 48 | 0.42 | 1.12
172 | j264 | j209 | 63 |  | 29 | 0.36 | 1.06
173 | j209 | j289 | 63 |  | 22 | 0.36 | 1.06
174 | j209 | j169 | 63 |  | 22 | 0.36 | 1.06
175 | j205 | j181 | 63 |  | 119 | 0.36 | 1.06
176 | j181 | j202 | 63 |  | 72 | 0.36 | 1.06
177 | j181 | j181a | 63 |  | 198 | 0.36 | 1.06
[5 empty] | 20071.9 | [9 empty] | 1184.198
|  | Representative PMPL - BRCCPL (JV) Pratapgarh |  |  |  |  | Representative Medhaj Techno Concept Pvt Ltd (TPI) Pratapgarh |  |  |  |  | Representative UP Jal Nigam (Rural) Pratapgarh
[5 empty] | 63 | 75 | 90 | 110 | 125 | 140 | 160 | 200
[5 empty] | 16335.7 | 150 | 60.3 | 311.1 | 500.5 | 579.3 | 625 | 1510 | 20071.9

## brahapur 2
GOVERNMENT OF UTTAR PRADESH
STATE WATER & SANITATION MISSION ( SWSM )
Joint Measurement Report of Pipe Line
Name of the Work :- Survey , Design Preparation of DPR , Construction , Commissioning and O&M for 10 Years of Various Rural Water Supply Projects in the state of Uttar Pradesh as Per Request for Proposal for Division " Prayagraj "
Name of the Agency : POWER MECH PROJECTS LIMITED – BHOORATHNOM CONSTRUCTIONS COMPANY PRIVATE LIMITED (JV), Hyderabad.
Name OF Scheme |  | :brahapur 2
Block |  | : Mangraura
Total Scope |  | :
JMR No. |  | : 1
Date of JMR |  | :
Sr. No. | Start Node | End Node | Dia | Pipe Length (as per Drawing) | Pipe Length (as per Site) | Width | Depth | Quantity | Type OF Road | Dismantling Length | Dismantling Width | Dismantling Quantity | Restoration Length | Restoration Width | Restoration Quantity | Restoration Status | Remark
1 | j205 | j202 | 63 |  | 3.5 | 0.363 | 1.063 |  | b.t crossing | 3.5 | 0.363 | 1.2705 | 3.5 | 0.363 | 1.2705 | done
2 | j205 | j202 | 63 |  | 89.1 | 0.363 | 1.063 |  | brick road | 89.1 | 0.363 | 32.3433 | 89.1 | 0.363 | 32.3433 | done
3 | j205 | j202 | 63 |  | 105.3 | 0.363 | 1.063
4 | j234 | j220 | 63 |  | 61.1 | 0.363 | 1.063
5 | j220 | j218 | 63 |  | 27 | 0.363 | 1.063 |  | brick road | 27 | 0.363 | 9.801 | 27 | 0.363 | 9.801 | done
6 | j218 | j200 | 63 |  | 83.3 | 0.363 | 1.063
7 | j291 | j263 | 63 |  | 51.1 | 0.363 | 1.063 |  | brick road | 51.1 | 0.363 | 18.5493 | 51.1 | 0.363 | 18.5493 | done
8 | j326 | 286 | 63 |  | 96.3 | 0.363 | 1.063 |  | brick road | 96.3 | 0.363 | 34.9569 | 96.3 | 0.363 | 34.9569 | done
9 | j286 | j282 | 63 |  | 35 | 0.363 | 1.063
10 | j286 | j293 | 63 |  | 36.1 | 0.363 | 1.063
11 | j326 | j169 | 63 |  | 98.1 | 0.363 | 1.063
12 | j224 | j273 | 63 |  | 70.2 | 0.363 | 1.063 |  | brick road | 70.2 | 0.363 | 25.4826 | 70.2 | 0.363 | 25.4826 | done
13 | j175 | j273 | 63 |  | 77.1 | 0.363 | 1.063
14 | j224 | j273 | 63 |  | 7 | 0.363 | 1.063 |  | b.t road crossing | 7 | 0.363 | 2.541 | 7 | 0.363 | 2.541 | done
15 | j273 | j247 | 63 |  | 56 | 0.363 | 1.063 |  | brick road | 56 | 0.363 | 20.328 | 56 | 0.363 | 20.328 | done
16 | j247 | j303 | 63 |  | 30.9 | 0.363 | 1.063
17 | j247 | j294 | 63 |  | 9.6 | 0.363 | 1.063
18 | j246 | j294 | 63 |  | 246.3 | 0.363 | 1.063
19 | j259 | j102 | 110 |  | 53.4 | 0.41 | 1.11
20 | j246 | j294 | 63 |  | 5 | 0.363 | 1.063 |  | b.t road crossing | 5 | 0.363 | 1.815 | 5 | 0.363 | 1.815 | done
21 | j248 | j171 | 110 |  | 89.1 | 0.41 | 1.11 |  | brick road | 89.1 | 0.41 | 36.531 | 89.1 | 0.41 | 36.531 | done
22 | j109 | j145 | 63 |  | 110.7 | 0.363 | 1.063
23 | j194 | j122 | 63 |  | 29.3 | 0.363 | 1.063
24 | j122 | j170 | 63 |  | 11.2 | 0.363 | 1.063 |  | brick road | 11.2 | 0.363 | 4.0656 | 11.2 | 0.363 | 4.0656 | done
25 | j122 | j170 | 63 |  | 21.7 | 0.363 | 1.063
26 | j170 | j296 | 63 |  | 62.2 | 0.363 | 1.063 |  | brick road | 62.2 | 0.363 | 22.5786 | 62.2 | 0.363 | 22.5786 | done
27 | j296 | j145 | 63 |  | 19.3 | 0.363 | 1.063
28 | j229 | j197 | 140 |  | 39.1 | 0.44 | 1.14
29 | j177 | j168 | 63 |  | 55.3 | 0.363 | 1.063 | [10 empty] | 224
30 | j138 | j48 | 63 |  | 56.3 | 0.363 | 1.063
31 | j159 | j173 | 63 |  | 66.8 | 0.363 | 1.063
32 | j235 | j158 | 63 |  | 290.3 | 0.363 | 1.063
33 | j158 | j167 | 63 |  | 4.7 | 0.363 | 1.063 |  | b.t road crossing | 4.7 | 0.363 | 1.7061 | 4.7 | 0.363 | 1.7061 | done
34 | j158 | j167 | 63 |  | 46 | 0.363 | 1.063
35 | j7a | j7b | 200 |  | 38.3 | 0.5 | 1.2
36 | j138 | j48 | 63 |  | 4 | 0.363 | 1.063 |  | road crossing | 4 | 0.363 | 1.452 | 4 | 0.363 | 1.452 | done
37 | j92 | j329 | 63 | 174 | 157 | 0.363 | 1.063
38 | j271(1) | j271(2) | 63 |  | 270 | 0.363 | 1.063 | [10 empty] | 24037
39 | j155 | j155(1) | 63 |  | 105 | 0.363 | 1.063 | [10 empty] | 375
40 | j265 | j284 | 63 | 33 | 46 | 0.363 | 1.063 | [10 empty] | 20509
41 | j265 | j280 | 63 | 29 | 49 | 0.363 | 1.063
42 | j265 | j314 | 63 | 15 | 19 | 0.363 | 1.063
43 | j102 | j80 | 63 |  | 130.2 | 0.363 | 1.063 | [10 empty] | 531
44 | j307 | j308 | 63 |  | 68.5 | 0.363 | 1.063
45 | j6(1) | j6(2) | 63 |  | 383.2 | 0.363 | 1.063
46 | j20 | j20(1) | 63 |  | 275.3 | 0.363 | 1.063 | [10 empty] | 6410.4
47 | j246 | j351 | 63 | 191 | 219.3 | 0.363 | 1.063
[5 empty] | 3908.2 | [9 empty] | 213.4209
Representative PMPL - BRCCPL (JV) Pratapgarh | [5 empty] | Representative Medhaj Techno Concept Pvt Ltd (TPI) Pratapgarh | [5 empty] | Representative UP Jal Nigam (Rural) Pratapgarh
390.3
|  | 63 | 75 | 90 | 110 | 125 | 140 | 160 | 200
|  | 3688.3 | 0 | 0 | 142.5 | 0 | 39.1 | 0 | 38.3