## madhura arani ganj 4
GOVERNMENT OF UTTAR PRADESH
STATE WATER & SANITATION MISSION ( SWSM )
Joint Measurement Report of Pipe Line
Name of the Work :- Survey , Design Preparation of DPR , Construction , Commissioning and O&M for 10 Years of Various Rural Water Supply Projects in the state of Uttar Pradesh as Per Request for Proposal for Division " Prayagraj "
Name of the Agency : POWER MECH PROJECTS LIMITED – BHOORATHNOM CONSTRUCTIONS COMPANY PRIVATE LIMITED (JV), Hyderabad.
Name OF Scheme |  | :madhura rani ganj
Block |  | : Mangraura
Total Scope |  | :
JMR No. |  | : 1
Date of JMR |  | :
Sr. No. | Start Node | End Node | Dia | Pipe Length (as per Drawing) | Pipe Length (as per Site) | Width | Depth | Quantity | Type OF Road | Dismantling Length | Dismantling Width | Dismantling Quantity | Restoration Length | Restoration Width | Restoration Quantity | Restoration Status | Remark
1 | OHT | j1(1) | 250 |  | 368 | 0.55 | 1.25
2 | j1(1) | j1 | 200 |  | 272 | 0.5 | 1.2
3 | j1(1) | j2 | 200 |  | 26 | 0.5 | 1.2 |  | brick road | 0.5 | 26 | 13 | 0.5 | 26 | 13 | done
4 | j2 | j23 | 200 |  | 106 | 0.5 | 1.2
5 | j590 | j592 | 63 |  | 219 | 0.36 | 1.06
6 | j162 | j230 | 63 |  | 525 | 0.36 | 1.06
7 | j38 | j138 | 63 |  | 325.4 | 0.36 | 1.06
8 | j21 | j22 | 63 |  | 300 | 0.36 | 1.06 | [11 empty] | 22411
9 | j44 | j44(1) | 63 |  | 156.2 | 0.36 | 1.06 | [10 empty] | 22447.5
10 | j112 | j112(1) | 63 |  | 205.3 | 0.36 | 1.06 | [10 empty] | 11740.3 | 36545.2
[5 empty] | 2502.9 | [12 empty] | 2502.9
Representative PMPL - BRCCPL (JV) Pratapgarh | [6 empty] | Representative Medhaj Techno Concept Pvt Ltd (TPI) Pratapgarh |  |  |  |  | Representative UP Jal Nigam (Rural) Pratapgarh | [5 empty] | 36690.7

## MADHURA RANI GANJ
MADHURA RANI GANJ AND SARAOULI(JMR) BLOCK-MANGRAURA | [9 empty] | MADHURA RANI GANJ AND SARAOULI(JMR) BLOCK-MANGRAURA
Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | Dia of pipe(MM) | Pipe Length (M) | CUMMULATIVE | Depth(M) | REMARK | Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | Dia of pipe(MM) | Pipe Length (M) | CUMMULATIVE | Depth(M) | REMARK
1 | J137 | J132 |  |  | 63 | 27 | 27 | 1.06 |  | 1 | j542 | j491 | brick road | 0.36 | 63 | 100.7 | 100.7 | 1.06
2 | J142 | J143 |  |  | 63 | 86.1 | 113.1 | 1.06 |  | 2 | j380 | j399 | interlocking | 0.46 | 63 | 125.8 | 226.5 | 1.06
3 | J147 | J148 |  |  | 63 | 48.1 | 161.2 | 1.06 |  | 3 | j399 | j403 | interlocking | 0.46 | 63 | 25.2 | 251.7 | 1.06
4 | J147 | J148 | BRICK ROAD | 0.36 | 63 | 33.6 | 194.8 | 1.06 |  | 4 | j403 | j411 | interlocking | 0.46 | 63 | 30.1 | 281.8 | 1.06
5 | J148A | J148 |  |  | 63 | 9.3 | 204.1 | 1.06 |  | 5 | j411 | j418 | interlocking | 0.46 | 63 | 57.2 | 339 | 1.06
6 | J148 | J148B |  |  | 63 | 53.2 | 257.3 | 1.06 |  | 6 | j411 | j418 |  |  | 63 | 23.2 | 362.2 | 1.06
7 | J180 | J149 |  |  | 63 | 91.3 | 348.6 | 1.06 |  | 7 | j380 | j399 | culvert |  | 63 | 2 | 364.2 | 1.06
8 | J147 | J187 |  |  | 63 | 146.1 | 494.7 | 1.06 |  | 8 | j380 | j399 | b.t road | 0.36 | 63 | 6.7 | 370.9 | 1.06
9 | J187 | J196 |  |  | 63 | 175.8 | 670.5 | 1.06 |  | 9 | j447a | j447b |  |  | 63 | 10.2 | 381.1 | 1.06
10 | J196 | J197 |  |  | 63 | 37.1 | 707.6 | 1.06 |  | 10 | j129 | j130 | brickroad | 0.36 | 63 | 25.1 | 406.2 | 1.06
11 | J192 | J193 |  |  | 63 | 25 | 732.6 | 1.06 |  | 11 | j34 | j35 | b.t road | 0.36 | 63 | 5 | 411.2 | 1.06
12 | J192 | J187 |  |  | 63 | 24.7 | 757.3 | 1.06 |  | 12 | j34 | j35 | cc | 0.36 | 63 | 103.1 | 514.3 | 1.06
13 | J192 | J198 |  |  | 63 | 129.2 | 886.5 | 1.06 |  | 13 | j133 | j134 | cc | 0.36 | 63 | 113.2 | 627.5 | 1.06
14 | J198 | J196 |  |  | 63 | 34.5 | 921 | 1.06 |  | 14 | j134 | j136 | cc | 0.36 | 63 | 54 | 681.5 | 1.06
15 | J198 | J228 |  |  | 63 | 536.8 | 1457.8 | 1.06 |  | 15 | j134 | j135 | cc | 0.36 | 63 | 24.8 | 706.3 | 1.06
16 | J3 | J10 | B.T ROAD | 0.36 | 63 | 45.7 | 1503.5 | 1.06 |  | 16 | j133 | j138 | interlocking | 0.46 | 63 | 85.1 | 791.4 | 1.06
17 | J3 | J11 |  |  | 63 | 119.2 | 1622.7 | 1.06 |  | 17 | j138 | j160 | cc | 0.36 | 63 | 47.1 | 838.5 | 1.06
18 | J27 | J26 |  |  | 63 | 85.5 | 1708.2 | 1.06 |  | 18 | j138 | j139 | cc | 0.36 | 63 | 78.3 | 916.8 | 1.06
19 | J28 | 41 |  |  | 63 | 155 | 1863.2 | 1.06 |  | 19 | j25 | j38 | b.t road | 0.36 | 63 | 4 | 920.8 | 1.06
20 | J91A | J91B |  |  | 63 | 18.6 | 1881.8 | 1.06 |  | 20 | j25 | j38 |  |  | 63 | 15.3 | 936.1 | 1.06
21 | J91 | J91A | B.T ROAD | 0.36 | 63 | 27 | 1908.8 | 1.06 |  | 21 | j25 | j38 | interlocking | 0.46 | 63 | 33.1 | 969.2 | 1.06
22 | J91A | J90 |  |  | 63 | 18.1 | 1926.9 | 1.06 |  | 22 | j25 | j38 | cc | 0.36 | 63 | 93.5 | 1062.7 | 1.06
23 | J90 | J94 |  |  | 63 | 39.6 | 1966.5 | 1.06 |  | 23 | j39 | j38 | cc | 0.36 | 63 | 47.6 | 1110.3 | 1.06
24 | J90 | J86 |  |  | 63 | 31.8 | 1998.3 | 1.06 |  | 24 | j38 | j79 | cc | 0.36 | 63 | 80.8 | 1191.1 | 1.06
25 | J86 | J97 |  |  | 63 | 71 | 2069.3 | 1.06 |  | 25 | j27 | j27a |  |  | 63 | 37.2 | 1228.3 | 1.06
26 | J97 | J94 |  |  | 63 | 42.7 | 2112 | 1.06 |  | 26 | j27 | j27a | b.t road | 0.36 | 63 | 3 | 1231.3 | 1.06
27 | J97 | J98 |  |  | 63 | 63.6 | 2175.6 | 1.06 |  | 27 | j30 | j31 | cc | 0.36 | 63 | 73.1 | 1304.4 | 1.06
28 | J98 | J99 |  |  | 63 | 20 | 2195.6 | 1.06 |  | 28 | j55 | j50 |  |  | 90 | 77.6 | 1382 | 1.09
29 | J98 | J106 |  |  | 63 | 44.1 | 2239.7 | 1.06 |  | 29 | j63 | j74 |  |  | 90 | 101.3 | 1483.3 | 1.09
30 | J100 | J101 |  |  | 63 | 45.7 | 2285.4 | 1.06 |  | 30 | j126 | j129 | brick road | 0.41 | 110 | 30.2 | 1513.5 | 1.1
31 | J100 | J103 |  |  | 63 | 28.4 | 2313.8 | 1.06 |  | 31 | j2 | j3 |  |  | 110 | 195.6 | 1709.1 | 1.1
32 | J103 | J105 |  |  | 63 | 35.3 | 2349.1 | 1.06 |  | 32 | j2 | j3 | b.t road | 0.41 | 110 | 5 | 1714.1 | 1.1
33 | J103 | J103A |  |  | 63 | 46.3 | 2395.4 | 1.06 |  | 33 | j441 | j459 |  |  | 110 | 140.9 | 1855 | 1.1
34 | J84 | J100 |  |  | 63 | 64.7 | 2460.1 | 1.06 |  | 34 | j448 | j454 |  |  | 140 | 118.6 | 1973.6 | 1.14
35 | J105 | J92 |  |  | 63 | 64.1 | 2524.2 | 1.06 |  | 35 | j425 | j437 |  |  | 140 | 91.3 | 2064.9 | 1.14
36 | J128 | J76 |  |  | 63 | 59.4 | 2583.6 | 1.06 |  | 36 | j437 | j441 |  |  | 140 | 110.1 | 2175 | 1.14
37 | J123 | J122 |  |  | 63 | 37.2 | 2620.8 | 1.06 |  | 37 | j451 | j447 |  |  | 140 | 44.2 | 2219.2 | 1.14
38 | J61 | J49 |  |  | 63 | 318.2 | 2939 | 1.06 |  | 38 | j50 | j49 |  |  | 140 | 189.7 | 2408.9 | 1.14
39 | J47 | J48 |  |  | 63 | 72.4 | 3011.4 | 1.06 |  | 39 | j45 | j63 |  |  | 140 | 291.1 | 2700 | 1.14
40 | J49 | J51 |  |  | 63 | 104 | 3115.4 | 1.06 |  | 40 | j120 | j123 | brick road | 0.44 | 140 | 26.2 | 2726.2 | 1.14
41 | J51 | J52 |  |  | 63 | 19.6 | 3135 | 1.06 |  | 41 | j123 | j126 | brick road | 0.44 | 140 | 48.1 | 2774.3 | 1.14
42 | J51 | J50 |  |  | 63 | 223 | 3358 | 1.06 |  | 42 | j77 | j72 | b.t road | 0.44 | 140 | 206.2 | 2980.5 | 1.14
43 | J55 | J58 |  |  | 63 | 190.2 | 3548.2 | 1.06 |  | 43 | j442 | j448 |  |  | 160 | 167.5 | 3148 | 1.16
44 | J63 | J66 |  |  | 63 | 130.2 | 3678.4 | 1.06 |  | 44 | j49 | j47 |  |  | 160 | 215 | 3363 | 1.16
45 | J32 | J33 |  |  | 63 | 37.1 | 3715.5 | 1.06 |  | 45 | j47 | j45 |  |  | 160 | 701.1 | 4064.1 | 1.16
46 | J32 | J32A |  |  | 63 | 56.4 | 3771.9 | 1.06 |  | 46 | j47 | j45 | culvert |  | 160 | 3 | 4067.1 | 1.16
47 | J32 | J32B |  |  | 63 | 21.3 | 3793.2 | 1.06 |  | 47 | j45 | j34 |  |  | 160 | 206 | 4273.1 | 1.16
48 | J32A | J40 |  |  | 63 | 187.7 | 3980.9 | 1.06 |  | 48 | j34 | j30 |  |  | 160 | 90 | 4363.1 | 1.16
49 | J29 | J21 |  |  | 63 | 187.3 | 4168.2 | 1.06 |  | 49 | j30 | j29 |  |  | 160 | 15 | 4378.1 | 1.16
50 | J21 | J22 |  |  | 63 | 174.6 | 4342.8 | 1.06 |  | 50 | j29 | j25 |  |  | 160 | 168 | 4546.1 | 1.16
51 | J21A | J21 |  |  | 63 | 9.1 | 4351.9 | 1.06 |  | 51 | j25 | j24 |  |  | 160 | 54.9 | 4601 | 1.16
52 | J21A | J21B |  |  | 63 | 32.1 | 4384 | 1.06 |  | 52 | j24 | j23 |  |  | 160 | 88.8 | 4689.8 | 1.16
53 | J21A | J20 |  |  | 63 | 37.1 | 4421.1 | 1.06 |  | 53 | j24 | j23 | b.t road | 0.46 | 160 | 7.2 | 4697 | 1.16
54 | J20 | J19 |  |  | 63 | 46.3 | 4467.4 | 1.06 |  | 54 | j23 | j26 |  |  | 160 | 127.2 | 4824.2 | 1.16
55 | J20 | J17 |  |  | 63 | 51.1 | 4518.5 | 1.06 |  | 55 | j26 | j28 |  |  | 160 | 7.7 | 4831.9 | 1.16
56 | J17 | J19 |  |  | 63 | 10.6 | 4529.1 | 1.06 |  | 56 | j28 | j46 |  |  | 160 | 195.7 | 5027.6 | 1.16
57 | J17 | J15 |  |  | 63 | 46.2 | 4575.3 | 1.06 |  | 57 | j46 | j72 |  |  | 160 | 234.1 | 5261.7 | 1.16
58 | J15 | J15A |  |  | 63 | 27.3 | 4602.6 | 1.06 |  | 58 | j72 | j110 |  |  | 160 | 165.3 | 5427 | 1.16
59 | J15 | J16 |  |  | 63 | 26.8 | 4629.4 | 1.06 |  | 59 | j72 | j110 | b.t road | 0.46 | 160 | 4.6 | 5431.6 | 1.16
60 | J13 | J14 |  |  | 63 | 39.2 | 4668.6 | 1.06 |  | 60 | j113 | j115 |  |  | 160 | 60 | 5491.6 | 1.16
61 | J590 | J618 |  |  | 63 | 101.3 | 4769.9 | 1.06 |  | 61 | j115 | j120 | brick road | 0.46 | 160 | 338.3 | 5829.9 | 1.16
62 | J618 | J628 |  |  | 63 | 29 | 4798.9 | 1.06 |  | 62 | j216 | j215 |  |  | 160 | 263.1 | 6093 | 1.16
63 | J628 | J630 |  |  | 63 | 53.7 | 4852.6 | 1.06 |  | 63 | j167 | j182 |  |  | 160 | 152.1 | 6245.1 | 1.16
64 | J618 | J627 |  |  | 63 | 194.7 | 5047.3 | 1.06 |  | 64 | j310 | j309 | b.t road | 0.5 | 200 | 270.7 | 6515.8 | 1.2
65 | J627 | J644 |  |  | 63 | 63.4 | 5110.7 | 1.06 |  | 65 | j310 | j283 | b.t road | 0.5 | 200 | 119.7 | 6635.5 | 1.2
66 | J628 | J644 |  |  | 63 | 218.7 | 5329.4 | 1.06 |  | 66 | j283 | j228 | b.t road | 0.5 | 200 | 223.2 | 6858.7 | 1.2
67 | J576 | J627 |  |  | 63 | 214 | 5543.4 | 1.06 |  | 67 | j228 | j216 | b.t road | 0.5 | 200 | 248.5 | 7107.2 | 1.2
68 | J644 | J658 |  |  | 63 | 469.6 | 6013 | 1.06 |  | 68 | j216 | j170 | b.t road | 0.5 | 200 | 357.2 | 7464.4 | 1.2
69 | J658 | J657 |  |  | 63 | 153.4 | 6166.4 | 1.06 |  | 69 | j216 | j170 |  |  | 200 | 76.8 | 7541.2 | 1.2
70 | J657 | J624 |  |  | 63 | 388 | 6554.4 | 1.06 |  | 70 | j170 | j169 |  |  | 200 | 68.5 | 7609.7 | 1.2
71 | J624 | J620 |  |  | 63 | 185 | 6739.4 | 1.06 |  | 71 | j169 | j167 |  |  | 200 | 191.2 | 7800.9 | 1.2
72 | J624 | J595 | B.T ROAD | 0.36 | 63 | 3.3 | 6742.7 | 1.06 |  | 72 | j169 | j167 | b.t road | 0.5 | 200 | 5 | 7805.9 | 1.2
73 | J624 | J595 |  |  | 63 | 113.6 | 6856.3 | 1.06 |  | 73 | j167 | j166 | b.t road | 0.5 | 200 | 25.1 | 7831 | 1.2
74 | J595 | J596 |  |  | 63 | 74.5 | 6930.8 | 1.06 |  | 74 | j166 | j159 | b.t road | 0.5 | 200 | 92.7 | 7923.7 | 1.2
75 | J595 | J587 |  |  | 63 | 47.1 | 6977.9 | 1.06 |  | 75 | j159 | j146 | b.t road | 0.5 | 200 | 119.5 | 8043.2 | 1.2
76 | J587 | J525A |  |  | 63 | 36 | 7013.9 | 1.06 |  | 76 | j159 | j141 | b.t road | 0.5 | 200 | 85.1 | 8128.3 | 1.2
77 | J525A | J525B |  |  | 63 | 29.2 | 7043.1 | 1.06 |  | 77 | j141 | j113 | b.t road | 0.5 | 200 | 133.5 | 8261.8 | 1.2
78 | J525A | J511 |  |  | 63 | 162.1 | 7205.2 | 1.06 |  | 78 | j113 | j27 | b.t road | 0.5 | 200 | 212.3 | 8474.1 | 1.2
79 | J511A | J511B |  |  | 63 | 41.2 | 7246.4 | 1.06 |  | 79 | j27 | j23 | b.t road | 0.5 | 200 | 61 | 8535.1 | 1.2
80 | J587 | J639 | B.T ROAD | 0.36 | 63 | 2.5 | 7248.9 | 1.06 |  | 80 | j27 | j23 | culvert |  | 200 | 4.7 | 8539.8 | 1.2
81 | J587 | J639 |  |  | 63 | 421.6 | 7670.5 | 1.06 |  | 81 | j27 | j23 | b.t road | 0.5 | 200 | 12.3 | 8552.1 | 1.2
82 | J639 | J638 |  |  | 63 | 2.1 | 7672.6 | 1.06 |  | 82 | j502 | j493 | brick road | 0.5 | 200 | 19.2 | 8571.3 | 1.2
83 | J638 | J657 |  |  | 63 | 237 | 7909.6 | 1.06 |  | 83 | j493 | j491 | brick road | 0.5 | 200 | 101 | 8672.3 | 1.2
84 | J658 | J648 |  |  | 63 | 218.4 | 8128 | 1.06 |  | 84 | j491 | j489 | brick road | 0.5 | 200 | 29.3 | 8701.6 | 1.2
85 | J648 | J638 |  |  | 63 | 142.6 | 8270.6 | 1.06 |  | 85 | j489 | j485 |  | 0.5 | 200 | 45 | 8746.6 | 1.2
86 | J648 | J640 |  |  | 63 | 51.4 | 8322 | 1.06 |  | 86 | j485 | j481 | brick road | 0.5 | 200 | 46.4 | 8793 | 1.2
87 | J640 | J616 |  |  | 63 | 128 | 8450 | 1.06 |  | 87 | j487 | j486 | b.t road | 0.5 | 200 | 65.8 | 8858.8 | 1.2
88 | J616 | J617 |  |  | 63 | 38 | 8488 | 1.06 |  | 88 | j486 | j482 | b.t road | 0.5 | 200 | 75.6 | 8934.4 | 1.2
89 | J616 | J537 |  |  | 63 | 3.9 | 8491.9 | 1.06 |  | 89 | j481 | j483 | b.t road | 0.5 | 200 | 57.3 | 8991.7 | 1.2
90 | J616 | J537 | BRICK ROAD | 0.36 | 63 | 5.4 | 8497.3 | 1.06 |  | 90 | j480 | j477 |  | 0.5 | 200 | 70.6 | 9062.3 | 1.2
91 | J616 | J537 |  |  | 63 | 258.1 | 8755.4 | 1.06 |  | 91 | j477 | j379 |  | 0.5 | 200 | 98.8 | 9161.1 | 1.2
92 | J544 | J545 |  |  | 63 | 103.1 | 8858.5 | 1.06 |  | 92 | j379 | j376 |  | 0.5 | 200 | 45.6 | 9206.7 | 1.2
93 | J567 | J633 |  |  | 63 | 386.2 | 9244.7 | 1.06 |  | 93 | j495 | j487 |  | 0.46 | 160 | 87.8 | 9294.5 | 1.16
94 | J633 | J640 |  |  | 63 | 73.4 | 9318.1 | 1.06 |  | 94 | j433 | j492 |  | 0.46 | 160 | 167.8 | 9462.3 | 1.16
95 | J633 | J634 |  |  | 63 | 35.2 | 9353.3 | 1.06 |  | 95 | j433 | j442 | brick road | 0.46 | 160 | 27.1 | 9489.4 | 1.16
96 | J639 | J601 |  |  | 63 | 163.7 | 9517 | 1.06 |  | 96 | j511 | j514 |  | 0.44 | 140 | 25.1 | 9514.5 | 1.14
97 | J601 | J593 |  |  | 63 | 109.1 | 9626.1 | 1.06 |  | 97 | j511 | j514 | interlocking | 0.46 | 140 | 152.8 | 9667.3 | 1.14
98 | J593 | J568 |  |  | 63 | 90.7 | 9716.8 | 1.06 |  | 98 | j447 | j442 |  |  | 140 | 20 | 9687.3 | 1.14
99 | J568 | J569 |  |  | 63 | 49.2 | 9766 | 1.06 |  | 99 | j447 | j442 | brick road | 0.44 | 140 | 52 | 9739.3 | 1.14
100 | J568 | J562 |  |  | 63 | 52.1 | 9818.1 | 1.06 |  | 100 | j24 | j12 |  |  | 110 | 122.7 | 9862 | 1.1
101 | J562 | J563 |  |  | 63 | 38.2 | 9856.3 | 1.06 |  | 101 | j12 | j1 |  |  | 110 | 105.3 | 9967.3 | 1.1
102 | J562 | J557 |  |  | 63 | 20.6 | 9876.9 | 1.06 |  | 102 | j77 | j92 |  |  | 110 | 77.8 | 10045.1 | 1.1
103 | J557 | J529 |  |  | 63 | 68.2 | 9945.1 | 1.06 |  | 103 | j77 | j84 |  |  | 110 | 74.8 | 10119.9 | 1.1
104 | J557 | J543 |  |  | 63 | 120.2 | 10065.3 | 1.06 |  | 104 | j570 | j590 |  |  | 110 | 106.4 | 10226.3 | 1.1
105 | J543 | J509 |  |  | 63 | 153.6 | 10218.9 | 1.06 |  | 105 | j84 | j86 |  |  | 90 | 79.2 | 10305.5 | 1.09
106 | J509 | J529 |  |  | 63 | 51.3 | 10270.2 | 1.06 |  | 106 | j489 | j490 |  |  | 63 | 32 | 10337.5 | 1.06
107 | J543 | J546 |  |  | 63 | 28.3 | 10298.5 | 1.06 |  | 107 | j447a | j447b |  |  | 63 | 31 | 10368.5 | 1.06
108 | J546 | J552 |  |  | 63 | 89.3 | 10387.8 | 1.06 |  | 108 | j456 | j457 |  |  | 63 | 21.1 | 10389.6 | 1.06
109 | J546 | J547 |  |  | 63 | 45.2 | 10433 | 1.06 |  | 109 | j74 | j75 | interlocking | 0.46 | 63 | 97 | 10486.6 | 1.06
110 | j546 | j558 |  |  | 63 | 94.1 | 10527.1 | 1.06 |  | 110 | j162 | j165 | brick road | 0.36 | 63 | 298.7 | 10785.3 | 1.06
111 | j558 | j542 |  |  | 63 | 63.3 | 10590.4 | 1.06 |  | 111 | j45 | j133 | interlocking | 0.46 | 63 | 133 | 10918.3 | 1.06
112 | j558 | j542 | BRICK ROAD | 0.36 | 63 | 76.3 | 10666.7 | 1.06 |  | 112 | j111 | j128 | brick road | 0.36 | 63 | 238.4 | 11156.7 | 1.06
113 | j542 | j559 |  |  | 63 | 64.5 | 10731.2 | 1.06 |  | 113 | j128 | j130 | brick road | 0.36 | 63 | 11.2 | 11167.9 | 1.06
114 | j559 | j558 |  |  | 63 | 90.6 | 10821.8 | 1.06 |  | 114 | j130 | j137 | brick road | 0.36 | 63 | 44.5 | 11212.4 | 1.06
115 | j559 | j593 |  |  | 63 | 152.5 | 10974.3 | 1.06 |  | 115 | j137 | j142 | brick road | 0.36 | 63 | 45.5 | 11257.9 | 1.06
116 | j601 | j530 |  |  | 63 | 5.8 | 10980.1 | 1.06 |  | 116 | j142 | j147 | brick road | 0.36 | 63 | 22.3 | 11280.2 | 1.06
117 | j601 | j530 | BRICK ROAD | 0.36 | 63 | 210.7 | 11190.8 | 1.06 |  | 117 | j381 | j382 | b.t road | 0.44 | 140 | 6.2 | 11286.4 | 1.14
118 | j504 | j506 |  |  | 63 | 225.7 | 11416.5 | 1.06 |  | 118 | j381 | j382 |  |  | 140 | 29.7 | 11316.1 | 1.14
119 | j590a | j585 |  |  | 63 | 34.8 | 11451.3 | 1.06 |  | 119 | j382 | j386 |  |  | 140 | 34.3 | 11350.4 | 1.14
120 | j585 | j574 |  |  | 63 | 52.3 | 11503.6 | 1.06 |  | 120 | j398 | j393 | brickroad | 0.44 | 140 | 50.6 | 11401 | 1.14
121 | j574 | j570a |  |  | 63 | 44.9 | 11548.5 | 1.06 |  | 121 | j401 | j414 | brickroad | 0.36 | 63 | 6.5 | 11407.5 | 1.06
122 | j570a | j570b |  |  | 63 | 18.1 | 11566.6 | 1.06 |  | 122 | j310 | j376 | b.t road | 0.5 | 200 | 6.9 | 11414.4 | 1.2
123 | j570a | j570c |  |  | 63 | 29.7 | 11596.3 | 1.06 |  | 123 | j587 | j639 | b.t road | 0.36 | 63 | 3.5 | 11417.9 | 1.06
124 | j578 | j575 |  |  | 63 | 51.6 | 11647.9 | 1.06 |  | 124 | j504 | j506 | b.t road | 0.36 | 63 | 7 | 11424.9 | 1.06
125 | j575 | j574 |  |  | 63 | 10.1 | 11658 | 1.06 |  | 125 | j536 | j538 | b.t road | 0.36 | 63 | 6.5 | 11431.4 | 1.06
126 | j575 | j580 |  |  | 63 | 29.7 | 11687.7 | 1.06 |  | 126 | j574 | j575 | b.t road | 0.36 | 63 | 6.9 | 11438.3 | 1.06
127 | j585 | j581 |  |  | 63 | 141.1 | 11828.8 | 1.06 |  | 127 | j7 | j7a |  |  | 63 | 302 | 11740.3 | 1.06
128 | j379 | j502 |  |  | 63 | 292 | 12120.8 | 1.06 |  |  |  |  | 63 | 90 | 110 | 140 | 160 | 200
129 | j514 | j619 |  |  | 63 | 134.2 | 12255 | 1.06 |  |  |  |  | 2611.5 | 258.1 | 858.7 | 1496.2 | 3547.3 | 2968.5 | 11740.3
130 | j514 | j619 | BRICK ROAD | 0.36 | 63 | 323 | 12578 | 1.06 |  | POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
131 | j401 | j414 |  |  | 63 | 182 | 12760 | 1.06 |  | DESIGNATION |  |  |  | DESIGNATION |  |  | DESIGNATION
132 | j414 | j419 |  |  | 63 | 52.8 | 12812.8 | 1.06 |  | NAME |  |  |  | NAME |  |  | NAME
133 | j419 | j422 |  |  | 63 | 30 | 12842.8 | 1.06 |  | SIGN.with date |  |  |  | SIGN.with date |  |  | SIGN.with date
134 | j416 | j419 |  |  | 63 | 5.2 | 12848 | 1.06
135 | j416 | j417 |  |  | 63 | 24 | 12872 | 1.06 | [9 empty] | 33727.7
136 | j416 | j418 |  |  | 63 | 47 | 12919 | 1.06 | [9 empty] | 34187.8
137 | j418 | j423 |  |  | 63 | 56 | 12975 | 1.06
138 | j382 | j383 |  |  | 63 | 49.8 | 13024.8 | 1.06
139 | j386 | j387 |  |  | 63 | 23.6 | 13048.4 | 1.06
140 | j386 | j388 |  |  | 63 | 28.3 | 13076.7 | 1.06
141 | j414 | j407 |  |  | 63 | 15 | 13091.7 | 1.06 | [5 empty] | 398.556
142 | j414 | j407 | BRICK ROAD | 0.36 | 63 | 3.9 | 13095.6 | 1.06 | [5 empty] | 93.242 |  | 1048
143 | j407 | j408 |  |  | 63 | 40 | 13135.6 | 1.06 | [5 empty] | 30.06 |  | 433.27
144 | j451 | j455a |  |  | 63 | 82.4 | 13218 | 1.06 | [5 empty] | 649.5008 |  |  | 1139.272
145 | j455a | j455b |  |  | 63 | 49 | 13267 | 1.06 | [5 empty] | 340.078
146 | j455a | j455c |  |  | 63 | 80 | 13347 | 1.06 | [5 empty] | 1109.2128
147 | j455c | j462 |  |  | 63 | 63.6 | 13410.6 | 1.06 | [5 empty] | 257.58
148 | j455c | j466 |  |  | 63 | 54.5 | 13465.1 | 1.06
149 | j466 | j471 |  |  | 63 | 64 | 13529.1 | 1.06
150 | j466 | j464 |  |  | 63 | 30.6 | 13559.7 | 1.06
151 | j464 | j468 |  |  | 63 | 59.2 | 13618.9 | 1.06
152 | j468 | j471 |  |  | 63 | 20.4 | 13639.3 | 1.06
153 | j468 | j469 |  |  | 63 | 28 | 13667.3 | 1.06
154 | j464 | j459 |  |  | 63 | 186 | 13853.3 | 1.06
155 | j459 | j440 |  |  | 63 | 175 | 14028.3 | 1.06
156 | j440 | j440a |  |  | 63 | 28.2 | 14056.5 | 1.06
157 | j440a | j440b |  |  | 63 | 27.1 | 14083.6 | 1.06
158 | j440a | j440c |  |  | 63 | 26.6 | 14110.2 | 1.06
159 | j487 | j488 |  |  | 63 | 42.3 | 14152.5 | 1.06
160 | j487 | j476 |  |  | 63 | 197 | 14349.5 | 1.06
161 | j476 | j478 |  |  | 63 | 46.5 | 14396 | 1.06
162 | j478 | j479a | BRICK ROAD | 0.36 | 63 | 12.2 | 14408.2 | 1.06
163 | j479a | j479 | BRICK ROAD | 0.36 | 63 | 6.5 | 14414.7 | 1.06
164 | j479a | j479 |  |  | 63 | 14.2 | 14428.9 | 1.06
165 | j479a | j479b |  |  | 63 | 30.6 | 14459.5 | 1.06
166 | j478 | j480 |  |  | 63 | 40.9 | 14500.4 | 1.06
167 | j476 | j476a |  |  | 63 | 95.2 | 14595.6 | 1.06
168 | j476a | j398 |  |  | 63 | 94.4 | 14690 | 1.06
169 | j477 | j485 |  |  | 63 | 80.2 | 14770.2 | 1.06
170 | j485 | j477 |  |  | 63 | 51.2 | 14821.4 | 1.06
171 | j482 | j486 |  |  | 63 | 89.8 | 14911.2 | 1.06
172 | j495 | j499 |  |  | 63 | 46.3 | 14957.5 | 1.06
173 | j499 | j500 |  |  | 63 | 53.7 | 15011.2 | 1.06
174 | j499 | j501 |  |  | 63 | 71.2 | 15082.4 | 1.06
175 | j495 | j498 |  |  | 63 | 45.2 | 15127.6 | 1.06
176 | j496 | j498 |  |  | 63 | 40.3 | 15167.9 | 1.06
177 | j552a | j552b |  |  | 63 | 28.2 | 15196.1 | 1.06
178 | j519 | j523 |  |  | 63 | 65.3 | 15261.4 | 1.06
179 | j523 | j521 |  |  | 63 | 14 | 15275.4 | 1.06
180 | j523 | j525 |  |  | 63 | 51.2 | 15326.6 | 1.06
181 | j523 | j521 |  |  | 63 | 23.4 | 15350 | 1.06
182 | j594 | j598 | BRICK ROAD | 0.36 | 63 | 3.3 | 15353.3 | 1.06
183 | j594 | j598 |  |  | 63 | 173 | 15526.3 | 1.06
184 | j608 | j609 |  |  | 63 | 118 | 15644.3 | 1.06
185 | j608 | j609 |  |  | 63 | 2.5 | 15646.8 | 1.06
186 | j527 | j513 |  |  | 63 | 55.4 | 15702.2 | 1.06
187 | j553 | j554 |  |  | 63 | 35.7 | 15737.9 | 1.06
188 | j553a | j553b |  |  | 63 | 35.1 | 15773 | 1.06
189 | j520 | j522 |  |  | 63 | 21 | 15794 | 1.06
190 | j531a | j531b |  |  | 63 | 80.5 | 15874.5 | 1.06
191 | j493 | j494 |  |  | 63 | 68.9 | 15943.4 | 1.06
192 | j526 | j530 | interlocking | 0.46 | 63 | 21.7 | 15965.1 | 1.06
193 | j530 | j600 | interlocking | 0.46 | 63 | 181 | 16146.1 | 1.06
194 | j530 | j600 |  |  | 63 | 161.5 | 16307.6 | 1.06
194 | j600 | j601 | BRICK ROAD | 0.36 | 63 | 51.2 | 16358.8 | 1.06
195 | j600 | j602 | BRICK ROAD | 0.36 | 63 | 53.2 | 16412 | 1.06
196 | j602 | j603 |  |  | 63 | 62.8 | 16474.8 | 1.06
197 | j602 | j616 | BRICK ROAD | 0.36 | 63 | 21.7 | 16496.5 | 1.06
198 | j645 | j635 |  |  | 63 | 76.3 | 16572.8 | 1.06
199 | j604 | j606 |  |  | 63 | 59.2 | 16632 | 1.06
200 | j604 | j605 |  |  | 63 | 89.2 | 16721.2 | 1.06
201 | j626 | j625 |  |  | 63 | 30.2 | 16751.4 | 1.06
202 | j570 | j572 |  |  | 63 | 38 | 16789.4 | 1.06
203 | j576a | j576b |  |  | 63 | 41.5 | 16830.9 | 1.06
204 | j381 | j391 | B.T ROAD | 0.36 | 63 | 5 | 16835.9 | 1.06
205 | j435 | j439 |  |  | 63 | 32.2 | 16868.1 | 1.06
206 | j428 | j438 | culvert |  | 63 | 2.4 | 16870.5 | 1.06
207 | j428 | j438 | BRICK ROAD | 0.36 | 63 | 95.5 | 16966 | 1.06
208 | j438 | j443 | BRICK ROAD | 0.36 | 63 | 50.9 | 17016.9 | 1.06
209 | j443 | j444 | BRICK ROAD | 0.36 | 63 | 2.3 | 17019.2 | 1.06
210 | j443 | j444 |  |  | 63 | 33.3 | 17052.5 | 1.06
211 | j438 | j429 | BRICK ROAD | 0.36 | 63 | 2.7 | 17055.2 | 1.06
212 | j438 | j429 |  |  | 63 | 63.3 | 17118.5 | 1.06
213 | j427a | j427b | BRICK ROAD | 0.36 | 63 | 37.1 | 17155.6 | 1.06
214 | j427 | j428 | BRICK ROAD | 0.36 | 63 | 32.2 | 17187.8 | 1.06
215 | j427a | j429 | BRICK ROAD | 0.36 | 63 | 8.1 | 17195.9 | 1.06
216 | j429 | j430 | BRICK ROAD | 0.36 | 63 | 23.7 | 17219.6 | 1.06
217 | j429 | j424 |  |  | 63 | 47.9 | 17267.5 | 1.06
218 | j424 | j426 |  |  | 63 | 3.9 | 17271.4 | 1.06
219 | j424 | j426 | BRICK ROAD | 0.36 | 63 | 53.6 | 17325 | 1.06
220 | j424 | j426 |  |  | 63 | 24 | 17349 | 1.06
221 | j424 | j409 |  |  | 63 | 76.6 | 17425.6 | 1.06
222 | j409 | j510 |  |  | 63 | 99.4 | 17525 | 1.06
223 | j536 | j538 |  |  | 63 | 89.7 | 17614.7 | 1.06
224 | j506 | j508 |  |  | 63 | 29.2 | 17643.9 | 1.06
225 | j487 | j495 |  |  | 63 | 27 | 17670.9 | 1.06
226 | j570 | j567 |  |  | 140 | 149 | 17819.9 | 1.14
227 | j567 | j544 |  |  | 140 | 197.6 | 18017.5 | 1.14
228 | j425 | j450 |  |  | 140 | 243.6 | 18261.1 | 1.14
229 | j450 | j456 |  |  | 140 | 50.5 | 18311.6 | 1.14
230 | j450 | j451 |  |  | 140 | 73 | 18384.6 | 1.14
231 | j451 | j447 |  |  | 140 | 260 | 18644.6 | 1.14
232 | j451 | j448 |  |  | 140 | 444 | 19088.6 | 1.14
233 | j544 | j537 |  |  | 160 | 164 | 19252.6 | 1.16
234 | j537 | j526 |  |  | 160 | 190 | 19442.6 | 1.16
235 | j526 | j502 |  |  | 160 | 100.2 | 19542.8 | 1.16
236 | j381 | j391 |  |  | 160 | 16.1 | 19558.9 | 1.16
237 | j391 | j425 |  |  | 160 | 324.3 | 19883.2 | 1.16
238 | j431 | j428 |  |  | 160 | 18.3 | 19901.5 | 1.16
239 | j427a | j427 |  |  | 160 | 41.6 | 19943.1 | 1.16
240 | j409 | j406 |  |  | 160 | 205.2 | 20148.3 | 1.16
241 | j406 | j427 |  |  | 160 | 188.6 | 20336.9 | 1.16
242 | j406 | j401 |  |  | 160 | 12.1 | 20349 | 1.16
243 | j401 | j391 |  |  | 160 | 133.6 | 20482.6 | 1.16
244 | j495 | j505 |  |  | 160 | 105.3 | 20587.9 | 1.16
245 | j505 | j511 |  |  | 160 | 79.7 | 20667.6 | 1.16
246 | j376 | j371 |  |  | 200 | 188.4 | 20856 | 1.2
247 | j376 | j371 | culvert |  | 200 | 14.3 | 20870.3 | 1.2
248 | j376 | j371 |  |  | 200 | 754 | 21624.3 | 1.2
249 | j371 | j316 |  |  | 200 | 503.7 | 22128 | 1.2
250 | j376 | j380 |  |  | 200 | 190.3 | 22318.3 | 1.2
251 | j380 | j381 |  |  | 200 | 129.2 | 22447.5 | 1.2
|  |  | 63 | 140 | 160 | 200
|  |  | 17670.9 | 1417.7 | 1579 | 1779.9 | 22447.5
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  | SIGN.with date |  |  |  | 20282.4
2913.9
5126.3
|  |  | ROAD RESTORATION | [7 empty] | 4748.4
TYPE OF ROAD | 63 | 75 | 90 | 110 | 140 | 160 | 200 | AVG WIDTH | Cummilative |  | 258.1
BRICK ROAD | 1107.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0.36 | 398.556 | 1047 | 858.7
B.T ROAD | 83.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.36 | 30.06
interlocking | 202.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0.46 | 93.242
cc | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  | SIGN.with date
3824.4
2311.5
875

## MADHURA RANI GANJ(TANISH-2)
MADHURA RANI GANJ AND SARAOULI(JMR) BLOCK-MANGRAURA
Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | Dia of pipe(MM) | Pipe Length (M) | CUMMULATIVE | Depth(M) | REMARK
1 | j542 | j491 | brick road | 0.36 | 63 | 100.7 | 100.7 | 1.06
2 | j380 | j399 | interlocking | 0.46 | 63 | 125.8 | 226.5 | 1.06
3 | j399 | j403 | interlocking | 0.46 | 63 | 25.2 | 251.7 | 1.06
4 | j403 | j411 | interlocking | 0.46 | 63 | 30.1 | 281.8 | 1.06
5 | j411 | j418 | interlocking | 0.46 | 63 | 57.2 | 339 | 1.06
6 | j411 | j418 |  |  | 63 | 23.2 | 362.2 | 1.06
7 | j380 | j399 | culvert |  | 63 | 2 | 364.2 | 1.06
8 | j380 | j399 | b.t road | 0.36 | 63 | 6.7 | 370.9 | 1.06
9 | j447a | j447b |  |  | 63 | 10.2 | 381.1 | 1.06
10 | j129 | j130 | brick road | 0.36 | 63 | 25.1 | 406.2 | 1.06
11 | j34 | j35 | b.t road | 0.36 | 63 | 5 | 411.2 | 1.06
12 | j34 | j35 | cc | 0.36 | 63 | 103.1 | 514.3 | 1.06
13 | j133 | j134 | cc | 0.36 | 63 | 113.2 | 627.5 | 1.06
14 | j134 | j136 | cc | 0.36 | 63 | 54 | 681.5 | 1.06
15 | j134 | j135 | cc | 0.36 | 63 | 24.8 | 706.3 | 1.06
16 | j133 | j138 | interlocking | 0.46 | 63 | 85.1 | 791.4 | 1.06
17 | j138 | j160 | cc | 0.36 | 63 | 47.1 | 838.5 | 1.06
18 | j138 | j139 | cc | 0.36 | 63 | 78.3 | 916.8 | 1.06
19 | j25 | j38 | b.t road | 0.36 | 63 | 4 | 920.8 | 1.06
20 | j25 | j38 |  |  | 63 | 15.3 | 936.1 | 1.06
21 | j25 | j38 | interlocking | 0.46 | 63 | 33.1 | 969.2 | 1.06
22 | j25 | j38 | cc | 0.36 | 63 | 93.5 | 1062.7 | 1.06
23 | j39 | j38 | cc | 0.36 | 63 | 47.6 | 1110.3 | 1.06
24 | j38 | j79 | cc | 0.36 | 63 | 80.8 | 1191.1 | 1.06
25 | j27 | j27a |  |  | 63 | 37.2 | 1228.3 | 1.06
26 | j27 | j27a | b.t road | 0.36 | 63 | 3 | 1231.3 | 1.06
27 | j30 | j31 | cc | 0.36 | 63 | 73.1 | 1304.4 | 1.06
28 | j55 | j50 |  |  | 90 | 77.6 | 1382 | 1.09
29 | j63 | j74 |  |  | 90 | 101.3 | 1483.3 | 1.09
30 | j126 | j129 | brick road | 0.41 | 110 | 30.2 | 1513.5 | 1.1
31 | j2 | j3 |  |  | 110 | 195.6 | 1709.1 | 1.1
32 | j2 | j3 | b.t road | 0.41 | 110 | 5 | 1714.1 | 1.1
33 | j441 | j459 |  |  | 110 | 140.9 | 1855 | 1.1
34 | j448 | j454 |  |  | 140 | 118.6 | 1973.6 | 1.14
35 | j425 | j437 |  |  | 140 | 91.3 | 2064.9 | 1.14
36 | j437 | j441 |  |  | 140 | 110.1 | 2175 | 1.14
37 | j451 | j447 |  |  | 140 | 44.2 | 2219.2 | 1.14
38 | j50 | j49 |  |  | 140 | 189.7 | 2408.9 | 1.14
39 | j45 | j63 |  |  | 140 | 291.1 | 2700 | 1.14
40 | j120 | j123 | brick road | 0.44 | 140 | 26.2 | 2726.2 | 1.14
41 | j123 | j126 | brick road | 0.44 | 140 | 48.1 | 2774.3 | 1.14
42 | j77 | j72 | b.t road | 0.44 | 140 | 206.2 | 2980.5 | 1.14
43 | j442 | j448 |  |  | 160 | 167.5 | 3148 | 1.16
44 | j49 | j47 |  |  | 160 | 215 | 3363 | 1.16
45 | j47 | j45 |  |  | 160 | 701.1 | 4064.1 | 1.16
46 | j47 | j45 | culvert |  | 160 | 3 | 4067.1 | 1.16
47 | j45 | j34 |  |  | 160 | 206 | 4273.1 | 1.16
48 | j34 | j30 |  |  | 160 | 90 | 4363.1 | 1.16
49 | j30 | j29 |  |  | 160 | 15 | 4378.1 | 1.16
50 | j29 | j25 |  |  | 160 | 168 | 4546.1 | 1.16
51 | j25 | j24 |  |  | 160 | 54.9 | 4601 | 1.16
52 | j24 | j23 |  |  | 160 | 88.8 | 4689.8 | 1.16
53 | j24 | j23 | b.t road | 0.46 | 160 | 7.2 | 4697 | 1.16
54 | j23 | j26 |  |  | 160 | 127.2 | 4824.2 | 1.16
55 | j26 | j28 |  |  | 160 | 7.7 | 4831.9 | 1.16
56 | j28 | j46 |  |  | 160 | 195.7 | 5027.6 | 1.16
57 | j46 | j72 |  |  | 160 | 234.1 | 5261.7 | 1.16
58 | j72 | j110 |  |  | 160 | 165.3 | 5427 | 1.16
59 | j72 | j110 | b.t road | 0.46 | 160 | 4.6 | 5431.6 | 1.16
60 | j113 | j115 |  |  | 160 | 60 | 5491.6 | 1.16
61 | j115 | j120 | brick road | 0.46 | 160 | 338.3 | 5829.9 | 1.16
62 | j216 | j215 |  |  | 160 | 263.1 | 6093 | 1.16
63 | j167 | j182 |  |  | 160 | 152.1 | 6245.1 | 1.16
64 | j310 | j309 | b.t road | 0.5 | 200 | 270.7 | 6515.8 | 1.2
65 | j310 | j283 | b.t road | 0.5 | 200 | 119.7 | 6635.5 | 1.2
66 | j283 | j228 | b.t road | 0.5 | 200 | 223.2 | 6858.7 | 1.2
67 | j228 | j216 | b.t road | 0.5 | 200 | 248.5 | 7107.2 | 1.2
68 | j216 | j170 | b.t road | 0.5 | 200 | 357.2 | 7464.4 | 1.2
69 | j216 | j170 | b.t road | 0.5 | 200 | 76.8 | 7541.2 | 1.2
70 | j170 | j169 | b.t road | 0.5 | 200 | 68.5 | 7609.7 | 1.2
71 | j169 | j167 | b.t road | 0.5 | 200 | 191.2 | 7800.9 | 1.2
72 | j169 | j167 | b.t road | 0.5 | 200 | 5 | 7805.9 | 1.2
73 | j167 | j166 | b.t road | 0.5 | 200 | 25.1 | 7831 | 1.2
74 | j166 | j159 | b.t road | 0.5 | 200 | 92.7 | 7923.7 | 1.2
75 | j159 | j146 | b.t road | 0.5 | 200 | 119.5 | 8043.2 | 1.2
76 | j159 | j141 | b.t road | 0.5 | 200 | 85.1 | 8128.3 | 1.2
77 | j141 | j113 | b.t road | 0.5 | 200 | 133.5 | 8261.8 | 1.2 |  |  | 1253.95
78 | j113 | j27 | b.t road | 0.5 | 200 | 212.3 | 8474.1 | 1.2 |  |  | 140.01
79 | j27 | j23 | b.t road | 0.5 | 200 | 61 | 8535.1 | 1.2
80 | j27 | j23 | culvert |  | 200 | 4.7 | 8539.8 | 1.2
81 | j27 | j23 | b.t road | 0.5 | 200 | 12.3 | 8552.1 | 1.2
82 | j502 | j493 | brick road | 0.5 | 200 | 19.2 | 8571.3 | 1.2
83 | j493 | j491 | brick road | 0.5 | 200 | 101 | 8672.3 | 1.2
84 | j491 | j489 | brick road | 0.5 | 200 | 29.3 | 8701.6 | 1.2
85 | j489 | j485 |  |  | 200 | 45 | 8746.6 | 1.2
86 | j485 | j481 | brick road | 0.5 | 200 | 46.4 | 8793 | 1.2
87 | j487 | j486 | b.t road | 0.5 | 200 | 65.8 | 8858.8 | 1.2
88 | j486 | j482 | b.t road | 0.5 | 200 | 75.6 | 8934.4 | 1.2 |  | 1313.315
89 | j481 | j483 | b.t road | 0.5 | 200 | 57.3 | 8991.7 | 1.2
90 | j480 | j477 |  | 0.5 | 200 | 70.6 | 9062.3 | 1.2
91 | j477 | j379 |  | 0.5 | 200 | 98.8 | 9161.1 | 1.2
92 | j379 | j376 |  | 0.5 | 200 | 45.6 | 9206.7 | 1.2
93 | j495 | j487 | b.t road | 0.46 | 160 | 87.8 | 9294.5 | 1.16
94 | j433 | j492 |  |  | 160 | 167.8 | 9462.3 | 1.16
95 | j433 | j442 | brick road | 0.46 | 160 | 27.1 | 9489.4 | 1.16
96 | j511 | j514 |  | 0.44 | 140 | 25.1 | 9514.5 | 1.14
97 | j511 | j514 | interlocking | 0.46 | 140 | 152.8 | 9667.3 | 1.14
98 | j447 | j442 |  |  | 140 | 20 | 9687.3 | 1.14
99 | j447 | j442 | brick road | 0.44 | 140 | 52 | 9739.3 | 1.14
100 | j24 | j12 |  |  | 110 | 122.7 | 9862 | 1.1
101 | j12 | j1 |  |  | 110 | 105.3 | 9967.3 | 1.1
102 | j77 | j92 |  |  | 110 | 77.8 | 10045.1 | 1.1
103 | j77 | j84 |  |  | 110 | 74.8 | 10119.9 | 1.1
104 | j570 | j590 |  |  | 110 | 106.4 | 10226.3 | 1.1
105 | j84 | j86 |  |  | 90 | 79.2 | 10305.5 | 1.09
106 | j489 | j490 |  |  | 63 | 32 | 10337.5 | 1.06
107 | j447a | j447b |  |  | 63 | 31 | 10368.5 | 1.06
108 | j456 | j457 |  |  | 63 | 21.1 | 10389.6 | 1.06
109 | j74 | j75 | interlocking | 0.46 | 63 | 97 | 10486.6 | 1.06
110 | j162 | j165 | b.t road | 0.36 | 63 | 298.7 | 10785.3 | 1.06
111 | j45 | j133 | b.t road | 0.36 | 63 | 133 | 10918.3 | 1.06
112 | j111 | j128 | b.t road | 0.36 | 63 | 238.4 | 11156.7 | 1.06
113 | j128 | j130 | b.t road | 0.36 | 63 | 11.2 | 11167.9 | 1.06
114 | j130 | j137 | b.t road | 0.36 | 63 | 44.5 | 11212.4 | 1.06
115 | j137 | j142 | b.t road | 0.36 | 63 | 45.5 | 11257.9 | 1.06
116 | j142 | j147 | b.t road | 0.36 | 63 | 22.3 | 11280.2 | 1.06
117 | j381 | j382 | b.t road | 0.44 | 140 | 6.2 | 11286.4 | 1.14
118 | j381 | j382 |  |  | 140 | 29.7 | 11316.1 | 1.14
119 | j382 | j386 |  |  | 140 | 34.3 | 11350.4 | 1.14
120 | j398 | j393 | brick road | 0.44 | 140 | 50.6 | 11401 | 1.14
121 | j401 | j414 | brick road | 0.36 | 63 | 6.5 | 11407.5 | 1.06
122 | j310 | j376 | b.t road | 0.5 | 200 | 6.9 | 11414.4 | 1.2
123 | j587 | j639 | b.t road | 0.36 | 63 | 3.5 | 11417.9 | 1.06
124 | j504 | j506 | b.t road | 0.36 | 63 | 7 | 11424.9 | 1.06
125 | j536 | j538 | b.t road | 0.36 | 63 | 6.5 | 11431.4 | 1.06
126 | j574 | j575 | culvert | 0.36 | 63 | 6.9 | 11438.3 | 1.06
127 | j7 | j7a |  |  | 63 | 302 | 11740.3 | 1.06
|  |  | 63 | 90 | 110 | 140 | 160 | 200
|  |  | 2611.5 | 258.1 | 858.7 | 1496.2 | 3547.3 | 2968.5 | 11740.3
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  | SIGN.with date
ROAD RESTORATION
TYPE OF ROAD | 63 | 75 | 90 | 110 | 140 | 160 | 200 | AVG WIDTH | Cummilative
brick road | 132.3 | 0 | 0 | 30.2 | 176.9 | 365.4 | 195.9 | 0.416 | 374.6912
b.t road | 829.3 | 0 | 0 | 5 | 212.4 | 99.6 | 2507.9 | 0.461 | 1684.5862
interlocking | 453.5 | 0 | 0 | 0 | 152.8 | 0 | 0 | 0.36 | 218.268
cc | 715.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.466 | 333.423
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  | SIGN.with date

## madhra rani (ags)
MADHURA RANI GANJ AND SARAOULI(JMR) BLOCK-MANGRAURA
Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | Dia of pipe(MM) | Pipe Length (M) | CUMMULATIVE | Depth(M) | REMARK
1 | j341 | j354 |  |  | 63 | 101 | 101
2 | j344 | j341 |  |  | 63 | 7.3 | 108.3
3 | j337 | j337a |  |  | 63 | 15.5 | 123.8
4 | j344 | j347 |  |  | 63 | 56.2 | 180
5 | j341 | j366 |  |  | 63 | 197.1 | 377.1
6 | j341 | j366 | B.T ROAD |  | 63 | 19.3 | 396.4
7 | J341 | J366 |  |  | 63 | 173.2 | 569.6
8 | J366 | J368 |  |  | 63 | 152.7 | 722.3
9 | J368 | J369 |  |  | 63 | 54.8 | 777.1
10 | J368 | J362 |  |  | 63 | 150 | 927.1
11 | J366 | J355 | B.T ROAD |  | 63 | 3.2 | 930.3
12 | J366 | J355 |  |  | 63 | 127.6 | 1057.9
13 | J355 | J360 |  |  | 63 | 125.5 | 1183.4
14 | J351 | J350 |  |  | 63 | 123 | 1306.4
15 | J322 | J336 |  |  | 63 | 240 | 1546.4
16 | J324 | j333 |  |  | 63 | 111.7 | 1658.1
17 | j324 | j325 |  |  | 63 | 20.2 | 1678.3
18 | j324 | j322 |  |  | 63 | 38.8 | 1717.1
19 | j270 | j289 |  |  | 63 | 246 | 1963.1
20 | j289 | j306 |  |  | 63 | 291.1 | 2254.2
21 | j306 | j301 |  |  | 63 | 245.2 | 2499.4
22 | j306 | j301 | brick road |  | 63 | 3.1 | 2502.5
23 | j301 | j304 | brick road |  | 63 | 40.2 | 2542.7
24 | j304 | j305 |  |  | 63 | 61.1 | 2603.8
25 | j304 | j302a | brick road |  | 63 | 115.1 | 2718.9
26 | j304 | j302a | brick road |  | 63 | 4 | 2722.9
27 | j302a | j302b |  |  | 63 | 24.1 | 2747
28 | j302a | j302 |  |  | 63 | 15.6 | 2762.6
29 | j302 | j303 | brick road |  | 63 | 7.5 | 2770.1
30 | j302 | j303 | brick road |  | 63 | 32.1 | 2802.2
31 | j302 | j303 |  |  | 63 | 70.2 | 2872.4
32 | j302 | j299 | brick road |  | 63 | 8 | 2880.4
33 | j302 | j299 | brick road |  | 63 | 20 | 2900.4
34 | j302 | j299 | brick road |  | 63 | 3.2 | 2903.6
35 | j299 | j300 |  |  | 63 | 75.5 | 2979.1
36 | j299 | j297 |  |  | 63 | 40.5 | 3019.6
37 | j297 | j298 |  |  | 63 | 36.1 | 3055.7
38 | j298a | j298 |  |  | 63 | 14 | 3069.7
39 | j298 | j298b |  |  | 63 | 22 | 3091.7
40 | j297 | j295 |  |  | 63 | 93.2 | 3184.9
41 | j295 | j293 |  |  | 63 | 104.5 | 3289.4
42 | j293 | j288 | brick road |  | 63 | 55 | 3344.4
43 | j293 | j288 |  |  | 63 | 11 | 3355.4
44 | j293 | j290 |  |  | 63 | 10.5 | 3365.9
45 | j290 | j286 |  |  | 63 | 15.5 | 3381.4
46 | j286 | j285 |  |  | 63 | 88.3 | 3469.7
47 | j295 | j294 |  |  | 63 | 171 | 3640.7
48 | j265 | j266 |  |  | 63 | 340.1 | 3980.8
49 | j266 | j267 |  |  | 63 | 61 | 4041.8
50 | j267a | j267b |  |  | 63 | 12.9 | 4054.7
51 | j266 | j268 |  |  | 63 | 29.2 | 4083.9
52 | j265 | j264 |  |  | 63 | 216 | 4299.9
53 | j264 | j262 |  |  | 63 | 219.1 | 4519
54 | j262 | j263 |  |  | 63 | 35 | 4554
55 | j262 | j256 |  |  | 63 | 50 | 4604
56 | j256 | j255 | B.T ROAD |  | 63 | 3.8 | 4607.8
57 | j256 | j255 | brick road |  | 63 | 6.2 | 4614
58 | j255 | j260 |  |  | 63 | 118 | 4732
59 | j255 | j249 | brick road |  | 63 | 64.1 | 4796.1
60 | j249 | j253 | brick road |  | 63 | 17.2 | 4813.3
61 | j249 | j253 |  |  | 63 | 15 | 4828.3
62 | j249 | j244 |  |  | 63 | 13 | 4841.3
63 | j244 | j250 |  |  | 63 | 116.1 | 4957.4
64 | j244 | j231 |  |  | 63 | 58.2 | 5015.6
65 | j244 | j231 | brick road |  | 63 | 25 | 5040.6
66 | j244 | j231 |  |  | 63 | 94 | 5134.6
67 | j252 | j250 |  |  | 63 | 81 | 5215.6
68 | j250 | j244 |  |  | 63 | 51 | 5266.6
69 | j250 | j251 |  |  | 63 | 49.1 | 5315.7
70 | j250a | j250b |  |  | 63 | 57 | 5372.7
71 | j224 | j225 |  |  | 63 | 53.2 | 5425.9
72 | j225 | j226 |  |  | 63 | 146.1 | 5572
73 | j225 | j227 | B.T ROAD |  | 63 | 3.4 | 5575.4
74 | j225 | j227 |  |  | 63 | 56.5 | 5631.9
75 | j221 | j222 |  |  | 63 | 67 | 5698.9
76 | j216 | j220 |  |  | 63 | 321.1 | 6020
77 | j171 | j170 |  |  | 63 | 65.9 | 6085.9
78 | j171 | j172 |  |  | 63 | 78.5 | 6164.4
79 | j171 | j173 | interlocking |  | 63 | 21.5 | 6185.9
80 | j173 | j177 |  |  | 63 | 48.5 | 6234.4
81 | j173 | j174 | interlocking |  | 63 | 5.4 | 6239.8
82 | j173 | j174 | brick road |  | 63 | 3.7 | 6243.5
83 | j173 | j174 |  |  | 63 | 22.4 | 6265.9
84 | j174 | j175 |  |  | 63 | 55.3 | 6321.2
85 | j174 | j177 |  |  | 63 | 125.6 | 6446.8
86 | j169 | j146 |  |  | 63 | 474 | 6920.8
87 | j182 | j183 |  |  | 63 | 158.5 | 7079.3
88 | j166 | j160 |  |  | 63 | 68.1 | 7147.4
89 | j160 | j161 |  |  | 63 | 39 | 7186.4
90 | j160 | j138 |  |  | 63 | 474.2 | 7660.6
91 | j160 | j159 |  |  | 63 | 180 | 7840.6
92 | j145 | j152 |  |  | 63 | 213 | 8053.6
93 | j140 | j157 |  |  | 63 | 116 | 8169.6
94 | j113 | j114 |  |  | 63 | 78 | 8247.6
95 | j273 | j274 |  |  | 63 | 160 | 8407.6
96 | j274 | j277 | B.T ROAD |  | 63 | 3 | 8410.6
97 | j274 | j277 |  |  | 63 | 206 | 8616.6
98 | j274 | j275 |  |  | 63 | 32 | 8648.6
99 | j275 | j276 | B.T ROAD |  | 63 | 3 | 8651.6
100 | j275 | j276 |  |  | 63 | 81.2 | 8732.8
101 | j275 | j278 |  |  | 63 | 134.5 | 8867.3
102 | j278a | j278b |  |  | 63 | 18.8 | 8886.1
103 | j301 | j269 |  |  | 63 | 308.5 | 9194.6
104 | j301 | j269 | interlocking |  | 63 | 36.2 | 9230.8
105 | j301 | j269 |  |  | 63 | 111.1 | 9341.9
106 | j296 | j245 |  |  | 63 | 248 | 9589.9
107 | j245 | j246 |  |  | 63 | 8.5 | 9598.4
108 | j246 | j247 |  |  | 63 | 45.1 | 9643.5
109 | j246 | j246a |  |  | 63 | 6.3 | 9649.8
110 | j246a | j246b |  |  | 63 | 29.2 | 9679
111 | j246a | j246c |  |  | 63 | 4.3 | 9683.3 |  |  |  | 12393.8
112 | j246c | j246d |  |  | 63 | 24.7 | 9708 |  |  |  | 15344.8
113 | j246 | j248 |  |  | 63 | 140.3 | 9848.3
114 | j236 | j243 |  |  | 63 | 58 | 9906.3
115 | j236 | j211 |  |  | 63 | 573.5 | 10479.8
116 | j236 | j233 |  |  | 63 | 469.1 | 10948.9
117 | j233 | j234 |  |  | 63 | 107 | 11055.9
118 | j233 | j230 |  |  | 63 | 116 | 11171.9
119 | j230 | j223 |  |  | 63 | 176.6 | 11348.5
120 | j230 | j240 |  |  | 63 | 183.1 | 11531.6
121 | j240 | j269 | interlocking |  | 63 | 3 | 11534.6
122 | j240 | j269 |  |  | 63 | 247.4 | 11782
123 | j306 | j313 | B.T ROAD |  | 63 | 3 | 11785
124 | j306 | j313 |  |  | 63 | 170.1 | 11955.1
125 | j306 | j313 | culvert |  | 63 | 12 | 11967.1
126 | j306 | j313 | B.T ROAD |  | 63 | 12 | 11979.1
127 | j306 | j313 |  |  | 63 | 656 | 12635.1
128 | j265 | j270 |  |  | 110 | 65 | 12700.1
129 | j337 | j337a |  |  | 140 | 67.7 | 12767.8
130 | j337a(1) | j337a | B.T ROAD |  | 140 | 5.3 | 12773.1
131 | j337a(1) | j344 |  |  | 140 | 17.1 | 12790.2
132 | j344 | j341 |  |  | 140 | 24.3 | 12814.5
133 | j315 | j322 |  |  | 140 | 122.3 | 12936.8
134 | j315 | j322 | B.T ROAD |  | 140 | 4 | 12940.8
135 | j315 | j322 |  |  | 140 | 63 | 13003.8
136 | j315 | j322 |  |  | 140 | 20.1 | 13023.9
137 | j265 | j264 |  |  | 140 | 216 | 13239.9
138 | j264 | j252 |  |  | 140 | 79 | 13318.9
139 | j264 | j252 | B.T ROAD |  | 140 | 10.2 | 13329.1
140 | j315 | j337 |  |  | 160 | 197.1 | 13526.2
141 | j309 | j315 |  |  | 160 | 320 | 13846.2
142 | j309 | j315 | culvert |  | 160 | 9.1 | 13855.3 |  |  |  | 316.7
143 | j309 | j315 |  |  | 160 | 400 | 14255.3
144 | j252 | j243 |  |  | 160 | 121.4 | 14376.7
145 | j243 | j231 |  |  | 160 | 144.4 | 14521.1
146 | j231 | j224 |  |  | 160 | 56.1 | 14577.2
147 | j252 | j243 |  |  | 160 | 121.4 | 14698.6
148 | j243 | j231 |  |  | 160 | 144.4 | 14843
149 | j231 | j224 |  |  | 160 | 56.1 | 14899.1
150 | j224 | j221 | B.T ROAD |  | 160 | 3.5 | 14902.6
151 | j224 | j221 |  |  | 160 | 164 | 15066.6
152 | j221 | j215 |  |  | 160 | 252 | 15318.6
153 | j309 | j273 | B.T ROAD |  | 160 | 7 | 15325.6
154 | j309 | j273 |  |  | 160 | 495.4 | 15821
155 | j273 | j243 | B.T ROAD |  | 160 | 3 | 15824
156 | j273 | j243 |  |  | 160 | 121 | 15945
157 | j273 | j243 | B.T ROAD |  | 160 | 3 | 15948
|  | 63 | 110 | 140 | 160
|  | 12635.1 | 65 | 629 | 2618.9 |  | 15948
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  | SIGN.with date
[5 empty] | 178.3 | 150
316.7

## madhura rani ganj ags2
GOVERNMENT OF UTTAR PRADESH
STATE WATER & SANITATION MISSION ( SWSM )
Joint Measurement Report of Pipe Line
Name of the Work :- Survey , Design Preparation of DPR , Construction , Commissioning and O&M for 10 Years of Various Rural Water Supply Projects in the state of Uttar Pradesh as Per Request for Proposal for Division " Prayagraj "
Name of the Agency : POWER MECH PROJECTS LIMITED – BHOORATHNOM CONSTRUCTIONS COMPANY PRIVATE LIMITED (JV), Hyderabad.
Name OF Scheme |  | : madhura rani ganj 5
Block |  | : MANGRAURA
Total Scope |  | :
JMR No. |  | : 2
Date of JMR |  | :
Sr. No. | Start Node | End Node | Dia | Pipe Length (as per Site) | Excavation Width | Depth | Quantity | Type OF Road | Dismantling Length | Dismantling Width | Dismantling Quantity | Restoration Length | Restoration Width | Restoration Quantity | Restoration Status | Remark
1 | j240 | j233 | 63 | 433.2
2 | j78 | j78(1) | 63 | 80
Representative PMPL - BRCCPL (JV) Pratapgarh | [6 empty] | Representative Medhaj Techno Concept Pvt Ltd (TPI) Pratapgarh |  |  |  |  | Representative UP Jal Nigam (Rural) Pratapgarh
[17 empty] | Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
[17 empty] | Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
[17 empty] | TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
[17 empty] | Contractor:- |  | Power Mech Project Ltd.
[17 empty] | Block :- |  | Mangraura
[17 empty] | GP :- |  | madhura rani ganj | [5 empty] | Date
[17 empty] | Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
[17 empty] | 1 | j240 | j233 | 63 | 433.2 | 6 | 3 | 1 | 4 | no
[17 empty] | POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
[17 empty] | DESIGNATION |  |  |  | DESIGNATION |  |  | DESIGNATION
[17 empty] | NAME |  |  |  | NAME |  |  | NAME
[17 empty] | SIGN.with date |  |  |  | SIGN.with date |  |  | SIGN.with date