## aurangabad HT
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | AURANGABAD | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | 137 | 138 | 63 | 92.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
2 | 137 | 128 | 75 | 142.8 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
3 | 137 | 128 | 75 | 11.7 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
4 | 128 | 135 | 63 | 121.9 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
5 | 128 | 135 | 63 | 37 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
6 | 135a | 135b | 63 | 55.4 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
7 | 135a | 135b | 63 | 6 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
8 | 136 | 135 | 63 | 134 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
9 | 135 | 130 | 63 | 40.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
10 | 130 | 132 | 63 | 84.5 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
11 | 130a | 130b | 63 | 61.4 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
12 | 130 | 126 | 63 | 50.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
13 | 130 | 126 | 63 | 28.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
14 | 130 | 126 | 63 | 148.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
15 | 128 | 126 | 75 | 20 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
16 | 128 | 126 | 75 | 19.7 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
17 | 128 | 126 | 75 | 88.4 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
18 | 126 | 56 | 75 | 2.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
19 | 126 | 56 | 75 | 128.5 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
20 | 126 | 56 | 75 | 7 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
21 | 56 | 38 | 160 | 298.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
22 | 56 | 122 | 160 | 91.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
23 | 56 | 122 | 160 | 56.9 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
24 | 56 | 122 | 160 | 76.4 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
25 | 56 | 122 | 160 | 4.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
26 | 122 | 124 | 160 | 6 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
27 | 122 | 124 | 160 | 170 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
28 | 124 | 125 | 63 | 92.6 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
29 | 124 | 124a | 160 | 14.9 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
30 | 124a | 143 | 160 | 174.3 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
31 | 124a | 124b | 63 | 39.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
32 | 143 | 142 | 63 | 200.5 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
33 | 143 | 145 | 160 | 113 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
34 | 143 | 145 | 160 | 5.9 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
35 | 146 | 145 | 160 | 7.6 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
36 | 145 | 144 | 75 | 230.6 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
37 | 145 | 144 | 75 | 9.8 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
38 | 144 | 149 | 140 | 298.6 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | no
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | AURANGABAD | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | 144 | 149 | 140 | 63.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
2 | 149 | 154 | 140 | 6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
3 | 149 | 154 | 140 | 152.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
4 | 149 | 154 | 140 | 14.7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
5 | 154 | 164 | 110 | 91.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
6 | 154 | 164 | 110 | 140 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
7 | 164 | 166 | 160 | 68.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
8 | 164 | 166 | 160 | 31 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
9 | 166 | 166a | 75 | 20 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
10 | 166a | 170 | 75 | 276 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
11 | 170 | 172 | 75 | 92.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
12 | 172 | 166 | 160 | 128.7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
13 | 166a | 167 | 75 | 29.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
14 | 164 | 160 | 160 | 100.9 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
15 | 154 | 160 | 63 | 110.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
16 | 154 | 160 | 63 | 92.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
17 | 154 | 153 | 140 | 51 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
18 | 153 | 158 | 160 | 292.9 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
19 | 153 | 146 | 160 | 214.9 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
20 | 144 | 122 | 140 | 47 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
21 | 144 | 122 | 140 | 6.8 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
22 | 144 | 122 | 140 | 192 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
23 | 144 | 122 | 140 | 8 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
24 | 144 | 122 | 140 | 80.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
25 | 224 | 228 | 90 | 53.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
26 | 228 | 231 | 90 | 10.8 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
27 | 228 | 225 | 63 | 3.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
28 | 228 | 225 | 63 | 89.4 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
29 | 231 | 232 | 63 | 59.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
30 | 231 | 233 | 63 | 162.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
31 | 225 | 228 | 90 | 5.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
32 | 224 | 227 | 90 | 51.7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
33 | 227 | 227a | 63 | 22.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
34 | 227 | 230 | 90 | 103.4 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
35 | 230 | 230a | 90 | 45.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
36 | 230 | 226 | 90 | 62.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
37 | 226 | 229 | 63 | 175.9 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | AURANGABAD | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | 230 | 236 | 90 | 177.4 | 5.5 | 3.3 | 1 | 4.3 | no
2 | 236 | 239 | 63 | 204.7 | 5.5 | 3.3 | 1 | 4.3 | no
3 | 236 | 223a | 90 | 225.4 | 5.5 | 3.3 | 1 | 4.3 | no
4 | 223a | 223b | 90 | 68.7 | 5.5 | 3.3 | 1 | 4.3 | no
5 | 223a | 223 | 90 | 172.4 | 5.5 | 3.3 | 1 | 4.3 | no
6 | 223 | 234a | 90 | 182.9 | 5.5 | 3.3 | 1 | 4.3 | no
7 | 234a | 234b | 75 | 205.8 | 5.5 | 3.3 | 1 | 4.3 | no
8 | 234 | 234c | 75 | 27.3 | 5.5 | 3.3 | 1 | 4.3 | no
9 | 234 | 234d | 75 | 70.1 | 5.5 | 3.3 | 1 | 4.3 | no
10 | 237 | 234 | 63 | 45.5 | 5.5 | 3.3 | 1 | 4.3 | no
11 | 234 | 234a | 75 | 55.3 | 5.5 | 3.3 | 1 | 4.3 | no
12 | 223 | 193 | 90 | 447.9 | 5.5 | 3.3 | 1 | 4.3 | no
13 | 223 | 193 | 90 | 7 | 5.5 | 3.3 | 1 | 4.3 | no
14 | 193 | 195 | 140 | 7.4 | 5.5 | 3.3 | 1 | 4.3 | no
15 | 193 | 195 | 140 | 88.9 | 5.5 | 3.3 | 1 | 4.3 | no
16 | 195 | 196 | 140 | 29.1 | 5.5 | 3.3 | 1 | 4.3 | no
17 | 196 | 197 | 63 | 54.4 | 5.5 | 3.3 | 1 | 4.3 | no
18 | 192 | 195 | 140 | 98.4 | 5.5 | 3.3 | 1 | 4.3 | no
19 | 192 | 193 | 90 | 65.6 | 5.5 | 3.3 | 1 | 4.3 | no
20 | 192 | 192a | 140 | 45.8 | 5.5 | 3.3 | 1 | 4.3 | no
21 | 192a | 192b | 63 | 24.3 | 5.5 | 3.3 | 1 | 4.3 | no
22 | 192a | 181 | 140 | 172.5 | 5.5 | 3.3 | 1 | 4.3 | no
23 | 181 | 187 | 140 | 44.7 | 5.5 | 3.3 | 1 | 4.3 | no
24 | 187 | 193 | 140 | 171.1 | 5.5 | 3.3 | 1 | 4.3 | no
25 | 187 | 193 | 140 | 5 | 5.5 | 3.3 | 1 | 4.3 | no
26 | 181 | 179 | 160 | 29.7 | 5.5 | 3.3 | 1 | 4.3 | no
27 | 181 | 179 | 160 | 55.3 | 5.5 | 3.3 | 1 | 4.3 | no
28 | 179 | 180 | 75 | 160.3 | 5.5 | 3.3 | 1 | 4.3 | no
29 | 179 | 178 | 160 | 151.5 | 5.5 | 3.3 | 1 | 4.3 | no
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | AURANGABAD | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | 178 | 206 | 160 | 373.2 | 6KG/CM2 | 4 | 1 | 5 | NO
2 | 206 | 213 | 160 | 184.5 | 6KG/CM2 | 4 | 1 | 5 | NO
3 | 213 | 214 | 90 | 52.2 | 6KG/CM2 | 4 | 1 | 5 | NO
4 | 214 | 215 | 63 | 114.5 | 6KG/CM2 | 4 | 1 | 5 | NO
5 | 214 | 215 | 63 | 61.2 | 6KG/CM2 | 4 | 1 | 5 | NO
6 | 213 | 218 | 140 | 31 | 6KG/CM2 | 4 | 1 | 5 | NO
7 | 213 | 218 | 140 | 139.3 | 6KG/CM2 | 4 | 1 | 5 | NO
8 | 224 | 218 | 110 | 206.1 | 6KG/CM2 | 4 | 1 | 5 | NO
9 | 172 | 178 | 160 | 423.2 | 6KG/CM2 | 4 | 1 | 5 | NO
10 | 217 | 223 | 90 | 366.3 | 6KG/CM2 | 4 | 1 | 5 | NO
11 | 196 | 198 | 140 | 252.2 | 6KG/CM2 | 4 | 1 | 5 | NO
12 | 198 | 199 | 140 | 141.5 | 6KG/CM2 | 4 | 1 | 5 | NO
13 | 199 | 207 | 75 | 29 | 6KG/CM2 | 4 | 1 | 5 | NO
14 | 199 | 207 | 75 | 5 | 6KG/CM2 | 4 | 1 | 5 | NO
15 | 199 | 207 | 75 | 95 | 6KG/CM2 | 4 | 1 | 5 | NO
16 | 199 | 207 | 75 | 41 | 6KG/CM2 | 4 | 1 | 5 | NO
17 | 199 | 207 | 75 | 29 | 6KG/CM2 | 4 | 1 | 5 | NO
18 | 210 | 204 | 75 | 56 | 6KG/CM2 | 4 | 1 | 5 | NO
19 | 19 | 11 | 63 | 61.7 | 6KG/CM2 | 4 | 1 | 5 | NO
20 | 11 | 12 | 63 | 95.3 | 6KG/CM2 | 4 | 1 | 5 | NO
21 | 11 | 14 | 63 | 93.2 | 6KG/CM2 | 4 | 1 | 5 | NO
22 | 5 | 6 | 63 | 183.4 | 6KG/CM2 | 4 | 1 | 5 | NO
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | AURANGABAD | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | 9 | 17 | 200 | 228.3 | 5 | 3.3 | 1 | 4.3 | NO
2 | 17 | 23 | 63 | 101.2 | 5 | 3.3 | 1 | 4.3 | NO
3 | 23 | 22 | 200 | 40.2 | 5 | 3.3 | 1 | 4.3 | NO
4 | 22 | 20 | 200 | 35.4 | 5 | 3.3 | 1 | 4.3 | NO
5 | 20 | 21 | 63 | 50.5 | 5 | 3.3 | 1 | 4.3 | NO
6 | 20 | 17 | 200 | 42.4 | 5 | 3.3 | 1 | 4.3 | NO
7 | 22 | 38 | 160 | 177.2 | 5 | 3.3 | 1 | 4.3 | NO
8 | 22 | 38 | 160 | 5 | 5 | 3.3 | 1 | 4.3 | NO
9 | 1 | 3 | 63 | 67.2 | 5 | 3.3 | 1 | 4.3 | NO
10 | 1 | 3 | 63 | 82.2 | 5 | 3.3 | 1 | 4.3 | NO
11 | 23 | 27 | 200 | 158.8 | 5 | 3.3 | 1 | 4.3 | NO
12 | 27 | 30 | 63 | 5 | 5 | 3.3 | 1 | 4.3 | NO
13 | 27 | 30 | 63 | 273.3 | 5 | 3.3 | 1 | 4.3 | NO
14 | 27 | 37 | 200 | 172.3 | 5 | 3.3 | 1 | 4.3 | NO
15 | 37 | 39 | 63 | 34.1 | 5 | 3.3 | 1 | 4.3 | NO
16 | 37 | 37a | 63 | 115.6 | 5 | 3.3 | 1 | 4.3 | NO
17 | 37a | 37b | 63 | 106.8 | 5 | 3.3 | 1 | 4.3 | NO
18 | 37 | 42 | 200 | 481.1 | 5 | 3.3 | 1 | 4.3 | NO
19 | 42 | 43 | 200 | 98 | 5 | 3.3 | 1 | 4.3 | NO
20 | 42 | 43 | 200 | 88.1 | 5 | 3.3 | 1 | 4.3 | NO
21 | 43 | 43a | 63 | 136.4 | 5 | 3.3 | 1 | 4.3 | NO
22 | 43 | 41 | 200 | 303.2 | 5 | 3.3 | 1 | 4.3 | NO
23 | 41 | 36 | 75 | 137 | 5 | 3.3 | 1 | 4.3 | NO
24 | 36 | 34 | 63 | 67.2 | 5 | 3.3 | 1 | 4.3 | NO
25 | 36 | 28 | 63 | 207.8 | 5 | 3.3 | 1 | 4.3 | NO
26 | 41 | 122 | 140 | 472 | 5 | 3.3 | 1 | 4.3 | NO
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | AURANGABAD | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | 42 | 48 | 140 | 211.8 | 5.5 | 3.2 | 1 | 4.2 | NO
2 | 48 | 49 | 63 | 156.5 | 5.5 | 3.2 | 1 | 4.2 | NO
3 | 48 | 57 | 140 | 110.5 | 5.5 | 3.2 | 1 | 4.2 | NO
4 | 48 | 57 | 140 | 25.6 | 5.5 | 3.2 | 1 | 4.2 | NO
5 | 57 | 58 | 63 | 55.8 | 5.5 | 3.2 | 1 | 4.2 | NO
6 | 63 | 68 | 75 | 114.9 | 5.5 | 3.2 | 1 | 4.2 | NO
7 | 68 | 69 | 75 | 33.4 | 5.5 | 3.2 | 1 | 4.2 | NO
8 | 67 | 69 | 63 | 185 | 5.5 | 3.2 | 1 | 4.2 | NO
9 | 82 | 71 | 75 | 62 | 5.5 | 3.2 | 1 | 4.2 | NO
10 | 66 | 67 | 75 | 81.2 | 5.5 | 3.2 | 1 | 4.2 | NO
11 | 57 | 62 | 140 | 139.1 | 5.5 | 3.2 | 1 | 4.2 | NO
12 | 62 | 90 | 63 | 310 | 5.5 | 3.2 | 1 | 4.2 | NO
13 | 62 | 92 | 140 | 220 | 5.5 | 3.2 | 1 | 4.2 | NO
14 | 92 | 95 | 75 | 93.6 | 5.5 | 3.2 | 1 | 4.2 | NO
15 | 95 | 98 | 63 | 135.9 | 5.5 | 3.2 | 1 | 4.2 | NO
16 | 95 | 96 | 63 | 5 | 5.5 | 3.2 | 1 | 4.2 | NO
17 | 95 | 96 | 63 | 39 | 5.5 | 3.2 | 1 | 4.2 | NO
18 | 92 | 94 | 110 | 201.7 | 5.5 | 3.2 | 1 | 4.2 | NO
19 | 92 | 101 | 110 | 142.2 | 5.5 | 3.2 | 1 | 4.2 | NO
20 | 101 | 104 | 110 | 70.2 | 5.5 | 3.2 | 1 | 4.2 | NO
21 | 104 | 106 | 110 | 119.6 | 5.5 | 3.2 | 1 | 4.2 | NO
22 | 106 | 107 | 110 | 15.6 | 5.5 | 3.2 | 1 | 4.2 | NO
23 | 107 | 109 | 63 | 20.7 | 5.5 | 3.2 | 1 | 4.2 | NO
24 | 107 | 112 | 63 | 88.9 | 5.5 | 3.2 | 1 | 4.2 | NO
25 | 116 | 119 | 63 | 3 | 5.5 | 3.2 | 1 | 4.2 | NO
26 | 116 | 119 | 63 | 69 | 5.5 | 3.2 | 1 | 4.2 | NO
27 | 116 | 113 | 63 | 89 | 5.5 | 3.2 | 1 | 4.2 | NO
28 | 116 | 108 | 63 | 41.6 | 5.5 | 3.2 | 1 | 4.2 | NO
29 | 108 | 109 | 75 | 48 | 5.5 | 3.2 | 1 | 4.2 | NO
30 | 109 | 115 | 63 | 20.8 | 5.5 | 3.2 | 1 | 4.2 | NO
31 | 109 | 106 | 75 | 39.6 | 5.5 | 3.2 | 1 | 4.2 | NO
32 | 108 | 103 | 75 | 111 | 5.5 | 3.2 | 1 | 4.2 | NO
33 | 108 | 103 | 75 | 6 | 5.5 | 3.2 | 1 | 4.2 | NO
34 | 105 | 104 | 75 | 203.2 | 5.5 | 3.2 | 1 | 4.2 | NO
35 | 163 | 161 | 75 | 89.6 | 5.5 | 3.2 | 1 | 4.2 | NO
36 | 161 | 162 | 63 | 112.3 | 5.5 | 3.2 | 1 | 4.2 | NO
37 | 173 | 174 | 63 | 107.5 | 5.5 | 3.2 | 1 | 4.2 | NO
38 | 59 | 61 | 140 | 75.1 | 5.5 | 3.2 | 1 | 4.2 | NO
39 | 85 | 86 | 63 | 41.1 | 5.5 | 3.2 | 1 | 4.2 | NO
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date