## HASTHARA HYDRO
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | Hathsara | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | J1 | OHT | 125 | 6 | 6 | 3 | 1 | 4 | no
2 | J1 | J2 | 125 | 114 | 6 | 3 | 1 | 4 | no
3 | J39 | J42 | 110 | 29.8 | 6 | 3 | 1 | 4 | no
4 | J42 | J59 | 110 | 48.5 | 6 | 3 | 1 | 4 | no
5 | J125(1) | J125 | 110 | 69.3 | 6 | 3 | 1 | 4 | no
6 | J125(1) | J125 | 110 | 6.7 | 6 | 3 | 1 | 4 | no
7 | j59 | j105 | 110 | 48.6 | 6 | 3 | 1 | 4 | no
8 | j105 | j108 | 110 | 64.6 | 6 | 3 | 1 | 4 | no
9 | j108 | j124 | 110 | 125.4 | 6 | 3 | 1 | 4 | no
10 | j125 | j160 | 63 | 1.8 | 6 | 3 | 1 | 4 | no
11 | j125 | j160 | 63 | 80 | 6 | 3 | 1 | 4 | no
12 | j125 | j160 | 63 | 4.3 | 6 | 3 | 1 | 4 | no
13 | j125 | j160 | 63 | 53.2 | 6 | 3 | 1 | 4 | no
14 | j170 | j171 | 63 | 94.8 | 6 | 3 | 1 | 4 | no
15 | j171 | j174 | 63 | 77.1 | 6 | 3 | 1 | 4 | no
16 | j174 | j177 | 63 | 81 | 6 | 3 | 1 | 4 | no
17 | j177 | j181 | 63 | 122.5 | 6 | 3 | 1 | 4 | no
18 | j181 | j184 | 63 | 219.4 | 6 | 3 | 1 | 4 | no
19 | j184 | j185 | 63 | 41.6 | 6 | 3 | 1 | 4 | no
20 | j185 | j183 | 63 | 19.4 | 6 | 3 | 1 | 4 | no
21 | j174 | j168(1) | 63 | 128.3 | 6 | 3 | 1 | 4 | no
22 | j168(1) | j168(2) | 63 | 69.6 | 6 | 3 | 1 | 4 | no
23 | j168(1) | j168 | 63 | 115 | 6 | 3 | 1 | 4 | no
24 | j168 | j169 | 63 | 76.5 | 6 | 3 | 1 | 4 | no
25 | j169 | j166 | 63 | 1.8 | 6 | 3 | 1 | 4 | no
26 | j169 | j166 | 63 | 830.5 | 6 | 3 | 1 | 4 | no
27 | J166 | J165 | 63 | 2 | 6 | 3 | 1 | 4 | no
28 | J166 | J136 | 63 | 192 | 6 | 3 | 1 | 4 | no
29 | J136(1) | J136 | 63 | 8.6 | 6 | 3 | 1 | 4 | no
30 | J136(1) | J137 | 63 | 38.9 | 6 | 3 | 1 | 4 | no
31 | J137 | J143 | 63 | 44.1 | 6 | 3 | 1 | 4 | no
32 | J137 | J134 | 63 | 43 | 6 | 3 | 1 | 4 | no
33 | J136(1) | J134 | 63 | 82 | 6 | 3 | 1 | 4 | no
34 | J134 | J131 | 63 | 38.4 | 6 | 3 | 1 | 4 | no
35 | J131 | J129 | 63 | 28 | 6 | 3 | 1 | 4 | no
36 | J131 | J130 | 63 | 71.2 | 6 | 3 | 1 | 4 | no
37 | J130 | J129 | 63 | 37 | 6 | 3 | 1 | 4 | no
38 | J132 | J115 | 63 | 154 | 6 | 3 | 1 | 4 | no
39 | J130 | J132 | 63 | 48.2 | 6 | 3 | 1 | 4 | no
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | Hathsara | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | J2 | J5 | 110 | 273.2 | 5.5 | 3.3 | 1 | 4.3 | no
2 | J5 | J25 | 110 | 6.6 | 5.5 | 3.3 | 1 | 4.3 | no
3 | J5 | J25 | 110 | 76 | 5.5 | 3.3 | 1 | 4.3 | no
4 | J5 | J25 | 110 | 55.8 | 5.5 | 3.3 | 1 | 4.3 | no
5 | J25 | J34 | 110 | 57.8 | 5.5 | 3.3 | 1 | 4.3 | no
6 | J34 | J37 | 110 | 41.2 | 5.5 | 3.3 | 1 | 4.3 | no
7 | J37 | J38 | 110 | 39.3 | 5.5 | 3.3 | 1 | 4.3 | no
8 | J38 | J39 | 110 | 49.9 | 5.5 | 3.3 | 1 | 4.3 | no
9 | J115 | J103 | 63 | 2 | 5.5 | 3.3 | 1 | 4.3 | no
10 | J115 | J109 | 63 | 96.1 | 5.5 | 3.3 | 1 | 4.3 | no
11 | J115 | J101 | 63 | 40 | 5.5 | 3.3 | 1 | 4.3 | no
12 | J109 | J110 | 63 | 7.7 | 5.5 | 3.3 | 1 | 4.3 | no
13 | J109 | J110 | 63 | 21.7 | 5.5 | 3.3 | 1 | 4.3 | no
14 | J109 | J110 | 63 | 31.1 | 5.5 | 3.3 | 1 | 4.3 | no
15 | J109 | J110 | 63 | 23 | 5.5 | 3.3 | 1 | 4.3 | no
16 | J110 | J149 | 63 | 6.5 | 5.5 | 3.3 | 1 | 4.3 | no
17 | J110 | J149 | 63 | 455.1 | 5.5 | 3.3 | 1 | 4.3 | no
18 | J149 | J155 | 63 | 143.7 | 5.5 | 3.3 | 1 | 4.3 | no
19 | J155 | J154 | 63 | 30.5 | 5.5 | 3.3 | 1 | 4.3 | no
20 | J155 | J156 | 63 | 39.5 | 5.5 | 3.3 | 1 | 4.3 | no
21 | J156 | J153 | 63 | 12 | 5.5 | 3.3 | 1 | 4.3 | no
22 | J156 | J161 | 63 | 136 | 5.5 | 3.3 | 1 | 4.3 | no
23 | J161 | 162 | 63 | 14 | 5.5 | 3.3 | 1 | 4.3 | no
24 | J162 | J146 | 63 | 275.5 | 5.5 | 3.3 | 1 | 4.3 | no
25 | J162 | J164 | 63 | 232.7 | 5.5 | 3.3 | 1 | 4.3 | no
26 | J161 | J149 | 63 | 226.3 | 5.5 | 3.3 | 1 | 4.3 | no
27 | J180 | J102 | 63 | 167.6 | 5.5 | 3.3 | 1 | 4.3 | no
28 | J102 | J99 | 63 | 50.3 | 5.5 | 3.3 | 1 | 4.3 | no
29 | J102 | J76 | 63 | 223.1 | 5.5 | 3.3 | 1 | 4.3 | no
30 | J3 | J11 | 63 | 2 | 5.5 | 3.3 | 1 | 4.3 | no
31 | J34 | J36 | 63 | 2.4 | 5.5 | 3.3 | 1 | 4.3 | no
32 | J34 | J36 | 63 | 15.5 | 5.5 | 3.3 | 1 | 4.3 | no
33 | J37 | J23 | 63 | 51 | 5.5 | 3.3 | 1 | 4.3 | no
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | Hathsara | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | J3 | J1 | 110 | 155 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
2 | J4 | J3 | 90 | 116.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
3 | J163 | J176 | 90 | 188.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
4 | J163 | J125(1) | 90 | 180.4 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
5 | J37 | J23 | 63 | 11.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
6 | J37 | J23 | 63 | 3.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
7 | J23 | J24 | 63 | 55.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
8 | J23 | J12 | 63 | 60 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
9 | J12(1) | J12(2) | 63 | 3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
10 | J12(1) | J12(2) | 63 | 27.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
11 | J5 | J28 | 63 | 327.7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
12 | J28(1) | J28(2) | 63 | 71.7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
13 | J28(2) | J28 | 63 | 47.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
14 | J28 | J21 | 63 | 4 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
15 | J28 | J21 | 63 | 251 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
16 | J21 | J19 | 63 | 40.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
17 | J19 | J22 | 63 | 18.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
18 | J19 | J17 | 63 | 52.9 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
19 | J17 | J18 | 63 | 57.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
20 | J17 | J11 | 63 | 101.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
21 | J11 | J13 | 63 | 53.8 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
22 | J11 | J36 | 63 | 101.8 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
23 | J4 | J16 | 63 | 101.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
24 | J4 | J16 | 63 | 138.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
25 | J16 | J13 | 63 | 62 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
26 | J16 | J30 | 63 | 87.4 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
27 | J30 | J22 | 63 | 84.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
28 | J30 | J22 | 63 | 8 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
29 | J30 | J103 | 63 | 95.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
30 | J103 | J136 | 63 | 3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
31 | J103 | J136 | 63 | 303 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
32 | J103 | J115 | 63 | 128 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
33 | J103 | J115 | 63 | 138.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
34 | J103 | J100 | 63 | 363 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
35 | J103 | J100 | 63 | 409 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | Hathsara | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | J76 | J4 | 75 | 480 | 6 | 3 | 1 | 4 | no
2 | J76 | J74 | 75 | 6 | 6 | 3 | 1 | 4 | no
3 | J25 | J29 | 75 | 4 | 6 | 3 | 1 | 4 | no
4 | J25 | J29 | 75 | 16 | 6 | 3 | 1 | 4 | no
5 | J25 | J29 | 75 | 3 | 6 | 3 | 1 | 4 | no
6 | J187 | J189 | 75 | 92.9 | 6 | 3 | 1 | 4 | no
7 | J187 | J176 | 75 | 3 | 6 | 3 | 1 | 4 | no
8 | J187 | J176 | 75 | 676.3 | 6 | 3 | 1 | 4 | no
9 | J100 | J168 | 63 | 3 | 6 | 3 | 1 | 4 | no
10 | J100 | J168 | 63 | 122.5 | 6 | 3 | 1 | 4 | no
11 | J100 | J168 | 63 | 60 | 6 | 3 | 1 | 4 | no
12 | J100 | J168 | 63 | 127.2 | 6 | 3 | 1 | 4 | no
13 | J100 | J38 | 63 | 161.6 | 6 | 3 | 1 | 4 | no
14 | J29 | J31 | 63 | 27.8 | 6 | 3 | 1 | 4 | no
15 | J29 | J31 | 63 | 25.7 | 6 | 3 | 1 | 4 | no
16 | J29 | J31 | 63 | 15 | 6 | 3 | 1 | 4 | no
17 | J29 | J31 | 63 | 15.5 | 6 | 3 | 1 | 4 | no
18 | J31(1) | J31(2) | 63 | 2.3 | 6 | 3 | 1 | 4 | no
19 | J31(1) | J31(2) | 63 | 32.5 | 6 | 3 | 1 | 4 | no
20 | J31 | J32 | 63 | 31 | 6 | 3 | 1 | 4 | no
21 | J31 | J33 | 63 | 19.5 | 6 | 3 | 1 | 4 | no
22 | J33(1) | J33(2) | 63 | 41 | 6 | 3 | 1 | 4 | no
23 | J33(2) | J33 | 63 | 186.9 | 6 | 3 | 1 | 4 | no
24 | J189 | J90 | 63 | 23.5 | 6 | 3 | 1 | 4 | no
25 | J189 | J191 | 63 | 249.5 | 6 | 3 | 1 | 4 | no
26 | J191 | J201 | 63 | 37.5 | 6 | 3 | 1 | 4 | no
27 | J191 | J192 | 63 | 155 | 6 | 3 | 1 | 4 | no
28 | J192(1) | J202 | 63 | 83.8 | 6 | 3 | 1 | 4 | no
29 | J192(1) | J202 | 63 | 3 | 6 | 3 | 1 | 4 | no
30 | J202 | J206 | 63 | 92 | 6 | 3 | 1 | 4 | no
31 | J202 | J217 | 63 | 135.3 | 6 | 3 | 1 | 4 | no
32 | J217 | J218 | 63 | 25 | 6 | 3 | 1 | 4 | no
33 | J217 | J215 | 63 | 141.2 | 6 | 3 | 1 | 4 | no
34 | J215 | J215(1) | 63 | 42.5 | 6 | 3 | 1 | 4 | no
35 | J215 | J213 | 63 | 16 | 6 | 3 | 1 | 4 | no
36 | J187 | J188 | 63 | 165.5 | 6 | 3 | 1 | 4 | no
37 | J163 | J141 | 63 | 3.3 | 6 | 3 | 1 | 4 | no
38 | J163 | J141 | 63 | 275 | 6 | 3 | 1 | 4 | no
39 | J141(1) | J141 | 63 | 27 | 6 | 3 | 1 | 4 | no
40 | J76 | J242 | 63 | 313.5 | 6 | 3 | 1 | 4 | no
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | Hathsara | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | J242 | J227 | 63 | 683.7 | 5.5 | 3.3 | 1 | 4.3 | no
2 | J242 | J227 | 63 | 6 | 5.5 | 3.3 | 1 | 4.3 | no
3 | J242 | J242(1) | 63 | 153 | 5.5 | 3.3 | 1 | 4.3 | no
4 | J76 | J242 | 63 | 116 | 5.5 | 3.3 | 1 | 4.3 | no
5 | J242(2) | J242(3) | 63 | 38.5 | 5.5 | 3.3 | 1 | 4.3 | no
6 | J242(3) | J242(4) | 63 | 20.5 | 5.5 | 3.3 | 1 | 4.3 | no
7 | J242(5) | J242(6) | 63 | 37.8 | 5.5 | 3.3 | 1 | 4.3 | no
8 | J76 | J242 | 63 | 6 | 5.5 | 3.3 | 1 | 4.3 | no
9 | J242 | J240 | 63 | 30.8 | 5.5 | 3.3 | 1 | 4.3 | no
10 | J240 | J241 | 63 | 89.6 | 5.5 | 3.3 | 1 | 4.3 | no
11 | J240 | J239 | 63 | 62 | 5.5 | 3.3 | 1 | 4.3 | no
12 | J242 | J245 | 63 | 47.5 | 5.5 | 3.3 | 1 | 4.3 | no
13 | J245 | J249 | 63 | 241.1 | 5.5 | 3.3 | 1 | 4.3 | no
14 | J249 | J250 | 63 | 3 | 5.5 | 3.3 | 1 | 4.3 | no
15 | J249(1) | J250(1) | 63 | 10.7 | 5.5 | 3.3 | 1 | 4.3 | no
16 | J250(1) | J250(2) | 63 | 30 | 5.5 | 3.3 | 1 | 4.3 | no
17 | J250(1) | J251 | 63 | 127.5 | 5.5 | 3.3 | 1 | 4.3 | no
18 | j39 | j36 | 63 | 34.8 | 5.5 | 3.3 | 1 | 4.3 | no
19 | j42 | j44 | 63 | 29.9 | 5.5 | 3.3 | 1 | 4.3 | no
20 | j44 | j53 | 63 | 37.1 | 5.5 | 3.3 | 1 | 4.3 | no
21 | j44 | j43 | 63 | 37.8 | 5.5 | 3.3 | 1 | 4.3 | no
22 | j48 | j70 | 63 | 41.2 | 5.5 | 3.3 | 1 | 4.3 | no
23 | j48 | j70 | 63 | 31.6 | 5.5 | 3.3 | 1 | 4.3 | no
24 | j48 | j70 | 63 | 88.9 | 5.5 | 3.3 | 1 | 4.3 | no
25 | j46 | j45 | 63 | 65.1 | 5.5 | 3.3 | 1 | 4.3 | no
26 | j49 | j46 | 63 | 47.8 | 5.5 | 3.3 | 1 | 4.3 | no
27 | j43 | j46 | 63 | 43.3 | 5.5 | 3.3 | 1 | 4.3 | no
28 | j43 | j46 | 63 | 2.6 | 5.5 | 3.3 | 1 | 4.3 | no
29 | j43 | j41 | 63 | 45.9 | 5.5 | 3.3 | 1 | 4.3 | no
30 | j45 | j40 | 63 | 3.1 | 5.5 | 3.3 | 1 | 4.3 | no
31 | j45 | j40 | 63 | 10.7 | 5.5 | 3.3 | 1 | 4.3 | no
32 | j42 | j29 | 63 | 77.6 | 5.5 | 3.3 | 1 | 4.3 | no
33 | j42 | j29 | 63 | 44.2 | 5.5 | 3.3 | 1 | 4.3 | no
34 | j42 | j48 | 63 | 31.3 | 5.5 | 3.3 | 1 | 4.3 | no
35 | j48 | j47 | 63 | 34.9 | 5.5 | 3.3 | 1 | 4.3 | no
36 | j40 | j29 | 63 | 81.2 | 5.5 | 3.3 | 1 | 4.3 | no
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | Hathsara | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | 97 | 95 | 63 | 3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
2 | 97 | 96 | 63 | 23 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
3 | 98 | 97 | 63 | 38.9 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
4 | 108 | 98 | 110 | 76 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
5 | 181a | 181b | 63 | 150 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
6 | 125 | 120 | 110 | 6.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
7 | 108 | 125 | 110 | 130.9 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
8 | 108 | 118 | 63 | 35 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
9 | 108 | 118 | 63 | 150.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
10 | 108 | 118 | 63 | 3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
11 | 108 | 118 | 63 | 80 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
12 | 108a | 108b | 63 | 65 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
13 | 40 | 29 | 63 | 20.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
14 | 41 | 40 | 63 | 15 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
15 | 189 | 187 | 75 | 79 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
16 | 178 | 176 | 90 | 30 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
17 | 255 | 256 | 63 | 80 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
18 | 255 | 257 | 63 | 50 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
19 | 253 | 255 | 63 | 123.9 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
20 | 253a | 253b | 63 | 30.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
21 | 253 | 254 | 63 | 101.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
22 | 231a | 231b | 63 | 10.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
23 | 231 | 253 | 63 | 598.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
24 | 33a | 33b | 63 | 350.9 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
25 | 88a | 88b | 63 | 16.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | Hathsara | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | 77a | 77b | 63 | 25.6 | 5.5 | 3.3 | 1 | 4.3 | no
2 | 77 | 88 | 63 | 175.4 | 5.5 | 3.3 | 1 | 4.3 | no
3 | 77 | 80 | 63 | 125.6 | 5.5 | 3.3 | 1 | 4.3 | no
4 | 77 | 75 | 63 | 6.3 | 5.5 | 3.3 | 1 | 4.3 | no
5 | 75 | 74 | 63 | 56.1 | 5.5 | 3.3 | 1 | 4.3 | no
6 | 70 | 75 | 63 | 70 | 5.5 | 3.3 | 1 | 4.3 | no
7 | 70 | 55 | 63 | 3 | 5.5 | 3.3 | 1 | 4.3 | no
8 | 61a | 61b | 63 | 16.9 | 5.5 | 3.3 | 1 | 4.3 | no
9 | 61 | 70 | 63 | 91 | 5.5 | 3.3 | 1 | 4.3 | no
10 | 61 | 62 | 63 | 35.1 | 5.5 | 3.3 | 1 | 4.3 | no
11 | 61 | 62 | 63 | 3 | 5.5 | 3.3 | 1 | 4.3 | no
12 | 60 | 62 | 63 | 15 | 5.5 | 3.3 | 1 | 4.3 | no
13 | 64a | 64b | 63 | 10.9 | 5.5 | 3.3 | 1 | 4.3 | no
14 | 60a | 60b | 63 | 30.1 | 5.5 | 3.3 | 1 | 4.3 | no
15 | 15 | 93 | 63 | 250 | 5.5 | 3.3 | 1 | 4.3 | no
16 | 38a | 38b | 63 | 20 | 5.5 | 3.3 | 1 | 4.3 | no
17 | 249a | 249b | 63 | 60 | 5.5 | 3.3 | 1 | 4.3 | no
18 | 60 | 64 | 63 | 87 | 5.5 | 3.3 | 1 | 4.3 | no
19 | 57 | 60 | 63 | 34 | 5.5 | 3.3 | 1 | 4.3 | no
20 | 57 | 58 | 63 | 38 | 5.5 | 3.3 | 1 | 4.3 | no
21 | 49a | 49b | 63 | 50 | 5.5 | 3.3 | 1 | 4.3 | no
22 | 49 | 57 | 63 | 93 | 5.5 | 3.3 | 1 | 4.3 | no
23 | 59 | 49 | 63 | 89.9 | 5.5 | 3.3 | 1 | 4.3 | no
24 | 98 | 59 | 110 | 55 | 5.5 | 3.3 | 1 | 4.3 | no
25 | 98a | 98b | 63 | 25 | 5.5 | 3.3 | 1 | 4.3 | no
26 | 97 | 95 | 63 | 73 | 5.5 | 3.3 | 1 | 4.3 | no
27 | 97a | 97b | 63 | 80.1 | 5.5 | 3.3 | 1 | 4.3 | no
28 | 5 | 7 | 63 | 154 | 5.5 | 3.3 | 1 | 4.3 | no
29 | 5 | 8 | 110 | 30 | 5.5 | 3.3 | 1 | 4.3 | no
30 | 5a | 5b | 63 | 69 | 5.5 | 3.3 | 1 | 4.3 | no
31 | 43a | 43b | 63 | 85.3 | 5.5 | 3.3 | 1 | 4.3 | no
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date