## hasthara
HATHSARA (JMR) BLOCK-MANGRAURA
s.no | Start Node | End Node | Type of Road | WIDTH OF EXCAVATION | Dia of pipe(MM) | Pipe Length (M) | CUMMULATIVE | Depth(M) | REMARK
1 | j125 | j160 | interlocking | 0.363 | 63 | 1.8 | 1.8 | 1.063
2 | j125 | j160 |  |  | 63 | 80 | 81.8 | 1.063
3 | j125 | j160 | interlocking | 0.363 | 63 | 4.3 | 86.1 | 1.063
4 | j125 | j160 |  |  | 63 | 53.2 | 139.3 | 1.063
5 | j170 | j171 |  |  | 63 | 94.8 | 234.1 | 1.063
6 | j171 | j174 |  |  | 63 | 77.1 | 311.2 | 1.063
7 | j174 | j177 |  |  | 63 | 81 | 392.2 | 1.063
8 | j177 | j181 |  |  | 63 | 122.5 | 514.7 | 1.063
9 | j181 | j184 |  |  | 63 | 219.4 | 734.1 | 1.063
10 | j184 | j185 |  |  | 63 | 41.6 | 775.7 | 1.063
11 | j185 | j183 |  |  | 63 | 19.4 | 795.1 | 1.063
12 | j174 | j168(1) |  |  | 63 | 128.3 | 923.4 | 1.063
13 | j168(1) | j168(2) |  |  | 63 | 69.6 | 993 | 1.063
14 | j168(1) | j168 |  |  | 63 | 115 | 1108 | 1.063
15 | j168 | j169 |  |  | 63 | 76.5 | 1184.5 | 1.063
16 | j169 | j166 | BRICK ROAD | 0.363 | 63 | 1.8 | 1186.3 | 1.063
17 | j169 | j166 |  |  | 63 | 830.5 | 2016.8 | 1.063
18 | J166 | J165 |  |  | 63 | 2 | 2018.8 | 1.063
19 | J166 | J136 |  |  | 63 | 192 | 2210.8 | 1.063
20 | J136(1) | J136 |  |  | 63 | 8.6 | 2219.4 | 1.063
21 | J136(1) | J137 |  |  | 63 | 38.9 | 2258.3 | 1.063
22 | J137 | J143 |  |  | 63 | 44.1 | 2302.4 | 1.063
23 | J137 | J134 |  |  | 63 | 43 | 2345.4 | 1.063
24 | J136(1) | J134 |  |  | 63 | 82 | 2427.4 | 1.063
25 | J134 | J131 |  |  | 63 | 38.4 | 2465.8 | 1.063
26 | J131 | J129 |  |  | 63 | 28 | 2493.8 | 1.063
27 | J131 | J130 |  |  | 63 | 71.2 | 2565 | 1.063
28 | J130 | J129 |  |  | 63 | 37 | 2602 | 1.063
29 | J132 | J115 |  |  | 63 | 154 | 2756 | 1.063
30 | J130 | J132 |  |  | 63 | 48.2 | 2804.2 | 1.063
31 | J115 | J103 | BRICK ROAD | 0.363 | 63 | 2 | 2806.2 | 1.063
32 | J115 | J109 |  |  | 63 | 96.1 | 2902.3 | 1.063
33 | J115 | J101 |  |  | 63 | 40 | 2942.3 | 1.063
34 | J109 | J110 | BRICK ROAD | 0.363 | 63 | 7.7 | 2950 | 1.063
35 | J109 | J110 | BRICK ROAD | 0.363 | 63 | 21.7 | 2971.7 | 1.063
36 | J109 | J110 | BRICK ROAD | 0.363 | 63 | 31.1 | 3002.8 | 1.063
37 | J109 | J110 | BRICK ROAD | 0.363 | 63 | 23 | 3025.8 | 1.063
38 | J110 | J149 | BRICK ROAD | 0.363 | 63 | 6.5 | 3032.3 | 1.063
39 | J110 | J149 |  |  | 63 | 455.1 | 3487.4 | 1.063
40 | J149 | J155 |  |  | 63 | 143.7 | 3631.1 | 1.063
41 | J155 | J154 |  |  | 63 | 30.5 | 3661.6 | 1.063
42 | J155 | J156 |  |  | 63 | 39.5 | 3701.1 | 1.063
43 | J156 | J153 |  |  | 63 | 12 | 3713.1 | 1.063
44 | J156 | J161 |  |  | 63 | 136 | 3849.1 | 1.063
45 | J161 | 162 |  |  | 63 | 14 | 3863.1 | 1.063
46 | J162 | J146 |  |  | 63 | 275.5 | 4138.6 | 1.063
47 | J162 | J164 |  |  | 63 | 232.7 | 4371.3 | 1.063
48 | J161 | J149 |  |  | 63 | 226.3 | 4597.6 | 1.063
49 | J180 | J102 |  |  | 63 | 167.6 | 4765.2 | 1.063
50 | J102 | J99 |  |  | 63 | 50.3 | 4815.5 | 1.063
51 | J102 | J76 |  |  | 63 | 223.1 | 5038.6 | 1.063
52 | J3 | J11 |  |  | 63 | 2 | 5040.6 | 1.063
53 | J34 | J36 | BRICK ROAD | 0.363 | 63 | 2.4 | 5043 | 1.063
54 | J34 | J36 |  |  | 63 | 15.5 | 5058.5 | 1.063
55 | J37 | J23 | BRICK ROAD | 0.363 | 63 | 51 | 5109.5 | 1.063
56 | J37 | J23 |  |  | 63 | 11.6 | 5121.1 | 1.063
57 | J37 | J23 | BRICK ROAD | 0.363 | 63 | 3.6 | 5124.7 | 1.063
58 | J23 | J24 |  |  | 63 | 55.1 | 5179.8 | 1.063
59 | J23 | J12 | BRICK ROAD | 0.363 | 63 | 60 | 5239.8 | 1.063
60 | J12(1) | J12(2) | BRICK ROAD | 0.363 | 63 | 3 | 5242.8 | 1.063
61 | J12(1) | J12(2) |  |  | 63 | 27.5 | 5270.3 | 1.063
62 | J5 | J28 |  |  | 63 | 327.7 | 5598 | 1.063
63 | J28(1) | J28(2) |  |  | 63 | 71.7 | 5669.7 | 1.063
64 | J28(2) | J28 |  |  | 63 | 47.6 | 5717.3 | 1.063
65 | J28 | J21 | BRICK ROAD | 0.363 | 63 | 4 | 5721.3 | 1.063
66 | J28 | J21 |  |  | 63 | 251 | 5972.3 | 1.063
67 | J21 | J19 |  |  | 63 | 40.6 | 6012.9 | 1.063
68 | J19 | J22 |  |  | 63 | 18.2 | 6031.1 | 1.063
69 | J19 | J17 |  |  | 63 | 52.9 | 6084 | 1.063
70 | J17 | J18 |  |  | 63 | 57.3 | 6141.3 | 1.063
71 | J17 | J11 |  |  | 63 | 101.1 | 6242.4 | 1.063
72 | J11 | J13 |  |  | 63 | 53.8 | 6296.2 | 1.063
73 | J11 | J36 |  |  | 63 | 101.8 | 6398 | 1.063
74 | J4 | J16 | interlocking | 0.363 | 63 | 101.3 | 6499.3 | 1.063
75 | J4 | J16 |  |  | 63 | 138.5 | 6637.8 | 1.063
76 | J16 | J13 |  |  | 63 | 62 | 6699.8 | 1.063
77 | J16 | J30 |  |  | 63 | 87.4 | 6787.2 | 1.063
78 | J30 | J22 | BRICK ROAD | 0.363 | 63 | 84.5 | 6871.7 | 1.063
79 | J30 | J22 |  |  | 63 | 8 | 6879.7 | 1.063
80 | J30 | J103 | BRICK ROAD | 0.363 | 63 | 95.5 | 6975.2 | 1.063
81 | J103 | J136 | BRICK ROAD | 0.363 | 63 | 3 | 6978.2 | 1.063
82 | J103 | J136 |  |  | 63 | 303 | 7281.2 | 1.063
83 | J103 | J115 | BRICK ROAD | 0.363 | 63 | 128 | 7409.2 | 1.063
84 | J103 | J115 |  |  | 63 | 138.5 | 7547.7 | 1.063
85 | J103 | J100 | BRICK ROAD | 0.363 | 63 | 363 | 7910.7 | 1.063
86 | J103 | J100 | BRICK ROAD | 0.363 | 63 | 409 | 8319.7 | 1.063
87 | J100 | J168 | BRICK ROAD | 0.363 | 63 | 3 | 8322.7 | 1.063
88 | J100 | J168 |  |  | 63 | 122.5 | 8445.2 | 1.063
89 | J100 | J168 | BRICK ROAD | 0.363 | 63 | 60 | 8505.2 | 1.063
90 | J100 | J168 |  |  | 63 | 127.2 | 8632.4 | 1.063
91 | J100 | J38 | BRICK ROAD | 0.363 | 63 | 161.6 | 8794 | 1.063
92 | J29 | J31 |  |  | 63 | 27.8 | 8821.8 | 1.063
93 | J29 | J31 |  |  | 63 | 25.7 | 8847.5 | 1.063
94 | J29 | J31 | BRICK ROAD | 0.363 | 63 | 15 | 8862.5 | 1.063
95 | J29 | J31 |  |  | 63 | 15.5 | 8878 | 1.063
96 | J31(1) | J31(2) | BRICK ROAD | 0.363 | 63 | 2.3 | 8880.3 | 1.063
97 | J31(1) | J31(2) |  |  | 63 | 32.5 | 8912.8 | 1.063
98 | J31 | J32 |  |  | 63 | 31 | 8943.8 | 1.063
99 | J31 | J33 |  |  | 63 | 19.5 | 8963.3 | 1.063
100 | J33(1) | J33(2) |  |  | 63 | 41 | 9004.3 | 1.063
101 | J33(2) | J33 |  |  | 63 | 186.9 | 9191.2 | 1.063
102 | J189 | J90 |  |  | 63 | 23.5 | 9214.7 | 1.063
103 | J189 | J191 |  |  | 63 | 249.5 | 9464.2 | 1.063
104 | J191 | J201 |  |  | 63 | 37.5 | 9501.7 | 1.063
105 | J191 | J192 |  |  | 63 | 155 | 9656.7 | 1.063
106 | J192(1) | J202 |  |  | 63 | 83.8 | 9740.5 | 1.063
107 | J192(1) | J202 | B.T ROAD | 0.363 | 63 | 3 | 9743.5 | 1.063
108 | J202 | J206 |  |  | 63 | 92 | 9835.5 | 1.063
109 | J202 | J217 |  |  | 63 | 135.3 | 9970.8 | 1.063
110 | J217 | J218 |  |  | 63 | 25 | 9995.8 | 1.063
111 | J217 | J215 |  |  | 63 | 141.2 | 10137 | 1.063
112 | J215 | J215(1) |  |  | 63 | 42.5 | 10179.5 | 1.063
113 | J215 | J213 |  |  | 63 | 16 | 10195.5 | 1.063
114 | J187 | J188 |  |  | 63 | 165.5 | 10361 | 1.063
115 | J163 | J141 | B.T ROAD | 0.363 | 63 | 3.3 | 10364.3 | 1.063
116 | J163 | J141 |  |  | 63 | 275 | 10639.3 | 1.063
117 | J141(1) | J141 |  |  | 63 | 27 | 10666.3 | 1.063
118 | J76 | J242 |  |  | 63 | 313.5 | 10979.8 | 1.063
119 | J242 | J227 |  |  | 63 | 683.7 | 11663.5 | 1.063
120 | J242 | J227 | B.T ROAD | 0.363 | 63 | 6 | 11669.5 | 1.063
121 | J242 | J242(1) |  |  | 63 | 153 | 11822.5 | 1.063
122 | J76 | J242 |  |  | 63 | 116 | 11938.5 | 1.063
123 | J242(2) | J242(3) |  |  | 63 | 38.5 | 11977 | 1.063
124 | J242(3) | J242(4) |  |  | 63 | 20.5 | 11997.5 | 1.063
125 | J242(5) | J242(6) |  |  | 63 | 37.8 | 12035.3 | 1.063
126 | J76 | J242 | BRICK ROAD | 0.363 | 63 | 6 | 12041.3 | 1.063
127 | J242 | J240 | BRICK ROAD | 0.363 | 63 | 30.8 | 12072.1 | 1.063
128 | J240 | J241 | BRICK ROAD | 0.363 | 63 | 89.6 | 12161.7 | 1.063
129 | J240 | J239 |  |  | 63 | 62 | 12223.7 | 1.063
130 | J242 | J245 |  |  | 63 | 47.5 | 12271.2 | 1.063
131 | J245 | J249 |  |  | 63 | 241.1 | 12512.3 | 1.063
132 | J249 | J250 | B.T ROAD | 0.363 | 63 | 3 | 12515.3 | 1.063
133 | J249(1) | J250(1) |  |  | 63 | 10.7 | 12526 | 1.063
134 | J250(1) | J250(2) |  |  | 63 | 30 | 12556 | 1.063
135 | J250(1) | J251 |  |  | 63 | 127.5 | 12683.5 | 1.063
136 | j39 | j36 |  |  | 63 | 34.8 | 12718.3 | 1.063
137 | j42 | j44 | BRICK ROAD | 0.363 | 63 | 29.9 | 12748.2 | 1.063
138 | j44 | j53 | BRICK ROAD | 0.363 | 63 | 37.1 | 12785.3 | 1.063
139 | j44 | j43 | BRICK ROAD | 0.363 | 63 | 37.8 | 12823.1 | 1.063
140 | j48 | j70 | BRICK ROAD | 0.363 | 63 | 41.2 | 12864.3 | 1.063
141 | j48 | j70 | BRICK ROAD | 0.363 | 63 | 31.6 | 12895.9 | 1.063
142 | j48 | j70 | BRICK ROAD | 0.363 | 63 | 88.9 | 12984.8 | 1.063
143 | j46 | j45 |  |  | 63 | 65.1 | 13049.9 | 1.063
144 | j49 | j46 | interlocking | 0.363 | 63 | 47.8 | 13097.7 | 1.063
145 | j43 | j46 |  |  | 63 | 43.3 | 13141 | 1.063
146 | j43 | j46 |  |  | 63 | 2.6 | 13143.6 | 1.063
147 | j43 | j41 | BRICK ROAD | 0.363 | 63 | 45.9 | 13189.5 | 1.063
148 | j45 | j40 | interlocking | 0.363 | 63 | 3.1 | 13192.6 | 1.063
149 | j45 | j40 |  |  | 63 | 10.7 | 13203.3 | 1.063
150 | j42 | j29 | interlocking | 0.363 | 63 | 77.6 | 13280.9 | 1.063
151 | j42 | j29 |  |  | 63 | 44.2 | 13325.1 | 1.063
152 | j42 | j48 | BRICK ROAD | 0.363 | 63 | 31.3 | 13356.4 | 1.063
153 | j48 | j47 |  |  | 63 | 34.9 | 13391.3 | 1.063
154 | j40 | j29 | BRICK ROAD |  | 63 | 81.2 | 13472.5 | 1.063
155 | J76 | J4 |  |  | 75 | 480 | 13952.5 | 1.075
156 | J76 | J74 | interlocking | 0.375 | 75 | 6 | 13958.5 | 1.075
157 | J25 | J29 | BRICK ROAD | 0.375 | 75 | 4 | 13962.5 | 1.075
158 | J25 | J29 |  |  | 75 | 16 | 13978.5 | 1.075 |  | 13605.1
159 | J25 | J29 | interlocking | 0.375 | 75 | 3 | 13981.5 | 1.075 |  | 141
160 | J187 | J189 |  |  | 75 | 92.9 | 14074.4 | 1.075
161 | J187 | J176 | B.T ROAD | 0.375 | 75 | 3 | 14077.4 | 1.075
162 | J187 | J176 |  |  | 75 | 676.3 | 14753.7 | 1.075 |  | 15323.5
163 | J4 | J3 |  |  | 90 | 116.6 | 14870.3 | 1.09
164 | J163 | J176 |  |  | 90 | 188.5 | 15058.8 | 1.09
165 | J163 | J125(1) |  |  | 90 | 180.4 | 15239.2 | 1.09
166 | J3 | J1 |  |  | 110 | 155 | 15394.2 | 1.11 |  | 1752.3
167 | J2 | J5 | BRICK ROAD | 0.41 | 110 | 273.2 | 15667.4 | 1.11
168 | J5 | J25 | BRICK ROAD | 0.41 | 110 | 6.6 | 15674 | 1.11
169 | J5 | J25 | BRICK ROAD | 0.41 | 110 | 76 | 15750 | 1.11
170 | J5 | J25 | BRICK ROAD | 0.41 | 110 | 55.8 | 15805.8 | 1.11
171 | J25 | J34 | BRICK ROAD | 0.41 | 110 | 57.8 | 15863.6 | 1.11
172 | J34 | J37 | BRICK ROAD | 0.41 | 110 | 41.2 | 15904.8 | 1.11
173 | J37 | J38 | BRICK ROAD | 0.41 | 110 | 39.3 | 15944.1 | 1.11
174 | J38 | J39 | BRICK ROAD | 0.41 | 110 | 49.9 | 15994 | 1.11
175 | J39 | J42 | BRICK ROAD | 0.41 | 110 | 29.8 | 16023.8 | 1.11
176 | J42 | J59 | BRICK ROAD | 0.41 | 110 | 48.5 | 16072.3 | 1.11
177 | J125(1) | J125 |  |  | 110 | 69.3 | 16141.6 | 1.11
178 | J125(1) | J125 | interlocking | 0.41 | 110 | 6.7 | 16148.3 | 1.11
179 | j59 | j105 |  |  | 110 | 48.6 | 16196.9 | 1.11
180 | j105 | j108 |  |  | 110 | 64.6 | 16261.5 | 1.11
181 | j108 | j124 |  |  | 110 | 125.4 | 16386.9 | 1.11
182 | J1 | OHT |  |  | 125 | 6 | 16392.9 | 1.125
183 | J1 | J2 |  |  | 125 | 114 | 16506.9 | 1.125
| 63 | 75 | 90 | 110 | 125
| 13472.5 | 1281.2 | 485.5 | 1147.7 | 120 |  | 16506.9
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  | SIGN.with date
20730.9

## hasthara 2
HATHSARA (JMR) BLOCK-MANGRAURA
s.no | Start Node | End Node | Type of Road | WIDTH OF EXCAVATION | Dia of pipe(MM) | Pipe Length (M) | CUMMULATIVE | Depth(M) | REMARK
1 | 97 | 95 | brick road |  | 63 | 3 | 3
2 | 97 | 96 | brick road |  | 63 | 23 | 26
3 | 98 | 97 | brick road |  | 63 | 38.9 | 64.9
4 | 108 | 98 |  |  | 110 | 76 | 140.9
5 | 181a | 181b |  |  | 63 | 150 | 290.9
6 | 125 | 120 | interlocking |  | 110 | 6.5 | 297.4
7 | 108 | 125 |  |  | 110 | 130.9 | 428.3
8 | 108 | 118 | brick road |  | 63 | 35 | 463.3
9 | 108 | 118 |  |  | 63 | 150.1 | 613.4
10 | 108 | 118 | brick road |  | 63 | 3 | 616.4
11 | 108 | 118 |  |  | 63 | 80 | 696.4
12 | 108a | 108b |  |  | 63 | 65 | 761.4
13 | 40 | 29 |  |  | 63 | 20.5 | 781.9
14 | 41 | 40 |  |  | 63 | 15 | 796.9
15 | 189 | 187 |  |  | 75 | 79 | 875.9
16 | 178 | 176 |  |  | 90 | 30 | 905.9
17 | 255 | 256 |  |  | 63 | 80 | 985.9
18 | 255 | 257 |  |  | 63 | 50 | 1035.9
19 | 253 | 255 |  |  | 63 | 123.9 | 1159.8
20 | 253a | 253b |  |  | 63 | 30.1 | 1189.9
21 | 253 | 254 |  |  | 63 | 101.2 | 1291.1
22 | 231a | 231b |  |  | 63 | 10.3 | 1301.4
23 | 231 | 253 |  |  | 63 | 598.5 | 1899.9
24 | 33a | 33b |  |  | 63 | 350.9 | 2250.8
25 | 88a | 88b |  |  | 63 | 16.1 | 2266.9
26 | 77a | 77b |  |  | 63 | 25.6 | 2292.5
27 | 77 | 88 |  |  | 63 | 175.4 | 2467.9
28 | 77 | 80 |  |  | 63 | 125.6 | 2593.5
29 | 77 | 75 | interlocking |  | 63 | 6.3 | 2599.8
30 | 75 | 74 |  |  | 63 | 56.1 | 2655.9
31 | 70 | 75 |  |  | 63 | 70 | 2725.9
32 | 70 | 55 | brick road |  | 63 | 3 | 2728.9
33 | 61a | 61b |  |  | 63 | 16.9 | 2745.8
34 | 61 | 70 |  |  | 63 | 91 | 2836.8
35 | 61 | 62 |  |  | 63 | 35.1 | 2871.9
36 | 61 | 62 | brick road |  | 63 | 3 | 2874.9
37 | 60 | 62 |  |  | 63 | 15 | 2889.9
38 | 64a | 64b |  |  | 63 | 10.9 | 2900.8
39 | 60a | 60b |  |  | 63 | 30.1 | 2930.9
40 | 15 | 93 |  |  | 63 | 250 | 3180.9
41 | 38a | 38b |  |  | 63 | 20 | 3200.9
42 | 249a | 249b |  |  | 63 | 60 | 3260.9
43 | 60 | 64 | brick road |  | 63 | 87 | 3347.9
44 | 57 | 60 |  |  | 63 | 34 | 3381.9
45 | 57 | 58 |  |  | 63 | 38 | 3419.9
46 | 49a | 49b |  |  | 63 | 50 | 3469.9
47 | 49 | 57 |  |  | 63 | 93 | 3562.9
48 | 59 | 49 |  |  | 63 | 89.9 | 3652.8
49 | 98 | 59 |  |  | 110 | 55 | 3707.8
50 | 98a | 98b |  |  | 63 | 25 | 3732.8
51 | 97 | 95 |  |  | 63 | 73 | 3805.8
52 | 97a | 97b |  |  | 63 | 80.1 | 3885.9
53 | 5 | 7 |  |  | 63 | 154 | 4039.9
54 | 5 | 8 |  |  | 110 | 30 | 4069.9
55 | 5a | 5b |  |  | 63 | 69 | 4138.9
56 | 43a | 43b |  |  | 63 | 85.3 | 4224.2
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  | SIGN.with date
|  | 63 | 75 | 110 | 90
|  | 3816.8 | 79 | 298.4 | 30 | 4224.2
16506.9
20731.1

## ROAD RESTORATION
hasthara(road restoration)
Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | Dia of pipe(MM) | Pipe Length (M) | sqmeter | REMARK
1 | j125 | j160 | interlocking | 0.46 | 63 | 1.8 | 0.828
2 | j125 | j160 | interlocking | 0.46 | 63 | 4.3 | 1.978
3 | j169 | j166 | BRICK ROAD | 0.46 | 63 | 1.8 | 0.828
4 | J115 | J103 | BRICK ROAD | 0.46 | 63 | 2 | 0.92
5 | J109 | J110 | BRICK ROAD | 0.46 | 63 | 7.7 | 3.542
6 | J109 | J110 | BRICK ROAD | 0.46 | 63 | 21.7 | 9.982
7 | J109 | J110 | BRICK ROAD | 0.46 | 63 | 31.1 | 14.306
8 | J109 | J110 | BRICK ROAD | 0.46 | 63 | 23 | 10.58
9 | J110 | J149 | BRICK ROAD | 0.46 | 63 | 6.5 | 2.99
10 | J34 | J36 | BRICK ROAD | 0.46 | 63 | 2.4 | 1.104
11 | J37 | J23 | BRICK ROAD | 0.46 | 63 | 51 | 23.46
12 | J37 | J23 | BRICK ROAD | 0.46 | 63 | 3.6 | 1.656
13 | J23 | J12 | BRICK ROAD | 0.46 | 63 | 60 | 27.6
14 | J12(1) | J12(2) | BRICK ROAD | 0.46 | 63 | 3 | 1.38
15 | J28 | J21 | BRICK ROAD | 0.46 | 63 | 4 | 1.84
16 | J4 | J16 | interlocking | 0.46 | 63 | 101.3 | 46.598
17 | J30 | J22 | BRICK ROAD | 0.46 | 63 | 84.5 | 38.87
18 | J30 | J103 | BRICK ROAD | 0.46 | 63 | 95.5 | 43.93
19 | J103 | J136 | BRICK ROAD | 0.46 | 63 | 3 | 1.38
20 | J103 | J115 | BRICK ROAD | 0.46 | 63 | 128 | 58.88
21 | J103 | J100 | BRICK ROAD | 0.46 | 63 | 363 | 166.98
22 | J103 | J100 | BRICK ROAD | 0.46 | 63 | 409 | 188.14
23 | J100 | J168 | BRICK ROAD | 0.46 | 63 | 3 | 1.38
24 | J100 | J168 | BRICK ROAD | 0.46 | 63 | 60 | 27.6
25 | J100 | J38 | BRICK ROAD | 0.46 | 63 | 161.6 | 74.336
26 | J29 | J31 | BRICK ROAD | 0.46 | 63 | 15 | 6.9
27 | J31(1) | J31(2) | BRICK ROAD | 0.46 | 63 | 2.3 | 1.058
28 | J192(1) | J202 | B.T ROAD | 0.46 | 63 | 3 | 1.38
29 | J163 | J141 | B.T ROAD | 0.46 | 63 | 3.3 | 1.518
30 | J242 | J227 | B.T ROAD | 0.46 | 63 | 6 | 2.76
31 | J76 | J242 | BRICK ROAD | 0.46 | 63 | 6 | 2.76
32 | J242 | J240 | BRICK ROAD | 0.46 | 63 | 30.8 | 14.168
33 | J240 | J241 | BRICK ROAD | 0.46 | 63 | 89.6 | 41.216
34 | J249 | J250 | B.T ROAD | 0.46 | 63 | 3 | 1.38
35 | j42 | j44 | BRICK ROAD | 0.46 | 63 | 29.9 | 13.754
36 | j44 | j53 | BRICK ROAD | 0.46 | 63 | 37.1 | 17.066
37 | j44 | j43 | BRICK ROAD | 0.46 | 63 | 37.8 | 17.388
38 | j48 | j70 | BRICK ROAD | 0.46 | 63 | 41.2 | 18.952
39 | j48 | j70 | BRICK ROAD | 0.46 | 63 | 31.6 | 14.536
40 | j48 | j70 | BRICK ROAD | 0.46 | 63 | 88.9 | 40.894
41 | j49 | j46 | interlocking | 0.46 | 63 | 47.8 | 21.988
42 | j43 | j41 | BRICK ROAD | 0.46 | 63 | 45.9 | 21.114
43 | j45 | j40 | interlocking | 0.46 | 63 | 3.1 | 1.426
44 | j42 | j29 | interlocking | 0.46 | 63 | 77.6 | 35.696
45 | j42 | j48 | BRICK ROAD | 0.46 | 63 | 31.3 | 14.398
46 | j40 | j29 | BRICK ROAD | 0.46 | 63 | 81.2 | 37.352
47 | J76 | J74 | interlocking | 0.46 | 75 | 6 | 2.76
48 | J25 | J29 | BRICK ROAD | 0.46 | 75 | 4 | 1.84
49 | J25 | J29 | interlocking | 0.46 | 75 | 3 | 1.38
50 | J187 | J176 | B.T ROAD | 0.46 | 75 | 3 | 1.38
51 | J2 | J5 | BRICK ROAD | 0.46 | 110 | 273.2 | 125.672
52 | J5 | J25 | BRICK ROAD | 0.46 | 110 | 6.6 | 3.036
53 | J5 | J25 | BRICK ROAD | 0.46 | 110 | 76 | 34.96
54 | J5 | J25 | BRICK ROAD | 0.46 | 110 | 55.8 | 25.668
55 | J25 | J34 | BRICK ROAD | 0.46 | 110 | 57.8 | 26.588
56 | J34 | J37 | BRICK ROAD | 0.46 | 110 | 41.2 | 18.952
57 | J37 | J38 | BRICK ROAD | 0.46 | 110 | 39.3 | 18.078
58 | J38 | J39 | BRICK ROAD | 0.46 | 110 | 49.9 | 22.954
59 | J39 | J42 | BRICK ROAD | 0.46 | 110 | 29.8 | 13.708
60 | J42 | J59 | BRICK ROAD | 0.46 | 110 | 48.5 | 22.31
61 | J125(1) | J125 | interlocking | 0.46 | 110 | 6.7 | 3.082
62 | 97 | 95 | brick road | 0.46 | 63 | 3 | 1.38
63 | 97 | 96 | brick road | 0.46 | 63 | 23 | 10.58
64 | 98 | 97 | brick road | 0.46 | 63 | 38.9 | 17.894
65 | 125 | 120 | interlocking | 0.46 | 110 | 6.5 | 2.99
66 | 108 | 118 | brick road | 0.46 | 63 | 35 | 16.1
67 | 108 | 118 | brick road | 0.46 | 63 | 3 | 1.38
68 | 77 | 75 | interlocking | 0.46 | 63 | 6.3 | 2.898
69 | 70 | 55 | brick road | 0.46 | 63 | 3 | 1.38
70 | 61 | 62 | brick road | 0.46 | 63 | 3 | 1.38
71 | 60 | 64 | brick road | 0.46 | 63 | 87 | 40.02
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  | SIGN.with date