## DARAOULI
DARAOULI(JMR) BLOCK-MANGRAURA
Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | Dia of pipe(MM) | Pipe Length (M) | CUMMULATIVE | REMARK
1 | J184 | 183 | INTERLOCKING | 0.46 | 63 | 63.4 | 63.4
2 | 183 | 195 | KC |  | 63 | 77.9 | 141.3
3 | 195 | 196 | KC |  | 63 | 22 | 163.3
4 | 184 | 228 | BOE | 0.46 | 63 | 20.5 | 183.8
5 | 228 | 225 | BOE | 0.46 | 63 | 21 | 204.8
6 | 228 | 246 | BOE | 0.46 | 63 | 40.8 | 245.6
7 | 246 | 177 | KC |  | 63 | 50 | 295.6
8 | 246 | 242 | BOE | 0.46 | 63 | 43 | 338.6
9 | 242 | 226 | BOE | 0.46 | 63 | 96.1 | 434.7
10 | 242 | 179 | BOE | 0.46 | 63 | 81 | 515.7
11 | 235 | 173 | KC |  | 63 | 112 | 627.7
12 | 173A | 173B | KC |  | 63 | 65 | 692.7
13 | 224 | 215 | KC |  | 63 | 20 | 712.7
14 | 178 | 152 | BOE | 0.46 | 63 | 28 | 740.7
15 | 152 | 167 | BOE | 0.46 | 63 | 25 | 765.7
16 | 170 | 127 | BOE | 0.46 | 63 | 31 | 796.7
17 | 125 | 124 | BOE | 0.46 | 63 | 63 | 859.7
18 | 147 | 117 | INTERLOCKING | 0.46 | 63 | 135 | 994.7
19 | 161 | 136 | KC |  | 63 | 164 | 1158.7
20 | 136 | 132 | KC |  | 63 | 60 | 1218.7
21 | 136 | 139 | KC |  | 63 | 51 | 1269.7
22 | 139 | 121 | B.T. ROAD | 0.36 | 63 | 3.5 | 1273.2 | ROAD CROSSING
23 | 139 | 121 | KC |  | 63 | 71.2 | 1344.4
24 | 139 | 153 | KC |  | 63 | 62.1 | 1406.5
25 | 153 | 150 |  |  | 63 | 4.5 | 1411 | CULVERT
26 | 153 | 150 | KC |  | 63 | 210.5 | 1621.5
27 | 150 | 192 | BOE | 0.46 | 63 | 20.2 | 1641.7
28 | 150 | 212 | KC |  | 63 | 31.4 | 1673.1
29 | 212 | 134 | KC |  | 63 | 180 | 1853.1
30 | 212 | 157 | KC |  | 63 | 52 | 1905.1
31 | 157 | 130 | B.T. ROAD | 0.36 | 63 | 3 | 1908.1 | ROAD CROSSING
32 | 157 | 130 | KC |  | 63 | 187 | 2095.1
33 | 130 | 116 | KC |  | 63 | 475 | 2570.1
34 | 116 | 123 | KC |  | 63 | 114.5 | 2684.6
35 | 157 | 138 | B.T. ROAD | 0.36 | 63 | 5 | 2689.6 | ROAD CROSSING
36 | 157 | 138 | KC |  | 63 | 111.5 | 2801.1
37 | 138 | 134 | KC |  | 63 | 36 | 2837.1
38 | 134 | 166 | KC |  | 63 | 30 | 2867.1
39 | 138 | 187 | KC |  | 63 | 69.2 | 2936.3
40 | 187 | 182 | B.T. ROAD | 0.36 | 63 | 7.2 | 2943.5 | ROAD CROSSING
41 | 182 | 168 | BOE | 0.46 | 63 | 48.7 | 2992.2
42 | 166 | 168 | BOE | 0.46 | 63 | 46.3 | 3038.5
43 | 182 | 190 | KC |  | 63 | 79.4 | 3117.9
44 | 170 | 188 | B.T. ROAD | 0.36 | 63 | 4.5 | 3122.4 | ROAD CROSSING
45 | 170 | 188 | KC |  | 63 | 329.5 | 3451.9
46 | 188 | 154 | KC |  | 63 | 279 | 3730.9
47 | 154 | 158 | KC |  | 63 | 22 | 3752.9
48 | 158 | 181 | KC |  | 63 | 80 | 3832.9
49 | 181 | 244 | KC |  | 63 | 125 | 3957.9
50 | 199 | 165 | B.T. ROAD | 0.36 | 63 | 4 | 3961.9 | ROAD CROSSING
51 | 199 | 165 | INTERLOCKING | 0.46 | 63 | 175 | 4136.9
52 | 199 | 165 | KC |  | 63 | 256 | 4392.9
53 | 186 | 151 | B.T. ROAD | 0.36 | 63 | 4 | 4396.9 | ROAD CROSSING
54 | 186 | 151 | KC |  | 63 | 147 | 4543.9
55 | 186 | 151 | BOE | 0.46 | 63 | 32 | 4575.9
56 | 151 | 180 | KC |  | 63 | 40.7 | 4616.6
57 | 151 | 194 | KC |  | 63 | 74.8 | 4691.4
58 | 165 | 201 | INTERLOCKING | 0.46 | 63 | 60 | 4751.4
59 | 201 | 131 | INTERLOCKING | 0.46 | 63 | 87.5 | 4838.9
60 | 131 | 140 | INTERLOCKING | 0.46 | 63 | 75 | 4913.9
61 | 140 | 223 | BOE | 0.46 | 63 | 86 | 4999.9
62 | 140 | 148 | KC |  | 63 | 103 | 5102.9
63 | 140 | 148 | INTERLOCKING | 0.46 | 63 | 63 | 5165.9
64 | 148 | 162 | BOE | 0.46 | 63 | 12 | 5177.9
65 | 148 | 162 | KC |  | 63 | 138 | 5315.9 |  |  | 20.5
66 | 131 | 143 | INTERLOCKING | 0.46 | 63 | 74.6 | 5390.5
67 | 143 | 155 | KC |  | 63 | 68.5 | 5459 |  |  | 40.8
68 | 143 | 149 | INTERLOCKING | 0.46 | 63 | 78.8 | 5537.8
69 | 149 | 118 | KC |  | 63 | 252 | 5789.8 |  |  | 96.1
70 | 118 | 144 | KC |  | 63 | 25 | 5814.8 |  |  | 81
71 | 118 | 232 | KC |  | 63 | 127 | 5941.8 |  |  | 53
72 | 149 | 169 | KC |  | 63 | 74 | 6015.8
73 | 169 | 172 | KC |  | 63 | 75 | 6090.8 |  |  | 31
74 | 172 | 207 | KC |  | 63 | 31 | 6121.8 |  |  | 63
75 | 172 | 243 | B.T. ROAD | 0.36 | 63 | 4 | 6125.8 | ROAD CROSSING
76 | 172 | 243 | KC |  | 63 | 125 | 6250.8 |  |  | 20.2
77 | 169 | 230 | BOE | 0.46 | 63 | 40 | 6290.8
78 | 169 | 230 | B.T. ROAD | 0.36 | 63 | 4 | 6294.8 | ROAD CROSSING
79 | 169 | 230 | KC |  | 63 | 88 | 6382.8 |  |  | 7.2
80 | 232 | 218 |  |  | 63 | 3 | 6385.8 | CULVERT |  | 48.7
81 | 232 | 218 | B.T. ROAD | 0.36 | 63 | 4 | 6389.8 | ROAD CROSSING
82 | 232 | 218 | KC |  | 63 | 184 | 6573.8 |  |  | 46.3
83 | 218 | 229 | KC |  | 63 | 52 | 6625.8 |  |  | 32
84 | 229 | 220 | KC |  | 63 | 66 | 6691.8 |  |  | 60
85 | 190 | 206 | KC |  | 63 | 66 | 6757.8 |  |  | 87.5
86 | 190 | 202 | KC |  | 63 | 61.3 | 6819.1 |  |  | 75
87 | J169 | J149 | INTERLOCKING | 0.46 | 63 | 74 | 6893.1
88 | 202 | 240 | BOE | 0.46 | 63 | 77.3 | 6970.4
89 | 202 | 210 | KC |  | 63 | 36 | 7006.4 |  |  | 63
90 | 210 | 233 | B.T. ROAD | 0.36 | 63 | 3.5 | 7009.9 | ROAD CROSSING
91 | 210 | 233 | KC |  | 63 | 59.5 | 7069.4 |  |  | 12
92 | 233 | 213 | KC |  | 63 | 347.2 | 7416.6 |  |  | 74.6
93 | 213 | 209 | B.T. ROAD | 0.36 | 63 | 5 | 7421.6 | ROAD CROSSING
94 | 213 | 209 | BOE | 0.46 | 63 | 97.7 | 7519.3
95 | 213 | 187 | B.T | 0.36 | 63 | 3 | 7522.3 | ROAD CROSSING
96 | 213 | 187 | KC |  | 63 | 577 | 8099.3 |  |  | 5
97 | J220 | J229 | INTERLOCKING | 0.46 | 63 | 66 | 8165.3
98 | 233 | 208 | B.T | 0.36 | 63 | 5 | 8170.3 | ROAD CROSSING
99 | 233 | 208 | KC |  | 63 | 104 | 8274.3 |  |  | 3
100 | 208 | 193 | KC |  | 63 | 43 | 8317.3 |  |  | 5
101 | 208 | 185 | KC |  | 63 | 94 | 8411.3 |  |  | 16.7
102 | 185 | 222 | KC |  | 63 | 131 | 8542.3 |  |  | 3
103 | 222 | 236 | KC |  | 63 | 178 | 8720.3 |  |  | 127
104 | 233 | 226 | KC |  | 63 | 210.1 | 8930.4 |  |  | 130
105 | 226 | 203 | KC |  | 63 | 47.5 | 8977.9 |  |  | 3
106 | 203 | 241 | KC |  | 63 | 88.2 | 9066.1 |  |  | 21
107 | J218 | J229 | INTERLOCKING | 0.46 | 63 | 52 | 9118.1
108 | 179 | 184 | INTERLOCKING | 0.46 | 63 | 16.7 | 9134.8
109 | 218 | 238 | INTERLOCKING | 0.46 | 63 | 4 | 9138.8 | ROAD CROSSING
110 | 218 | 238 | KC |  | 63 | 158 | 9296.8 |  |  | 30.3
111 | 238 | 237 | B.T | 0.36 | 63 | 3 | 9299.8 | ROAD CROSSING
112 | 238 | 237 | BOE | 0.46 | 63 | 127 | 9426.8
113 | 237 | 231 | BOE | 0.46 | 63 | 130 | 9556.8
114 | 237 | 231 | KC |  | 63 | 78 | 9634.8
115 | 238 | 214 | KC |  | 63 | 115 | 9749.8
116 | 214 | 197 | KC |  | 63 | 114 | 9863.8
117 | 214 | 236 | B.T | 0.36 | 63 | 3 | 9866.8 | ROAD CROSSING
118 | 214 | 236 | KC |  | 63 | 79 | 9945.8
119 | 236 | 234 | KC |  | 63 | 40 | 9985.8
120 | 234 | 227 | KC |  | 63 | 31 | 10016.8
121 | 234 | 239 | KC |  | 63 | 42 | 10058.8
122 | 239 | 205 | KC |  | 63 | 35 | 10093.8
123 | 239 | 221 | KC |  | 63 | 44 | 10137.8
124 | 245 | 248 | KC |  | 63 | 100 | 10237.8
125 | J160 | J136 | KC |  | 63 | 59.9 | 10297.7
126 | J194 | J165 | KC |  | 63 | 91 | 10388.7
127 | J220 | J196 | INTERLOCKING | 0.46 | 63 | 171.6 | 10560.3
128 | J220 | J196 | KC |  | 63 | 202.4 | 10762.7
129 | J165 | J161 | INTERLOCKING | 0.46 | 63 | 21 | 10783.7
130 | J165 | J161 | BOE | 0.46 | 63 | 10 | 10793.7
131 | J161 | J201 | INTERLOCKING | 0.46 | 63 | 30.3 | 10824
132 | J162 | J244 | KC |  | 63 | 40 | 10864
133 | 231 | 245 | KC |  | 75 | 207 | 11071
134 | 204 | 179 | INTERLOCKING | 0.46 | 90 | 55 | 11126
135 | 232 | 231 |  |  | 90 | 8 | 11134 | CULVERT
136 | 232 | 231 | B.T. ROAD | 0.36 | 90 | 5 | 11139 | ROAD CROSSING
137 | 232 | 231 | KC |  | 90 | 320 | 11459
138 | J204 | J230 | INTERLOCKING | 0.46 | 90 | 4 | 11463
139 | J204 | J230 | KC |  | 90 | 7 | 11470
140 | 230 | 232 | KC |  | 90 | 196.3 | 11666.3
141 | 241 | 243 | KC |  | 110 | 30 | 11696.3
142 | 243 | 235 | KC |  | 110 | 47 | 11743.3
143 | 224 | 235 | KC |  | 110 | 95 | 11838.3
144 | 224 | 286 | KC |  | 110 | 88 | 11926.3
145 | 186 | 178 | KC |  | 110 | 25 | 11951.3
146 | 178 | 199 | BOE | 0.46 | 110 | 11 | 11962.3
147 | 199 | 170 | KC |  | 110 | 151 | 12113.3
148 | 241 | 204 | B.T. ROAD | 0.36 | 110 | 5 | 12118.3 | ROAD CROSSING
149 | 241 | 204 | KC |  | 110 | 69 | 12187.3
150 | 123 | 112 | KC |  | 125 | 174 | 12361.3
151 | 112 | 107 | B.T. ROAD | 0.36 | 125 | 4 | 12365.3 | ROAD CROSSING
152 | 112 | 107 | KC |  | 125 | 179 | 12544.3 | `
153 | 170 | 160 | B.T. ROAD | 0.36 | 125 | 6 | 12550.3 | ROAD CROSSING
154 | 170 | 160 | KC |  | 125 | 65 | 12615.3
155 | 160 | 141 | KC |  | 125 | 53 | 12668.3
156 | 141 | 137 | KC |  | 125 | 35 | 12703.3
157 | 137 | 125 | KC |  | 125 | 42 | 12745.3
158 | 125 | 122 | KC |  | 125 | 44 | 12789.3 |  |  |  | 693
159 | 122 | 147 | KC |  | 125 | 52 | 12841.3
160 | 147 | 123 | KC |  | 125 | 42 | 12883.3
|  | 63 | 75 | 90 | 110 | 125
|  | 10864 | 207 | 595.3 | 521 | 696 | 12883.3
|  | 12362 | 207 | 596 | 509 | 775
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  | SIGN.with date
Abstract (Bill Breakup)
1 | Dia of Pipe | WO/DPR Qty's | Laying, Jointing, Backfilling - 60% |  |  |  | Gap Closing- 5% |  |  |  | Hydro Test - 15% |  |  |  | FHTC Stretch - 10%
|  |  | Laying Up to Date | Laying Qty Billed up to Date | Qty Billed Up to Previous | This Bill Qty (Laying) | WO/DPR Qty's | GAP Closing Billed Qty up to Date | GAP Closing Qty Up to Previous | This Bill Qty (GAP Closing) | WO/DPR Qty's | Hydro Test Qty Billed up to Date | Hydro Test Qty Up to Previous | This Bill Qty (Hydro Test ) | FHTC Stretch Qty Billed up to Date | FHTC Stretch Qty Billed Up to Previous | This Bill Qty (FHTC Stretch Billed )
1.1 | 63 mm HDPE |  | 10864 | 10864 | 9822 | 1042 |  | 10864 | 10864 | 10864 |  | 10864 | 10864 | 10864
1.2 | 75 mm HDPE |  | 207 | 207 | 207 | 0 |  | 207 | 207 | 207 |  | 207 | 207 | 207
1.3 | 90 mm HDPE |  | 595.3 | 595.3 | 596 | -0.7 |  | 595.3 | 595.3 | 595.3 |  | 595.3 | 595.3 | 595.3
1.4 | 110mm HDPE |  | 521 | 521 | 510 | 11 |  | 521 | 521 | 521 |  | 521 | 521 | 521
1.5 | 125mm HDPE |  | 696 | 696 | 696 | 0 |  | 696 | 696 | 696 |  | 696 | 696 | 696
1.6 | 140mm HDPE |  |  | 0
1.7 | 160mm HDPE |  |  | 0
1.8 | 180mm HDPE |  |  | 0
1.9 | 200mm HDPE |  |  | 0
Sub Total = |  |  | 12883.3 | 12883.3 | 11831 | 1052.3 |  | 12883.3 | 12883.3 | 12883.3 |  | 12883.3 | 12883.3 | 12883.3
Sub-Contractor Site Engineer (Sr.Eng/ DY.M-SMX ) (Dy.M-PMX ) AGM Project Incharge

## restoration
DARAOULI(JMR ROAD RESTORATION) BLOCK-MANGRAURA
Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | Dia of pipe(MM) | Pipe Length (M) | SQM | REMARK
1 | J184 | 183 | INTERLOCKING | 0.46 | 63 | 63.4 | 29.164 | DONE
2 | 184 | 228 | BOE | 0.46 | 63 | 20.5 | 9.43 | DONE
3 | 228 | 225 | BOE | 0.46 | 63 | 21 | 9.66 | DONE
4 | 228 | 246 | BOE | 0.46 | 63 | 40.8 | 18.768 | DONE
5 | 246 | 242 | BOE | 0.46 | 63 | 43 | 19.78 | DONE
6 | 242 | 226 | BOE | 0.46 | 63 | 96.1 | 44.206 | DONE
7 | 242 | 179 | BOE | 0.46 | 63 | 81 | 37.26 | DONE
8 | 178 | 152 | BOE | 0.46 | 63 | 28 | 12.88 | DONE
9 | 152 | 167 | BOE | 0.46 | 63 | 25 | 11.5 | DONE
10 | 170 | 127 | BOE | 0.46 | 63 | 31 | 14.26 | DONE
11 | 125 | 124 | BOE | 0.46 | 63 | 63 | 28.98 | DONE
12 | 147 | 117 | INTERLOCKING | 0.46 | 63 | 135 | 62.1 | DONE
13 | 139 | 121 | B.T. ROAD | 0.36 | 63 | 3.5 | 1.26 | DONE
14 | 150 | 192 | BOE | 0.46 | 63 | 20.2 | 9.292 | DONE
15 | 157 | 130 | B.T. ROAD | 0.36 | 63 | 3 | 1.08 | DONE
16 | 157 | 138 | B.T. ROAD | 0.36 | 63 | 5 | 1.8 | DONE
17 | 187 | 182 | B.T. ROAD | 0.36 | 63 | 7.2 | 2.592 | DONE
18 | 182 | 168 | BOE | 0.46 | 63 | 48.7 | 22.402 | DONE
19 | 166 | 168 | BOE | 0.46 | 63 | 46.3 | 21.298 | DONE
20 | 170 | 188 | B.T. ROAD | 0.36 | 63 | 4.5 | 1.62 | DONE
21 | 199 | 165 | B.T. ROAD | 0.36 | 63 | 4 | 1.44 | DONE
22 | 199 | 165 | INTERLOCKING | 0.46 | 63 | 175 | 80.5 | DONE
23 | 186 | 151 | B.T. ROAD | 0.36 | 63 | 4 | 1.44 | DONE
24 | 186 | 151 | BOE | 0.46 | 63 | 32 | 14.72 | DONE
25 | 165 | 201 | INTERLOCKING | 0.46 | 63 | 60 | 27.6 | DONE
26 | 201 | 131 | INTERLOCKING | 0.46 | 63 | 87.5 | 40.25 | DONE
27 | 131 | 140 | INTERLOCKING | 0.46 | 63 | 75 | 34.5 | DONE
28 | 140 | 223 | BOE | 0.46 | 63 | 86 | 39.56 | DONE
29 | 140 | 148 | INTERLOCKING | 0.46 | 63 | 63 | 28.98 | DONE
30 | 148 | 162 | BOE | 0.46 | 63 | 12 | 5.52 | DONE
31 | 131 | 143 | INTERLOCKING | 0.46 | 63 | 74.6 | 34.316 | DONE
32 | 143 | 149 | INTERLOCKING | 0.46 | 63 | 78.8 | 36.248 | DONE
33 | 172 | 243 | B.T. ROAD | 0.36 | 63 | 4 | 1.44 | DONE
34 | 169 | 230 | BOE | 0.46 | 63 | 40 | 18.4 | DONE
35 | 169 | 230 | B.T. ROAD | 0.36 | 63 | 4 | 1.44 | DONE
36 | 232 | 218 | B.T. ROAD | 0.36 | 63 | 4 | 1.44 | DONE
37 | J169 | J149 | INTERLOCKING | 0.46 | 63 | 74 | 34.04 | DONE
38 | 202 | 240 | BOE | 0.46 | 63 | 77.3 | 35.558 | DONE
39 | 210 | 233 | B.T. ROAD | 0.36 | 63 | 3.5 | 1.26 | DONE
40 | 213 | 209 | B.T. ROAD | 0.36 | 63 | 5 | 1.8 | DONE
41 | 213 | 209 | BOE | 0.46 | 63 | 97.7 | 44.942 | DONE
42 | 213 | 187 | B.T | 0.36 | 63 | 3 | 1.08 | DONE
43 | J220 | J229 | INTERLOCKING | 0.46 | 63 | 66 | 30.36 | DONE
44 | 233 | 208 | B.T | 0.36 | 63 | 5 | 1.8 | DONE
45 | J218 | J229 | INTERLOCKING | 0.46 | 63 | 52 | 23.92 | DONE
46 | 179 | 184 | INTERLOCKING | 0.46 | 63 | 16.7 | 7.682 | DONE
47 | 218 | 238 | INTERLOCKING | 0.46 | 63 | 4 | 1.84 | DONE
48 | 238 | 237 | B.T | 0.36 | 63 | 3 | 1.08 | DONE
49 | 238 | 237 | BOE | 0.46 | 63 | 127 | 58.42 | DONE
50 | 237 | 231 | BOE | 0.46 | 63 | 130 | 59.8 | DONE
51 | 214 | 236 | B.T | 0.36 | 63 | 3 | 1.08 | DONE
52 | J220 | J196 | INTERLOCKING | 0.46 | 63 | 171.6 | 78.936 | DONE
53 | J165 | J161 | INTERLOCKING | 0.46 | 63 | 21 | 9.66 | DONE
54 | J165 | J161 | BOE | 0.46 | 63 | 10 | 4.6 | DONE
55 | J161 | J201 | INTERLOCKING | 0.46 | 63 | 30.3 | 13.938 | DONE
56 | 204 | 179 | INTERLOCKING | 0.46 | 90 | 55 | 25.3 | DONE
57 | 232 | 231 | B.T. ROAD | 0.36 | 90 | 5 | 1.8 | DONE
58 | J204 | J230 | INTERLOCKING | 0.46 | 90 | 4 | 1.84 | DONE
59 | 178 | 199 | BOE | 0.46 | 110 | 11 | 5.06 | DONE
60 | 241 | 204 | B.T. ROAD | 0.36 | 110 | 5 | 1.8 | DONE
61 | 112 | 107 | B.T. ROAD | 0.36 | 125 | 4 | 1.44 | DONE
62 | 170 | 160 | B.T. ROAD | 0.36 | 125 | 6 | 2.16 | DONE