## shivapur khurd
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | shivapur khurd | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | OHT | j1 | 125 | 29.6 | 6 | 3 | 1 | 4 | no
2 | j9 | j9a | 75 | 55.5 | 6 | 3 | 1 | 4 | no
3 | j11 | j9a | 75 | 101.9 | 6 | 3 | 1 | 4 | no
4 | j9(1) | j9(2) | 75 | 8.7 | 6 | 3 | 1 | 4 | no
5 | j1 | 75(a) | 75 | 187.4 | 6 | 3 | 1 | 4 | no
6 | j75a | J75 | 75 | 5.1 | 6 | 3 | 1 | 4 | no
7 | j75a | J75 | 75 | 300.6 | 6 | 3 | 1 | 4 | no
8 | j2 | j3 | 75 | 34.8 | 6 | 3 | 1 | 4 | no
9 | J76 | J75 | 75 | 3 | 6 | 3 | 1 | 4 | no
10 | J76 | J75 | 75 | 3.6 | 6 | 3 | 1 | 4 | no
11 | j1 | 75(a) | 75 | 5.1 | 6 | 3 | 1 | 4 | no
12 | j52 | j39 | 63 | 460.7 | 6 | 3 | 1 | 4 | no
13 | j39 | j35 | 63 | 40.5 | 6 | 3 | 1 | 4 | no
14 | j35 | j24 | 63 | 58.4 | 6 | 3 | 1 | 4 | no
15 | j24 | j28 | 63 | 52.3 | 6 | 3 | 1 | 4 | no
16 | j24 | j21 | 63 | 23 | 6 | 3 | 1 | 4 | no
17 | j21 | j15 | 63 | 33.3 | 6 | 3 | 1 | 4 | no
18 | J15 | J16 | 63 | 19.1 | 6 | 3 | 1 | 4 | no
19 | J15 | J11 | 63 | 14.2 | 6 | 3 | 1 | 4 | no
20 | J9(A) | J9(b) | 63 | 25.7 | 6 | 3 | 1 | 4 | no
21 | J75(A) | J75(B) | 63 | 133.8 | 6 | 3 | 1 | 4 | no
22 | J75(A) | J75(B) | 63 | 2.6 | 6 | 3 | 1 | 4 | no
23 | J2(A) | J6 | 63 | 77.4 | 6 | 3 | 1 | 4 | no
24 | J6 | J8 | 63 | 33.4 | 6 | 3 | 1 | 4 | no
25 | J6 | J8 | 63 | 10.4 | 6 | 3 | 1 | 4 | no
26 | J6 | J4 | 63 | 25.1 | 6 | 3 | 1 | 4 | no
27 | J6 | J4 | 63 | 15 | 6 | 3 | 1 | 4 | no
28 | J4 | J5 | 63 | 8.5 | 6 | 3 | 1 | 4 | no
29 | J4 | J5 | 63 | 3.1 | 6 | 3 | 1 | 4 | no
30 | J4 | J5 | 63 | 143.1 | 6 | 3 | 1 | 4 | no
31 | J3 | J4 | 63 | 14.4 | 6 | 3 | 1 | 4 | no
32 | J3 | J4 | 63 | 7.5 | 6 | 3 | 1 | 4 | no
33 | J67(A) | J84 | 63 | 84.4 | 6 | 3 | 1 | 4 | no
34 | J67(A) | J84 | 63 | 141.8 | 6 | 3 | 1 | 4 | no
35 | J67(A) | J79 | 63 | 101.5 | 6 | 3 | 1 | 4 | no
36 | J67(A) | J67 | 63 | 4.2 | 6 | 3 | 1 | 4 | no
37 | J67(A) | J67 | 63 | 85.7 | 6 | 3 | 1 | 4 | no
38 | J67 | J82 | 63 | 165.5 | 6 | 3 | 1 | 4 | no
39 | J67 | J61 | 63 | 86.5 | 6 | 3 | 1 | 4 | no
40 | J46 | J61 | 63 | 4.2 | 6 | 3 | 1 | 4 | no
41 | J46 | J61 | 63 | 4.1 | 6 | 3 | 1 | 4 | no
42 | J61 | J45 | 63 | 185.5 | 6 | 3 | 1 | 4 | no
43 | J61 | J45 | 63 | 49.5 | 6 | 3 | 1 | 4 | no
44 | J45 | J40 | 63 | 3 | 6 | 3 | 1 | 4 | no
45 | J45 | J40 | 63 | 73.2 | 6 | 3 | 1 | 4 | no
46 | J40 | J41 | 63 | 51.6 | 6 | 3 | 1 | 4 | no
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | shivapur khurd | [5 empty] | DATE
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | j2 | j2(a) | 110 | 15.6 | 5.5 | 3.3 | 1 | 4.3 | no
2 | j2(a) | j1 | 110 | 68.9 | 5.5 | 3.3 | 1 | 4.3 | no
3 | j9 | j2 | 90 | 13.1 | 5.5 | 3.3 | 1 | 4.3 | no
4 | j87 | j76 | 75 | 162.3 | 5.5 | 3.3 | 1 | 4.3 | no
5 | j97 | j94 | 75 | 3.6 | 5.5 | 3.3 | 1 | 4.3 | no
6 | j97 | j94 | 75 | 128.9 | 5.5 | 3.3 | 1 | 4.3 | no
7 | j97 | j94 | 75 | 728 | 5.5 | 3.3 | 1 | 4.3 | no
8 | j76 | j43 | 75 | 3.4 | 5.5 | 3.3 | 1 | 4.3 | no
9 | j76 | j43 | 75 | 8.3 | 5.5 | 3.3 | 1 | 4.3 | no
10 | j76 | j43 | 75 | 265.6 | 5.5 | 3.3 | 1 | 4.3 | no
11 | j43 | j46 | 75 | 156.2 | 5.5 | 3.3 | 1 | 4.3 | no
12 | j17 | j9 | 75 | 111 | 5.5 | 3.3 | 1 | 4.3 | no
13 | j17 | j9 | 75 | 3.8 | 5.5 | 3.3 | 1 | 4.3 | no
14 | j9 | j43 | 75 | 241.9 | 5.5 | 3.3 | 1 | 4.3 | no
15 | j9 | j43 | 75 | 3 | 5.5 | 3.3 | 1 | 4.3 | no
16 | J40 | J39 | 63 | 3 | 5.5 | 3.3 | 1 | 4.3 | no
17 | J40 | J39 | 63 | 41.4 | 5.5 | 3.3 | 1 | 4.3 | no
18 | j45 | j53 | 63 | 7.8 | 5.5 | 3.3 | 1 | 4.3 | no
19 | j45 | j53 | 63 | 48.5 | 5.5 | 3.3 | 1 | 4.3 | no
20 | j53 | j49 | 63 | 5.8 | 5.5 | 3.3 | 1 | 4.3 | no
21 | j53 | j49 | 63 | 9 | 5.5 | 3.3 | 1 | 4.3 | no
22 | j53 | j49 | 63 | 32.5 | 5.5 | 3.3 | 1 | 4.3 | no
23 | j53 | j58 | 63 | 6.1 | 5.5 | 3.3 | 1 | 4.3 | no
24 | j53 | j58 | 63 | 16.1 | 5.5 | 3.3 | 1 | 4.3 | no
25 | J5A | J5B | 63 | 72.7 | 5.5 | 3.3 | 1 | 4.3 | no
26 | j58 | j58(1) | 63 | 4 | 5.5 | 3.3 | 1 | 4.3 | no
27 | j58 | j58(1) | 63 | 3.8 | 5.5 | 3.3 | 1 | 4.3 | no
28 | j58(1) | j64a | 63 | 9.8 | 5.5 | 3.3 | 1 | 4.3 | no
29 | j58(1) | j64a | 63 | 37.6 | 5.5 | 3.3 | 1 | 4.3 | no
30 | j64a | j64b | 63 | 49 | 5.5 | 3.3 | 1 | 4.3 | no
31 | j64a | j64 | 63 | 104.7 | 5.5 | 3.3 | 1 | 4.3 | no
32 | j64 | j66 | 63 | 27.2 | 5.5 | 3.3 | 1 | 4.3 | no
33 | j64 | j65 | 63 | 9 | 5.5 | 3.3 | 1 | 4.3 | no
34 | j64 | j65 | 63 | 11 | 5.5 | 3.3 | 1 | 4.3 | no
35 | j58(1) | j59 | 63 | 35.5 | 5.5 | 3.3 | 1 | 4.3 | no
36 | j58 | j60 | 63 | 85.2 | 5.5 | 3.3 | 1 | 4.3 | no
37 | j58 | j60 | 63 | 15.7 | 5.5 | 3.3 | 1 | 4.3 | no
38 | j35 | j35(a) | 63 | 22.9 | 5.5 | 3.3 | 1 | 4.3 | no
39 | j35a | j35b | 63 | 1.9 | 5.5 | 3.3 | 1 | 4.3 | no
40 | j35a | j35b | 63 | 14.5 | 5.5 | 3.3 | 1 | 4.3 | no
41 | j35(1a) | j35(2b) | 63 | 42.4 | 5.5 | 3.3 | 1 | 4.3 | no
42 | j35(3b) | j35(4b) | 63 | 10.3 | 5.5 | 3.3 | 1 | 4.3 | no
43 | j35(a) | j30a | 63 | 6.4 | 5.5 | 3.3 | 1 | 4.3 | no
44 | j30(1) | j30(2) | 63 | 31.1 | 5.5 | 3.3 | 1 | 4.3 | no
45 | j30a | j30 | 63 | 59.4 | 5.5 | 3.3 | 1 | 4.3 | no
46 | j30a | j30 | 63 | 5.6 | 5.5 | 3.3 | 1 | 4.3 | no
47 | j73a | j73b | 63 | 2.4 | 5.5 | 3.3 | 1 | 4.3 | no
48 | j73a | j73b | 63 | 37.1 | 5.5 | 3.3 | 1 | 4.3 | no
49 | j73 | j73a | 63 | 3.7 | 5.5 | 3.3 | 1 | 4.3 | no
50 | j73a | j72 | 63 | 36.6 | 5.5 | 3.3 | 1 | 4.3 | no
51 | j72 | j74 | 63 | 65.1 | 5.5 | 3.3 | 1 | 4.3 | no
52 | j72 | j74 | 63 | 45.7 | 5.5 | 3.3 | 1 | 4.3 | no
53 | j72 | j70 | 63 | 69.7 | 5.5 | 3.3 | 1 | 4.3 | no
54 | j70 | j71 | 63 | 54.6 | 5.5 | 3.3 | 1 | 4.3 | no
55 | j70 | j71 | 63 | 3.2 | 5.5 | 3.3 | 1 | 4.3 | no
56 | j70 | j68 | 63 | 52.3 | 5.5 | 3.3 | 1 | 4.3 | no
57 | j68 | j69 | 63 | 9.6 | 5.5 | 3.3 | 1 | 4.3 | no
58 | j68 | j69 | 63 | 37 | 5.5 | 3.3 | 1 | 4.3 | no
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | shivapur khurd | [5 empty] | DATE
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | j90 | j94 | 75 | 137.1 | 5.5 | 3.5 | 1 | 4.5 | No
2 | j90 | j87 | 75 | 226.5 | 5.5 | 3.5 | 1 | 4.5 | No
3 | j35a | j35b | 63 | 1.9 | 5.5 | 3.5 | 1 | 4.5 | No
4 | j35a | j35b | 63 | 14.5 | 5.5 | 3.5 | 1 | 4.5 | No
5 | j35(1a) | j35(2b) | 63 | 42.4 | 5.5 | 3.5 | 1 | 4.5 | No
6 | j35(3b) | j35(4b) | 63 | 10.3 | 5.5 | 3.5 | 1 | 4.5 | No
7 | j35(a) | j30a | 63 | 6.4 | 5.5 | 3.5 | 1 | 4.5 | No
8 | j30(1) | j30(2) | 63 | 31.1 | 5.5 | 3.5 | 1 | 4.5 | No
9 | j30a | j30 | 63 | 59.4 | 5.5 | 3.5 | 1 | 4.5 | No
10 | j30a | j30 | 63 | 5.6 | 5.5 | 3.5 | 1 | 4.5 | No
11 | j73a | j73b | 63 | 2.4 | 5.5 | 3.5 | 1 | 4.5 | No
12 | j73a | j73b | 63 | 37.1 | 5.5 | 3.5 | 1 | 4.5 | No
13 | j73 | j73a | 63 | 3.7 | 5.5 | 3.5 | 1 | 4.5 | No
14 | j73a | j72 | 63 | 36.6 | 5.5 | 3.5 | 1 | 4.5 | No
15 | j72 | j74 | 63 | 65.1 | 5.5 | 3.5 | 1 | 4.5 | No
16 | j72 | j74 | 63 | 45.7 | 5.5 | 3.5 | 1 | 4.5 | No
17 | j72 | j70 | 63 | 69.7 | 5.5 | 3.5 | 1 | 4.5 | No
18 | j70 | j71 | 63 | 54.6 | 5.5 | 3.5 | 1 | 4.5 | No
19 | j70 | j71 | 63 | 3.2 | 5.5 | 3.5 | 1 | 4.5 | No
20 | j70 | j68 | 63 | 52.3 | 5.5 | 3.5 | 1 | 4.5 | No
21 | j68 | j69 | 63 | 9.6 | 5.5 | 3.5 | 1 | 4.5 | No
22 | j68 | j69 | 63 | 37 | 5.5 | 3.5 | 1 | 4.5 | No
23 | j68 | j67(a) | 63 | 284 | 5.5 | 3.5 | 1 | 4.5 | No
24 | j99 | j99a | 63 | 3.3 | 5.5 | 3.5 | 1 | 4.5 | No
25 | j99 | j99a | 63 | 8.1 | 5.5 | 3.5 | 1 | 4.5 | No
26 | j99 | j99a | 63 | 6.9 | 5.5 | 3.5 | 1 | 4.5 | No
27 | j99a | j99b | 63 | 2.2 | 5.5 | 3.5 | 1 | 4.5 | No
28 | j99a | j99b | 63 | 20.4 | 5.5 | 3.5 | 1 | 4.5 | No
29 | j99(a) | j102 | 63 | 19.1 | 5.5 | 3.5 | 1 | 4.5 | No
30 | j102 | j106 | 63 | 29.5 | 5.5 | 3.5 | 1 | 4.5 | No
31 | j106 | j112 | 63 | 88.2 | 5.5 | 3.5 | 1 | 4.5 | No
32 | j106 | j112 | 63 | 53.1 | 5.5 | 3.5 | 1 | 4.5 | No
33 | j106 | j110 | 63 | 25.4 | 5.5 | 3.5 | 1 | 4.5 | No
34 | j106 | j110 | 63 | 55.1 | 5.5 | 3.5 | 1 | 4.5 | No
35 | j111 | j110 | 63 | 33.9 | 5.5 | 3.5 | 1 | 4.5 | No
36 | j110 | j109 | 63 | 34 | 5.5 | 3.5 | 1 | 4.5 | No
37 | j103 | j101 | 63 | 126.4 | 5.5 | 3.5 | 1 | 4.5 | No
38 | j101 | j115 | 63 | 136.6 | 5.5 | 3.5 | 1 | 4.5 | No
39 | j101 | j115 | 63 | 57.1 | 5.5 | 3.5 | 1 | 4.5 | No
40 | j115 | j118 | 63 | 55.2 | 5.5 | 3.5 | 1 | 4.5 | No
41 | j101 | j97 | 63 | 77.4 | 5.5 | 3.5 | 1 | 4.5 | No
42 | j97 | j99 | 63 | 3 | 5.5 | 3.5 | 1 | 4.5 | No
43 | j97 | j99 | 63 | 118.2 | 5.5 | 3.5 | 1 | 4.5 | No
44 | j91 | j90 | 63 | 128.8 | 5.5 | 3.5 | 1 | 4.5 | No
45 | j94 | j88 | 63 | 166.3 | 5.5 | 3.5 | 1 | 4.5 | No
46 | j87 | j88 | 63 | 161 | 5.5 | 3.5 | 1 | 4.5 | No
47 | j46 | j61 | 63 | 115.1 | 5.5 | 3.5 | 1 | 4.5 | No
48 | j46 | j33a | 63 | 169 | 5.5 | 3.5 | 1 | 4.5 | No
49 | j33a | j33b | 63 | 27 | 5.5 | 3.5 | 1 | 4.5 | No
50 | j33a | j33 | 63 | 12.5 | 5.5 | 3.5 | 1 | 4.5 | No
51 | j33 | j29 | 63 | 22.3 | 5.5 | 3.5 | 1 | 4.5 | No
52 | j33 | j29 | 63 | 20.6 | 5.5 | 3.5 | 1 | 4.5 | No
53 | j33 | j30 | 63 | 12 | 5.5 | 3.5 | 1 | 4.5 | No
54 | j33 | j30 | 63 | 21 | 5.5 | 3.5 | 1 | 4.5 | No
55 | j33 | j30 | 63 | 19.8 | 5.5 | 3.5 | 1 | 4.5 | No
56 | j33 | j30 | 63 | 91 | 5.5 | 3.5 | 1 | 4.5 | No
57 | j21 | j26 | 63 | 13.2 | 5.5 | 3.5 | 1 | 4.5 | No
58 | j21 | j26 | 63 | 32.2 | 5.5 | 3.5 | 1 | 4.5 | No
59 | j26 | j30 | 63 | 30.5 | 5.5 | 3.5 | 1 | 4.5 | No
60 | j26 | j17a | 63 | 11.6 | 5.5 | 3.5 | 1 | 4.5 | No
61 | j26 | j17a | 63 | 52.5 | 5.5 | 3.5 | 1 | 4.5 | No
62 | j17a | j17b | 63 | 13.6 | 5.5 | 3.5 | 1 | 4.5 | No
63 | j17a | j17 | 63 | 46.2 | 5.5 | 3.5 | 1 | 4.5 | No
64 | J80 | J81 | 63 | 29.5 | 5.5 | 3.5 | 1 | 4.5 | No
65 | J56 | J57 | 63 | 35 | 5.5 | 3.5 | 1 | 4.5 | No
66 | J73C | J73D | 63 | 63.8 | 5.5 | 3.5 | 1 | 4.5 | No
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date