## bhausiya
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | Bhausiya | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | j5 | j2 | 160 | 53.2 | 6 | 3 | 1 | 4 | no
2 | j2 | j1 | 160 | 71.6 | 6 | 3 | 1 | 4 | no
3 | j1 | j3 | 160 | 37.7 | 6 | 3 | 1 | 4 | no
4 | j1 | oht | 160 | 23 | 6 | 3 | 1 | 4 | no
5 | j3 | j4 | 160 | 49 | 6 | 3 | 1 | 4 | no
6 | j7 | j9 | 160 | 60 | 6 | 3 | 1 | 4 | no
7 | j55 | j56 | 63 | 37.4 | 6 | 3 | 1 | 4 | no
8 | j68 | j63 | 63 | 38.7 | 6 | 3 | 1 | 4 | no
9 | j68 | j69 | 63 | 17 | 6 | 3 | 1 | 4 | no
10 | j69 | j76 | 63 | 127.3 | 6 | 3 | 1 | 4 | no
11 | j76 | j78 | 63 | 71.2 | 6 | 3 | 1 | 4 | no
12 | j69 | j66 | 63 | 60.5 | 6 | 3 | 1 | 4 | no
13 | j68 | j74 | 63 | 95.1 | 6 | 3 | 1 | 4 | no
14 | j68 | j74 | 63 | 1.5 | 6 | 3 | 1 | 4 | no
15 | j74 | j64 | 63 | 110 | 6 | 3 | 1 | 4 | no
16 | j74 | j78 | 63 | 59.1 | 6 | 3 | 1 | 4 | no
17 | j78 | j82 | 63 | 72.2 | 6 | 3 | 1 | 4 | no
18 | j82 | j86 | 63 | 25.1 | 6 | 3 | 1 | 4 | no
19 | j86 | j88 | 63 | 50.7 | 6 | 3 | 1 | 4 | no
20 | j88 | j90 | 63 | 29.7 | 6 | 3 | 1 | 4 | no
21 | j88 | j89 | 63 | 35 | 6 | 3 | 1 | 4 | no
22 | j89 | j90 | 63 | 3.4 | 6 | 3 | 1 | 4 | no
23 | j90 | j91 | 63 | 15.4 | 6 | 3 | 1 | 4 | no
24 | j91 | j96 | 63 | 69.5 | 6 | 3 | 1 | 4 | no
25 | j90 | j105 | 63 | 142.8 | 6 | 3 | 1 | 4 | no
26 | j105 | j108 | 63 | 25.6 | 6 | 3 | 1 | 4 | no
27 | j108 | j109 | 63 | 26.6 | 6 | 3 | 1 | 4 | no
28 | j109 | j111 | 63 | 317.2 | 6 | 3 | 1 | 4 | no
29 | j124 | j125 | 63 | 197 | 6 | 3 | 1 | 4 | no
30 | j125 | j126 | 63 | 27.7 | 6 | 3 | 1 | 4 | no
31 | j125 | j116 | 63 | 111.3 | 6 | 3 | 1 | 4 | no
32 | j116 | j113 | 63 | 106.1 | 6 | 3 | 1 | 4 | no
33 | j116 | j115 | 63 | 119.6 | 6 | 3 | 1 | 4 | no
34 | j115 | j114 | 63 | 42.7 | 6 | 3 | 1 | 4 | no
35 | j114 | j112 | 63 | 3 | 6 | 3 | 1 | 4 | no
36 | j114 | j112 | 63 | 25 | 6 | 3 | 1 | 4 | no
37 | j114 | j112 | 63 | 31 | 6 | 3 | 1 | 4 | no
38 | j114 | j112 | 63 | 5 | 6 | 3 | 1 | 4 | no
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | Bhausiya | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | j9 | j11 | 160 | 87.8 | 5.5 | 3.3 | 1 | 4.3 | no
2 | j11 | j15 | 140 | 35.2 | 5.5 | 3.3 | 1 | 4.3 | no
3 | j15 | j33 | 140 | 143 | 5.5 | 3.3 | 1 | 4.3 | no
4 | j14 | j5 | 140 | 184.3 | 5.5 | 3.3 | 1 | 4.3 | no
5 | j33 | j42 | 140 | 185.4 | 5.5 | 3.3 | 1 | 4.3 | no
6 | j42 | j46 | 140 | 9 | 5.5 | 3.3 | 1 | 4.3 | no
7 | j42 | j46 | 140 | 66.8 | 5.5 | 3.3 | 1 | 4.3 | no
8 | j75 | j62 | 125 | 60.6 | 5.5 | 3.3 | 1 | 4.3 | no
9 | j62 | j46 | 125 | 44.3 | 5.5 | 3.3 | 1 | 4.3 | no
10 | j112 | j113 | 63 | 17.5 | 5.5 | 3.3 | 1 | 4.3 | no
11 | j113 | j104 | 63 | 21.4 | 5.5 | 3.3 | 1 | 4.3 | no
12 | j104 | j102 | 63 | 15.8 | 5.5 | 3.3 | 1 | 4.3 | no
13 | j114 | j75 | 63 | 130.7 | 5.5 | 3.3 | 1 | 4.3 | no
14 | j114 | j75 | 63 | 32.3 | 5.5 | 3.3 | 1 | 4.3 | no
15 | j114 | j75 | 63 | 60.5 | 5.5 | 3.3 | 1 | 4.3 | no
16 | j114 | j75 | 63 | 6.3 | 5.5 | 3.3 | 1 | 4.3 | no
17 | j70 | j71 | 63 | 9.8 | 5.5 | 3.3 | 1 | 4.3 | no
18 | j71 | j72 | 63 | 50.7 | 5.5 | 3.3 | 1 | 4.3 | no
19 | j71 | j73 | 63 | 224 | 5.5 | 3.3 | 1 | 4.3 | no
20 | j70 | j128 | 63 | 300 | 5.5 | 3.3 | 1 | 4.3 | no
21 | j128 | j136 | 63 | 367.1 | 5.5 | 3.3 | 1 | 4.3 | no
22 | j128 | j133 | 63 | 264.3 | 5.5 | 3.3 | 1 | 4.3 | no
23 | j133 | j131 | 63 | 147.1 | 5.5 | 3.3 | 1 | 4.3 | no
24 | j131 | j132 | 63 | 74.7 | 5.5 | 3.3 | 1 | 4.3 | no
25 | j131 | j84 | 63 | 581.3 | 5.5 | 3.3 | 1 | 4.3 | no
26 | j139 | j147 | 63 | 56.8 | 5.5 | 3.3 | 1 | 4.3 | no
27 | j147 | j153 | 63 | 86 | 5.5 | 3.3 | 1 | 4.3 | no
28 | j153 | j159 | 63 | 23.1 | 5.5 | 3.3 | 1 | 4.3 | no
29 | j159 | j158 | 63 | 49.9 | 5.5 | 3.3 | 1 | 4.3 | no
30 | j159 | j160 | 63 | 36.9 | 5.5 | 3.3 | 1 | 4.3 | no
31 | j159 | j160 | 63 | 30 | 5.5 | 3.3 | 1 | 4.3 | no
32 | j174 | j173 | 63 | 102 | 5.5 | 3.3 | 1 | 4.3 | no
33 | j173 | j175 | 63 | 150.3 | 5.5 | 3.3 | 1 | 4.3 | no
34 | j175 | j178 | 63 | 43.8 | 5.5 | 3.3 | 1 | 4.3 | no
35 | j178 | j177 | 63 | 28.7 | 5.5 | 3.3 | 1 | 4.3 | no
36 | j178 | j177 | 63 | 10.5 | 5.5 | 3.3 | 1 | 4.3 | no
37 | j178 | j177 | 63 | 31 | 5.5 | 3.3 | 1 | 4.3 | no
38 | j178 | j177 | 63 | 2.4 | 5.5 | 3.3 | 1 | 4.3 | no
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | Bhausiya | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | j14 | j17 | 140 | 84 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
2 | j17 | j23 | 140 | 73.8 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
3 | j23 | j28 | 140 | 2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
4 | j23 | j28 | 140 | 109.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
5 | j28 | j35 | 140 | 135.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
6 | j75 | j79 | 125 | 155 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
7 | j79 | j81 | 125 |  | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
8 | j81 | j84 | 125 | 61.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
9 | j35 | j38 | 110 | 134.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
10 | j43 | j45 | 110 | 83.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
11 | j45 | j48 | 110 | 58 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
12 | j48 | j55 | 90 | 31.7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
13 | j48 | j49 | 63 | 9 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
14 | j49 | j50 | 63 | 98.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
15 | j50 | j51 | 63 | 19 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
16 | j51 | j60 | 63 | 43.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
17 | j60 | j49 | 63 | 98 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
18 | j60 | j64 | 63 | 47 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
19 | j51 | 52 | 63 | 90.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
20 | j64 | j65 | 63 | 97 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
21 | j65a | j65b | 63 | 93.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
22 | j146 | j149 | 63 | 25 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
23 | j149 | j163 | 63 | 106 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
24 | j42 | j34 | 63 | 46 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
25 | j16 | j18 | 63 | 40 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
26 | j18 | j24 | 63 | 52 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
27 | j24 | 25 | 63 | 58 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
28 | j26 | j30 | 63 | 78 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
29 | j152 | j147 | 63 | 236.8 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
30 | j152 | j127 | 63 | 299.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
31 | j127 | j126 | 63 | 190.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
32 | j126 | j129 | 63 | 83.9 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
33 | j129 | j150 | 63 | 287.4 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
34 | j150 | j151 | 63 | 3.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
35 | j150 | j151 | 63 | 3.4 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
36 | j150 | j151 | 63 | 21.7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
37 | j151 | j155 | 63 | 25.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
38 | j151 | j155 | 63 | 10.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | Bhausiya | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | j61 | j47 | 90 | 162.5 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
2 | j56 | j53 | 90 | 36 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
3 | j53 | j61 | 90 | 3.4 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
4 | j53 | j61 | 90 | 2.9 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
5 | j53 | j61 | 90 | 86.4 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
6 | j59 | j55 | 90 | 28.5 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
7 | j46 | j47 | 90 | 73.7 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
8 | j61 | j70 | 90 | 133.8 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
9 | j84 | j95 | 90 | 60.8 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
10 | j95 | j127 | 75 | 31 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
11 | j42 | j34 | 63 | 154.9 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
12 | j13 | j16 | 63 | 51.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
13 | j16 | j15 | 63 | 25 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
14 | j16 | j15 | 63 | 37.6 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
15 | j16 | j15 | 63 | 125 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
16 | j23 | j25 | 63 | 122.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
17 | j23a | j23b | 63 | 68 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
18 | j35 | j36 | 63 | 24.7 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
19 | j36 | j37 | 63 | 96.7 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
20 | j35 | j36 | 63 | 1.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
21 | j45 | j44 | 63 | 70.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
22 | j9 | j10 | 63 | 192 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
23 | j11 | j12 | 63 | 196 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
24 | j33 | j32 | 63 | 117 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
25 | j160 | j161 | 63 | 63.9 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
26 | j160 | j161 | 63 | 20 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
27 | j160 | j162 | 63 | 2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
28 | j160 | j162 | 63 | 173 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
29 | j162 | j184 | 63 | 116 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
30 | j184 | j181 | 63 | 95 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
31 | j184 | j181 | 63 | 34.7 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
32 | j181 | j182 | 63 | 10.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
33 | j182 | j179 | 63 | 2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
34 | j182 | j179 | 63 | 25.6 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
35 | j181 | j171 | 63 | 7 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
36 | j181 | j171 | 63 | 23 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
37 | j177 | j174 | 63 | 23 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
38 | j177 | j174 | 63 | 145.6 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
39 | j174 | j152 | 63 | 143 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
40 | j174 | j152 | 63 | 174 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
41 | j152 | j152(1) | 63 | 31 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
42 | j152 | j152(2) | 63 | 28.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
43 | j152 | j152(3) | 63 | 77 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
44 | j152 | j152(4) | 63 | 173.4 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
45 | j152 | j152(5) | 63 | 4 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
46 | j164 | j165 | 63 | 126.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
47 | j164 | j166 | 63 | 4 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
48 | j164 | j166 | 63 | 72.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
49 | j166 | j167 | 63 | 51.8 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
50 | j167 | j171 | 63 | 28.6 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
51 | j167 | j171 | 63 | 14.8 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
52 | j167 | j171 | 63 | 12.6 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
53 | j167 | j171 | 63 | 27.5 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
54 | j167 | j171 | 63 | 42 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
55 | j171 | j169 | 63 | 111.7 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
56 | j169 | j166 | 63 | 18 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
57 | j169 | j166 | 63 | 15.4 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | Bhausiya | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | j61 | j47 | 90 | 162.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
2 | j56 | j53 | 90 | 36 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
3 | j53 | j61 | 90 | 3.4 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
4 | j53 | j61 | 90 | 2.9 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
5 | j53 | j61 | 90 | 86.4 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
6 | j59 | j55 | 90 | 28.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
7 | j46 | j47 | 90 | 73.7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
8 | j61 | j70 | 90 | 133.8 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
9 | j5 | j6 | 90 | 542.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
10 | j95 | j127 | 75 | 171 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
11 | j127 | j139 | 75 | 333.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
12 | j2 | j13 | 63 | 156 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
13 | j13 | j14 | 63 | 42.9 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
14 | j11 | j12 | 63 | 196 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
15 | j33 | j32 | 63 | 117 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
16 | j9 | j10 | 63 | 192 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
17 | j136 | j137 | 63 | 202.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
18 | j136 | j140 | 63 | 96.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
19 | j140 | j143 | 63 | 40.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
20 | j143 | j141 | 63 | 41 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
21 | j141 | j138 | 63 | 38.4 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
22 | j141 | j138 | 63 | 9.8 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
23 | j143 | j144 | 63 | 29.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
24 | j133 | j134 | 63 | 42.7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
25 | j133 | j134 | 63 | 8.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
26 | j134 | j135 | 63 | 46 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
27 | j134 | j138 | 63 | 18.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
28 | j138 | j146 | 63 | 5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
29 | j138 | j146 | 63 | 48 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
30 | j138 | j146 | 63 | 63.8 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
31 | j156 | j163 | 63 | 103 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
32 | j163a | j163b | 63 | 26.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
33 | j163 | j173 | 63 | 175.8 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
34 | j182 | j183 | 63 | 46 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
35 | j182 | j183 | 63 | 21 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
36 | j95 | j102 | 63 | 50.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
37 | j2 | j13 | 63 | 156 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
38 | j13 | j14 | 63 | 42.9 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
39 | 171 | 172 | 63 | 169.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
40 | 171 | 172 | 63 | 3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
41 | 124 | 121 | 63 | 421.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
42 | 124 | 122 | 63 | 121.7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date