## bhausiya
GOVERNMENT OF UTTAR PRADESH
STATE WATER & SANITATION MISSION ( SWSM )
Joint Measurement Report of Pipe Line
Name of the Work :- Survey , Design Preparation of DPR , Construction , Commissioning and O&M for 10 Years of Various Rural Water Supply Projects in the state of Uttar Pradesh as Per Request for Proposal for Division " Prayagraj "
Name of the Agency : POWER MECH PROJECTS LIMITED – BHOORATHNOM CONSTRUCTIONS COMPANY PRIVATE LIMITED (JV), Hyderabad.
Name OF Scheme |  | : Bhausiya
Block |  | : Mangraura
Total Scope |  | :
JMR No. |  | : 1
Date of JMR |  | :
Sr. No. | Start Node | End Node | Dia | Pipe Length (as per Drawing) | Pipe Length (as per Site) | Width | Depth | Quantity | Type OF Road | Dismantling Length | Dismantling Width | Dismantling Quantity | Restoration Length | Restoration Width | Restoration Quantity | Restoration Status | Remark
1 | j55 | j56 | 63 | 40 | 37.4 | 0.363 | 1.063
2 | j68 | j63 | 63 | 43 | 38.7 | 0.363 | 1.063
3 | j68 | j69 | 63 | 13 | 17 | 0.363 | 1.063
4 | j69 | j76 | 63 | 124 | 127.3 | 0.363 | 1.063
5 | j76 | j78 | 63 |  | 71.2 | 0.363 | 1.063
6 | j69 | j66 | 63 | 108 | 60.5 | 0.363 | 1.063
7 | j68 | j74 | 63 | 86 | 95.1 | 0.363 | 1.063
8 | j68 | j74 | 63 |  | 1.5 | 0.363 | 1.063 | [9 empty] | culvert
9 | j74 | j64 | 63 | 158 | 110 | 0.363 | 1.063
10 | j74 | j78 | 63 | 52 | 59.1 | 0.363 | 1.063
11 | j78 | j82 | 63 | 79 | 72.2 | 0.363 | 1.063
12 | j82 | j86 | 63 | 31 | 25.1 | 0.363 | 1.063
13 | j86 | j88 | 63 | 48 | 50.7 | 0.363 | 1.063
14 | j88 | j90 | 63 | 33 | 29.7 | 0.363 | 1.063
15 | j88 | j89 | 63 | 35 | 35 | 0.363 | 1.063
16 | j89 | j90 | 63 |  | 3.4 | 0.363 | 1.063 | 1.312 | brick road | 3.4 | 0.363 | 1.2342 | 3.4 | 0.363 | 1.2342
17 | j90 | j91 | 63 |  | 15.4 | 0.363 | 1.063
18 | j91 | j96 | 63 | 121 | 69.5 | 0.363 | 1.063 | 26.8179 | brick road | 69.5 | 0.363 | 25.2285 | 69.5 | 0.363 | 25.2285
19 | j90 | j105 | 63 | 134 | 142.8 | 0.363 | 1.063
20 | j105 | j108 | 63 |  | 25.6 | 0.363 | 1.063
21 | j108 | j109 | 63 | 27 | 26.6 | 0.363 | 1.063
22 | j109 | j111 | 63 | 213 | 317.2 | 0.363 | 1.063
23 | j124 | j125 | 63 | 197 | 197 | 0.363 | 1.063
24 | j125 | j126 | 63 | 17 | 27.7 | 0.363 | 1.063
25 | j125 | j116 | 63 | 114 | 111.3 | 0.363 | 1.063
26 | j116 | j113 | 63 | 139 | 106.1 | 0.363 | 1.063
27 | j116 | j115 | 63 | 117 | 119.6 | 0.363 | 1.063
28 | j115 | j114 | 63 | 40 | 42.7 | 0.363 | 1.063
29 | j114 | j112 | 63 | 65 | 3 | 0.363 | 1.063
30 | j114 | j112 | 63 |  | 25 | 0.363 | 1.063 | 9.6467 | brick road | 25 | 0.363 | 9.075 | 25 | 0.363 | 9.075
31 | j114 | j112 | 63 |  | 31 | 0.363 | 1.063 | 11.9619 | brick road | 31 | 0.363 | 11.253 | 31 | 0.363 | 11.253
32 | j114 | j112 | 63 |  | 5 | 0.363 | 1.063 | 1.9293 | brick road | 5 | 0.363 | 1.815 | 5 | 0.363 | 1.815
33 | j112 | j113 | 63 | 16 | 17.5 | 0.363 | 1.063
34 | j113 | j104 | 63 | 25 | 21.4 | 0.363 | 1.063
35 | j104 | j102 | 63 | 16 | 15.8 | 0.363 | 1.063
36 | j114 | j75 | 63 | 229 | 130.7 | 0.363 | 1.063
37 | j114 | j75 | 63 |  | 32.3 | 0.363 | 1.063 | 12.4636 | brick road | 32.3 | 0.363 | 11.7249 | 32.3 | 0.363 | 11.7249
38 | j114 | j75 | 63 |  | 60.5 | 0.363 | 1.063 | 23.3451 | brick road | 60.5 | 0.363 | 21.9615 | 60.5 | 0.363 | 21.9615
39 | j114 | j75 | 63 |  | 6.3 | 0.363 | 1.063 | 2.431 | brick road | 6.3 | 0.363 | 2.2869 | 6.3 | 0.363 | 2.2869
40 | j70 | j71 | 63 | 16 | 9.8 | 0.363 | 1.063
41 | j71 | j72 | 63 | 70 | 50.7 | 0.363 | 1.063
42 | j71 | j73 | 63 | 185 | 224 | 0.363 | 1.063
43 | j70 | j128 | 63 | 319 | 300 | 0.363 | 1.063
44 | j128 | j136 | 63 | 349 | 367.1 | 0.363 | 1.063
45 | j128 | j133 | 63 | 263 | 264.3 | 0.363 | 1.063
46 | j133 | j131 | 63 | 148 | 147.1 | 0.363 | 1.063
47 | j131 | j132 | 63 | 74 | 74.7 | 0.363 | 1.063
48 | j131 | j84 | 63 | 596 | 581.3 | 0.363 | 1.063
49 | j139 | j147 | 63 | 55 | 56.8 | 0.363 | 1.063
50 | j147 | j153 | 63 | 80 | 86 | 0.363 | 1.063
51 | j153 | j159 | 63 | 25 | 23.1 | 0.363 | 1.063
52 | j159 | j158 | 63 | 59 | 49.9 | 0.363 | 1.063
53 | j159 | j160 | 63 | 69 | 36.9 | 0.363 | 1.063 | 14.2386 | brick road | 36.9 | 0.363 | 13.3947 | 36.9 | 0.363 | 13.3947
54 | j159 | j160 | 63 |  | 30 | 0.363 | 1.063 | 11.5761 | brick road | 30 | 0.363 | 10.89 | 30 | 0.363 | 10.89
55 | j174 | j173 | 63 | 102 | 102 | 0.363 | 1.063
56 | j173 | j175 | 63 | 141 | 150.3 | 0.363 | 1.063
57 | j175 | j178 | 63 | 42 | 43.8 | 0.363 | 1.063
58 | j178 | j177 | 63 | 75 | 28.7 | 0.363 | 1.063
59 | j178 | j177 | 63 |  | 10.5 | 0.363 | 1.063 | 4.0516 | brick road | 10.5 | 0.363 | 3.8115 | 10.5 | 0.363 | 3.8115
60 | j178 | j177 | 63 |  | 31 | 0.363 | 1.063
61 | j178 | j177 | 63 |  | 2.4 | 0.363 | 1.063 | 0.92609 | brick road | 2.4 | 0.363 | 0.8712 | 2.4 | 0.363 | 0.8712
62 | j152 | j147 | 63 | 461 | 236.8 | 0.363 | 1.063
63 | j152 | j127 | 63 | 374 | 299.2 | 0.363 | 1.063
64 | j127 | j126 | 63 | 185 | 190.6 | 0.363 | 1.063
65 | j126 | j129 | 63 | 87 | 83.9 | 0.363 | 1.063
66 | j129 | j150 | 63 | 280 | 287.4 | 0.363 | 1.063
67 | j150 | j151 | 63 | 46 | 3.3 | 0.363 | 1.063 | 1.2734 | brick road | 3.3 | 0.363 | 1.1979 | 3.3 | 0.363 | 1.1979
68 | j150 | j151 | 63 |  | 3.4 | 0.363 | 1.063 | 1.312 | brick road | 3.4 | 0.363 | 1.2342 | 3.4 | 0.363 | 1.2342
69 | j150 | j151 | 63 |  | 21.7 | 0.363 | 1.063 | 8.3734 | brick road | 21.7 | 0.363 | 7.8771 | 21.7 | 0.363 | 7.8771
70 | j151 | j155 | 63 | 39 | 25.1 | 0.363 | 1.063 | 9.6853 | brick road | 25.1 | 0.363 | 9.1113 | 25.1 | 0.363 | 9.1113
71 | j151 | j155 | 63 |  | 10.5 | 0.363 | 1.063 | 4.0516 | brick road | 10.5 | 0.363 | 3.8115 | 10.5 | 0.363 | 3.8115
72 | j160 | j161 | 63 | 96 | 63.9 | 0.363 | 1.063 | 24.657 | brick road | 63.9 | 0.363 | 23.1957 | 63.9 | 0.363 | 23.1957
73 | j160 | j161 | 63 |  | 20 | 0.363 | 1.063 | 7.7174 | brick road | 20 | 0.363 | 7.26 | 20 | 0.363 | 7.26
74 | j160 | j162 | 63 |  | 2 | 0.363 | 1.063 | 0.77174 | brick road | 2 | 0.363 | 0.726 | 2 | 0.363 | 0.726
75 | j160 | j162 | 63 | 150 | 173 | 0.363 | 1.063
76 | j162 | j184 | 63 |  | 116 | 0.363 | 1.063
77 | j184 | j181 | 63 | 134 | 95 | 0.363 | 1.063
78 | j184 | j181 | 63 |  | 34.7 | 0.363 | 1.063 | 13.3897 | brick road | 34.7 | 0.363 | 12.5961 | 34.7 | 0.363 | 12.5961
79 | j181 | j182 | 63 | 23 | 10.3 | 0.363 | 1.063
80 | j182 | j179 | 63 | 65 | 2 | 0.363 | 1.063 | 0.77174 | brick road | 2 | 0.363 | 0.726 | 2 | 0.363 | 0.726
81 | j182 | j179 | 63 |  | 25.6 | 0.363 | 1.063
82 | j181 | j171 | 63 | 38 | 7 | 0.363 | 1.063 | 2.7011 | brick road | 7 | 0.363 | 2.541 | 7 | 0.363 | 2.541
83 | j181 | j171 | 63 |  | 23 | 0.363 | 1.063 | 8.875 | brick road | 23 | 0.363 | 8.349 | 23 | 0.363 | 8.349
84 | j177 | j174 | 63 | 139 | 23 | 0.363 | 1.063 | 8.875 | brick road | 23 | 0.363 | 8.349 | 23 | 0.363 | 8.349
85 | j177 | j174 | 63 |  | 145.6 | 0.363 | 1.063 | 56.1825 | brick road | 145.6 | 0.363 | 52.8528 | 145.6 | 0.363 | 52.8528
86 | j174 | j152 | 63 | 351 | 143 | 0.363 | 1.063 | 55.1793 | brick road | 143 | 0.363 | 51.909 | 143 | 0.363 | 51.909
87 | j174 | j152 | 63 |  | 174 | 0.363 | 1.063 | 67.1412 | brick road | 174 | 0.363 | 63.162 | 174 | 0.363 | 63.162
88 | j152 | j152(1) | 63 |  | 31 | 0.363 | 1.063 | 11.9619 | brick road | 31 | 0.363 | 11.253 | 31 | 0.363 | 11.253
89 | j152 | j152(2) | 63 |  | 28.2 | 0.363 | 1.063
90 | j152 | j152(3) | 63 |  | 77 | 0.363 | 1.063
91 | j152 | j152(4) | 63 |  | 173.4 | 0.363 | 1.063
92 | j152 | j152(5) | 63 |  | 4 | 0.363 | 1.063 | 1.5435 | b.t road | 4 | 0.363 | 1.452
93 | j164 | j165 | 63 | 142 | 126.1 | 0.363 | 1.063
94 | j164 | j166 | 63 | 72 | 4 | 0.363 | 1.063 | 1.5435 | brick road | 4 | 0.363 | 1.452 | 4 | 0.363 | 1.452
95 | j164 | j166 | 63 |  | 72.3 | 0.363 | 1.063
96 | j166 | j167 | 63 | 49 | 51.8 | 0.363 | 1.063
97 | j167 | j171 | 63 | 99 | 28.6 | 0.363 | 1.063
98 | j167 | j171 | 63 |  | 14.8 | 0.363 | 1.063 | 5.7109 | brick road | 14.8 | 0.363 | 5.3724 | 14.8 | 0.363 | 5.3724
99 | j167 | j171 | 63 |  | 12.6 | 0.363 | 1.063
100 | j167 | j171 | 63 |  | 27.5 | 0.363 | 1.063 | 10.6114 | brick road | 27.5 | 0.363 | 9.9825 | 27.5 | 0.363 | 9.9825
101 | j167 | j171 | 63 |  | 42 | 0.363 | 1.063 | 16.2065 | brick road | 42 | 0.363 | 15.246 | 42 | 0.363 | 15.246
102 | j171 | j169 | 63 | 107 | 111.7 | 0.363 | 1.063
103 | j169 | j166 | 63 | 34 | 18 | 0.363 | 1.063 | 6.9456 | brick road | 18 | 0.363 | 6.534 | 18 | 0.363 | 6.534
104 | j169 | j166 | 63 |  | 15.4 | 0.363 | 1.063
105 | 171 | 172 | 63 |  | 169.1 | 0.363 | 1.063
106 | 171 | 172 | 63 |  | 3 | 0.363 | 1.063 | 1.1576 | brick road | 3 | 0.363 | 1.089 | 3 | 0.363 | 1.089
107 | 124 | 121 | 63 | 367 | 421.3 | 0.363 | 1.063
108 | 124 | 122 | 63 | 115 | 121.7 | 0.363 | 1.063
109 | j95 | j127 | 75 | 195 | 171 | 0.375 | 1.075
110 | j127 | j139 | 75 | 326 | 333.2 | 0.375 | 1.075
111 | j61 | j47 | 90 | 154 | 162.5 | 0.39 | 1.09
112 | j56 | j53 | 90 | 41 | 36 | 0.39 | 1.09
113 | j53 | j61 | 90 | 85 | 3.4 | 0.39 | 1.09
114 | j53 | j61 | 90 |  | 2.9 | 0.39 | 1.09 | [9 empty] | culvert
115 | j53 | j61 | 90 |  | 86.4 | 0.39 | 1.09
116 | j59 | j55 | 90 | 28 | 28.5 | 0.39 | 1.09
117 | j46 | j47 | 90 | 79 | 73.7 | 0.39 | 1.09
118 | j61 | j70 | 90 | 122 | 133.8 | 0.39 | 1.09
119 | j75 | j62 | 125 | 66 | 60.6 | 0.425 | 1.125 | 28.9744 | brick road | 60.6 | 0.425 | 25.755 | 60.6 | 0.425 | 25.755
120 | j62 | j46 | 125 | 46 | 44.3 | 0.425 | 1.125
121 | j2 | j13 | 63 | 166 | 156 | 0.363 | 1.063
122 | j13 | j14 | 63 | 48 | 42.9 | 0.363 | 1.063
123 | j11 | j12 | 63 | 137 | 196 | 0.363 | 1.063
124 | j33 | j32 | 63 | 118 | 117 | 0.363 | 1.063
125 | j9 | j10 | 63 | 39 | 192 | 0.363 | 1.063
126 | j136 | j137 | 63 | 27 | 202.3 | 0.363 | 1.063
127 | j136 | j140 | 63 | 85 | 96.3 | 0.363 | 1.063
128 | j140 | j143 | 63 | 50 | 40.3 | 0.363 | 1.063 | 15.5505 | brick road | 40.3 | 0.363 | 14.6289 | 40.3 | 0.363 | 14.6289
129 | j143 | j141 | 63 | 40 | 41 | 0.363 | 1.063
130 | j141 | j138 | 63 | 98 | 38.4 | 0.363 | 1.063 | 14.8174 | brick road | 38.4 | 0.363 | 13.9392 | 38.4 | 0.363 | 13.9392
131 | j141 | j138 | 63 |  | 9.8 | 0.363 | 1.063
132 | j143 | j144 | 63 |  | 29.6 | 0.363 | 1.063
133 | j133 | j134 | 63 | 45 | 42.7 | 0.363 | 1.063
134 | j133 | j134 | 63 |  | 8.5 | 0.363 | 1.063 | 3.2799 | b.t road | 8.5 | 0.363 | 3.0855
135 | j134 | j135 | 63 | 28 | 46 | 0.363 | 1.063
136 | j134 | j138 | 63 | 18 | 18.6 | 0.363 | 1.063
137 | j138 | j146 | 63 | 159 | 5 | 0.363 | 1.063 | 1.9293 | brick road | 5 | 0.363 | 1.815 | 5 | 0.363 | 1.815
138 | j138 | j146 | 63 |  | 48 | 0.363 | 1.063 | 18.5217 | brick road | 48 | 0.363 | 17.424 | 48 | 0.363 | 17.424
139 | j138 | j146 | 63 |  | 63.8 | 0.363 | 1.063
140 | j156 | j163 | 63 | 94 | 103 | 0.363 | 1.063
141 | j163a | j163b | 63 |  | 26.6 | 0.363 | 1.063
142 | j163 | j173 | 63 | 193 | 175.8 | 0.363 | 1.063
143 | j182 | j183 | 63 |  | 46 | 0.363 | 1.063 | 17.75 | brick road | 46 | 0.363 | 16.698 | 46 | 0.363 | 16.698
144 | j182 | j183 | 63 |  | 21 | 0.363 | 1.063
145 | j95 | j102 | 63 | 72 | 50.2 | 0.363 | 1.063
146 | j2 | j13 | 63 | 166 | 156 | 0.363 | 1.063
147 | j13 | j14 | 63 | 48 | 42.9 | 0.363 | 1.063
148 | j14 | j5 | 140 | 181 | 184.3 | 0.44 | 1.14 | 92.4449 | b.t road | 184.3 | 0.44 | 81.092
149 | j5 | j6 | 90 | 543 | 542.6 | 0.39 | 1.09 | 230.6593 | b.t road | 542.6 | 0.39 | 211.614
150 | j5 | j2 | 160 | 57 | 53.2 | 0.46 | 1.16
151 | j2 | j1 | 160 | 38 | 71.6 | 0.46 | 1.16
152 | j1 | j3 | 160 | 69 | 37.7 | 0.46 | 1.16
153 | j1 | oht | 160 | 23 | 23 | 0.46 | 1.16
154 | j3 | j4 | 160 | 52 | 49 | 0.46 | 1.16
155 | j7 | j9 | 160 | 56 | 60 | 0.46 | 1.16
156 | j9 | j10 | 63 | 39 | 192 | 0.363 | 1.063
157 | j9 | j11 | 160 | 87 | 87.8 | 0.46 | 1.16
158 | j11 | j12 | 63 | 137 | 196 | 0.363 | 1.063
159 | j11 | j15 | 140 | 35 | 35.2 | 0.44 | 1.14
160 | j15 | j33 | 140 | 145 | 143 | 0.44 | 1.14
161 | j33 | j32 | 63 | 118 | 117 | 0.363 | 1.063
162 | j33 | j42 | 140 | 180 | 185.4 | 0.44 | 1.14
163 | j42 | j46 | 140 | 69 | 9 | 0.44 | 1.14 | 4.5144 | cc | 9 | 0.44 | 3.96 | 9 | 0.44 | 3.96
164 | j42 | j46 | 140 |  | 66.8 | 0.44 | 1.14 | 33.5069 | brick road | 66.8 | 0.44 | 29.392 | 66.8 | 0.44 | 29.392
165 | j75 | j79 | 125 | 75 | 155 | 0.425 | 1.125 | 74.1094 | interlocking | 150 | 0.46 | 69 | 150 | 0.46 | 69
166 | j79 | j81 | 125 | 70 |  | 0.425 | 1.125
167 | j81 | j84 | 125 | 64 | 64.5 | 0.425 | 1.125 | 30.8391 | brick road | 61.5 | 0.425 | 26.1375 | 61.5 | 0.425 | 26.1375
168 | j84 | j95 | 90 | 62 | 60.8 | 0.39 | 1.09 | 25.8461 | brick road | 60.8 | 0.39 | 23.712 | 60.8 | 0.39 | 23.712
169 | j95 | j127 | 75 | 195 | 31 | 0.375 | 1.075
170 | j42 | j34 | 63 | 223 | 154.9 | 0.363 | 1.063
171 | j13 | j16 | 63 | 47 | 51.2 | 0.363 | 1.063
172 | j16 | j15 | 63 | 188 | 25 | 0.363 | 1.063
173 | j16 | j15 | 63 |  | 37.6 | 0.363 | 1.063 | 14.5087 | brick road | 37.6 | 0.363 | 13.6488 | 37.6 | 0.363 | 13.6488
174 | j16 | j15 | 63 |  | 125 | 0.363 | 1.063
175 | j14 | j17 | 140 | 81 | 84 | 0.44 | 1.14
176 | j17 | j23 | 140 | 58 | 73.8 | 0.44 | 1.14
177 | j23 | j25 | 63 | 113 | 122.3 | 0.363 | 1.063
178 | j23 | j28 | 140 |  | 2 | 0.44 | 1.14 |  | culvert
179 | j23 | j28 | 140 | 138 | 109.5 | 0.44 | 1.14
180 | j23a | j23b | 63 |  | 68 | 0.363 | 1.063
181 | j28 | j35 | 140 | 114 | 135.5 | 0.44 | 1.14
182 | j35 | j36 | 63 |  | 24.7 | 0.363 | 1.063
183 | j36 | j37 | 63 |  | 96.7 | 0.363 | 1.063
184 | j35 | j36 | 63 |  | 1.3 | 0.363 | 1.063 |  | culvert
185 | j35 | j38 | 110 | 122 | 134.3 | 0.41 | 1.11
186 | j43 | j45 | 110 | 109 | 83.2 | 0.41 | 1.11
187 | j45 | j44 | 63 | 73 | 70.2 | 0.363 | 1.063
188 | j45 | j48 | 110 | 37 | 58 | 0.41 | 1.11
189 | j48 | j55 | 90 |  | 31.7 | 0.39 | 1.09
190 | j48 | j49 | 63 | 13 | 9 | 0.363 | 1.063
191 | j49 | j50 | 63 | 97 | 98.3 | 0.363 | 1.063
192 | j50 | j51 | 63 | 22 | 19 | 0.363 | 1.063
193 | j51 | j60 | 63 | 40 | 43.1 | 0.363 | 1.063
194 | j60 | j49 | 63 | 95 | 98 | 0.363 | 1.063
195 | j60 | j64 | 63 | 81 | 47 | 0.363 | 1.063
196 | j51 | 52 | 63 | 32 | 90.6 | 0.363 | 1.063
197 | j64 | j65 | 63 | 93 | 97 | 0.363 | 1.063
198 | j65a | j65b | 63 |  | 93.5 | 0.363 | 1.063
199 | j146 | j149 | 63 |  | 25 | 0.363 | 1.063
200 | j149 | j163 | 63 |  | 106 | 0.363 | 1.063
201 | j42 | j34 | 63 |  | 46 | 0.363 | 1.063
202 | j16 | j18 | 63 |  | 40 | 0.363 | 1.063 | 15.4348 | interlocking | 40 | 0.46 | 18.4 | 40 | 0.46 | 18.4
203 | j18 | j24 | 63 |  | 52 | 0.363 | 1.063 | 20.0652 | interlocking | 52 | 0.46 | 23.92 | 52 | 0.46 | 23.92
204 | j24 | 25 | 63 |  | 58 | 0.363 | 1.063 | 22.3804 | brick road | 58 | 0.363 | 21.054 | 58 | 0.363 | 21.054 |  |  | 649.942
205 | j26 | j30 | 63 |  | 78 | 0.363 | 1.063 | 30.0978 | brick road | 78 | 0.363 | 28.314 | 78 | 0.363 | 28.314
111.32
Total |  |  |  | 15285 | 16834.1 |  |  | 1142.5679 |  | 2746.7 |  | 1064.4158 | 2007.3 |  | 767.1723
|  | Representative PMPL - BRCCPL (JV) Pratapgarh |  |  |  |  | Representative Medhaj Techno Concept Pvt Ltd (TPI) Pratapgarh |  |  |  |  | Representative UP Jal Nigam (Rural) Pratapgarh | [6 empty] | 231
[19 empty] | 51975 | 10395
|  |  | 63 | 63 | 75 | 90 | 110 | 125 | 140 | 160 | [8 empty] | 24520 | 4904
|  |  | 13125.9 | 13125.9 | 535.2 | 1162.3 | 275.5 | 324.4 | 1028.5 | 382.3 | 16834.1 | [7 empty] | 76495 | 15299 | 61196

## RESTORATION
GOVERNMENT OF UTTAR PRADESH
STATE WATER & SANITATION MISSION ( SWSM )
Joint Measurement Report of Pipe Line
Name of the Work :- Survey , Design Preparation of DPR , Construction , Commissioning and O&M for 10 Years of Various Rural Water Supply Projects in the state of Uttar Pradesh as Per Request for Proposal for Division " Prayagraj "
Name of the Agency : POWER MECH PROJECTS LIMITED – BHOORATHNOM CONSTRUCTIONS COMPANY PRIVATE LIMITED (JV), Hyderabad.
Name OF Scheme |  | : Bhausiya
Block |  | : Mangraura
Total Scope |  | :
JMR No. |  | : 1
Date of JMR |  | :
Sr. No. | Start Node | End Node | Dia | Pipe Length (as per Drawing) | Pipe Length (as per Site) | Width | Depth | Quantity | Type OF Road | Dismantling Length | Dismantling Width | Dismantling Quantity | Restoration Length | Restoration Width | Restoration Quantity | Restoration Status | Remark
1 | j89 | j90 | 63 | 3.4 | 0.363 | 1.063 | 1.312 | brick road | 3.4 | 0.363 | 1.2342 | 3.4 | 0.363 | 1.2342 |  |  | DONE
2 | j91 | j96 | 63 | 69.5 | 0.363 | 1.063 | 26.8179 | brick road | 69.5 | 0.363 | 25.2285 | 69.5 | 0.363 | 25.2285 |  |  | DONE
3 | j114 | j112 | 63 | 25 | 0.363 | 1.063 | 9.6467 | brick road | 25 | 0.363 | 9.075 | 25 | 0.363 | 9.075 |  |  | DONE
4 | j114 | j112 | 63 | 31 | 0.363 | 1.063 | 11.9619 | brick road | 31 | 0.363 | 11.253 | 31 | 0.363 | 11.253 |  |  | DONE
5 | j114 | j112 | 63 | 5 | 0.363 | 1.063 | 1.9293 | brick road | 5 | 0.363 | 1.815 | 5 | 0.363 | 1.815 |  |  | DONE
6 | j114 | j75 | 63 | 32.3 | 0.363 | 1.063 | 12.4636 | brick road | 32.3 | 0.363 | 11.7249 | 32.3 | 0.363 | 11.7249 |  |  | DONE
7 | j114 | j75 | 63 | 60.5 | 0.363 | 1.063 | 23.3451 | brick road | 60.5 | 0.363 | 21.9615 | 60.5 | 0.363 | 21.9615 |  |  | DONE
8 | j114 | j75 | 63 | 6.3 | 0.363 | 1.063 | 2.431 | brick road | 6.3 | 0.363 | 2.2869 | 6.3 | 0.363 | 2.2869 |  |  | DONE
9 | j159 | j160 | 63 | 36.9 | 0.363 | 1.063 | 14.2386 | brick road | 36.9 | 0.363 | 13.3947 | 36.9 | 0.363 | 13.3947 |  |  | DONE
10 | j159 | j160 | 63 | 30 | 0.363 | 1.063 | 11.5761 | brick road | 30 | 0.363 | 10.89 | 30 | 0.363 | 10.89 |  |  | DONE
11 | j178 | j177 | 63 | 10.5 | 0.363 | 1.063 | 4.0516 | brick road | 10.5 | 0.363 | 3.8115 | 10.5 | 0.363 | 3.8115 |  |  | DONE
12 | j178 | j177 | 63 | 2.4 | 0.363 | 1.063 | 0.92609 | brick road | 2.4 | 0.363 | 0.8712 | 2.4 | 0.363 | 0.8712 |  |  | DONE
13 | j150 | j151 | 63 | 3.3 | 0.363 | 1.063 | 1.2734 | brick road | 3.3 | 0.363 | 1.1979 | 3.3 | 0.363 | 1.1979 |  |  | DONE
14 | j150 | j151 | 63 | 3.4 | 0.363 | 1.063 | 1.312 | brick road | 3.4 | 0.363 | 1.2342 | 3.4 | 0.363 | 1.2342 |  |  | DONE
15 | j150 | j151 | 63 | 21.7 | 0.363 | 1.063 | 8.3734 | brick road | 21.7 | 0.363 | 7.8771 | 21.7 | 0.363 | 7.8771 |  |  | DONE
16 | j151 | j155 | 63 | 25.1 | 0.363 | 1.063 | 9.6853 | brick road | 25.1 | 0.363 | 9.1113 | 25.1 | 0.363 | 9.1113 |  |  | DONE
17 | j151 | j155 | 63 | 10.5 | 0.363 | 1.063 | 4.0516 | brick road | 10.5 | 0.363 | 3.8115 | 10.5 | 0.363 | 3.8115 |  |  | DONE
18 | j160 | j161 | 63 | 63.9 | 0.363 | 1.063 | 24.657 | brick road | 63.9 | 0.363 | 23.1957 | 63.9 | 0.363 | 23.1957 |  |  | DONE
19 | j160 | j161 | 63 | 20 | 0.363 | 1.063 | 7.7174 | brick road | 20 | 0.363 | 7.26 | 20 | 0.363 | 7.26 |  |  | DONE
20 | j160 | j162 | 63 | 2 | 0.363 | 1.063 | 0.77174 | brick road | 2 | 0.363 | 0.726 | 2 | 0.363 | 0.726 |  |  | DONE
21 | j184 | j181 | 63 | 34.7 | 0.363 | 1.063 | 13.3897 | brick road | 34.7 | 0.363 | 12.5961 | 34.7 | 0.363 | 12.5961 |  |  | DONE
22 | j182 | j179 | 63 | 2 | 0.363 | 1.063 | 0.77174 | brick road | 2 | 0.363 | 0.726 | 2 | 0.363 | 0.726 |  |  | DONE
23 | j181 | j171 | 63 | 7 | 0.363 | 1.063 | 2.7011 | brick road | 7 | 0.363 | 2.541 | 7 | 0.363 | 2.541 |  |  | DONE
24 | j181 | j171 | 63 | 23 | 0.363 | 1.063 | 8.875 | brick road | 23 | 0.363 | 8.349 | 23 | 0.363 | 8.349 |  |  | DONE
25 | j177 | j174 | 63 | 23 | 0.363 | 1.063 | 8.875 | brick road | 23 | 0.363 | 8.349 | 23 | 0.363 | 8.349 |  |  | DONE
26 | j177 | j174 | 63 | 145.6 | 0.363 | 1.063 | 56.1825 | brick road | 145.6 | 0.363 | 52.8528 | 145.6 | 0.363 | 52.8528 |  |  | DONE
27 | j174 | j152 | 63 | 143 | 0.363 | 1.063 | 55.1793 | brick road | 143 | 0.363 | 51.909 | 143 | 0.363 | 51.909 |  |  | DONE
28 | j174 | j152 | 63 | 174 | 0.363 | 1.063 | 67.1412 | brick road | 174 | 0.363 | 63.162 | 174 | 0.363 | 63.162 |  |  | DONE
29 | j152 | j152(1) | 63 | 31 | 0.363 | 1.063 | 11.9619 | brick road | 31 | 0.363 | 11.253 | 31 | 0.363 | 11.253 |  |  | DONE
30 | j152 | j152(5) | 63 | 4 | 0.363 | 1.063 | 1.5435 | b.t road | 4 | 0.363 | 1.452 | [5 empty] | DONE
31 | j164 | j166 | 63 | 4 | 0.363 | 1.063 | 1.5435 | brick road | 4 | 0.363 | 1.452 | 4 | 0.363 | 1.452 |  |  | DONE
32 | j167 | j171 | 63 | 14.8 | 0.363 | 1.063 | 5.7109 | brick road | 14.8 | 0.363 | 5.3724 | 14.8 | 0.363 | 5.3724 |  |  | DONE
33 | j167 | j171 | 63 | 27.5 | 0.363 | 1.063 | 10.6114 | brick road | 27.5 | 0.363 | 9.9825 | 27.5 | 0.363 | 9.9825 |  |  | DONE
34 | j167 | j171 | 63 | 42 | 0.363 | 1.063 | 16.2065 | brick road | 42 | 0.363 | 15.246 | 42 | 0.363 | 15.246 |  |  | DONE
35 | j169 | j166 | 63 | 18 | 0.363 | 1.063 | 6.9456 | brick road | 18 | 0.363 | 6.534 | 18 | 0.363 | 6.534 |  |  | DONE
36 | 171 | 172 | 63 | 3 | 0.363 | 1.063 | 1.1576 | brick road | 3 | 0.363 | 1.089 | 3 | 0.363 | 1.089 |  |  | DONE
37 | j75 | j62 | 125 | 60.6 | 0.425 | 1.125 | 28.9744 | brick road | 60.6 | 0.425 | 25.755 | 60.6 | 0.425 | 25.755 |  |  | DONE
38 | j140 | j143 | 63 | 40.3 | 0.363 | 1.063 | 15.5505 | brick road | 40.3 | 0.363 | 14.6289 | 40.3 | 0.363 | 14.6289 |  |  | DONE
39 | j141 | j138 | 63 | 38.4 | 0.363 | 1.063 | 14.8174 | brick road | 38.4 | 0.363 | 13.9392 | 38.4 | 0.363 | 13.9392 |  |  | DONE
40 | j133 | j134 | 63 | 8.5 | 0.363 | 1.063 | 3.2799 | b.t road | 8.5 | 0.363 | 3.0855 | [5 empty] | DONE
41 | j138 | j146 | 63 | 5 | 0.363 | 1.063 | 1.9293 | brick road | 5 | 0.363 | 1.815 | 5 | 0.363 | 1.815 |  |  | DONE
42 | j138 | j146 | 63 | 48 | 0.363 | 1.063 | 18.5217 | brick road | 48 | 0.363 | 17.424 | 48 | 0.363 | 17.424 |  |  | DONE
43 | j182 | j183 | 63 | 46 | 0.363 | 1.063 | 17.75 | brick road | 46 | 0.363 | 16.698 | 46 | 0.363 | 16.698 |  |  | DONE
44 | j14 | j5 | 140 | 184.3 | 0.44 | 1.14 | 92.4449 | b.t road | 184.3 | 0.44 | 81.092 | [5 empty] | DONE
45 | j5 | j6 | 90 | 542.6 | 0.39 | 1.09 | 230.6593 | b.t road | 542.6 | 0.39 | 211.614 | [5 empty] | DONE
46 | j42 | j46 | 140 | 9 | 0.44 | 1.14 | 4.5144 | cc | 9 | 0.44 | 3.96 | 9 | 0.44 | 3.96 |  |  | DONE
47 | j42 | j46 | 140 | 66.8 | 0.44 | 1.14 | 33.5069 | brick road | 66.8 | 0.44 | 29.392 | 66.8 | 0.44 | 29.392 |  |  | DONE
48 | j75 | j79 | 125 | 155 | 0.425 | 1.125 | 74.1094 | interlocking | 150 | 0.46 | 69 | 150 | 0.46 | 69 |  |  | DONE
49 | j81 | j84 | 125 | 64.5 | 0.425 | 1.125 | 30.8391 | brick road | 61.5 | 0.425 | 26.1375 | 61.5 | 0.425 | 26.1375 |  |  | DONE
50 | j84 | j95 | 90 | 60.8 | 0.39 | 1.09 | 25.8461 | brick road | 60.8 | 0.39 | 23.712 | 60.8 | 0.39 | 23.712 |  |  | DONE
51 | j16 | j15 | 63 | 37.6 | 0.363 | 1.063 | 14.5087 | brick road | 37.6 | 0.363 | 13.6488 | 37.6 | 0.363 | 13.6488 |  |  | DONE
52 | j16 | j18 | 63 | 40 | 0.363 | 1.063 | 15.4348 | interlocking | 40 | 0.46 | 18.4 | 40 | 0.46 | 18.4 |  |  | DONE
53 | j18 | j24 | 63 | 52 | 0.363 | 1.063 | 20.0652 | interlocking | 52 | 0.46 | 23.92 | 52 | 0.46 | 23.92 |  |  | DONE
54 | j24 | 25 | 63 | 58 | 0.363 | 1.063 | 22.3804 | brick road | 58 | 0.363 | 21.054 | 58 | 0.363 | 21.054 |  |  | DONE
55 | j26 | j30 | 63 | 78 | 0.363 | 1.063 | 30.0978 | brick road | 78 | 0.363 | 28.314 | 78 | 0.363 | 28.314 |  |  | DONE