## BHAIDPUR HYDRO
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | bhaidpur | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | J12 | J10 | 160 | 129.1 | 5.5 | 3.3 | 1 | 4.3 | NO
2 | J12 | J10 | 160 | 4 | 5.5 | 3.3 | 1 | 4.3 | NO
3 | J10 | J11 | 160 | 122.1 | 5.5 | 3.3 | 1 | 4.3 | NO
4 | J10 | J11 | 160 | 3 | 5.5 | 3.3 | 1 | 4.3 | NO
5 | J60 | J91 | 140 | 377.4 | 5.5 | 3.3 | 1 | 4.3 | NO
6 | J60 | J91 | 140 | 5.6 | 5.5 | 3.3 | 1 | 4.3 | NO
7 | J60 | J91 | 140 | 159.2 | 5.5 | 3.3 | 1 | 4.3 | NO
8 | J7 | J5 | 63 | 88 | 5.5 | 3.3 | 1 | 4.3 | NO
9 | J3 | J4 | 63 | 86.6 | 5.5 | 3.3 | 1 | 4.3 | NO
10 | j93 | j95 | 63 | 33.6 | 5.5 | 3.3 | 1 | 4.3 | NO
11 | J93 | J105A | 63 | 95.6 | 5.5 | 3.3 | 1 | 4.3 | NO
12 | J105A | J105B | 63 | 97.1 | 5.5 | 3.3 | 1 | 4.3 | NO
13 | J129 | J130A | 63 | 24.9 | 5.5 | 3.3 | 1 | 4.3 | NO
14 | J130A | J130 | 63 | 15.7 | 5.5 | 3.3 | 1 | 4.3 | NO
15 | J130 | J132(1) | 63 | 12.9 | 5.5 | 3.3 | 1 | 4.3 | NO
16 | J132(1) | J132(2) | 63 | 38.8 | 5.5 | 3.3 | 1 | 4.3 | NO
17 | J132(1) | J132 | 63 | 36.6 | 5.5 | 3.3 | 1 | 4.3 | NO
18 | J136 | J137 | 63 | 31.3 | 5.5 | 3.3 | 1 | 4.3 | NO
19 | J8 | J9 | 63 | 166.8 | 5.5 | 3.3 | 1 | 4.3 | NO
20 | J94A | J94B | 63 | 46.1 | 5.5 | 3.3 | 1 | 4.3 | NO
21 | J13A | J13B | 63 | 37.7 | 5.5 | 3.3 | 1 | 4.3 | NO
22 | J25 | J26 | 63 | 14.1 | 5.5 | 3.3 | 1 | 4.3 | NO
23 | J39A | J40 | 63 | 67.2 | 5.5 | 3.3 | 1 | 4.3 | NO
24 | J39A | J40 | 63 | 11.2 | 5.5 | 3.3 | 1 | 4.3 | NO
25 | J44 | J55 | 63 | 241.2 | 5.5 | 3.3 | 1 | 4.3 | NO
26 | J57 | J62 | 63 | 3 | 5.5 | 3.3 | 1 | 4.3 | NO
27 | J57 | J62 | 63 | 166.1 | 5.5 | 3.3 | 1 | 4.3 | NO
28 | J57 | J63 | 63 | 19.7 | 5.5 | 3.3 | 1 | 4.3 | NO
29 | J63 | J77 | 63 | 57.4 | 5.5 | 3.3 | 1 | 4.3 | NO
30 | J77 | J78 | 63 | 48.8 | 5.5 | 3.3 | 1 | 4.3 | NO
31 | J77 | J84 | 63 | 59.8 | 5.5 | 3.3 | 1 | 4.3 | NO
32 | J84 | J84A | 63 | 2.7 | 5.5 | 3.3 | 1 | 4.3 | NO
33 | J84A | J85 | 63 | 155.8 | 5.5 | 3.3 | 1 | 4.3 | NO
34 | J84A | J88 | 63 | 470.2 | 5.5 | 3.3 | 1 | 4.3 | NO
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | bhaidpur | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | J1 | J8 | 160 | 102.8 | 5(kg/cm'2) | 3 | 1 | 4 | NO
2 | J8 | J10 | 160 | 143.1 | 5(kg/cm'2) | 3 | 1 | 4 | NO
3 | J10 | J60 | 160 | 157.8 | 5(kg/cm'2) | 3 | 1 | 4 | NO
4 | J17 | J12 | 125 | 118.7 | 5(kg/cm'2) | 3 | 1 | 4 | NO
5 | J12 | J28 | 125 | 3 | 5(kg/cm'2) | 3 | 1 | 4 | NO
6 | J12 | J28 | 125 | 1.7 | 5(kg/cm'2) | 3 | 1 | 4 | NO
7 | J11 | J13A | 110 | 68.2 | 5(kg/cm'2) | 3 | 1 | 4 | NO
8 | J13A | J25 | 110 | 45.1 | 5(kg/cm'2) | 3 | 1 | 4 | NO
9 | J25 | J34 | 110 | 93.5 | 5(kg/cm'2) | 3 | 1 | 4 | NO
10 | J34 | J39 | 110 | 63 | 5(kg/cm'2) | 3 | 1 | 4 | NO
11 | J94 | J116 | 75 | 63.2 | 5(kg/cm'2) | 3 | 1 | 4 | NO
12 | J129A | J129 | 75 | 157.7 | 5(kg/cm'2) | 3 | 1 | 4 | NO
13 | J129A | J129 | 75 | 13.4 | 5(kg/cm'2) | 3 | 1 | 4 | NO
14 | J68 | J65 | 63 | 74.1 | 5(kg/cm'2) | 3 | 1 | 4 | NO
15 | J68 | J65 | 63 | 5.2 | 5(kg/cm'2) | 3 | 1 | 4 | NO
16 | J68 | J65 | 63 | 141.8 | 5(kg/cm'2) | 3 | 1 | 4 | NO
17 | J65 | J17 | 63 | 98.9 | 5(kg/cm'2) | 3 | 1 | 4 | NO
18 | J17 | J21A | 63 | 11.2 | 5(kg/cm'2) | 3 | 1 | 4 | NO
19 | J17 | J21A | 63 | 122.5 | 5(kg/cm'2) | 3 | 1 | 4 | NO
20 | J21B | J22 | 63 | 109.8 | 5(kg/cm'2) | 3 | 1 | 4 | NO
21 | J21B | J22 | 63 | 24.9 | 5(kg/cm'2) | 3 | 1 | 4 | NO
22 | J21A | J21B | 63 | 19.8 | 5(kg/cm'2) | 3 | 1 | 4 | NO
23 | J11 | J27 | 63 | 73.1 | 5(kg/cm'2) | 3 | 1 | 4 | NO
24 | J11 | J27 | 63 | 3.2 | 5(kg/cm'2) | 3 | 1 | 4 | NO
25 | J27 | J49 | 63 | 43.2 | 5(kg/cm'2) | 3 | 1 | 4 | NO
26 | J27 | J49 | 63 | 6.9 | 5(kg/cm'2) | 3 | 1 | 4 | NO
27 | J27 | J36 | 63 | 140.9 | 5(kg/cm'2) | 3 | 1 | 4 | NO
28 | J34 | J36 | 63 | 108.1 | 5(kg/cm'2) | 3 | 1 | 4 | NO
29 | J34 | J36 | 63 | 1.8 | 5(kg/cm'2) | 3 | 1 | 4 | NO
30 | J36 | J47 | 63 | 60.1 | 5(kg/cm'2) | 3 | 1 | 4 | NO
31 | J47 | J52 | 63 | 33.4 | 5(kg/cm'2) | 3 | 1 | 4 | NO
32 | J52 | J63 | 63 | 7.4 | 5(kg/cm'2) | 3 | 1 | 4 | NO
33 | J52 | J63 | 63 | 49.6 | 5(kg/cm'2) | 3 | 1 | 4 | NO
34 | J52 | J53 | 63 | 2.4 | 5(kg/cm'2) | 3 | 1 | 4 | NO
35 | J52 | J53 | 63 | 62.8 | 5(kg/cm'2) | 3 | 1 | 4 | NO
36 | J53 | J53A | 63 | 11.4 | 5(kg/cm'2) | 3 | 1 | 4 | NO
37 | J53 | J53B | 63 | 15.5 | 5(kg/cm'2) | 3 | 1 | 4 | NO
38 | J47 | J42 | 63 | 100.6 | 5(kg/cm'2) | 3 | 1 | 4 | NO
39 | J42 | J49 | 63 | 58.7 | 5(kg/cm'2) | 3 | 1 | 4 | NO
40 | J49 | J49A | 63 | 11.3 | 5(kg/cm'2) | 3 | 1 | 4 | NO
41 | J28 | J49A | 63 | 21.6 | 5(kg/cm'2) | 3 | 1 | 4 | NO
42 | J28 | J28A | 63 | 43.3 | 5(kg/cm'2) | 3 | 1 | 4 | NO
43 | J28 | J12A | 63 | 114.9 | 5(kg/cm'2) | 3 | 1 | 4 | NO
44 | J12A | J12B | 63 | 42.1 | 5(kg/cm'2) | 3 | 1 | 4 | NO
45 | J12A | J12C | 63 | 30.1 | 5(kg/cm'2) | 3 | 1 | 4 | NO
46 | J12C | J43 | 63 | 28.9 | 5(kg/cm'2) | 3 | 1 | 4 | NO
47 | J12C | J28 | 63 | 25.4 | 5(kg/cm'2) | 3 | 1 | 4 | NO
48 | J49 | J59 | 63 | 112.2 | 5(kg/cm'2) | 3 | 1 | 4 | NO
49 | J59 | J75 | 63 | 25.5 | 5(kg/cm'2) | 3 | 1 | 4 | NO
50 | J59 | J14 | 63 | 40.6 | 5(kg/cm'2) | 3 | 1 | 4 | NO
51 | J14 | J14A | 63 | 20.2 | 5(kg/cm'2) | 3 | 1 | 4 | NO
52 | J14 | J50 | 63 | 80 | 5(kg/cm'2) | 3 | 1 | 4 | NO
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | bhaidpur | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | J5 | J3 | 125 | 104.9 | 6(KG/CM'2) | 4 | 1 | 5 | NO
2 | J3 | J1 | 125 | 63.6 | 6(KG/CM'2) | 4 | 1 | 5 | NO
3 | J91 | J94 | 125 | 3.8 | 6(KG/CM'2) | 4 | 1 | 5 | NO
4 | J91 | J94 | 125 | 157 | 6(KG/CM'2) | 4 | 1 | 5 | NO
5 | J91 | J92 | 125 | 67.6 | 6(KG/CM'2) | 4 | 1 | 5 | NO
6 | J92 | J93 | 125 | 89.1 | 6(KG/CM'2) | 4 | 1 | 5 | NO
7 | J39A | J44 | 90 | 139.1 | 6(KG/CM'2) | 4 | 1 | 5 | NO
8 | J39A | J44 | 90 | 3 | 6(KG/CM'2) | 4 | 1 | 5 | NO
9 | J39 | J57 | 90 | 115.9 | 6(KG/CM'2) | 4 | 1 | 5 | NO
10 | J59 | J64 | 63 | 59.8 | 6(KG/CM'2) | 4 | 1 | 5 | NO
11 | J64 | J64A | 63 | 18.2 | 6(KG/CM'2) | 4 | 1 | 5 | NO
12 | J64 | J64A | 63 | 31.5 | 6(KG/CM'2) | 4 | 1 | 5 | NO
13 | J64A | J37 | 63 | 65.6 | 6(KG/CM'2) | 4 | 1 | 5 | NO
14 | J37 | J33 | 63 | 39.8 | 6(KG/CM'2) | 4 | 1 | 5 | NO
15 | J33 | J32 | 63 | 16.8 | 6(KG/CM'2) | 4 | 1 | 5 | NO
16 | J33 | J23 | 63 | 26.7 | 6(KG/CM'2) | 4 | 1 | 5 | NO
17 | J64 | J69 | 63 | 27.4 | 6(KG/CM'2) | 4 | 1 | 5 | NO
18 | J69 | J75 | 63 | 47.8 | 6(KG/CM'2) | 4 | 1 | 5 | NO
19 | J75 | J59 | 63 | 63.5 | 6(KG/CM'2) | 4 | 1 | 5 | NO
20 | J75 | J80 | 63 | 20.7 | 6(KG/CM'2) | 4 | 1 | 5 | NO
21 | J75 | J80 | 63 | 40.1 | 6(KG/CM'2) | 4 | 1 | 5 | NO
22 | J75 | J80 | 63 | 3.2 | 6(KG/CM'2) | 4 | 1 | 5 | NO
23 | J80 | J80A | 63 | 27.1 | 6(KG/CM'2) | 4 | 1 | 5 | NO
24 | J80A | J81 | 63 | 14.5 | 6(KG/CM'2) | 4 | 1 | 5 | NO
25 | J80A | J80B | 63 | 26.2 | 6(KG/CM'2) | 4 | 1 | 5 | NO
26 | J80 | J82 | 63 | 34.9 | 6(KG/CM'2) | 4 | 1 | 5 | NO
27 | J82 | J83 | 63 | 51.5 | 6(KG/CM'2) | 4 | 1 | 5 | NO
28 | J82 | J84 | 63 | 63.5 | 6(KG/CM'2) | 4 | 1 | 5 | NO
29 | J69 | J71 | 63 | 20.1 | 6(KG/CM'2) | 4 | 1 | 5 | NO
30 | J71 | J72 | 63 | 13.4 | 6(KG/CM'2) | 4 | 1 | 5 | NO
31 | J71 | J72 | 63 | 50.1 | 6(KG/CM'2) | 4 | 1 | 5 | NO
32 | J71 | J71A | 63 | 146.1 | 6(KG/CM'2) | 4 | 1 | 5 | NO
33 | J71 | J71A | 63 | 47.2 | 6(KG/CM'2) | 4 | 1 | 5 | NO
34 | J71A | J71B | 63 | 23.2 | 6(KG/CM'2) | 4 | 1 | 5 | NO
35 | J71A | J73 | 63 | 13.7 | 6(KG/CM'2) | 4 | 1 | 5 | NO
36 | J71A | J73 | 63 | 22.2 | 6(KG/CM'2) | 4 | 1 | 5 | NO
37 | J73 | J72 | 63 | 64.8 | 6(KG/CM'2) | 4 | 1 | 5 | NO
38 | J72 | J72A | 63 | 24.6 | 6(KG/CM'2) | 4 | 1 | 5 | NO
39 | J72A | J72B | 63 | 17.9 | 6(KG/CM'2) | 4 | 1 | 5 | NO
40 | J72A | J70 | 63 | 72.4 | 6(KG/CM'2) | 4 | 1 | 5 | NO
41 | J73 | J70 | 63 | 31.2 | 6(KG/CM'2) | 4 | 1 | 5 | NO
42 | J70 | J65 | 63 | 3.5 | 6(KG/CM'2) | 4 | 1 | 5 | NO
43 | J70 | J65 | 63 | 74.8 | 6(KG/CM'2) | 4 | 1 | 5 | NO
44 | J132 | J136 | 63 | 22.9 | 6(KG/CM'2) | 4 | 1 | 5 | NO
45 | J132 | J136 | 63 | 95.5 | 6(KG/CM'2) | 4 | 1 | 5 | NO
46 | J136 | J136A | 63 | 60.1 | 6(KG/CM'2) | 4 | 1 | 5 | NO
47 | J136 | 142A | 63 | 25.7 | 6(KG/CM'2) | 4 | 1 | 5 | NO
48 | J142A | J142B | 63 | 31.4 | 6(KG/CM'2) | 4 | 1 | 5 | NO
49 | J142A | J142 | 63 | 74.1 | 6(KG/CM'2) | 4 | 1 | 5 | NO
50 | J142A | J142 | 63 | 75.1 | 6(KG/CM'2) | 4 | 1 | 5 | NO
51 | J146 | J142 | 63 | 43.7 | 6(KG/CM'2) | 4 | 1 | 5 | NO
52 | J129 | J135 | 63 | 272.8 | 6(KG/CM'2) | 4 | 1 | 5 | NO
53 | J135 | J138 | 63 | 176 | 6(KG/CM'2) | 4 | 1 | 5 | NO
54 | J138 | J139 | 63 | 6.5 | 6(KG/CM'2) | 4 | 1 | 5 | NO
55 | J138 | J139 | 63 | 48.2 | 6(KG/CM'2) | 4 | 1 | 5 | NO
56 | J138 | J146 | 63 | 158.6 | 6(KG/CM'2) | 4 | 1 | 5 | NO
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | bhaidpur | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | J92 | J99 | 90 | 98.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
2 | J92 | J99 | 90 | 88.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
3 | J92 | J99 | 90 | 43.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
4 | J39 | J39A | 90 | 5.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
5 | J94 | J129A | 75 | 84.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
6 | J94 | J129A | 75 | 3.8 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
7 | J94 | J129A | 75 | 80.7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
8 | J146 | J149 | 63 | 84.9 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
9 | J149 | J151 | 63 | 36.8 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
10 | J149 | J151 | 63 | 14.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
11 | J151 | J142 | 63 | 84.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
12 | J151 | J152 | 63 | 61.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
13 | J136 | J132 | 63 | 24.9 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
14 | J132 | J133 | 63 | 76.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
15 | J133 | J134 | 63 | 51.4 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
16 | J133 | J135 | 63 | 75.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
17 | J132 | J130 | 63 | 49.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
18 | J130 | J131 | 63 | 36.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
19 | J130 | J130A | 63 | 16.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
20 | J130A | J130B | 63 | 34.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
21 | J130A | J129 | 63 | 25.8 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
22 | J129A | J129B | 63 | 74.9 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
23 | J94 | J97A | 63 | 349.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
24 | J126 | J128 | 63 | 232.4 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
25 | J126 | J120 | 63 | 3.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
26 | J126 | J120 | 63 | 397.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
27 | J120 | J121 | 63 | 20.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
28 | J121 | J115 | 63 | 98.9 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
29 | J115 | J115A | 63 | 38 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
30 | J115A | J118 | 63 | 58.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
31 | J115A | J115B | 63 | 13.4 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
32 | J118 | J118A | 63 | 63.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
33 | J118 | J119 | 63 | 98.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
34 | J115 | J120 | 63 | 101.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
35 | J121 | J122 | 63 | 174.9 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
36 | J121 | J122 | 63 | 22.7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
37 | J109 | J100 | 63 | 78.4 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
38 | J100 | J101 | 63 | 51.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
39 | J100 | J99 | 63 | 66.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
40 | J99 | J102A | 63 | 115.4 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
41 | J102A | J102B | 63 | 65.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
42 | J102A | J102 | 63 | 5.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
43 | J102A | J102 | 63 | 54.8 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
44 | J102 | J103 | 63 | 57.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date