## padampur
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | Padampur
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation | Remarks
1 | J130 | J120 | 63 | 142.2 | 5.5 | 3 | 1 | 4 | no
2 | J75 | J81 | 63 | 8.2 | 5.5 | 3 | 1 | 4 | no
3 | J75 | J81 | 63 | 58.6 | 5.5 | 3 | 1 | 4 | no
4 | J81 | J98 | 63 | 105.8 | 5.5 | 3 | 1 | 4 | no
5 | J98 | J74 | 63 | 100.2 | 5.5 | 3 | 1 | 4 | no
6 | J74 | J56 | 63 | 144.7 | 5.5 | 3 | 1 | 4 | no
7 | J98 | J97 | 63 | 13.6 | 5.5 | 3 | 1 | 4 | no
8 | J97 | J71 | 63 | 87.5 | 5.5 | 3 | 1 | 4 | no
9 | J97 | J105 | 63 | 89.9 | 5.5 | 3 | 1 | 4 | no
10 | J97 | J105 | 63 | 3.4 | 5.5 | 3 | 1 | 4 | no
11 | J88 | J112 | 63 | 118.8 | 5.5 | 3 | 1 | 4 | no
12 | J112 | J127 | 63 | 162.3 | 5.5 | 3 | 1 | 4 | no
13 | J112 | J105 | 63 | 1.8 | 5.5 | 3 | 1 | 4 | no
14 | J88 | J115 | 63 | 146.6 | 5.5 | 3 | 1 | 4 | no
15 | J115 | J83 | 63 | 106.4 | 5.5 | 3 | 1 | 4 | no
16 | J115 | J83 | 63 | 3 | 5.5 | 3 | 1 | 4 | no
17 | J115 | J119 | 63 | 82.6 | 5.5 | 3 | 1 | 4 | no
18 | J119 | J101 | 63 | 56.6 | 5.5 | 3 | 1 | 4 | no
19 | J101 | J123 | 63 | 116.1 | 5.5 | 3 | 1 | 4 | no
20 | J101 | J96 | 63 | 63.1 | 5.5 | 3 | 1 | 4 | no
21 | J119 | J132 | 63 | 209.2 | 5.5 | 3 | 1 | 4 | no
22 | J113 | J129 | 63 | 2.6 | 5.5 | 3 | 1 | 4 | no
23 | J113 | J129 | 63 | 79.1 | 5.5 | 3 | 1 | 4 | no
24 | J113 | J130 | 63 | 45.5 | 5.5 | 3 | 1 | 4 | no
25 | J135 | J140A | 63 | 86.9 | 5.5 | 3 | 1 | 4 | no
26 | J135 | J140A | 63 | 3.1 | 5.5 | 3 | 1 | 4 | no
27 | J140A | J124 | 63 | 183.3 | 5.5 | 3 | 1 | 4 | no
28 | J92 | J91 | 63 | 2.8 | 5.5 | 3 | 1 | 4 | no
29 | J81 | J88 | 63 | 3.6 | 5.5 | 3 | 1 | 4 | no
30 | J81 | J88 | 63 | 150.6 | 5.5 | 3 | 1 | 4 | no
31 | J155 | J139 | 63 | 88.6 | 5.5 | 3 | 1 | 4 | no
32 | J155 | J150 | 63 | 106.1 | 5.5 | 3 | 1 | 4 | no
33 | J155 | J141 | 63 | 375.3 | 5.5 | 3 | 1 | 4 | no
34 | J141 | J153 | 63 | 52 | 5.5 | 3 | 1 | 4 | no
35 | J141 | J147 | 63 | 218.9 | 5.5 | 3 | 1 | 4 | no
36 | J147 | J122 | 63 | 148.6 | 5.5 | 3 | 1 | 4 | no
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  | DESIGNATION |  |  |  |  | DESIGNATION
NAME |  |  | NAME |  |  |  |  | NAME
SIGN.with date |  |  | SIGN.with date |  |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | Padampur
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation | Remarks
1 | J93 | J132 | 63 | 197.3 | 6 | 3.3 | 1 | 4.3 | no
2 | J44 | J41 | 63 | 52.3 | 6 | 3.3 | 1 | 4.3 | no
3 | J40 | J38 | 63 | 36.2 | 6 | 3.3 | 1 | 4.3 | no
4 | J12 | J22 | 63 | 171.7 | 6 | 3.3 | 1 | 4.3 | no
5 | J22 | J32 | 63 | 167.4 | 6 | 3.3 | 1 | 4.3 | no
6 | J22 | J32 | 63 | 4 | 6 | 3.3 | 1 | 4.3 | no
7 | J32 | J46 | 63 | 83.6 | 6 | 3.3 | 1 | 4.3 | no
8 | J22 | J14 | 63 | 78.1 | 6 | 3.3 | 1 | 4.3 | no
9 | J14 | J27 | 63 | 88.8 | 6 | 3.3 | 1 | 4.3 | no
10 | J14 | J27 | 63 | 1.4 | 6 | 3.3 | 1 | 4.3 | no
11 | J27 | J35 | 63 | 50.7 | 6 | 3.3 | 1 | 4.3 | no
12 | J32 | J28 | 63 | 59.3 | 6 | 3.3 | 1 | 4.3 | no
13 | J32 | J28 | 63 | 3 | 6 | 3.3 | 1 | 4.3 | no
14 | J35 | J36 | 63 | 92 | 6 | 3.3 | 1 | 4.3 | no
15 | J36 | J39 | 63 | 7.1 | 6 | 3.3 | 1 | 4.3 | no
16 | J26 | J36 | 63 | 43 | 6 | 3.3 | 1 | 4.3 | no
17 | J5 | J42 | 63 | 114.6 | 6 | 3.3 | 1 | 4.3 | no
18 | J42 | J34 | 63 | 21.9 | 6 | 3.3 | 1 | 4.3 | no
19 | J42 | J34 | 63 | 2.9 | 6 | 3.3 | 1 | 4.3 | no
20 | J34 | J33 | 63 | 44.5 | 6 | 3.3 | 1 | 4.3 | no
21 | J80 | J64 | 63 | 131.3 | 6 | 3.3 | 1 | 4.3 | no
22 | J64 | J52 | 63 | 33 | 6 | 3.3 | 1 | 4.3 | no
23 | J64 | J52 | 63 | 5 | 6 | 3.3 | 1 | 4.3 | no
24 | J52 | J121 | 63 | 196.9 | 6 | 3.3 | 1 | 4.3 | no
25 | J52 | J47 | 63 | 79.5 | 6 | 3.3 | 1 | 4.3 | no
26 | J64 | J53 | 63 | 282.1 | 6 | 3.3 | 1 | 4.3 | no
27 | J152 | J150 | 63 | 22.1 | 6 | 3.3 | 1 | 4.3 | no
28 | j78 | j51 | 63 | 685.6 | 6 | 3.3 | 1 | 4.3 | no
29 | j59 | j57 | 63 | 60.1 | 6 | 3.3 | 1 | 4.3 | no
30 | j45 | j59 | 63 | 250.3 | 6 | 3.3 | 1 | 4.3 | no
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  | DESIGNATION |  |  |  |  | DESIGNATION
NAME |  |  | NAME |  |  |  |  | NAME
SIGN.with date |  |  | SIGN.with date |  |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | Padampur
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation | Remarks
1 | j43 | j54 | 63 | 71.9 | 5.5 | 3.5 | 1 | 4.5 | No
2 | j94 | j131 | 63 | 86.6 | 5.5 | 3.5 | 1 | 4.5 | No
3 | j131 | j143 | 63 | 432 | 5.5 | 3.5 | 1 | 4.5 | No
4 | j131 | j143 | 63 | 2.6 | 5.5 | 3.5 | 1 | 4.5 | No
5 | j131 | j120 | 63 | 120.7 | 5.5 | 3.5 | 1 | 4.5 | No
6 | j149 | j120 | 63 | 174.4 | 5.5 | 3.5 | 1 | 4.5 | No
7 | j149 | j120 | 63 | 116.3 | 5.5 | 3.5 | 1 | 4.5 | No
8 | j34 | j31 | 63 | 158.2 | 5.5 | 3.5 | 1 | 4.5 | No
9 | J101 | J116 | 63 | 274.2 | 5.5 | 3.5 | 1 | 4.5 | No
10 | J6 | j30 | 63 | 130.8 | 5.5 | 3.5 | 1 | 4.5 | No
11 | j30 | j8 | 63 | 29 | 5.5 | 3.5 | 1 | 4.5 | No
12 | j92 | j91 | 63 | 62.1 | 5.5 | 3.5 | 1 | 4.5 | No
13 | J8 | J27 | 63 | 58.8 | 5.5 | 3.5 | 1 | 4.5 | No
14 | j8 | j26 | 63 | 146.8 | 5.5 | 3.5 | 1 | 4.5 | No
15 | j8 | j26 | 63 | 1.3 | 5.5 | 3.5 | 1 | 4.5 | No
16 | j8 | j26 | 63 | 5.4 | 5.5 | 3.5 | 1 | 4.5 | No
17 | j26 | j25 | 63 | 21.1 | 5.5 | 3.5 | 1 | 4.5 | No
18 | j26 | j36 | 63 | 3 | 5.5 | 3.5 | 1 | 4.5 | No
19 | J9 | J30 | 63 | 4.1 | 5.5 | 3.5 | 1 | 4.5 | No
20 | J9 | J30 | 63 | 163.4 | 5.5 | 3.5 | 1 | 4.5 | No
21 | J30 | J27 | 63 | 8 | 5.5 | 3.5 | 1 | 4.5 | No
22 | J30 | J27 | 63 | 75.1 | 5.5 | 3.5 | 1 | 4.5 | No
23 | J30 | J6 | 63 | 39.2 | 5.5 | 3.5 | 1 | 4.5 | No
24 | j6 | j8 | 63 | 29 | 5.5 | 3.5 | 1 | 4.5 | No
25 | j89 | j102 | 63 | 121.4 | 5.5 | 3.5 | 1 | 4.5 | No
26 | j117 | j113 | 63 | 50.1 | 5.5 | 3.5 | 1 | 4.5 | No
27 | j117 | j113 | 63 | 39.1 | 5.5 | 3.5 | 1 | 4.5 | No
28 | J93A | J132 | 63 | 197.3 | 5.5 | 3.5 | 1 | 4.5 | No
29 | J111 | J117 | 75 | 42.4 | 5.5 | 3.5 | 1 | 4.5 | No
30 | J147 | J118 | 75 | 3.2 | 5.5 | 3.5 | 1 | 4.5 | No
31 | J147 | J118 | 75 | 352.2 | 5.5 | 3.5 | 1 | 4.5 | No
32 | J147 | J118 | 75 | 8.6 | 5.5 | 3.5 | 1 | 4.5 | No
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  | DESIGNATION |  |  |  |  | DESIGNATION
NAME |  |  | NAME |  |  |  |  | NAME
SIGN.with date |  |  | SIGN.with date |  |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | Padampur
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation | Remarks
1 | j110 | j135 | 75 | 57.3 | 6 | 3 | 1 | 4 | No
2 | j135 | j117 | 75 | 97.1 | 6 | 3 | 1 | 4 | No
3 | J111 | J93A | 75 | 25.1 | 6 | 3 | 1 | 4 | No
4 | J93A | J89 | 75 | 116.6 | 6 | 3 | 1 | 4 | No
5 | J118 | J110 | 75 | 58.2 | 6 | 3 | 1 | 4 | No
6 | J118 | J92 | 75 | 4.6 | 6 | 3 | 1 | 4 | No
7 | J118 | J92 | 75 | 132.2 | 6 | 3 | 1 | 4 | No
8 | J92 | J80 | 90 | 156.6 | 6 | 3 | 1 | 4 | No
9 | J80 | J84 | 90 | 6.6 | 6 | 3 | 1 | 4 | No
10 | J80 | J84 | 90 | 54.4 | 6 | 3 | 1 | 4 | No
11 | J84 | J75 | 90 | 128.3 | 6 | 3 | 1 | 4 | No
12 | J84 | J89 | 90 | 3 | 6 | 3 | 1 | 4 | No
13 | J84 | J89 | 90 | 149.8 | 6 | 3 | 1 | 4 | No
14 | J75 | J43 | 110 | 284.4 | 6 | 3 | 1 | 4 | No
15 | j45 | j43 | 110 | 2.4 | 6 | 3 | 1 | 4 | No
16 | j45 | j43 | 110 | 3.3 | 6 | 3 | 1 | 4 | No
17 | j45 | j43 | 110 | 55.9 | 6 | 3 | 1 | 4 | No
18 | J44 | J45 | 125 | 201.9 | 6 | 3 | 1 | 4 | No
19 | J44 | J40 | 125 | 155.8 | 6 | 3 | 1 | 4 | No
20 | J40 | J31 | 125 | 58.2 | 6 | 3 | 1 | 4 | No
21 | J31 | J9 | 140 | 279.9 | 6 | 3 | 1 | 4 | No
22 | J9 | J12 | 160 | 4.4 | 6 | 3 | 1 | 4 | No
23 | J9 | J12 | 160 | 167.4 | 6 | 3 | 1 | 4 | No
24 | J12 | J22 | 160 | 7.9 | 6 | 3 | 1 | 4 | No
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  | DESIGNATION |  |  |  |  | DESIGNATION
NAME |  |  | NAME |  |  |  |  | NAME
SIGN.with date |  |  | SIGN.with date |  |  |  |  | SIGN.with date