## MALAAK
| HYDROSTATIC TEST FOR PRESSURE PIPES | [11 empty] | HYDROSTATIC TEST FOR PRESSURE PIPES | [11 empty] | HYDROSTATIC TEST FOR PRESSURE PIPES | [11 empty] | HYDROSTATIC TEST FOR PRESSURE PIPES | [11 empty] | HYDROSTATIC TEST FOR PRESSURE PIPES
Project:- |  | Rural water supply project Under JJM , Pratapgarh , Utter Pradesh | [9 empty] | Project:- |  | Rural water supply project Under JJM , Pratapgarh , Utter Pradesh | [9 empty] | Project:- |  | Rural water supply project Under JJM , Pratapgarh , Utter Pradesh | [9 empty] | Project:- |  | Rural water supply project Under JJM , Pratapgarh , Utter Pradesh | [9 empty] | Project:- |  | Rural water supply project Under JJM , Pratapgarh , Utter Pradesh
Client : - |  | State Water & Sanitation Mission Govt of Uttar Pradesh | [9 empty] | Client : - |  | State Water & Sanitation Mission Govt of Uttar Pradesh | [9 empty] | Client : - |  | State Water & Sanitation Mission Govt of Uttar Pradesh | [9 empty] | Client : - |  | State Water & Sanitation Mission Govt of Uttar Pradesh | [9 empty] | Client : - |  | State Water & Sanitation Mission Govt of Uttar Pradesh
TPI :- |  | Medhaj Techno Concept Pvt . Ltd. | [9 empty] | TPI :- |  | Medhaj Techno Concept Pvt . Ltd. | [9 empty] | TPI :- |  | Medhaj Techno Concept Pvt . Ltd. | [9 empty] | TPI :- |  | Medhaj Techno Concept Pvt . Ltd. | [9 empty] | TPI :- |  | Medhaj Techno Concept Pvt . Ltd.
Contractor :- |  | Power Mech Project Ltd. | [9 empty] | Contractor :- |  | Power Mech Project Ltd. | [9 empty] | Contractor :- |  | Power Mech Project Ltd. | [9 empty] | Contractor :- |  | Power Mech Project Ltd. | [9 empty] | Contractor :- |  | Power Mech Project Ltd.
Block: MANGRAURA, G.P-MALAK | [11 empty] | Block: MANGRAURA, G.P-MALAK | [11 empty] | Block: MANGRAURA, G.P-MALAK | [11 empty] | Block: MANGRAURA, G.P-MALAK | [11 empty] | Block: MANGRAURA, G.P-MALAK
Dail Log Ref. …………………. | [5 empty] | Tested as per CPHEEO …………………….. | [5 empty] | Dail Log Ref. …………………. | [5 empty] | Tested as per CPHEEO …………………….. | [5 empty] | Dail Log Ref. …………………. | [5 empty] | Tested as per CPHEEO …………………….. | [5 empty] | Dail Log Ref. …………………. | [5 empty] | Tested as per CPHEEO …………………….. | [5 empty] | Dail Log Ref. …………………. | [5 empty] | Tested as per CPHEEO ……………………..
Date | [5 empty] | Date of Testing | [5 empty] | Date | [5 empty] | Date of Testing | [5 empty] | Date | [5 empty] | Date of Testing | [5 empty] | Date | [5 empty] | Date of Testing | [5 empty] | Date | [5 empty] | Date of Testing
SL. No. | Material of Pipe | OD (MM) | Start Node | End Node | Length | Applied test pressure (kg/cm'2) | Time in Hrs |  |  | Observation | Remark | SL. No. | Material of Pipe | OD (MM) | Start Node | End Node | Length | Applied test pressure (kg/cm'2) | Time in Hrs |  |  | Observation | Remark | SL. No. | Material of Pipe | OD (MM) | Start Node | End Node | Length | Applied test pressure (kg/cm'2) | Time in Hrs |  |  | Observation | Remark | SL. No. | Material of Pipe | OD (MM) | Start Node | End Node | Length | Applied test pressure (kg/cm'2) | Time in Hrs |  |  | Observation | Remark | SL. No. | Material of Pipe | OD (MM) | Start Node | End Node | Length | Applied test pressure (kg/cm'2) | Time in Hrs |  |  | Observation | Remark
[7 empty] | Pressure rising time (Hrs) | Pressure Released time (Hrs) | Total Duration Hrs | [9 empty] | Pressure rising time (Hrs) | Pressure Released time (Hrs) | Total Duration Hrs | [9 empty] | Pressure rising time (Hrs) | Pressure Released time (Hrs) | Total Duration Hrs | [9 empty] | Pressure rising time (Hrs) | Pressure Released time (Hrs) | Total Duration Hrs | [9 empty] | Pressure rising time (Hrs) | Pressure Released time (Hrs) | Total Duration Hrs
1 | HDPE | 160 | J92 | J55 | 131 | 6kg/cm2 | 3 | 1 | 4 | NO |  | 1 | HDPE | 110 | j130 | j124 | 7 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 1 | HDPE | 110 | j139 | j116 | 110.4 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 1 | HDPE | 90 | j35 | j91 | 234 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 1 | HDPE |  | j136 | j126 | 218.6 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
2 | HDPE | 160 | J92 | J97 | 11.7 | 6kg/cm2 | 3 | 1 | 4 | NO |  | 2 | HDPE | 110 | j130 | j124 | 354.6 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 2 | HDPE | 110 | j116 | j118 | 14 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 2 | HDPE | 90 | j113 | j139 | 26.3 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 2 | HDPE |  | j136 | j126 | 101.4 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
3 | HDPE | 140 | j92 | j91 | 488 | 6kg/cm2 | 3 | 1 | 4 | NO |  | 3 | HDPE | 63 | j232 | j229 | 102 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 3 | HDPE | 63 | j57 | j67 | 11.5 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 3 | HDPE | 90 | j80 | j86 | 43 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 3 | HDPE |  | j136 | j126 | 6 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
4 | HDPE | 125 | j94 | j124 | 423 | 6kg/cm2 | 3 | 1 | 4 | NO |  | 4 | HDPE | 63 | j229 | j221 | 93 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 4 | HDPE | 63 | j67 | j83 | 45 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 4 | HDPE | 90 | j86 | j104 | 44.6 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 4 | HDPE |  | j136 | j126 | 322.5 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
5 | HDPE | 125 | j118 | j97 | 121.1 | 6kg/cm2 | 3 | 1 | 4 | NO |  | 5 | HDPE | 63 | j221 | j235 | 10 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 5 | HDPE | 63 | j67 | j88 | 66 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 5 | HDPE | 63 | j233 | j161 | 54.5 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 5 | HDPE |  | j136 | j126 | 18.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
6 | HDPE | 63 | j128 | j123 | 30 | 6kg/cm2 | 3 | 1 | 4 | NO |  | 6 | HDPE | 63 | j221 | j241 | 70 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 6 | HDPE | 63 | j88 | j73 | 45.4 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 6 | HDPE | 63 | j161 | j210 | 33.7 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 6 | HDPE |  | j160 | j156 | 33.3 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
7 | HDPE | 63 | j123 | j58 | 65.5 | 6kg/cm2 | 3 | 1 | 4 | NO |  | 7 | HDPE | 63 | j77 | j96 | 34 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 7 | HDPE | 63 | j88 | j134 | 133 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 7 | HDPE | 63 | j243 | j196 | 86.4 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 7 | HDPE |  | j160 | j169 | 92 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
8 | HDPE | 63 | j58 | j53 | 422 | 6kg/cm2 | 3 | 1 | 4 | NO |  | 8 | HDPE | 63 | j229a | j241a | 116 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 8 | HDPE | 63 | j47 | j30 | 37.7 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 8 | HDPE | 63 | j210 | j219 | 61.4 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 8 | HDPE |  | j169 | j208 | 30.6 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
9 | HDPE | 63 | j123 | j71 | 65.2 | 6kg/cm2 | 3 | 1 | 4 | NO |  | 9 | HDPE | 63 | j229 | j234 | 142 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 9 | HDPE | 63 | j30 | j36 | 39.4 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 9 | HDPE | 63 | j219 | j240 | 114.5 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 9 | HDPE |  | j169 | j125 | 56.5 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
10 | HDPE | 63 | j71 | j72 | 5.5 | 6kg/cm2 | 3 | 1 | 4 | NO |  | 10 | HDPE | 63 | j64 | j138 | 217.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 10 | HDPE | 63 | j30 | j35 | 127.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 10 | HDPE | 63 | j240 | j239 | 38.5 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 10 | HDPE |  | j169 | j125 | 13.4 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
11 | HDPE | 63 | j72 | j46 | 126 | 6kg/cm2 | 3 | 1 | 4 | NO |  | 11 | HDPE | 63 | j138 | j177 | 10.8 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 11 | HDPE | 63 | j124 | j120 | 10.7 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 11 | HDPE | 63 | j240 | j242 | 7.1 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 11 | HDPE |  | j169 | j125 | 15.8 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
12 | HDPE | 63 | j72 | j53 | 44.8 | 6kg/cm2 | 3 | 1 | 4 | NO |  | 12 | HDPE | 63 | j177 | j183 | 16.6 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 12 | HDPE | 63 | j120 | j27 | 281.9 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 12 | HDPE | 63 | j242 | j243 | 11.3 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 12 | HDPE |  | j125 | j113 | 19.8 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
13 | HDPE | 63 | j53 | j29 | 82.8 | 6kg/cm2 | 3 | 1 | 4 | NO |  | 13 | HDPE | 63 | j177 | j187 | 19.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 13 | HDPE | 63 | j27 | j11 | 112.7 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 13 | HDPE | 63 | j242 | j243 | 116 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 13 | HDPE |  | j142 | j127 | 39.4 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
14 | HDPE | 63 | j29 | j20 | 43.5 | 6kg/cm2 | 3 | 1 | 4 | NO |  | 14 | HDPE | 63 | j187 | j98 | 70 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 14 | HDPE | 63 | j11 | j14 | 44.7 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 14 | HDPE | 63 | j243 | j233 | 188 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 14 | HDPE |  | j142 | j131 | 25.5 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
15 | HDPE | 63 | j29 | j20 | 64.8 | 6kg/cm2 | 3 | 1 | 4 | NO |  | 15 | HDPE | 63 | j98 | j40 | 65 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 15 | HDPE | 63 | j11 | j10 | 14.8 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 15 | HDPE | 63 | j242 | j197 | 182 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 15 | HDPE |  | j131 | j170 | 37.7 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
16 | HDPE | 63 | j20 | j2 | 15.1 | 6kg/cm2 | 3 | 1 | 4 | NO |  | 16 | HDPE | 63 | j40 | j74 | 63.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 16 | HDPE | 63 | j10 | j5 | 37.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 16 | HDPE | 63 | j111 | j111a | 150.5 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 16 | HDPE |  | j131 | j135 | 12 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
17 | HDPE | 63 | j20 | j2 | 112 | 6kg/cm2 | 3 | 1 | 4 | NO |  | 17 | HDPE | 63 | j74 | j75 | 54 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 17 | HDPE | 63 | j5 | j9 | 32 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 17 | HDPE | 63 | j230 | j230a | 31 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 17 | HDPE |  | j131 | j135 | 27 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
18 | HDPE | 63 | j2 | j1 | 57.5 | 6kg/cm2 | 3 | 1 | 4 | NO |  | 18 | HDPE | 63 | j187 | j179 | 74.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 18 | HDPE | 63 | j9 | J63 | 121 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 18 | HDPE | 63 | j89 | j89a | 56.8 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 18 | HDPE |  | j81a | j81b | 37 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
19 | HDPE | 63 | j2 | j24 | 59.1 | 6kg/cm2 | 3 | 1 | 4 | NO |  | 19 | HDPE | 63 | j190 | j40 | 62.7 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 19 | HDPE | 63 | j63 | j93 | 53 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 19 | HDPE | 63 | j197 | j236 | 65 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 19 | HDPE |  | j110a | j110b | 36 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
20 | HDPE | 63 | j2 | j24 | 113.2 | 6kg/cm2 | 3 | 1 | 4 | NO |  | 20 | HDPE | 63 | j190 | j74 | 112.4 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 20 | HDPE | 63 | j93 | j94 | 112 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 20 | HDPE | 63 | j223 | j238 | 78 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 20 | HDPE |  | j100 | j100b | 96 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
21 | HDPE | 63 | j71 | j70 | 42.9 | 6kg/cm2 | 3 | 1 | 4 | NO |  | 21 | HDPE | 63 | j138 | j106 | 32.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 21 | HDPE | 63 | j94 | j133 | 133.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 21 | HDPE | 63 | j238 | j201 | 17 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 21 | HDPE |  | j152 | j99 | 108.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
22 | HDPE | 63 | j70 | j44 | 40.9 | 6kg/cm2 | 3 | 1 | 4 | NO |  | 22 | HDPE | 63 | j106 | j165 | 77.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 22 | HDPE | 63 | j133 | j108 | 58.5 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 22 | HDPE | 63 | j201 | j217 | 54.5 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 22 | HDPE |  | j99 | j188 | 103.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
23 | HDPE | 63 | j70 | j44 | 3 | 6kg/cm2 | 3 | 1 | 4 | NO |  | 23 | HDPE | 63 | j165 | j167 | 84.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 23 | HDPE | 63 | j108 | j134 | 96 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 23 | HDPE | 63 | j217 | j213 | 100.2 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 23 | HDPE |  | j99 | j200 | 75.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
24 | HDPE | 63 | j70 | j37 | 95.1 | 6kg/cm2 | 3 | 1 | 4 | NO |  | 24 | HDPE | 63 | j106 | j152 | 108.9 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 24 | HDPE | 63 | j54 | j65 | 61.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 24 | HDPE | 63 | j217 | j220 | 4.7 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 24 | HDPE |  | j216 | j207 | 71.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
25 | HDPE | 63 | j37 | j19 | 92.7 | 6kg/cm2 | 3 | 1 | 4 | NO |  | 25 | HDPE | 63 | j152 | 167 | 43.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 25 | HDPE | 63 | j55 | j43 | 9.4 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 25 | HDPE | 63 | j217 | j220 | 49.7 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 25 | HDPE |  | j198 | j150 | 142.5 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
26 | HDPE | 63 | j37 | j19 | 2.5 | 6kg/cm2 | 3 | 1 | 4 | NO |  | 26 | HDPE | 63 | j167 | j178 | 21.9 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 26 | HDPE | 63 | j43 | j41 | 109.5 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 26 | HDPE | 63 | j220 | j211 | 73.3 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 26 | HDPE |  | j207 | j200 | 21.3 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
27 | HDPE | 63 | j31 | j18 | 15.5 | 6kg/cm2 | 3 | 1 | 4 | NO |  | 27 | HDPE | 63 | j178 | j203 | 56.9 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 27 | HDPE | 63 | j122 | j147 | 40 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 27 | HDPE | 63 | j220 | j204 | 114.5 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 27 | HDPE |  | j200 | j192 | 68.6 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
28 | HDPE | 63 | j26 | j56 | 33.5 | 6kg/cm2 | 3 | 1 | 4 | NO |  | 28 | HDPE | 63 | j178 | j216 | 12.9 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 28 | HDPE | 63 | j147 | j119 | 23.7 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 28 | HDPE | 63 | j204 | j193 | 56 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 28 | HDPE |  | j150 | j168 | 28.4 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
29 | HDPE | 63 | j26 | j34 | 22.4 | 6kg/cm2 | 3 | 1 | 4 | NO |  | 29 | HDPE | 63 | j27 | j32 | 48.6 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 29 | HDPE | 63 | j147 | j139 | 51.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 29 | HDPE | 63 | j204 | j146 | 61 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 29 | HDPE |  | j168 | j164 | 109.8 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
30 | HDPE | 63 | j34 | j42 | 84.1 | 6kg/cm2 | 3 | 1 | 4 | NO |  | 30 | HDPE | 63 | j32 | j61 | 81.8 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 30 | HDPE | 63 | j116 | j117 | 7 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 30 | HDPE | 63 | j191 | j185 | 51.9 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 30 | HDPE |  | j164 | j112 | 61.7 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
31 | HDPE | 63 | j19 | j26 | 64.9 | 6kg/cm2 | 3 | 1 | 4 | NO |  | 31 | HDPE | 63 | j61 | j68 | 128.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 31 | HDPE | 63 | j116 | j117 | 14 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 31 | HDPE | 63 | j191 | j223 | 45.2 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 31 | HDPE |  | j168 | j181 | 82.3 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
32 | HDPE | 63 | j225 | j224 | 24 | 6kg/cm2 | 3 | 1 | 4 | NO |  | 32 | HDPE | 63 | j61 | j68 | 110.5 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 32 | HDPE | 63 | j116 | j116a | 165 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 32 | HDPE | 63 | j223 | j223a | 23.2 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 32 | HDPE |  | j181 | j132 | 144.5 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
33 | HDPE | 63 | j212 | j213 | 83.6 | 6kg/cm2 | 3 | 1 | 4 | NO |  | 33 | HDPE | 63 | j61 | j68 | 49 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 33 | HDPE | 63 | j116 | j116a | 26.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 33 | HDPE | 63 | j223a | j189 | 35.5 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 33 | HDPE |  | j192 | j136 | 149.6 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
34 | HDPE | 63 | j213 | j206 | 8.2 | 6kg/cm2 | 3 | 1 | 4 | NO |  | 34 | HDPE | 63 | j82 | j94 | 40 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 34 | HDPE | 63 | j122 | j122a | 55.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 34 | HDPE | 63 | j223a | j189 | 76.9 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 34 | HDPE |  | j154 | j107 | 14.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
35 | HDPE | 63 | j206 | j172 | 20.1 | 6kg/cm2 | 3 | 1 | 4 | NO |  | 35 | HDPE | 63 | j32 | j81 | 5 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 35 | HDPE | 63 | j35 | j21 | 154 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 35 | HDPE | 63 | j236a | j236b | 15.8 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 35 | HDPE |  | j150a | j150b | 124 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
36 | HDPE | 63 | j172 | j182 | 25 | 6kg/cm2 | 3 | 1 | 4 | NO |  | 36 | HDPE | 63 | j32 | j81 | 48 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 36 | HDPE | 63 | j27 | j21 | 3.7 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 36 | HDPE | 63 | j236 | j189 | 98.6 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 36 | HDPE |  | j150c | j150d | 32 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
37 | HDPE | 63 | j172 | j175 | 200 | 6kg/cm2 | 3 | 1 | 4 | NO |  | 37 | HDPE | 63 | j81 | j95 | 46 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 37 | HDPE | 63 | j27 | j21 | 8.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 37 | HDPE | 63 | j189 | j173 | 69 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 37 | HDPE |  | j150c | j150d | 3 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
38 | HDPE | 63 | j206 | j172 | 7 | 6kg/cm2 | 3 | 1 | 4 | NO |  | 38 | HDPE | 63 | j95 | j96 | 66.4 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 38 | HDPE | 63 | j55 | j54 | 10.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 38 | HDPE | 63 | j173 | j162 | 18.5 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 38 | HDPE |  | j207 | j200 | 7 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
39 | HDPE | 63 | j206 | j211 | 57 | 6kg/cm2 | 3 | 1 | 4 | NO |  | 39 | HDPE | 63 | j96 | j133 | 100.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 39 | HDPE | 63 | j228 | j230 | 163.5 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 39 | HDPE | 63 | j162 | j237 | 53.1 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 39 | HDPE |  | j154 | j107 | 7 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
40 | HDPE | 63 | j211 | j232 | 121.5 | 6kg/cm2 | 3 | 1 | 4 | NO |  | 40 | HDPE | 63 | j96 | j133 | 8 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 40 | HDPE | 63 | j230 | j89 | 58.6 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 40 | HDPE | 63 | j162 | j146 | 81 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 40 | HDPE |  | j147 | j139 | 7 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
|  | POWER MECH |  |  |  | MEDHAJ |  |  | JAL NIGAM U.P. |  |  | 41 | HDPE | 63 | j96 | j82 | 49.5 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 41 | HDPE | 63 | j230 | j231 | 52.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 41 | HDPE | 63 | j197 | j184 | 62 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 41 | HDPE |  | j225 | j195 | 8 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
Name: | [11 empty] | 42 | HDPE | 63 | j21 | j62 | 59.5 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 42 | HDPE | 63 | j231 | j89 | 86.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 42 | HDPE | 63 | j184 | j189 | 68 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 42 | HDPE |  | j172 | j175 | 46.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
Designation: | [11 empty] | 43 | HDPE | 63 | j62 | j81 | 69.5 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 43 | HDPE | 63 | j231 | j186 | 43.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 43 | HDPE | 63 | j212 | j224 | 104 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 43 | HDPE |  | J131A | J131B | 15.9 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
Signature: | [11 empty] | 44 | HDPE | 63 | j62 | j47 | 12.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 44 | HDPE | 63 | j186 | j114 | 37.6 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 44 | HDPE | 63 | j222 | j245 | 25 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 44 | HDPE |  | J131A | J131B | 17 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
Date: | [11 empty] | 45 | HDPE | 63 | j47 | j48 | 52 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 45 | HDPE | 63 | j114 | j111 | 70.5 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 45 | HDPE | 63 | j224 | j222 | 91 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 45 | HDPE |  | J125 | J142 | 26.7 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
[12 empty] | 46 | HDPE | 63 | j48 | j95 | 58 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 46 | HDPE | 63 | j111 | j161 | 170.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 46 | HDPE | 63 | j227 | j225 | 29.8 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 46 | HDPE |  | J125 | J142 | 50.4 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
[5 empty] | 3525.7 | [6 empty] | 47 | HDPE | 63 | j48 | j57 | 33.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 47 | HDPE | 63 | j110 | j151 | 83.8 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 47 | HDPE | 63 | j225 | j224 | 9 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 47 | HDPE |  | J186 | J231 | 43.6 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
[12 empty] | 48 | HDPE | 63 | j57 | j77 | 23.7 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 48 | HDPE | 63 | j145 | j140 | 45 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 48 | HDPE | 63 | j225 | j195 | 36.2 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 48 | HDPE |  | J80 | J79 | 30.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
[12 empty] | 49 | HDPE | 63 | j57 | j77 | 49.5 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 49 | HDPE | 63 | j145 | j174 | 25.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 49 | HDPE | 63 | j79 | j103 | 19.2 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 49 | HDPE |  | j37 | j130 | 260.4 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
[12 empty] | 50 | HDPE | 63 | j77 | j73 | 38.4 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 50 | HDPE | 63 | j174 | j226 | 27 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 50 | HDPE | 63 | j79 | j110 | 128.6 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 50 | HDPE |  | j139 | j212 | 355 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
[12 empty] | 51 | HDPE | 63 | j73 | j108 | 73.6 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 51 | HDPE | 63 | j186 | j226 | 80.5 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 51 | HDPE | 63 | j110 | j141 | 52.6 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 51 | HDPE |  | j196 | j113 | 202.3 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
[14 empty] | POWER MECH |  |  |  | MEDHAJ |  |  | JAL NIGAM U.P. |  |  | 52 | HDPE | 63 | j226 | j233 | 29.6 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 52 | HDPE | 63 | j86 | j90 | 33 | 5KG/CM2 | 3 | 1 | 4 | NO
[12 empty] | Name: | [13 empty] | POWER MECH |  |  |  | MEDHAJ |  |  | JAL NIGAM U.P. |  |  | 53 | HDPE | 63 | j90 | j87 | 22 | 5KG/CM2 | 3 | 1 | 4 | NO |  |  |  | POWER MECH |  |  |  | MEDHAJ |  |  | JAL NIGAM U.P.
[12 empty] | Designation: | [11 empty] | Name: | [11 empty] | 54 | HDPE | 63 | j90 | j118 | 122.7 | 5KG/CM2 | 3 | 1 | 4 | NO |  | Name:
[12 empty] | Signature: | [11 empty] | Designation: | [11 empty] | 55 | HDPE | 63 | j100 | j148 | 63 | 5KG/CM2 | 3 | 1 | 4 | NO |  | Designation:
[12 empty] | Date: | [11 empty] | Signature: | [11 empty] | 56 | HDPE | 63 | j100 | j163 | 69 | 5KG/CM2 | 3 | 1 | 4 | NO |  | Signature:
[24 empty] | Date: | [11 empty] | 57 | HDPE | 63 | j104 | j143 | 29 | 5KG/CM2 | 3 | 1 | 4 | NO |  | Date:
[17 empty] | 3381.2 | [18 empty] | 58 | HDPE | 63 | j143 | j149 | 26 | 5KG/CM2 | 3 | 1 | 4 | NO
[29 empty] | 3449.1 | [6 empty] | 59 | HDPE | 63 | j143 | j153 | 18 | 5KG/CM2 | 3 | 1 | 4 | NO | [6 empty] | 3654.7
[36 empty] | 60 | HDPE | 63 | j143 | j153 | 30 | 5KG/CM2 | 3 | 1 | 4 | NO
[36 empty] | 61 | HDPE | 63 | j153 | j155 | 14.6 | 5KG/CM2 | 3 | 1 | 4 | NO
[36 empty] | 62 | HDPE | 63 | j155 | j109 | 45.2 | 5KG/CM2 | 3 | 1 | 4 | NO
[36 empty] | 63 | HDPE | 63 | j155 | j129 | 55.9 | 5KG/CM2 | 3 | 1 | 4 | NO
[36 empty] | 64 | HDPE | 63 | j153 | j160 | 8.3 | 5KG/CM2 | 3 | 1 | 4 | NO
[38 empty] | POWER MECH |  |  |  | MEDHAJ |  |  | JAL NIGAM U.P.
[36 empty] | Name: | [17 empty] | 17895
Designation:
Signature:
Date:
3884.3