## choumari
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | choumari | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | J98 | J96 | 160 | 8 | 6 | 3 | 1 | 4 | no
2 | J98 | J96 | 160 | 34.5 | 6 | 3 | 1 | 4 | no
3 | J96 | J94 | 160 | 77.9 | 6 | 3 | 1 | 4 | no
4 | J94 | J93 | 160 | 8.5 | 6 | 3 | 1 | 4 | no
5 | J94 | J93 | 160 | 272.7 | 6 | 3 | 1 | 4 | no
6 | J94 | J93 | 160 | 7.1 | 6 | 3 | 1 | 4 | no
7 | J93 | J91 | 160 | 7.1 | 6 | 3 | 1 | 4 | no
8 | J93 | J91 | 160 | 83.4 | 6 | 3 | 1 | 4 | no
9 | J91 | J88 | 160 | 5.9 | 6 | 3 | 1 | 4 | no
10 | J91 | J88 | 160 | 221.9 | 6 | 3 | 1 | 4 | no
11 | J91 | J88 | 160 | 5.6 | 6 | 3 | 1 | 4 | no
12 | J91 | J88 | 160 | 120.1 | 6 | 3 | 1 | 4 | no
13 | J142 | J155 | 63 | 133.6 | 6 | 3 | 1 | 4 | no
14 | J155 | J154 | 63 | 75.9 | 6 | 3 | 1 | 4 | no
15 | J154 | J183 | 63 | 274.3 | 6 | 3 | 1 | 4 | no
16 | J183 | J183A | 63 | 3 | 6 | 3 | 1 | 4 | no
17 | J183 | J183A | 63 | 66.2 | 6 | 3 | 1 | 4 | no
18 | J183A | J183B | 63 | 66.6 | 6 | 3 | 1 | 4 | no
19 | J183A | J184 | 63 | 154.7 | 6 | 3 | 1 | 4 | no
20 | J184 | J184A | 63 | 18.8 | 6 | 3 | 1 | 4 | no
21 | J184 | J184B | 63 | 40.1 | 6 | 3 | 1 | 4 | no
22 | J208 | J198 | 63 | 108.9 | 6 | 3 | 1 | 4 | no
23 | J198 | J201 | 63 | 70.2 | 6 | 3 | 1 | 4 | no
24 | J201 | J202 | 63 | 23.4 | 6 | 3 | 1 | 4 | no
25 | J201 | J201A | 63 | 25.8 | 6 | 3 | 1 | 4 | no
26 | J201A | J201B | 63 | 35.7 | 6 | 3 | 1 | 4 | no
27 | J201A | J201C | 63 | 36.5 | 6 | 3 | 1 | 4 | no
28 | J198 | J196 | 63 | 107.5 | 6 | 3 | 1 | 4 | no
29 | J196 | J197 | 63 | 73.8 | 6 | 3 | 1 | 4 | no
30 | J196 | J194 | 63 | 282.8 | 6 | 3 | 1 | 4 | no
31 | J194 | J195 | 63 | 41.3 | 6 | 3 | 1 | 4 | no
32 | J194 | J189 | 63 | 162.6 | 6 | 3 | 1 | 4 | no
33 | J194 | J189 | 63 | 4.7 | 6 | 3 | 1 | 4 | no
34 | J189 | J190 | 63 | 4.7 | 6 | 3 | 1 | 4 | no
35 | J189 | J190 | 63 | 50.6 | 6 | 3 | 1 | 4 | no
36 | J189 | J188 | 63 | 100.8 | 6 | 3 | 1 | 4 | no
37 | J188 | J186 | 63 | 5.2 | 6 | 3 | 1 | 4 | no
38 | J188 | J186 | 63 | 355.7 | 6 | 3 | 1 | 4 | no
39 | J186 | J187 | 63 | 47.7 | 6 | 3 | 1 | 4 | no
40 | J186 | J186A | 63 | 113.4 | 6 | 3 | 1 | 4 | no
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | choumari | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | J88 | J80 | 160 | 334.1 | 5.5 | 3.3 | 1 | 4.3 | no
2 | J88 | J80 | 160 | 5.1 | 5.5 | 3.3 | 1 | 4.3 | no
3 | J88 | J80 | 160 | 1.2 | 5.5 | 3.3 | 1 | 4.3 | no
4 | J80 | J79 | 160 | 14.2 | 5.5 | 3.3 | 1 | 4.3 | no
5 | J80 | J79 | 160 | 10 | 5.5 | 3.3 | 1 | 4.3 | no
6 | J80 | J79 | 160 | 5.2 | 5.5 | 3.3 | 1 | 4.3 | no
7 | J79 | J56 | 160 | 172.1 | 5.5 | 3.3 | 1 | 4.3 | no
8 | J56 | J39 | 160 | 5.7 | 5.5 | 3.3 | 1 | 4.3 | no
9 | J56 | J39 | 160 | 118.3 | 5.5 | 3.3 | 1 | 4.3 | no
10 | J39 | J2 | 160 | 194 | 5.5 | 3.3 | 1 | 4.3 | no
11 | J2 | J1 | 160 | 29.5 | 5.5 | 3.3 | 1 | 4.3 | no
12 | J12 | J13 | 160 | 20 | 5.5 | 3.3 | 1 | 4.3 | no
13 | J13 | J9 | 160 | 76.3 | 5.5 | 3.3 | 1 | 4.3 | no
14 | J99 | J101 | 160 | 17.6 | 5.5 | 3.3 | 1 | 4.3 | no
15 | J186A | J186B | 63 | 3.3 | 5.5 | 3.3 | 1 | 4.3 | no
16 | J186A | J186B | 63 | 36.9 | 5.5 | 3.3 | 1 | 4.3 | no
17 | J186A | J186C | 63 | 66.7 | 5.5 | 3.3 | 1 | 4.3 | no
18 | J186C | J186D | 63 | 3.2 | 5.5 | 3.3 | 1 | 4.3 | no
19 | J186C | J186D | 63 | 41.6 | 5.5 | 3.3 | 1 | 4.3 | no
20 | J186C | J186E | 63 | 67.4 | 5.5 | 3.3 | 1 | 4.3 | no
21 | J186E | J186F | 63 | 3 | 5.5 | 3.3 | 1 | 4.3 | no
22 | J186E | J186F | 63 | 26.8 | 5.5 | 3.3 | 1 | 4.3 | no
23 | J186E | J150 | 63 | 46.1 | 5.5 | 3.3 | 1 | 4.3 | no
24 | J151 | J150A | 63 | 20.1 | 5.5 | 3.3 | 1 | 4.3 | no
25 | J150 | J149 | 63 | 3 | 5.5 | 3.3 | 1 | 4.3 | no
26 | J150 | J149 | 63 | 43.5 | 5.5 | 3.3 | 1 | 4.3 | no
27 | J138 | J154 | 63 | 127.4 | 5.5 | 3.3 | 1 | 4.3 | no
28 | J155 | J185 | 63 | 210.1 | 5.5 | 3.3 | 1 | 4.3 | no
29 | J185 | J185A | 63 | 31.5 | 5.5 | 3.3 | 1 | 4.3 | no
30 | J185A | J185B | 63 | 3 | 5.5 | 3.3 | 1 | 4.3 | no
31 | J185A | J185B | 63 | 47.2 | 5.5 | 3.3 | 1 | 4.3 | no
32 | J185A | J183 | 63 | 92.1 | 5.5 | 3.3 | 1 | 4.3 | no
33 | J185 | J189 | 63 | 7.8 | 5.5 | 3.3 | 1 | 4.3 | no
34 | J185 | J189 | 63 | 120.8 | 5.5 | 3.3 | 1 | 4.3 | no
35 | J188 | J192 | 63 | 76.6 | 5.5 | 3.3 | 1 | 4.3 | no
36 | J130 | J129 | 63 | 32.6 | 5.5 | 3.3 | 1 | 4.3 | no
37 | J122 | J121 | 63 | 27.1 | 5.5 | 3.3 | 1 | 4.3 | no
38 | J115 | J116 | 63 | 58.2 | 5.5 | 3.3 | 1 | 4.3 | no
39 | J116 | J136 | 63 | 130.2 | 5.5 | 3.3 | 1 | 4.3 | no
40 | J136 | J137 | 63 | 4 | 5.5 | 3.3 | 1 | 4.3 | no
41 | J136 | J137 | 63 | 110 | 5.5 | 3.3 | 1 | 4.3 | no
42 | J136 | J139 | 63 | 130.6 | 5.5 | 3.3 | 1 | 4.3 | no
43 | J113 | J107 | 63 | 326.8 | 5.5 | 3.3 | 1 | 4.3 | no
44 | J107 | J108 | 63 | 21.3 | 5.5 | 3.3 | 1 | 4.3 | no
45 | J94 | J95 | 63 | 24.8 | 5.5 | 3.3 | 1 | 4.3 | no
46 | J39 | J40 | 63 | 116.4 | 5.5 | 3.3 | 1 | 4.3 | no
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | choumari | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | J113 | J107 | 140 | 326.8 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
2 | J113 | J107 | 140 | 3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
3 | J107 | J98 | 140 | 225.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
4 | J107 | J98 | 140 | 29.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
5 | J107 | J98 | 140 | 57.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
6 | J98 | J96 | 160 | 34.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
7 | J150 | J150A | 75 | 3.7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
8 | J150A | J142 | 75 | 81.8 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
9 | J150A | J142 | 75 | 6.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
10 | J142 | J139 | 75 | 78.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
11 | J139 | J138 | 75 | 11.4 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
12 | J138 | J130 | 75 | 94.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
13 | J130 | J122 | 75 | 3.8 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
14 | J130 | J122 | 75 | 24.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
15 | J188 | J192 | 63 | 76.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
16 | J130 | J129 | 63 | 32.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
17 | J122 | J121 | 63 | 27.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
18 | J115 | J116 | 63 | 58.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
19 | J116 | J136 | 63 | 130.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
20 | J136 | J137 | 63 | 4 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
21 | J136 | J137 | 63 | 110 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
22 | J136 | J139 | 63 | 130.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
23 | J113 | J107 | 63 | 326.8 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
24 | J107 | J108 | 63 | 21.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
25 | J94 | J95 | 63 | 24.8 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
26 | J39 | J40 | 63 | 116.4 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
27 | J3 | J4 | 63 | 34.7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
28 | J48 | J63 | 63 | 166.4 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
29 | J63 | J66 | 63 | 4.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
30 | J63 | J66 | 63 | 80.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
31 | J78 | J64 | 63 | 194.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
32 | J78 | J74 | 63 | 131.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
33 | J74 | J76 | 63 | 10.8 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
34 | J74 | J73 | 63 | 121.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
35 | J74 | J73 | 63 | 3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
36 | J73 | J71 | 63 | 252.4 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
37 | J71 | J63 | 63 | 61.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
38 | J78 | J71 | 63 | 141.9 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
39 | J73 | J72 | 63 | 17.7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
40 | J72 | J59 | 63 | 79.7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
41 | J59 | J60 | 63 | 59.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
42 | J59 | J57 | 63 | 34.9 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
43 | J57 | J58 | 63 | 57.7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
44 | J57 | J57A | 63 | 17.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
45 | J55 | J48 | 63 | 143.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
46 | J36 | J26 | 63 | 94.4 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
47 | J45 | J46 | 63 | 57.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
48 | J72 | J81 | 63 | 51.4 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
49 | J72 | J81 | 63 | 23.9 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
50 | J81 | J82 | 63 | 38 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
51 | J81 | J85 | 63 | 96.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
52 | J81 | J83 | 63 | 4.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
53 | J85 | J86 | 63 | 3.8 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
54 | J83 | J86 | 63 | 20.7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
55 | J83 | J88 | 63 | 225.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
56 | J85 | J83 | 63 | 186.9 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
57 | J83 | J84 | 63 | 71.4 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
58 | J79 | J49 | 63 | 205.22 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
59 | J18 | J19 | 63 | 17.8 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
60 | J32A | J23 | 63 | 40.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
61 | J23 | J21 | 63 | 11.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
62 | J21 | J22 | 63 | 29.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
63 | J21 | J21A | 63 | 14.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
64 | J21 | J19 | 63 | 34.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
65 | J23 | J31 | 63 | 21.8 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
66 | J31 | J31A | 63 | 21.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | choumari | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | J112 | J115 | 110 | 132.8 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
2 | J115 | J113 | 110 | 52.8 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
3 | J2 | J3 | 110 | 17.6 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
4 | J3 | J5 | 110 | 57.7 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
5 | J5 | J10 | 110 | 39.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
6 | J113 | J116 | 75 | 55.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
7 | J14 | J24 | 75 | 14 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
8 | J24 | J48 | 75 | 81.4 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
9 | J57 | J55 | 75 | 86.8 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
10 | J26 | J45 | 75 | 43.3 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
11 | J83 | J80 | 75 | 69.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
12 | J49 | J45 | 75 | 31 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
13 | J26 | J18 | 75 | 20.8 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
14 | J104 | J103 | 75 | 6.6 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
15 | J112 | J127 | 75 | 104 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
16 | J127 | J128 | 75 | 23.6 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
17 | J104 | J103 | 75 | 6.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
18 | J104 | J103 | 75 | 141.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
19 | J105 | J112 | 90 | 134.6 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
20 | J56 | J31 | 63 | 29 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
21 | J56 | J31 | 63 | 51.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
22 | J181 | J178 | 63 | 264.9 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
23 | J178 | J180 | 63 | 91.4 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
24 | J178 | J179 | 63 | 3 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
25 | J178 | J179 | 63 | 78.3 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
26 | J178 | J156 | 63 | 311.8 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
27 | J156 | J160 | 63 | 3.4 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
28 | J156 | J160 | 63 | 40.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
29 | J160 | J159 | 63 | 16 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
30 | J160 | J161 | 63 | 14 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
31 | J161 | J162 | 63 | 31.6 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
32 | J161 | J163 | 63 | 45.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
33 | J163 | J164 | 63 | 74.3 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
34 | J163 | J167 | 63 | 95.9 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
35 | J156 | J156A | 63 | 59.9 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
36 | J156A | J156B | 63 | 2.9 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
37 | J156A | J156B | 63 | 58.9 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
38 | J156A | J156B | 63 | 13.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
39 | J175 | J177 | 63 | 3.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
40 | J175 | J177 | 63 | 133.7 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
41 | J175 | J176 | 63 | 2.8 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
42 | J175 | J176 | 63 | 99.3 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
43 | J156A | J175 | 63 | 140.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
44 | J156 | J93 | 63 | 624.7 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
45 | J156 | J93 | 63 | 20 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
46 | J156 | J93 | 63 | 3.6 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
47 | J99 | J100 | 63 | 3.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
48 | J99 | J100 | 63 | 70.3 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
49 | J127 | J140 | 63 | 416.6 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
50 | J140 | J141 | 63 | 74 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
51 | J140 | J143 | 63 | 203 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
52 | J143 | J147 | 63 | 248.5 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
53 | J128 | J131 | 63 | 158.4 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
54 | J128 | J131 | 63 | 4.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
55 | J131 | J135 | 63 | 298.9 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | choumari | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | J10 | J14 | 110 | 63.5 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
2 | J10 | J14 | 110 | 3.5 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
3 | J18 | J12 | 110 | 27.4 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
4 | J103 | J105 | 110 | 175.3 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
5 | J131 | J132 | 63 | 371.1 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
6 | J128 | J123 | 63 | 3 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
7 | J128 | J123 | 63 | 152.5 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
8 | J123 | J124 | 63 | 98.9 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
9 | J123 | J119 | 63 | 42.9 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
10 | J119 | J120 | 63 | 33 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
11 | J119 | J118 | 63 | 41.3 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
12 | J118 | J127 | 63 | 55.3 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
13 | J118 | J127 | 63 | 75.6 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
14 | J118 | J127 | 63 | 29 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
15 | J118 | J127 | 63 | 3.2 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
16 | J118 | J114 | 63 | 74.3 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
17 | J114 | J112 | 63 | 49.1 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
18 | J114 | J112 | 63 | 36.7 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
19 | J114 | J111 | 63 | 4.2 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
20 | J114 | J111 | 63 | 63 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
21 | J114 | J111 | 63 | 49.8 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
22 | J111 | J106 | 63 | 98.7 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
23 | J111 | J104 | 63 | 58 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
24 | J111 | J104 | 63 | 4 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
25 | J111 | J104 | 63 | 43.2 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date