## barasarai
HYDROSTATIC TEST FOR PRESSURE PIPES
[13 empty] | J4 | J5 | B.T ROAD |  | 63 | 3.2
Project:- |  | Rural water supply project Under JJM , Pratapgarh , Utter Pradesh | [10 empty] | J4 | J7 |  |  | 63 | 11.5
Client : - |  | State Water & Sanitation Mission Govt of Uttar Pradesh | [10 empty] | J22 | J21 |  |  | 63 | 9
TPI :- |  | Medhaj Techno Concept Pvt . Ltd. | [10 empty] | J22 | J21 | BRICK ROAD |  | 63 | 14
Contractor :- |  | Power Mech Project Ltd. | [10 empty] | J24 | J23 |  |  | 63 | 105
Block: MANGRAURA, G.P-BARASARI | [12 empty] | J25 | J39 |  |  | 63 | 78.5
Dail Log Ref. …………………. | [5 empty] | Tested as per CPHEEO …………………….. | [6 empty] | J23 | J39 | BRICK ROAD |  | 63 | 23.8
[13 empty] | J39 | J45 |  |  | 63 | 41.2
Date | [5 empty] | Date of Testing | [6 empty] | J45 | J53 |  |  | 63 | 74.8
SL. No. | Material of Pipe | OD (MM) | Start Node | End Node | Length | Applied test pressure (kg/cm'2) | Time in Hrs |  |  | Observation | Remark |  | J72 | J71 |  |  | 63 | 24.5
[7 empty] | Pressure rising time (Hrs) | Pressure Released time (Hrs) | Total Duration Hrs |  |  |  | J71 | J70 |  |  | 63 | 18.5
1 | HDPE | 140 | J10 | J49 | 403 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | J70 | J68 |  |  | 63 | 60
2 | HDPE | 140 | J49 | J54 | 121 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | J68 | J52 |  |  | 63 | 29.5
3 | HDPE | 140 | J54 | J55 | 29 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | J52 | J68 | BRICK ROAD |  | 63 | 55.4
4 | HDPE | 140 | J55 | J67 | 121.5 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | J52 | J50 |  |  | 63 | 25.4
5 | HDPE | 160 | J1 | J2 | 228 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | J52 | J46 |  |  | 63 | 15.4
6 | HDPE | 63 | J4 | J5 | 3.2 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | J46 | J45 |  |  | 63 | 77.3
7 | HDPE | 63 | J4 | J7 | 11.5 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | J39 | J38 |  |  | 63 | 24.5
8 | HDPE | 63 | J22 | J21 | 9 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | J38 | J37 | BRICK ROAD |  | 63 | 22.1
9 | HDPE | 63 | J22 | J21 | 14 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | J38 | J43 | BRICK ROAD |  | 63 | 47.5
10 | HDPE | 63 | J24 | J23 | 105 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | J43 | J46 |  |  | 63 | 19
11 | HDPE | 63 | J25 | J39 | 78.5 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | J43 | J44 | BRICK ROAD |  | 63 | 39.9
12 | HDPE | 63 | J23 | J39 | 23.8 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | J68 | J69 | BRICK ROAD |  | 63 | 18.4
13 | HDPE | 63 | J39 | J45 | 41.2 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | J73 | J74 | BRICK ROAD |  | 63 | 123.5
14 | HDPE | 63 | J45 | J53 | 74.8 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | J76 | J75 | BRICK ROAD |  | 63 | 68.2
15 | HDPE | 63 | J72 | J71 | 24.5 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | J76 | J71 |  |  | 63 | 95.7
16 | HDPE | 63 | J71 | J70 | 18.5 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | J70 | J75 |  |  | 63 | 61.5
17 | HDPE | 63 | J70 | J68 | 60 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | J89 | J90 | BRICK ROAD |  | 63 | 8.4
18 | HDPE | 63 | J68 | J52 | 29.5 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | J89 | J90 |  |  | 63 | 157
19 | HDPE | 63 | J52 | J68 | 55.4 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | J83 | J82 |  |  | 63 | 22.2
20 | HDPE | 63 | J52 | J50 | 25.4 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | J82 | J88 |  |  | 63 | 69.8
21 | HDPE | 63 | J52 | J46 | 15.4 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | J82 | J80 |  |  | 63 | 84.2
22 | HDPE | 63 | J46 | J45 | 77.3 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | J80 | J79 |  |  | 63 | 28.5
23 | HDPE | 63 | J39 | J38 | 24.5 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | J80 | J86 |  |  | 63 | 117.2
24 | HDPE | 63 | J38 | J37 | 22.1 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | J80 | J86 | BRICK ROAD |  | 63 | 16
25 | HDPE | 63 | J38 | J43 | 47.5 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | J86 | J81 | BRICK ROAD |  | 63 | 96.3
26 | HDPE | 63 | J43 | J46 | 19 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | J92 | J93 |  |  | 63 | 288.8
27 | HDPE | 63 | J43 | J44 | 39.9 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | J36 | J32 |  |  | 63 | 115.1
28 | HDPE | 63 | J68 | J69 | 18.4 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | J32 | J33 | BRICK ROAD |  | 63 | 34.2
29 | HDPE | 63 | J73 | J74 | 123.5 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | J32 | J30 | BRICK ROAD |  | 63 | 73.5
30 | HDPE | 63 | J76 | J75 | 68.2 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | J30 | J27 |  |  | 63 | 47
31 | HDPE | 63 | J76 | J71 | 95.7 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | J79 | J133 |  |  | 63 | 637
32 | HDPE | 63 | J70 | J75 | 61.5 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | J133 | J140 |  |  | 63 | 7
33 | HDPE | 63 | J89 | J90 | 8.4 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | J133 | J140 |  |  | 63 | 275.6
34 | HDPE | 63 | J89 | J90 | 157 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | J133 | J140 |  |  | 63 | 11
35 | HDPE | 63 | J83 | J82 | 22.2 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | J133 | J140 | B.T ROAD |  | 63 | 3
36 | HDPE | 63 | J82 | J88 | 69.8 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | J144 | J144A |  |  | 63 | 8
37 | HDPE | 63 | J82 | J80 | 84.2 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | J144A | J144B |  |  | 63 | 113
38 | HDPE | 63 | J80 | J79 | 28.5 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | J144A | J141 |  |  | 63 | 66.3
39 | HDPE | 63 | J80 | J86 | 117.2 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | J141 | J141A |  |  | 63 | 73
40 | HDPE | 63 | J80 | J86 | 16 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | J141 | J141B |  |  | 63 | 50
41 | HDPE | 63 | J86 | J81 | 96.3 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | J127 | J128 |  |  | 63 | 168
42 | HDPE | 63 | J92 | J93 | 288.8 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | J96 | J97 |  |  | 63 | 148.5
43 | HDPE | 63 | J36 | J32 | 115.1 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | J54 | J57 | B.T ROAD |  | 63 | 3
44 | HDPE | 63 | J32 | J33 | 34.2 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | J54 | J57 |  |  | 63 | 134
45 | HDPE | 63 | J32 | J30 | 73.5 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | J57 | J61 | B.T ROAD |  | 63 | 3
46 | HDPE | 63 | J30 | J27 | 47 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | J57 | J61 |  |  | 63 | 268.9
47 | HDPE | 63 | J79 | J133 | 637 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | J57 | J62 |  |  | 63 | 140
48 | HDPE | 63 | J133 | J140 | 7 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | J62 | J63 |  |  | 63 | 147
49 | HDPE | 63 | J133 | J140 | 275.6 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | J62 | J63 | B.T ROAD |  | 63 | 3
50 | HDPE | 63 | J133 | J140 | 11 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | J55 | J56 |  |  | 63 | 181.7
51 | HDPE | 63 | J133 | J140 | 3 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | J67 | J49 |  |  | 63 | 216.5
|  | POWER MECH |  |  |  | MEDHAJ |  |  | JAL NIGAM U.P. |  |  |  | J186 | J188 |  |  | 63 | 98
Name: | [12 empty] | J213 | J219 |  |  | 63 | 164
Designation: | [12 empty] | J213 | J217 |  |  | 63 | 88
Signature: | [12 empty] | J213 | J217 | BRICK ROAD |  | 63 | 30
Date: | [12 empty] | J217 | J226 | BRICK ROAD |  | 63 | 28
[13 empty] | J217 | J226 |  |  | 63 | 17.2
[13 empty] | J226 | J226A |  |  | 63 | 12.7
| HYDROSTATIC TEST FOR PRESSURE PIPES | [11 empty] | J226A | J226B |  |  | 63 | 12.2
[13 empty] | J226A | J226C |  |  | 63 | 36.3
[13 empty] | J209 | J207 |  |  | 63 | 12.4
[13 empty] | J209 | J208 |  |  | 63 | 46
Project:- |  | Rural water supply project Under JJM , Pratapgarh , Utter Pradesh | [10 empty] | J209A | J209B |  |  | 63 | 17.7
Client : - |  | State Water & Sanitation Mission Govt of Uttar Pradesh | [10 empty] | j201 | j201A |  |  | 63 | 26.3
TPI :- |  | Medhaj Techno Concept Pvt . Ltd. | [10 empty] | J210 | J210A | BRICK ROAD |  | 63 | 70
Contractor :- |  | Power Mech Project Ltd. | [10 empty] | J210A | J210B |  |  | 63 | 46.7
Block: MANGRAURA, G.P-BARASARI | [12 empty] | J210A | J212 | BRICK ROAD |  | 63 | 27.5
Dail Log Ref. …………………. | [5 empty] | Tested as per CPHEEO …………………….. | [6 empty] | J216 | J215 | B.T ROAD |  | 63 | 3
[13 empty] | J216 | J215 | BRICK ROAD |  | 63 | 32
Date | [5 empty] | Date of Testing | [6 empty] | J218 | J223 | B.T ROAD |  | 63 | 3
SL. No. | Material of Pipe | OD (MM) | Start Node | End Node | Length | Applied test pressure (kg/cm'2) | Time in Hrs |  |  | Observation | Remark |  | J218 | J223 |  |  | 63 | 64.3
[7 empty] | Pressure rising time (Hrs) | Pressure Released time (Hrs) | Total Duration Hrs |  |  |  | J200 | J199 |  |  | 63 | 125
1 | HDPE | 140 | J2 | J3 | 172.5 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | J223 | J224 | B.T ROAD |  | 63 | 3
2 | HDPE | 140 | J3 | J11 | 80 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | J223 | J224 | BRICK ROAD |  | 63 | 21
3 | HDPE | 140 | J3 | J4 | 19.8 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | J232 | J233 |  |  | 63 | 59.6
4 | HDPE | 140 | J4 | J10 | 29.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | J233 | J233A | B.T ROAD |  | 63 | 3
5 | HDPE | 140 | J4 | J10 | 3 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | J233 | J233A |  |  | 63 | 26.6
6 | HDPE | 140 | J10 | J49 | 3 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | J233A | J233B |  |  | 63 | 109.5
7 | HDPE | 63 | J144 | J144A | 8 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | J233A | J226 |  |  | 63 | 63
8 | HDPE | 63 | J144A | J144B | 113 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | J234 | J251 | INTERLOCKING |  | 63 | 107.3
9 | HDPE | 63 | J144A | J141 | 66.3 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | J251 | J254 | INTERLOCKING |  | 63 | 1.5
10 | HDPE | 63 | J141 | J141A | 73 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | J251 | J254 |  |  | 63 | 10
11 | HDPE | 63 | J141 | J141B | 50 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | J254 | J255 | BRICK ROAD |  | 63 | 32.1
12 | HDPE | 63 | J127 | J128 | 168 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | J254 | J255 |  |  | 63 | 87.2
13 | HDPE | 63 | J96 | J97 | 148.5 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | J251 | J252 | INTERLOCKING |  | 63 | 17.8
14 | HDPE | 63 | J54 | J57 | 3 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | J252 | J253 | INTERLOCKING |  | 63 | 4
15 | HDPE | 63 | J54 | J57 | 134 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | J252 | J253 |  |  | 63 | 11
16 | HDPE | 63 | J57 | J61 | 3 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | J252 | J249 | INTERLOCKING |  | 63 | 29
17 | HDPE | 63 | J57 | J61 | 268.9 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | J252 | J249 |  |  | 63 | 165
18 | HDPE | 63 | J57 | J62 | 140 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | J249 | J250 |  |  | 63 | 108.3
19 | HDPE | 63 | J62 | J63 | 147 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | J249 | J232 |  |  | 63 | 162
20 | HDPE | 63 | J62 | J63 | 3 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | J249 | J232 | BRICK ROAD |  | 63 | 23
21 | HDPE | 63 | J55 | J56 | 181.7 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | J157 | J154 |  |  | 63 | 79
22 | HDPE | 63 | J67 | J49 | 216.5 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | J157 | J155 |  |  | 63 | 10
23 | HDPE | 63 | J186 | J188 | 98 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | J138 | J139 |  |  | 63 | 18
24 | HDPE | 63 | J213 | J219 | 164 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | J1 | J3 |  |  | 63 | 305
25 | HDPE | 63 | J213 | J217 | 88 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | J52 | J46 |  |  | 63 | 314.6
26 | HDPE | 63 | J213 | J217 | 30 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | J114 | J117 | INTERLOCKING |  | 63 | 16.7
27 | HDPE | 63 | J217 | J226 | 28 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | J114 | J117 |  |  | 63 | 79.6
28 | HDPE | 63 | J217 | J226 | 17.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | J117 | J118 |  |  | 63 | 78
29 | HDPE | 63 | J226 | J226A | 12.7 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | J117 | J120 |  |  | 63 | 12.5
30 | HDPE | 63 | J226A | J226B | 12.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | J120 | J121 |  |  | 63 | 35.3
31 | HDPE | 63 | J226A | J226C | 36.3 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | J120 | J122 |  |  | 63 | 75
32 | HDPE | 63 | J209 | J207 | 12.4 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | J115 | J116 |  |  | 63 | 75
33 | HDPE | 63 | J209 | J208 | 46 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | J158 | J159 |  |  | 63 | 69
34 | HDPE | 63 | J209A | J209B | 17.7 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | J158 | J170 |  |  | 63 | 298.5
|  | POWER MECH |  |  |  | MEDHAJ |  |  | JAL NIGAM U.P. |  |  |  | J170 | J177 |  |  | 63 | 115.2
Name: | [12 empty] | J177 | J185 |  |  | 63 | 22.4
Designation: | [12 empty] | J177 | J185 | BRICK ROAD |  | 63 | 227
Signature: | [12 empty] | J177 | J171 |  |  | 63 | 107.3
Date: | [12 empty] | J170 | J166 |  |  | 63 | 90.8
[13 empty] | J166 | J169 |  |  | 63 | 70
[13 empty] | J166 | J161 |  |  | 63 | 61.6
| HYDROSTATIC TEST FOR PRESSURE PIPES | [11 empty] | J161 | J162 |  |  | 63 | 70
[13 empty] | J161 | j157 |  |  | 63 | 29.6
[13 empty] | J112 | J111 |  |  | 63 | 23.9
[13 empty] | J94 | J110 |  |  | 63 | 48.6
Project:- |  | Rural water supply project Under JJM , Pratapgarh , Utter Pradesh
Client : - |  | State Water & Sanitation Mission Govt of Uttar Pradesh | [10 empty] | J91 | J98 | BRICK ROAD |  | 63 | 190.8
TPI :- |  | Medhaj Techno Concept Pvt . Ltd. | [10 empty] | J91 | J98 |  |  | 63 | 11
Contractor :- |  | Power Mech Project Ltd. | [10 empty] | J98 | J99 |  |  | 63 | 11
Block: MANGRAURA, G.P-BARASARI | [12 empty] | J99 | J105 |  |  | 63 | 70
Dail Log Ref. …………………. | [5 empty] | Tested as per CPHEEO …………………….. | [6 empty] | J99 | J107 |  |  | 63 | 133.3
[13 empty] | J107 | J108 |  |  | 63 | 58
Date | [5 empty] | Date of Testing | [6 empty] | J107 | J109 |  |  | 63 | 113.8
SL. No. | Material of Pipe | OD (MM) | Start Node | End Node | Length | Applied test pressure (kg/cm'2) | Time in Hrs |  |  | Observation | Remark |  | J98 | J100 |  |  | 63 | 58.4
[7 empty] | Pressure rising time (Hrs) | Pressure Released time (Hrs) | Total Duration Hrs
1 | HDPE | 125 | J113 | J112 | 65.1 | 5KG/CM2 | 3 | 1 | 4 | NO |  |  | J110 | J114 |  |  | 63 | 188
2 | HDPE | 125 | J94 | J91 | 48 | 5KG/CM2 | 3 | 1 | 4 | NO |  |  | J114 | J113 |  |  | 63 | 21
3 | HDPE | 125 | J91 | J67 | 327 | 5KG/CM2 | 3 | 1 | 4 | NO |  |  | J114 | J113 |  |  | 63 | 1.8
4 | HDPE | 125 | J113 | J115 | 87.9 | 5KG/CM2 | 3 | 1 | 4 | NO |  |  | J82A | J82B |  |  | 63 | 31
5 | HDPE | 110 | J26 | J51 | 19 | 5KG/CM2 | 3 | 1 | 4 | NO |  |  | J23 | J18 |  |  | 63 | 124
6 | HDPE | 110 | J51 | J69 | 69 | 5KG/CM2 | 3 | 1 | 4 | NO |  |  | J209 | J209A |  |  | 75 | 33.3
7 | HDPE | 110 | J89 | J92 | 5 | 5KG/CM2 | 3 | 1 | 4 | NO |  |  | J146 | J158 |  |  | 75 | 282.1
8 | HDPE | 110 | J89 | J92 | 3 | 5KG/CM2 | 3 | 1 | 4 | NO |  |  | J155 | J151 |  |  | 75 | 185
9 | HDPE | 110 | J89 | J92 | 10 | 5KG/CM2 | 3 | 1 | 4 | NO |  |  | J151 | J145 |  |  | 75 | 95.5
10 | HDPE | 110 | J144 | J140 | 42 | 5KG/CM2 | 3 | 1 | 4 | NO |  |  | J151 | J154 |  |  | 75 | 129
11 | HDPE | 110 | J140 | J127 | 154.2 | 5KG/CM2 | 3 | 1 | 4 | NO |  |  | J154 | J160 |  |  | 75 | 86.6
12 | HDPE | 110 | J127 | J96 | 350 | 5KG/CM2 | 3 | 1 | 4 | NO |  |  | J10 | J22 | BRICK ROAD |  | 75 | 88
13 | HDPE | 110 | J127 | J96 | 6 | 5KG/CM2 | 3 | 1 | 4 | NO |  |  | J10 | J22 |  |  | 75 | 69
14 | HDPE | 110 | J96 | J92 | 28.7 | 5KG/CM2 | 3 | 1 | 4 | NO |  |  | J22 | J24 |  |  | 75 | 27.6
15 | HDPE | 110 | J144 | J186 | 182.8 | 5KG/CM2 | 3 | 1 | 4 | NO |  |  | J24 | J25 |  |  | 75 | 37.5
16 | HDPE | 110 | J186 | J192 | 152.7 | 5KG/CM2 | 3 | 1 | 4 | NO |  |  | J25 | J53 |  |  | 75 | 164.5
17 | HDPE | 110 | J192 | J196 | 8 | 5KG/CM2 | 3 | 1 | 4 | NO |  |  | J53 | J72 |  |  | 75 | 136.1
18 | HDPE | 110 | J192 | J196 | 177 | 5KG/CM2 | 3 | 1 | 4 | NO |  |  | J72 | J79 |  |  | 75 | 243
19 | HDPE | 110 | J11 | J19 | 144 | 5KG/CM2 | 3 | 1 | 4 | NO |  |  | J217 | J209 | BRICK ROAD |  | 75 | 62.2
20 | HDPE | 110 | J19 | J50 | 141 | 5KG/CM2 | 3 | 1 | 4 | NO |  |  | J209 | J198 |  |  | 75 | 151
21 | HDPE | 110 | J115 | J124 | 31 | 5KG/CM2 | 3 | 1 | 4 | NO |  |  | J201 | J201A |  |  | 75 | 72
22 | HDPE | 110 | J115 | J124 | 8 | 5KG/CM2 | 3 | 1 | 4 | NO |  |  | J216 | J218 |  |  | 75 | 30.2
23 | HDPE | 110 | J115 | J124 | 40 | 5KG/CM2 | 3 | 1 | 4 | NO |  |  | J218 | J200 |  |  | 75 | 4
24 | HDPE | 63 | j201 | j201A | 26.3 | 5KG/CM2 | 3 | 1 | 4 | NO |  |  | J200 | J223 |  |  | 75 | 55.8
25 | HDPE | 63 | J210 | J210A | 70 | 5KG/CM2 | 3 | 1 | 4 | NO |  |  | J223 | J232 |  |  | 75 | 102
26 | HDPE | 63 | J210A | J210B | 46.7 | 5KG/CM2 | 3 | 1 | 4 | NO |  |  | J192 | J193 |  |  | 90 | 42.5
27 | HDPE | 63 | J210A | J212 | 27.5 | 5KG/CM2 | 3 | 1 | 4 | NO |  |  | J196 | J213 |  |  | 90 | 278.5
28 | HDPE | 63 | J216 | J215 | 3 | 5KG/CM2 | 3 | 1 | 4 | NO |  |  | J196 | J198 |  |  | 90 | 48
29 | HDPE | 63 | J216 | J215 | 32 | 5KG/CM2 | 3 | 1 | 4 | NO |  |  | J198 | J201 |  |  | 90 | 46.5
30 | HDPE | 63 | J218 | J223 | 3 | 5KG/CM2 | 3 | 1 | 4 | NO |  |  | J198 | J201 | INTERLOCKING |  | 90 | 5
31 | HDPE | 63 | J218 | J223 | 64.3 | 5KG/CM2 | 3 | 1 | 4 | NO |  |  | J201 | J204 |  |  | 90 | 117
32 | HDPE | 63 | J200 | J199 | 125 | 5KG/CM2 | 3 | 1 | 4 | NO |  |  | J201 | J204 | B.T ROAD |  | 90 | 5
33 | HDPE | 63 | J223 | J224 | 3 | 5KG/CM2 | 3 | 1 | 4 | NO |  |  | J204 | J210 |  |  | 90 | 43
34 | HDPE | 63 | J223 | J224 | 21 | 5KG/CM2 | 3 | 1 | 4 | NO |  |  | J210 | J216 |  |  | 90 | 38.3
|  | POWER MECH |  |  |  | MEDHAJ |  |  | JAL NIGAM U.P. |  |  |  | J204 | J197 |  |  | 90 | 113
Name: | [12 empty] | J204 | J197 | B.T ROAD |  | 90 | 3
Designation: | [12 empty] | J197 | J145 |  |  | 90 | 663
Signature: | [12 empty] | J69 | J73 | BRICK ROAD |  | 110 | 50.9
Date: | [12 empty] | J73 | J76 |  |  | 110 | 9
[13 empty] | J73 | J76 | BRICK ROAD |  | 110 | 16.7
[13 empty] | J76 | J81 |  |  | 110 | 151.6
| HYDROSTATIC TEST FOR PRESSURE PIPES | [11 empty] | J81 | J89 | BRICK ROAD |  | 110 | 20
[13 empty] | J89 | J92 | culvert |  | 110 | 5
[13 empty] | J89 | J92 | B.T ROAD |  | 110 | 3
[13 empty] | J89 | J92 | BRICK ROAD |  | 110 | 10
Project:- |  | Rural water supply project Under JJM , Pratapgarh , Utter Pradesh | [10 empty] | J144 | J140 |  |  | 110 | 42
Client : - |  | State Water & Sanitation Mission Govt of Uttar Pradesh | [10 empty] | J140 | J127 |  |  | 110 | 154.2
TPI :- |  | Medhaj Techno Concept Pvt . Ltd. | [10 empty] | J127 | J96 |  |  | 110 | 350
Contractor :- |  | Power Mech Project Ltd. | [10 empty] | J127 | J96 | B.T ROAD |  | 110 | 6
Block: MANGRAURA, G.P-BARASARI | [12 empty] | J96 | J92 |  |  | 110 | 28.7
Dail Log Ref. …………………. | [5 empty] | Tested as per CPHEEO …………………….. | [6 empty] | J144 | J186 |  |  | 110 | 182.8
[13 empty] | J186 | J192 |  |  | 110 | 152.7
Date | [5 empty] | Date of Testing | [6 empty] | J192 | J196 | B.T ROAD |  | 110 | 8
SL. No. | Material of Pipe | OD (MM) | Start Node | End Node | Length | Applied test pressure (kg/cm'2) | Time in Hrs |  |  | Observation | Remark |  | J192 | J196 |  |  | 110 | 177
[7 empty] | Pressure rising time (Hrs) | Pressure Released time (Hrs) | Total Duration Hrs |  |  |  | J11 | J19 |  |  | 110 | 144
1 | HDPE | 110 | J69 | J73 | 50.9 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | J19 | J50 |  |  | 110 | 141
2 | HDPE | 110 | J73 | J76 | 9 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | J115 | J124 | BRICK ROAD |  | 110 | 31
3 | HDPE | 110 | J73 | J76 | 16.7 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | J115 | J124 | culvert |  | 110 | 8
4 | HDPE | 110 | J76 | J81 | 151.6 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | J115 | J124 |  |  | 110 | 40
5 | HDPE | 110 | J81 | J89 | 20 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
6 | HDPE | 75 | J209 | J209A | 33.3 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
7 | HDPE | 75 | J146 | J158 | 282.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
8 | HDPE | 75 | J155 | J151 | 185 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
9 | HDPE | 75 | J151 | J145 | 95.5 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | J26 | J51 |  |  | 110 | 19
10 | HDPE | 75 | J151 | J154 | 129 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | J51 | J69 |  |  | 110 | 69
11 | HDPE | 75 | J154 | J160 | 86.6 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | J113 | J112 |  |  | 125 | 65.1
12 | HDPE | 75 | J10 | J22 | 88 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | J94 | J91 |  |  | 125 | 48
13 | HDPE | 75 | J10 | J22 | 69 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | J91 | J67 |  |  | 125 | 327
14 | HDPE | 75 | J22 | J24 | 27.6 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | J113 | J115 | BRICK ROAD |  | 125 | 87.9
15 | HDPE | 75 | J24 | J25 | 37.5 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | J2 | J3 |  |  | 140 | 172.5
16 | HDPE | 75 | J25 | J53 | 164.5 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | J3 | J11 |  |  | 140 | 80
17 | HDPE | 75 | J53 | J72 | 136.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | J3 | J4 |  |  | 140 | 19.8
18 | HDPE | 75 | J72 | J79 | 243 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | J4 | J10 |  |  | 140 | 29.2
19 | HDPE | 75 | J217 | J209 | 62.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | J4 | J10 | B.T ROAD |  | 140 | 3
20 | HDPE | 75 | J209 | J198 | 151 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | J10 | J49 | culvert |  | 140 | 3
21 | HDPE | 75 | J201 | J201A | 72 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | J10 | J49 |  |  | 140 | 403
22 | HDPE | 75 | J216 | J218 | 30.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | J49 | J54 |  |  | 140 | 121
23 | HDPE | 63 | j201 | j201A | 26.3 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | J54 | J55 |  |  | 140 | 29
24 | HDPE | 63 | J210 | J210A | 70 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | J55 | J67 |  |  | 140 | 121.5
25 | HDPE | 63 | J210A | J210B | 46.7 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | J1 | J2 |  |  | 160 | 228
26 | HDPE | 63 | J210A | J212 | 27.5 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
27 | HDPE | 63 | J216 | J215 | 3 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
28 | HDPE | 63 | J216 | J215 | 32 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
29 | HDPE | 63 | J218 | J223 | 3 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
30 | HDPE | 63 | J218 | J223 | 64.3 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
31 | HDPE | 63 | J200 | J199 | 125 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
32 | HDPE | 63 | J223 | J224 | 3 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
33 | HDPE | 63 | J223 | J224 | 21 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
34 | HDPE | 63 | J232 | J233 | 59.6 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
35 | HDPE | 63 | J233 | J233A | 3 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
36 | HDPE | 63 | J233 | J233A | 26.6 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
37 | HDPE | 63 | J233A | J233B | 109.5 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
38 | HDPE | 63 | J233A | J226 | 63 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
39 | HDPE | 63 | J234 | J251 | 107.3 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
40 | HDPE | 63 | J251 | J254 | 1.5 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
41 | HDPE | 63 | J251 | J254 | 10 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
42 | HDPE | 63 | J254 | J255 | 32.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
43 | HDPE | 63 | J254 | J255 | 87.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
44 | HDPE | 63 | J251 | J252 | 17.8 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
45 | HDPE | 63 | J252 | J253 | 4 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
46 | HDPE | 63 | J252 | J253 | 11 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
47 | HDPE | 63 | J252 | J249 | 29 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
48 | HDPE | 63 | J252 | J249 | 165 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
49 | HDPE | 63 | J249 | J250 | 108.3 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
50 | HDPE | 63 | J249 | J232 | 162 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
51 | HDPE | 63 | J249 | J232 | 23 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
52 | HDPE | 63 | J157 | J154 | 79 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
53 | HDPE | 63 | J157 | J155 | 10 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
54 | HDPE | 63 | J138 | J139 | 18 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
55 | HDPE | 63 | J1 | J3 | 305 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
56 | HDPE | 63 | J114 | J117 | 16.7 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
57 | HDPE | 63 | J114 | J117 | 79.6 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
58 | HDPE | 63 | J117 | J118 | 78 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
|  | POWER MECH |  |  |  | MEDHAJ |  |  | JAL NIGAM U.P.
Name:
Designation:
Signature:
Date:
HYDROSTATIC TEST FOR PRESSURE PIPES
Project:- |  | Rural water supply project Under JJM , Pratapgarh , Utter Pradesh
Client : - |  | State Water & Sanitation Mission Govt of Uttar Pradesh
TPI :- |  | Medhaj Techno Concept Pvt . Ltd.
Contractor :- |  | Power Mech Project Ltd.
Block: MANGRAURA, G.P-BARASARI
Dail Log Ref. …………………. | [5 empty] | Tested as per CPHEEO ……………………..
Date | [5 empty] | Date of Testing
SL. No. | Material of Pipe | OD (MM) | Start Node | End Node | Length | Applied test pressure (kg/cm'2) | Time in Hrs |  |  | Observation | Remark
[7 empty] | Pressure rising time (Hrs) | Pressure Released time (Hrs) | Total Duration Hrs
1 | HDPE | 90 | J192 | J193 | 42.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
2 | HDPE | 90 | J196 | J213 | 278.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
3 | HDPE | 90 | J196 | J198 | 48 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
4 | HDPE | 90 | J198 | J201 | 46.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
5 | HDPE | 90 | J198 | J201 | 5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
6 | HDPE | 90 | J201 | J204 | 117 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
7 | HDPE | 90 | J201 | J204 | 5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
8 | HDPE | 90 | J204 | J210 | 43 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
9 | HDPE | 90 | J210 | J216 | 38.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | J218 | J200 |  |  | 75 | 4
10 | HDPE | 90 | J204 | J197 | 113 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | J200 | J223 |  |  | 75 | 55.8
11 | HDPE | 90 | J204 | J197 | 3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | J223 | J232 |  |  | 75 | 102
12 | HDPE | 90 | J197 | J145 | 663 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
13 | HDPE | 75 | J218 | J200 | 4 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
14 | HDPE | 75 | J200 | J223 | 55.8 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
15 | HDPE | 75 | J223 | J232 | 102 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
16 | HDPE | 63 | J117 | J120 | 12.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
17 | HDPE | 63 | J120 | J121 | 35.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
18 | HDPE | 63 | J120 | J122 | 75 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
19 | HDPE | 63 | J115 | J116 | 75 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
20 | HDPE | 63 | J158 | J159 | 69 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
21 | HDPE | 63 | J158 | J170 | 298.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
22 | HDPE | 63 | J170 | J177 | 115.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
23 | HDPE | 63 | J177 | J185 | 22.4 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
24 | HDPE | 63 | J177 | J185 | 227 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
25 | HDPE | 63 | J177 | J171 | 107.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
26 | HDPE | 63 | J170 | J166 | 90.8 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
27 | HDPE | 63 | J166 | J169 | 70 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
28 | HDPE | 63 | J166 | J161 | 61.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
29 | HDPE | 63 | J161 | J162 | 70 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
30 | HDPE | 63 | J161 | j157 | 29.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
31 | HDPE | 63 | J112 | J111 | 23.9 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
32 | HDPE | 63 | J94 | J110 | 48.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
33 | HDPE | 63 | J91 | J98 | 190.8 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
34 | HDPE | 63 | J91 | J98 | 11 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
35 | HDPE | 63 | J98 | J99 | 11 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO |  |  |  | 4181.6
36 | HDPE | 63 | J99 | J105 | 70 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO |  |  |  | 2593.9
37 | HDPE | 63 | J99 | J107 | 133.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO |  |  |  | 2521.2
38 | HDPE | 63 | J107 | J108 | 58 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO |  |  |  | 4483.4
39 | HDPE | 63 | J107 | J109 | 113.8 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO |  |  |  | 4008.4
40 | HDPE | 63 | J98 | J100 | 58.4 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO |  |  |  | 17788.5
41 | HDPE | 63 | J110 | J114 | 188 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO |  |  |  | 17474.1
42 | HDPE | 63 | J114 | J113 | 21 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
43 | HDPE | 63 | J114 | J113 | 1.8 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
44 | HDPE | 63 | J82A | J82B | 31 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
45 | HDPE | 63 | J23 | J18 | 124 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
|  | POWER MECH |  |  |  | MEDHAJ |  |  | JAL NIGAM U.P.
Name:
Designation:
Signature:
Date: