## Barasarai
BARASARAI(JMR) | [7 empty] | CUMMULATIVE | Remark
Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | Dia of pipe | Pipe Length (M) | As per dpr
1 | J4 | J5 | B.T ROAD |  | 63 | 3.2 | 12 | 3.2 |  | 3.2
2 | J4 | J7 |  |  | 63 | 11.5 | 45 | 14.7 |  | 11.5
3 | J22 | J21 |  |  | 63 | 9 | 21 | 23.7 |  | 9
4 | J22 | J21 | BRICK ROAD |  | 63 | 14 |  | 37.7 |  | 14
5 | J24 | J23 |  |  | 63 | 105 | 103 | 142.7 |  | 105
6 | J25 | J39 |  |  | 63 | 78.5 | 115 | 221.2 |  | 78.5
7 | J23 | J39 | BRICK ROAD |  | 63 | 23.8 | 22 | 245 |  | 23.8
8 | J39 | J45 |  |  | 63 | 41.2 | 40 | 286.2 |  | 41.2
9 | J45 | J53 |  |  | 63 | 74.8 | 77 | 361 |  | 74.8
10 | J72 | J71 |  |  | 63 | 24.5 | 26 | 385.5 |  | 24.5
11 | J71 | J70 |  |  | 63 | 18.5 | 16 | 404 |  | 18.5
12 | J70 | J68 |  |  | 63 | 60 | 59 | 464 |  | 60
13 | J68 | J52 |  |  | 63 | 29.5 | 90 | 493.5 |  | 29.5
14 | J52 | J68 | BRICK ROAD |  | 63 | 55.4 |  | 548.9 |  | 55.4
15 | J52 | J50 |  |  | 63 | 25.4 | 26 | 574.3 |  | 25.4
16 | J52 | J46 |  |  | 63 | 15.4 | 46 | 589.7 |  | 15.4
17 | J46 | J45 |  |  | 63 | 77.3 | 76 | 667 |  | 77.3
18 | J39 | J38 |  |  | 63 | 24.5 | 22 | 691.5 |  | 24.5
19 | J38 | J37 | BRICK ROAD |  | 63 | 22.1 | 25 | 713.6 |  | 22.1
20 | J38 | J43 | BRICK ROAD |  | 63 | 47.5 | 45 | 761.1 |  | 47.5
21 | J43 | J46 |  |  | 63 | 19 | 21 | 780.1 |  | 19
22 | J43 | J44 | BRICK ROAD |  | 63 | 39.9 | 44 | 820 |  | 39.9
23 | J68 | J69 | BRICK ROAD |  | 63 | 18.4 | 11 | 838.4 |  | 18.4
24 | J73 | J74 | BRICK ROAD |  | 63 | 123.5 | 124 | 961.9 |  | 123.5
25 | J76 | J75 | BRICK ROAD |  | 63 | 68.2 | 42 | 1030.1 |  | 68.2
26 | J76 | J71 |  |  | 63 | 95.7 | 117 | 1125.8 |  | 95.7
27 | J70 | J75 |  |  | 63 | 61.5 | 60 | 1187.3 |  | 61.5
28 | J89 | J90 | BRICK ROAD |  | 63 | 8.4 | 165 | 1195.7 |  | 8.4
29 | J89 | J90 |  |  | 63 | 157 |  | 1352.7 |  | 157
30 | J83 | J82 |  |  | 63 | 22.2 | 29 | 1374.9 |  | 22.2
31 | J82 | J88 |  |  | 63 | 69.8 | 60 | 1444.7 |  | 69.8
32 | J82 | J80 |  |  | 63 | 84.2 | 78 | 1528.9 |  | 84.2
33 | J80 | J79 |  |  | 63 | 28.5 | 28 | 1557.4 |  | 28.5
34 | J80 | J86 |  |  | 63 | 117.2 | 149 | 1674.6 |  | 117.2
35 | J80 | J86 | BRICK ROAD |  | 63 | 16 |  | 1690.6 |  | 16
36 | J86 | J81 | BRICK ROAD |  | 63 | 96.3 | 97 | 1786.9 |  | 96.3
37 | J92 | J93 |  |  | 63 | 288.8 | 303 | 2075.7 |  | 288.8
38 | J36 | J32 |  |  | 63 | 115.1 | 115 | 2190.8 |  | 115.1
39 | J32 | J33 | BRICK ROAD |  | 63 | 34.2 | 21 | 2225 |  | 34.2
40 | J32 | J30 | BRICK ROAD |  | 63 | 73.5 | 65 | 2298.5 |  | 73.5
41 | J30 | J27 |  |  | 63 | 47 | 27 | 2345.5 |  | 47
42 | J79 | J133 |  |  | 63 | 637 | 637 | 2982.5 |  | 637
43 | J133 | J140 |  |  | 63 | 7 | 295 | 2989.5 | culvert
44 | J133 | J140 |  |  | 63 | 275.6 |  | 3265.1 |  | 282.6
45 | J133 | J140 |  |  | 63 | 11 |  | 3276.1 |  | 11
46 | J133 | J140 | B.T ROAD |  | 63 | 3 |  | 3279.1 |  | 3
47 | J144 | J144A |  |  | 63 | 8 |  | 3287.1 |  | 8
48 | J144A | J144B |  |  | 63 | 113 |  | 3400.1 |  | 113
49 | J144A | J141 |  |  | 63 | 66.3 |  | 3466.4 |  | 66.3
50 | J141 | J141A |  |  | 63 | 73 |  | 3539.4 |  | 73
51 | J141 | J141B |  |  | 63 | 50 |  | 3589.4 |  | 50
52 | J127 | J128 |  |  | 63 | 168 | 122 | 3757.4 |  | 168
53 | J96 | J97 |  |  | 63 | 148.5 | 128 | 3905.9 |  | 148.5
54 | J54 | J57 | B.T ROAD |  | 63 | 3 | 134 | 3908.9 |  | 3
55 | J54 | J57 |  |  | 63 | 134 |  | 4042.9 |  | 134
56 | J57 | J61 | B.T ROAD |  | 63 | 3 |  | 4045.9 |  | 3
57 | J57 | J61 |  |  | 63 | 268.9 | 265 | 4314.8 |  | 268.9
58 | J57 | J62 |  |  | 63 | 140 | 138 | 4454.8 |  | 140
59 | J62 | J63 |  |  | 63 | 147 | 149 | 4601.8 |  | 147
60 | J62 | J63 | B.T ROAD |  | 63 | 3 |  | 4604.8 |  | 3
61 | J55 | J56 |  |  | 63 | 181.7 | 178 | 4786.5 |  | 181.7
62 | J67 | J49 |  |  | 63 | 216.5 | 215 | 5003 |  | 216.5
63 | J186 | J188 |  |  | 63 | 98 | 128 | 5101 |  | 98
64 | J213 | J219 |  |  | 63 | 164 | 156 | 5265 |  | 164
65 | J213 | J217 |  |  | 63 | 88 | 101 | 5353 |  | 88
66 | J213 | J217 | BRICK ROAD |  | 63 | 30 |  | 5383 |  | 30
67 | J217 | J226 | BRICK ROAD |  | 63 | 28 | 80 | 5411 |  | 28
68 | J217 | J226 |  |  | 63 | 17.2 |  | 5428.2 |  | 17.2
69 | J226 | J226A |  |  | 63 | 12.7 |  | 5440.9 |  | 12.7
70 | J226A | J226B |  |  | 63 | 12.2 |  | 5453.1 |  | 12.2
71 | J226A | J226C |  |  | 63 | 36.3 |  | 5489.4 |  | 36.3
72 | J209 | J207 |  |  | 63 | 12.4 | 26 | 5501.8 |  | 12.4
73 | J209 | J208 |  |  | 63 | 46 | 23 | 5547.8 |  | 46
74 | J209A | J209B |  |  | 63 | 17.7 |  | 5565.5 |  | 17.7
75 | j201 | j201A |  |  | 63 | 26.3 |  | 5591.8 |  | 26.3
76 | J210 | J210A | BRICK ROAD |  | 63 | 70 |  | 5661.8 |  | 70
77 | J210A | J210B |  |  | 63 | 46.7 |  | 5708.5 |  | 46.7
78 | J210A | J212 | BRICK ROAD |  | 63 | 27.5 |  | 5736 |  | 27.5
79 | J216 | J215 | B.T ROAD |  | 63 | 3 | 32 | 5739 |  | 3
80 | J216 | J215 | BRICK ROAD |  | 63 | 32 |  | 5771 |  | 32
81 | J218 | J223 | B.T ROAD |  | 63 | 3 | 66 | 5774 |  | 3
82 | J218 | J223 |  |  | 63 | 64.3 |  | 5838.3 |  | 64.3
83 | J200 | J199 |  |  | 63 | 125 | 122 | 5963.3 |  | 125
84 | J223 | J224 | B.T ROAD |  | 63 | 3 | 20 | 5966.3 |  | 3
85 | J223 | J224 | BRICK ROAD |  | 63 | 21 |  | 5987.3 |  | 21
86 | J232 | J233 |  |  | 63 | 59.6 | 62 | 6046.9 |  | 59.6
87 | J233 | J233A | B.T ROAD |  | 63 | 3 |  | 6049.9 |  | 3
88 | J233 | J233A |  |  | 63 | 26.6 |  | 6076.5 |  | 26.6
89 | J233A | J233B |  |  | 63 | 109.5 |  | 6186 |  | 109.5
90 | J233A | J226 |  |  | 63 | 63 |  | 6249 |  | 63
91 | J234 | J251 | INTERLOCKING |  | 63 | 107.3 | 176 | 6356.3 |  | 107.3
92 | J251 | J254 | INTERLOCKING |  | 63 | 1.5 | 11 | 6357.8 |  | 1.5
93 | J251 | J254 |  |  | 63 | 10 |  | 6367.8 |  | 10
94 | J254 | J255 | BRICK ROAD |  | 63 | 32.1 | 85 | 6399.9 |  | 32.1
95 | J254 | J255 |  |  | 63 | 87.2 |  | 6487.1 |  | 87.2
96 | J251 | J252 | INTERLOCKING |  | 63 | 17.8 | 18 | 6504.9 |  | 17.8
97 | J252 | J253 | INTERLOCKING |  | 63 | 4 | 25 | 6508.9 |  | 4
98 | J252 | J253 |  |  | 63 | 11 |  | 6519.9 |  | 11
99 | J252 | J249 | INTERLOCKING |  | 63 | 29 | 185 | 6548.9 |  | 29
100 | J252 | J249 |  |  | 63 | 165 |  | 6713.9 |  | 165
101 | J249 | J250 |  |  | 63 | 108.3 | 65 | 6822.2 |  | 108.3
102 | J249 | J232 |  |  | 63 | 162 | 182 | 6984.2 |  | 162
103 | J249 | J232 | BRICK ROAD |  | 63 | 23 |  | 7007.2 |  | 23
104 | J157 | J154 |  |  | 63 | 79 | 104 | 7086.2 |  | 79
105 | J157 | J155 |  |  | 63 | 10 | 10 | 7096.2 |  | 10
106 | J138 | J139 |  |  | 63 | 18 | 10 | 7114.2 |  | 18
107 | J1 | J3 |  |  | 63 | 305 | 305 | 7419.2 |  | 305
108 | J52 | J46 |  |  | 63 | 314.6 | 346 | 7733.8 |  | 34.6
109 | J114 | J117 | INTERLOCKING |  | 63 | 16.7 | 90 | 7750.5 |  | 16.7
110 | J114 | J117 |  |  | 63 | 79.6 |  | 7830.1 |  | 79.6
111 | J117 | J118 |  |  | 63 | 78 | 85 | 7908.1 |  | 78
112 | J117 | J120 |  |  | 63 | 12.5 | 16 | 7920.6 |  | 12.5
113 | J120 | J121 |  |  | 63 | 35.3 | 23 | 7955.9 |  | 35.3
114 | J120 | J122 |  |  | 63 | 75 | 75 | 8030.9 |  | 75
115 | J115 | J116 |  |  | 63 | 75 | 75 | 8105.9 |  | 75
116 | J158 | J159 |  |  | 63 | 69 | 65 | 8174.9 |  | 69
117 | J158 | J170 |  |  | 63 | 298.5 | 298 | 8473.4 |  | 298.5
118 | J170 | J177 |  |  | 63 | 115.2 | 110 | 8588.6 |  | 115.2
119 | J177 | J185 |  |  | 63 | 22.4 | 276 | 8611 |  | 22.4
120 | J177 | J185 | BRICK ROAD |  | 63 | 227 |  | 8838 |  | 227
121 | J177 | J171 |  |  | 63 | 107.3 | 111 | 8945.3 |  | 107.3
122 | J170 | J166 |  |  | 63 | 90.8 | 100 | 9036.1 |  | 90.8
123 | J166 | J169 |  |  | 63 | 70 | 72 | 9106.1 |  | 70
124 | J166 | J161 |  |  | 63 | 61.6 | 58 | 9167.7 |  | 61.6
125 | J161 | J162 |  |  | 63 | 70 | 75 | 9237.7 |  | 70
126 | J161 | j157 |  |  | 63 | 29.6 | 35 | 9267.3 |  | 29.6
127 | J112 | J111 |  |  | 63 | 23.9 | 19 | 9291.2 |  | 23.9
128 | J94 | J110 |  |  | 63 | 48.6 | 93 | 9339.8 |  |  | 48.6
129 | [7 empty] | 9339.8
130 | J91 | J98 | BRICK ROAD |  | 63 | 190.8 | 198 | 9530.6 |  |  | 90.8
131 | J91 | J98 |  |  | 63 | 11 |  | 9541.6 |  |  | 11
132 | J98 | J99 |  |  | 63 | 11 | 14 | 9552.6 |  |  | 11
133 | J99 | J105 |  |  | 63 | 70 | 70 | 9622.6 |  |  | 70
134 | J99 | J107 |  |  | 63 | 133.3 | 130 | 9755.9 |  |  | 133.3
135 | J107 | J108 |  |  | 63 | 58 | 61 | 9813.9 |  |  | 58
136 | J107 | J109 |  |  | 63 | 113.8 | 69 | 9927.7 |  |  | 113.8
137 | J98 | J100 |  |  | 63 | 58.4 | 56 | 9986.1 |  |  | 58.4
138 | [7 empty] | 9986.1
139 | J110 | J114 |  |  | 63 | 188 | 196 | 10174.1 |  |  | 188
140 | J114 | J113 |  |  | 63 | 21 | 21 | 10195.1 |  |  | 21
141 | J114 | J113 |  |  | 63 | 1.8 |  | 10196.9 |  |  | 1.8
142 | J82A | J82B |  |  | 63 | 31 |  | 10227.9 |  | 31
143 | J23 | J18 |  |  | 63 | 124 | 123 | 10351.9
144 | J209 | J209A |  |  | 75 | 33.3 |  | 10385.2 |  | 33.3
145 | J146 | J158 |  |  | 75 | 282.1 | 283 | 10667.3 |  |  | 282.1
146 | J155 | J151 |  |  | 75 | 185 | 180 | 10852.3 |  |  | 185
147 | J151 | J145 |  |  | 75 | 95.5 | 88 | 10947.8 |  |  | 95.5
148 | J151 | J154 |  |  | 75 | 129 | 128 | 11076.8 |  |  | 129
149 | J154 | J160 |  |  | 75 | 86.6 | 89 | 11163.4 |  |  | 86.6
150 | J10 | J22 | BRICK ROAD |  | 75 | 88 | 158 | 11251.4 |  | 88
151 | J10 | J22 |  |  | 75 | 69 |  | 11320.4 |  | 69
152 | J22 | J24 |  |  | 75 | 27.6 | 90 | 11348 |  | 27.6
153 | J24 | J25 |  |  | 75 | 37.5 | 15 | 11385.5 |  | 37.5
154 | J25 | J53 |  |  | 75 | 164.5 | 174 | 11550 |  | 164.5
155 | J53 | J72 |  |  | 75 | 136.1 | 141 | 11686.1 |  | 136.1
156 | J72 | J79 |  |  | 75 | 243 | 235 | 11929.1 |  | 243
157 | J217 | J209 | BRICK ROAD |  | 75 | 62.2 | 59 | 11991.3 |  | 62.2
158 | J209 | J198 |  |  | 75 | 151 | 197 | 12142.3 |  | 151
159 | J201 | J201A |  |  | 75 | 72 |  | 12214.3 |  | 72
160 | J216 | J218 |  |  | 75 | 30.2 | 28 | 12244.5 |  | 30.2
161 | J218 | J200 |  |  | 75 | 4 | 4 | 12248.5 |  | 4
162 | J200 | J223 |  |  | 75 | 55.8 | 57 | 12304.3 |  | 55.8
163 | J223 | J232 |  |  | 75 | 102 | 100 | 12406.3 |  | 102
164 | J192 | J193 |  |  | 90 | 42.5 | 42.5 | 12448.8 |  | 42.5
165 | J196 | J213 |  |  | 90 | 278.5 | 275 | 12727.3 |  | 278.5
166 | J196 | J198 |  |  | 90 | 48 | 52 | 12775.3 |  | 48
167 | J198 | J201 |  |  | 90 | 46.5 | 50 | 12821.8 |  | 46.5
168 | J198 | J201 | INTERLOCKING |  | 90 | 5 |  | 12826.8 |  | 5
169 | J201 | J204 |  |  | 90 | 117 | 120 | 12943.8 |  | 117
170 | J201 | J204 | B.T ROAD |  | 90 | 5 |  | 12948.8 |  | 5
171 | J204 | J210 |  |  | 90 | 43 | 43 | 12991.8 |  | 43
172 | J210 | J216 |  |  | 90 | 38.3 | 41 | 13030.1 |  | 38.3
173 | J204 | J197 |  |  | 90 | 113 | 115 | 13143.1 |  | 113
174 | J204 | J197 | B.T ROAD |  | 90 | 3 |  | 13146.1 |  | 3
175 | J197 | J145 |  |  | 90 | 663 | 666 | 13809.1 |  | 663
176 | J69 | J73 | BRICK ROAD |  | 110 | 50.9 | 48 | 13860 |  | 50.9
177 | J73 | J76 |  |  | 110 | 9 | 25 | 13869 |  | 9
178 | J73 | J76 | BRICK ROAD |  | 110 | 16.7 |  | 13885.7 |  | 16.7
179 | J76 | J81 |  |  | 110 | 151.6 | 143 | 14037.3 |  | 151.6
180 | J81 | J89 | BRICK ROAD |  | 110 | 20 | 42 | 14057.3 |  | 20
181 | J89 | J92 | culvert |  | 110 | 5 | 14 | 14062.3 | culvert
182 | J89 | J92 | B.T ROAD |  | 110 | 3 |  | 14065.3 |  | 3
183 | J89 | J92 | BRICK ROAD |  | 110 | 10 |  | 14075.3 |  | 15
184 | J144 | J140 |  |  | 110 | 42 | 54 | 14117.3 |  | 42
185 | J140 | J127 |  |  | 110 | 154.2 | 149 | 14271.5 |  | 154.2
186 | J127 | J96 |  |  | 110 | 350 | 352 | 14621.5 |  | 350
187 | J127 | J96 | B.T ROAD |  | 110 | 6 |  | 14627.5 |  | 6
188 | J96 | J92 |  |  | 110 | 28.7 | 28 | 14656.2 |  | 28.7
189 | J144 | J186 |  |  | 110 | 182.8 | 168 | 14839 |  | 182.8
190 | J186 | J192 |  |  | 110 | 152.7 | 150 | 14991.7 |  | 152.7
191 | J192 | J196 | B.T ROAD |  | 110 | 8 | 195 | 14999.7 |  | 8
192 | J192 | J196 |  |  | 110 | 177 |  | 15176.7 |  | 177
193 | J11 | J19 |  |  | 110 | 144 | 146 | 15320.7 |  | 144
194 | J19 | J50 |  |  | 110 | 141 | 160 | 15461.7 |  | 141
195 | J115 | J124 | BRICK ROAD |  | 110 | 31 | 30 | 15492.7
196 | J115 | J124 | culvert |  | 110 | 8 |  | 15500.7 | culvert
197 | J115 | J124 |  |  | 110 | 40 | 48 | 15540.7
198 | [7 empty] | 15540.7
199 | [7 empty] | 15540.7
200 | [7 empty] | 15540.7
201 | [7 empty] | 15540.7
202 | J26 | J51 |  |  | 110 | 19 |  | 15559.7
203 | J51 | J69 |  |  | 110 | 69 | 72 | 15628.7
204 | J113 | J112 |  |  | 125 | 65.1 | 68 | 15693.8 |  | 65.1
205 | J94 | J91 |  |  | 125 | 48 | 44 | 15741.8 |  | 204
206 | J91 | J67 |  |  | 125 | 327 | 333 | 16068.8 |  | 327
207 | J113 | J115 | BRICK ROAD |  | 125 | 87.9 | 88 | 16156.7
208 | J2 | J3 |  |  | 140 | 172.5 | 205 | 16329.2 |  | 172.5
209 | J3 | J11 |  |  | 140 | 80 | 81 | 16409.2 |  | 80
210 | J3 | J4 |  |  | 140 | 19.8 | 16 | 16429 |  | 19.8
211 | J4 | J10 |  |  | 140 | 29.2 | 295 | 16458.2 |  | 292
212 | J4 | J10 | B.T ROAD |  | 140 | 3 |  | 16461.2 |  | 3
213 | J10 | J49 | culvert |  | 140 | 3 | 409 | 16464.2 | culvert
214 | J10 | J49 |  |  | 140 | 403 |  | 16867.2 |  | 406
215 | J49 | J54 |  |  | 140 | 121 | 117 | 16988.2 |  | 121
216 | J54 | J55 |  |  | 140 | 29 | 42 | 17017.2 |  | 29
217 | J55 | J67 |  |  | 140 | 121.5 | 121 | 17138.7 |  | 121.5 |  | 262.5
218 | J1 | J2 |  |  | 160 | 228 | 228 | 17366.7 |  | 155 |  | 21.875
219
220
221
222
223
224
225
226
227
228
229
230
231
[6 empty] | 17366.7 |  |  |  | 16953.6
| 63 | 75 | 90 | 110 | 125 | 140 | 160
| 10351.9 | 2054.4 | 1402.8 | 1819.6 | 528 | 982 | 228
MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  |  | DESIGNATION
NAME |  |  |  |  | NAME
SIGN.with date |  |  |  |  | SIGN.with date
[11 empty] | POWER MECH PROJECT LIMITED -BRCPCL(JV). |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.)
[11 empty] | DESIGNATION |  | DESIGNATION | DESIGNATION
[11 empty] | NAME |  | NAME | NAME
[11 empty] | SIGN.with date |  | SIGN.with date | SIGN.with date

## barasarai 2
GOVERNMENT OF UTTAR PRADESH
STATE WATER & SANITATION MISSION ( SWSM )
Joint Measurement Report of Pipe Line
Name of the Work :- Survey , Design Preparation of DPR , Construction , Commissioning and O&M for 10 Years of Various Rural Water Supply Projects in the state of Uttar Pradesh as Per Request for Proposal for Division " Prayagraj "
Name of the Agency : POWER MECH PROJECTS LIMITED – BHOORATHNOM CONSTRUCTIONS COMPANY PRIVATE LIMITED (JV), Hyderabad.
Name OF Scheme |  | : Barasarai 2
Block |  | : MANGRAURA
Total Scope |  | :
JMR No. |  | : 2
Date of JMR |  | :
Sr. No. | Start Node | End Node | Dia | Pipe Length (as per Site) | Excavation Width | Depth | Quantity | Type OF Road | Dismantling Length | Dismantling Width | Dismantling Quantity | Restoration Length | Restoration Width | Restoration Quantity | Restoration Status | Remark
1 | j197 | j221 | 63 | 241
2 | j197 | j221 | 63 | 3 |  |  |  | B.t crossing
3 | j197 | j204 | 90 | 14 |  |  |  | B.t crossing
4 | j195 | j260 | 75 | 400
5 | j260(1) | j260(2) | 63 | 158
6 | j260(2) | j269 | 63 | 30
7 | j260(2) | j262 | 63 | 33
8 | j262 | j263 | 63 | 25.7
9 | j262 | j264 | 63 | 25.3
10 | j264 | j265 | 63 | 42.3
11 | j186 | j188 | 63 | 50
12 | j192 | j195 | 90 | 30
13 | j79 | j131 | 63 | 42.8
14 | j131 | j133 | 63 | 10
15 | j131 | j187 | 63 | 11
16 | j36 | j74 | 63 | 23 |  |  |  | brick road
17 | j36 | j74 | 63 | 40
18 | j36 | j74 | 63 | 34 |  |  |  | brick road
19 | j264 | j257 | 63 | 253.6
Representative PMPL - BRCCPL (JV) Pratapgarh | [6 empty] | Representative Medhaj Techno Concept Pvt Ltd (TPI) Pratapgarh |  |  |  |  | Representative UP Jal Nigam (Rural) Pratapgarh
[17 empty] | Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
[17 empty] | Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
[12 empty] | 18833.4 |  |  |  |  | TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
[17 empty] | Contractor:- |  | Power Mech Project Ltd.
[17 empty] | Block :- |  | Mangraura
[17 empty] | GP :- |  | madhura rani ganj | [5 empty] | Date
[17 empty] | Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
[17 empty] | 1 | j197 | j221 | 63 | 241 | 5.5 | 3.3 | 1 | 4.3 | no
[17 empty] | 2 | j197 | j221 | 63 | 3 | 5.5 | 3.3 | 1 | 4.3 | no
[17 empty] | 3 | j197 | j204 | 90 | 14 | 5.5 | 3.3 | 1 | 4.3 | no
[17 empty] | 4 | j195 | j260 | 75 | 400 | 5.5 | 3.3 | 1 | 4.3 | no
[17 empty] | 5 | j260(1) | j260(2) | 63 | 158 | 5.5 | 3.3 | 1 | 4.3 | no
[17 empty] | 6 | j260(2) | j269 | 63 | 30 | 5.5 | 3.3 | 1 | 4.3 | no
[17 empty] | 7 | j260(2) | j262 | 63 | 33 | 5.5 | 3.3 | 1 | 4.3 | no
[17 empty] | 8 | j262 | j263 | 63 | 25.7 | 5.5 | 3.3 | 1 | 4.3 | no
[17 empty] | 9 | j262 | j264 | 63 | 25.3 | 5.5 | 3.3 | 1 | 4.3 | no
[17 empty] | 10 | j264 | j265 | 63 | 42.3 | 5.5 | 3.3 | 1 | 4.3 | no
[17 empty] | 11 | j186 | j188 | 63 | 50 | 5.5 | 3.3 | 1 | 4.3 | no
[17 empty] | 12 | j192 | j195 | 90 | 30 | 5.5 | 3.3 | 1 | 4.3 | no
[17 empty] | 13 | j79 | j131 | 63 | 42.8 | 5.5 | 3.3 | 1 | 4.3 | no
[17 empty] | 14 | j131 | j133 | 63 | 10 | 5.5 | 3.3 | 1 | 4.3 | no
[17 empty] | 15 | j131 | j187 | 63 | 11 | 5.5 | 3.3 | 1 | 4.3 | no
[17 empty] | 16 | j36 | j74 | 63 | 23 | 5.5 | 3.3 | 1 | 4.3 | no
[17 empty] | 17 | j36 | j74 | 63 | 40 | 5.5 | 3.3 | 1 | 4.3 | no
[17 empty] | 18 | j36 | j74 | 63 | 34 | 5.5 | 3.3 | 1 | 4.3 | no
[17 empty] | 19 | j264 | j257 | 63 | 253.6 | 5.5 | 3.3 | 1 | 4.3 | no
[17 empty] | POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
[17 empty] | DESIGNATION |  |  |  | DESIGNATION |  |  | DESIGNATION
[17 empty] | NAME |  |  |  | NAME |  |  | NAME
[17 empty] | SIGN.with date |  |  |  | SIGN.with date |  |  | SIGN.with date