## attarasand khayathi
| HYDROSTATIC TEST FOR PRESSURE PIPES | [11 empty] | HYDROSTATIC TEST FOR PRESSURE PIPES
HYDROSTATIC TEST FOR PRESSURE PIPES
Project:- |  | Rural water supply project Under JJM , Pratapgarh , Utter Pradesh | [9 empty] | Project:- |  | Rural water supply project Under JJM , Pratapgarh , Utter Pradesh
Client : - |  | State Water & Sanitation Mission Govt of Uttar Pradesh | [9 empty] | Client : - |  | State Water & Sanitation Mission Govt of Uttar Pradesh
TPI :- |  | Medhaj Techno Concept Pvt . Ltd. | [9 empty] | TPI :- |  | Medhaj Techno Concept Pvt . Ltd.
Contractor :- |  | Power Mech Project Ltd. | [9 empty] | Contractor :- |  | Power Mech Project Ltd. | [9 empty] | Project:- |  | Rural water supply project Under JJM , Pratapgarh , Utter Pradesh
Block: MANGRAURA, G.P-ATTARASAND AND PARASPUR | [11 empty] | Block: MANGRAURA, G.P-ATTARASAND AND PARASPUR | [11 empty] | Client : - |  | State Water & Sanitation Mission Govt of Uttar Pradesh
Dail Log Ref. …………………. | [5 empty] | Tested as per CPHEEO …………………….. | [5 empty] | Dail Log Ref. …………………. | [5 empty] | Tested as per CPHEEO …………………….. | [5 empty] | TPI :- |  | Medhaj Techno Concept Pvt . Ltd.
[24 empty] | Contractor :- |  | Power Mech Project Ltd.
Date | [5 empty] | Date of Testing | [5 empty] | Date | [5 empty] | Date of Testing | [5 empty] | Block: MANGRAURA, G.P-ATTARASAND AND PARASPUR
SL. No. | Material of Pipe | OD (MM) | Start Node | End Node | Length | Applied test pressure (kg/cm'2) | Time in Hrs |  |  | Observation | Remark | SL. No. | Material of Pipe | OD (MM) | Start Node | End Node | Length | Applied test pressure (kg/cm'2) | Time in Hrs |  |  | Observation | Remark | Dail Log Ref. …………………. | [5 empty] | Tested as per CPHEEO ……………………..
[7 empty] | Pressure rising time (Hrs) | Pressure Released time (Hrs) | Total Duration Hrs | [9 empty] | Pressure rising time (Hrs) | Pressure Released time (Hrs) | Total Duration Hrs
1 | HDPE | 90 | J650 | J633 | 8.3 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 1 | HDPE | 63 | J638 | J266 | 41.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | Date | [5 empty] | Date of Testing
2 | HDPE | 90 | J633 | J711 | 126.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 2 | HDPE | 110 | J589 | J638 | 79.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | SL. No. | Material of Pipe | OD (MM) | Start Node | End Node | Length | Applied test pressure (kg/cm'2) | Time in Hrs |  |  | Observation | Remark
3 | HDPE | 90 | J711 | J457 | 78.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 3 | HDPE | 110 | J638 | J489 | 50.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO | [8 empty] | Pressure rising time (Hrs) | Pressure Released time (Hrs) | Total Duration Hrs
4 | HDPE | 75 | J395 | J270 | 87.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 4 | HDPE | 75 | J489 | J597 | 58.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 1 | HDPE | 110 | J714 | J718 | 195.1 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
5 | HDPE | 63 | J270 | J286 | 83.6 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 5 | HDPE | 63 | J597 | J605 | 13.9 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 2 | HDPE | 90 | J718 | J218 | 36.4 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
6 | HDPE | 90 | J711 | J719 | 26.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 6 | HDPE | 75 | J597 | J543 | 43.8 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 3 | HDPE | 63 | J218 | J448 | 26.6 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
7 | HDPE | 90 | J719 | J652 | 59.7 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 7 | HDPE | 63 | J543 | J606 | 142.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 4 | HDPE | 90 | J218 | J394 | 46.3 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
8 | HDPE | 90 | J652 | J612 | 22.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 8 | HDPE | 75 | J543 | J547 | 127.6 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 5 | HDPE | 90 | J462 | J394 | 46.6 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
9 | HDPE | 90 | J612 | J526 | 16.8 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 9 | HDPE | 63 | J588 | J547 | 133 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 6 | HDPE | 63 | J462 | J376 | 83.6 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
10 | HDPE | 90 | J526 | J538 | 13.6 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 10 | HDPE | 90 | J564 | J588 | 97.9 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 7 | HDPE | 63 | J524 | J382 | 120.4 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
11 | HDPE | 90 | J538 | J546 | 72.9 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 11 | HDPE | 75 | J547 | J564 | 53.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 8 | HDPE | 110 | J382 | J469 | 212.2 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
12 | HDPE | 90 | J546 | J614 | 89.8 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 12 | HDPE | 75 | J588 | J432 | 162.8 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 9 | HDPE | 75 | J469 | J338 | 44.5 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
13 | HDPE | 63 | J300 | J652 | 22.3 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 13 | HDPE | 90 | J564 | J614 | 578.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 10 | HDPE | 63 | J338 | J410 | 94.7 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
14 | HDPE | 63 | J159 | J423 | 150.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 14 | HDPE | 110 | J614 | J418 | 232.7 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 11 | HDPE | 63 | J338 | J171 | 24.6 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
15 | HDPE | 63 | J509 | J596 | 57.4 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 15 | HDPE | 110 | J418 | J372 | 72.5 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 12 | HDPE | 63 | J171 | J167 | 111.3 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
16 | HDPE | 63 | J596 | J405 | 75.6 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 16 | HDPE | 110 | J372 | J311 | 11.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 13 | HDPE | 75 | J469 | J463 | 75.1 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
17 | HDPE | 63 | J696 | J507 | 21.5 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 17 | HDPE | 110 | J311 | J287 | 21.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 14 | HDPE | 75 | J463 | J467 | 46.2 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
18 | HDPE | 63 | J501 | J151 | 49.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 18 | HDPE | 75 | J311 | J131 | 295.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 15 | HDPE | 75 | J467 | J478 | 49.7 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
19 | HDPE | 63 | J563 | J491 | 35.4 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 19 | HDPE | 110 | J287 | J589 | 272.6 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 16 | HDPE | 75 | J478 | J383 | 14.8 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
20 | HDPE | 63 | J427 | J73 | 139.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 20 | HDPE | 90 | J693 | J603 | 10.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 17 | HDPE | 75 | J383 | J382 | 81.3 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
21 | HDPE | 63 | J216 | J264 | 38.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 21 | HDPE | 90 | J603 | J313 | 182.8 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 18 | HDPE | 75 | J383 | J243 | 47.5 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
22 | HDPE | 63 | J264 | J420 | 23.4 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 22 | HDPE | 90 | J313 | J341 | 18.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 19 | HDPE | 75 | J358 | J201 | 108.7 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
23 | HDPE | 75 | J171 | J277 | 54.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 23 | HDPE | 90 | J424 | J194 | 68.4 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 20 | HDPE | 63 | J201 | J544 | 137.3 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
24 | HDPE | 75 | J735 | J696 | 57.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 24 | HDPE | 63 | J194 | J680 | 30.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 21 | HDPE | 63 | J484 | J166 | 169.4 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
25 | HDPE | 75 | J194 | J211 | 78.9 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 25 | HDPE | 110 | J194 | J395 | 98.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 22 | HDPE | 75 | J166 | J201 | 73.9 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
26 | HDPE | 75 | J211 | J128 | 39.8 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 26 | HDPE | 110 | J395 | J457 | 14.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 23 | HDPE | 75 | J166 | J131 | 93.3 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
27 | HDPE | 75 | J128 | J121 | 34.3 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 27 | HDPE | 90 | J457 | J496 | 98.5 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 24 | HDPE | 63 | J131 | J589 | 103.6 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
28 | HDPE | 75 | J121 | J106 | 32.6 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 28 | HDPE | 90 | J496 | J557 | 16.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 25 | HDPE | 63 | J462 | J374 | 83.6 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
29 | HDPE | 250 | J750 | J746 | 740 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 29 | HDPE | 90 | J557 | J508 | 38.4 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 26 | HDPE | 63 | J479 | J462 | 17.4 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
| POWER MECH |  |  |  |  | MEDHAJ |  |  | JAL NIGAM U.P. |  |  | 30 | HDPE | 90 | J508 | J325 | 58.7 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 27 | HDPE | 110 | J567 | J358 | 170.3 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
Name: | [11 empty] | 31 | HDPE | 90 | J325 | J699 | 57.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 28 | HDPE | 63 | J358 | J439 | 13.4 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
Designation: |  | K.ANWESH KUMAR REDDY | [9 empty] | 32 | HDPE | 63 | J508 | J650 | 70.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 29 | HDPE | 63 | J484 | J166 | 169.4 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
Signature: |  | S.E ENGINEER | [9 empty] | 33 | HDPE | 90 | J650 | J453 | 72.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 30 | HDPE | 63 | J547 | J588 | 10.3 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
Date: | [11 empty] | 34 | HDPE | 90 | J672 | J529 | 65.4 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 31 | HDPE | 75 | J358 | J201 | 108.7 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
[12 empty] | 35 | HDPE | 90 | J453 | J529 | 6.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 32 | HDPE | 75 | J469 | J338 | 44.5 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
|  | 63 | 75 | 90 | 250 | [6 empty] | 36 | HDPE | 75 | J529 |  | 292.8 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 33 | HDPE | 90 | J696 | J646 | 97.5 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
|  | 695.8 | 384.1 | 513.8 | 740 | [7 empty] | POWER MECH |  |  |  |  | MEDHAJ |  |  | JAL NIGAM U.P. |  |  | 34 | HDPE | 110 | J576 | J707 | 168.1 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
[12 empty] | Name: | [11 empty] | 35 | HDPE | 63 | J171 | J167 | 111.3 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
[12 empty] | Designation: |  | K.ANWESH KUMAR REDDY | [9 empty] | 36 | HDPE | 63 | J567 | J358 | 170.3 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
[12 empty] | Signature: |  | S.E ENGINEER | [9 empty] | 37 | HDPE | 63 | J484 | J166 | 169.4 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
| HYDROSTATIC TEST FOR PRESSURE PIPES | [10 empty] | Date: | [11 empty] | 38 | HDPE | 63 | J194 | J680 | 30.1 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
[25 empty] | POWER MECH |  |  |  |  | MEDHAJ |  |  | JAL NIGAM U.P.
[16 empty] | 63 | 75 | 90 | 110 |  |  |  |  | Name:
[16 empty] | 430.4 | 1033.6 | 1368.4 | 851.9 |  |  |  |  | Designation: |  | K.ANWESH KUMAR REDDY
Project:- |  | Rural water supply project Under JJM , Pratapgarh , Utter Pradesh | [21 empty] | Signature: |  | S.E ENGINEER
Client : - |  | State Water & Sanitation Mission Govt of Uttar Pradesh | [21 empty] | Date:
TPI :- |  | Medhaj Techno Concept Pvt . Ltd.
Contractor :- |  | Power Mech Project Ltd. | [23 empty] | 63 | 75 | 90 | 110
Block: MANGRAURA, G.P-ATTARSAND AND PARASPUR | [25 empty] | 1646.7 | 788.2 | 226.8 | 745.7
Dail Log Ref. …………………. | 2023-02-11 |  |  |  |  | Tested as per CPHEEO …………………….. | 2023-02-11 | [8 empty] | 63 | 75 | 90 | 110 | 250
[14 empty] | HYDRO |  | 3083.9 | 2760.9 | 2109 | 3011.5 | 740
Date11-2-2023 | [5 empty] | Date of Testing …………………………………. | 2023-02-11
SL. No. | Material of Pipe | ID (MM) | Start Node | End Node | Length | Appliede test pressure (kg/cm'2) | Time in Hrs |  |  | Observation | Remark
[7 empty] | Pressure rising time (Hrs) | Pressure Released time (Hrs) | Total Duration Hrs |  |  |  |  | JMR |  | #VALUE! | #VALUE! | #VALUE! | 3011.5 | #VALUE!
1 | HDPE | 110 | J164 | J430 | 642 | 5.5 | 11-02-2023(3:10)pm | 11-02-2023(6:10)pm | 3HRS
2 | HDPE | 110 | j430 | j567 | 216 | 5.5 | 11-02-2023(3:10)pm | 11-02-2023(6:10)pm | 3HRS | [6 empty] | #VALUE! | #VALUE! | #VALUE! | 0 | #VALUE!
3 | HDPE | 110 | j567 | j544 | 107 | 5.5 | 11-02-2023(3:10)pm | 11-02-2023(6:10)pm | 3HRS
4 | HDPE | 110 | j544 | j484 | 43.8 | 5.5 | 11-02-2023(3:10)pm | 11-02-2023(6:10)pm | 3HRS
5 | HDPE | 110 | j484 | j489 | 14.1 | 5.5 | 11-02-2023(3:10)pm | 11-02-2023(6:10)pm | 3HRS
6 | HDPE | 110 | j489 | j638 | 48 | 5.5 | 11-02-2023(3:10)pm | 11-02-2023(6:10)pm | 3HRS
7 | HDPE | 110 | j638 | j589 | 42 | 5.5 | 11-02-2023(3:10)pm | 11-02-2023(6:10)pm | 3HRS
8 | HDPE | 110 | j583 | j287 | 271 | 5.5 | 11-02-2023(3:10)pm | 11-02-2023(6:10)pm | 3HRS |  |  |  | 2333.7
9 | HDPE | 110 | j287 | j311 | 20 | 5.5 | 11-02-2023(3:10)pm | 11-02-2023(6:10)pm | 3HRS |  |  |  | 3684.3
10 | HDPE | 110 | j311 | j372 | 10 | 5.5 | 11-02-2023(3:10)pm | 11-02-2023(6:10)pm | 3HRS |  |  |  | 3407.4
11 | HDPE | 63 | j567 | j358 | 168 | 5.5 | 11-02-2023(3:10)pm | 11-02-2023(6:10)pm | 3HRS |  |  |  | 2279.9
12 | HDPE | 63 | j358 | j479 | 13 | 5.5 | 11-02-2023(3:10)pm | 11-02-2023(6:10)pm | 3HRS
13 | HDPE | 63 | j544 | j201 | 130 | 5.5 | 11-02-2023(3:10)pm | 11-02-2023(6:10)pm | 3HRS
14 | HDPE | 75 | j358 | j201 | 106 | 5.5 | 11-02-2023(3:10)pm | 11-02-2023(6:10)pm | 3HRS
15 | HDPE | 75 | j201 | j166 | 73 | 5.5 | 11-02-2023(3:10)pm | 11-02-2023(6:10)pm | 3HRS
16 | HDPE | 75 | j166 | j131 | 93 | 5.5 | 11-02-2023(3:10)pm | 11-02-2023(6:10)pm | 3HRS
17 | HDPE | 75 | j131 | j311 | 283 | 5.5 | 11-02-2023(3:10)pm | 11-02-2023(6:10)pm | 3HRS
|  | POWER MECH |  |  |  | MEDHAJ |  |  | JAL NIGAM U.P.
Name:
Designation:
Signature:
Date:
|  |  |  | 63 | 75 | 110
|  |  |  | 311 | 555 | 1413.9

## attarsand pr
| HYDROSTATIC TEST FOR PRESSURE PIPES | [11 empty] | HYDROSTATIC TEST FOR PRESSURE PIPES | [11 empty] | HYDROSTATIC TEST FOR PRESSURE PIPES
Project:- |  | Rural water supply project Under JJM , Pratapgarh , Utter Pradesh | [9 empty] | Project:- |  | Rural water supply project Under JJM , Pratapgarh , Utter Pradesh | [9 empty] | Project:- |  | Rural water supply project Under JJM , Pratapgarh , Utter Pradesh
Client : - |  | State Water & Sanitation Mission Govt of Uttar Pradesh | [9 empty] | Client : - |  | State Water & Sanitation Mission Govt of Uttar Pradesh | [9 empty] | Client : - |  | State Water & Sanitation Mission Govt of Uttar Pradesh
TPI :- |  | Medhaj Techno Concept Pvt . Ltd. | [9 empty] | TPI :- |  | Medhaj Techno Concept Pvt . Ltd. | [9 empty] | TPI :- |  | Medhaj Techno Concept Pvt . Ltd.
Contractor :- |  | Power Mech Project Ltd. | [9 empty] | Contractor :- |  | Power Mech Project Ltd. | [9 empty] | Contractor :- |  | Power Mech Project Ltd.
Block: MANGRAURA, G.P-ATTARSAND AND PARASPUR | [11 empty] | Block: MANGRAURA, G.P-ATTARSAND AND PARASPUR | [11 empty] | Block: MANGRAURA, G.P-ATTARSAND AND PARASPUR
Dail Log Ref. …………………. | [5 empty] | Tested as per CPHEEO …………………….. | [5 empty] | Dail Log Ref. …………………. | [5 empty] | Tested as per CPHEEO …………………….. | [5 empty] | Dail Log Ref. …………………. | [5 empty] | Tested as per CPHEEO ……………………..
Date | 2023-06-22 |  |  |  |  | Date of Testing | 2023-06-22 |  |  |  |  | Date | 2023-06-24 |  |  |  |  | Date of Testing |  | 2023-06-24 |  |  |  | Date | [5 empty] | Date of Testing
SL. No. | Material of Pipe | ID (MM) | Start Node | End Node | Length | Applied test pressure (kg/cm'2) | Time in Hrs |  |  | Observation | Remark | SL. No. | Material of Pipe | ID (MM) | Start Node | End Node | Length | Applied test pressure (kg/cm'2) | Time in Hrs |  |  | Observation | Remark | SL. No. | Material of Pipe | ID (MM) | Start Node | End Node | Length | Applied test pressure (kg/cm'2) | Time in Hrs |  |  | Observation | Remark
[7 empty] | Pressure rising time (Hrs) | Pressure Released time (Hrs) | Total Duration Hrs | [9 empty] | Pressure rising time (Hrs) | Pressure Released time (Hrs) | Total Duration Hrs | [9 empty] | Pressure rising time (Hrs) | Pressure Released time (Hrs) | Total Duration Hrs
1 | HDPE | 160 | j574 | j610 | 364.3 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 1 | HDPE | 110 | J738 | J733 | 180 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 1 | HDPE | 90 | J262 | J554 | 63.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
2 | HDPE | 63 | j610 | j667 | 27.5 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 2 | HDPE | 160 | J616 | J552 | 56.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 2 | HDPE | 90 | J554 | J428 | 97.5 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
3 | HDPE | 160 | j610 | j450 | 431.5 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 3 | HDPE | 63 | J552 | J578 | 33 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 3 | HDPE | 90 | J428 | J549 | 27.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
4 | HDPE | 160 | j450 | j616 | 45.1 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 4 | HDPE | 160 | J552 | J433 | 90.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 4 | HDPE | 90 | J428 | J517 | 182.7 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
5 | HDPE | 110 | j616 | j630 | 66.2 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 5 | HDPE | 75 | J433 | J475 | 107 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 5 | HDPE | 110 | J594 | J504 | 165 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
6 | HDPE | 63 | j630 | j259 | 286.6 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 6 | HDPE | 63 | J475 | J658 | 128 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 6 | HDPE | 110 | J504 | J490 | 30.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
7 | HDPE | 110 | j630 | j411 | 265 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 7 | HDPE | 63 | J475A | J658A | 69 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 7 | HDPE | 90 | J504 | J503 | 47.5 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
8 | HDPE | 63 | j411 | j295 | 34 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 8 | HDPE | 75 | J475 | J532 | 12.6 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 8 | HDPE | 110 | J503 | J247 | 40 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
9 | HDPE | 75 | j411 | j322 | 102.4 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 9 | HDPE | 63 | J532 | J758 | 56 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  |  |  | POWER MECH |  |  |  | MEDHAJ |  |  | JAL NIGAM U.P.
10 | HDPE | 63 | j322 | j153 | 21.7 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 10 | HDPE | 75 | J532 | J527 | 77.6 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | Name: |  | SHASHIRANJAN
11 | HDPE | 75 | j322 | j328 | 748.6 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 11 | HDPE | 75 | J527 | J494 | 53.8 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | Designation: |  | ENGINEER
12 | HDPE | 160 | j626 | j574 | 185.5 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 12 | HDPE | 75 | J527 | J461 | 41.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | Signature:
13 | HDPE | 110 | j574 | j339 | 96 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 13 | HDPE | 75 | J461 | J710 | 7.4 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | Date:
14 | HDPE | 75 | j339a | j624 | 96 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 14 | HDPE | 63 | J710 | J727 | 32.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
15 | HDPE | 110 | j339 | j568 | 52 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 15 | HDPE | 75 | J710 | J304 | 113.5 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
16 | HDPE | 63 | j568 | j184 | 96 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 16 | HDPE | 63 | J304 | J309 | 68 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
17 | HDPE | 110 | j568 | j619 | 58.5 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 17 | HDPE | 140 | J368 | J433 | 238.8 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
18 | HDPE | 75 | j619 | j611 | 83 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 18 | HDPE | 75 | J461 | J561 | 73.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
19 | HDPE | 63 | j611 | j587 | 78 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 19 | HDPE | 75 | J561 | J583 |  | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
20 | HDPE | 75 | j611 | j663 | 90 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 20 | HDPE | 75 | J583 | J680 |  | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
21 | HDPE | 63 | j663 | j653 | 53 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 21 | HDPE | 63 | J580 | J676 | 65 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
22 | HDPE | 75 | j663 | j666 | 77 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 22 | HDPE | 75 | J680 | J643 | 29 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
23 | HDPE | 75 | j666 | j624 | 35 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 23 | HDPE | 63 | J643 | J357 | 62 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
24 | HDPE | 63 | j666 | j642a | 88.3 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 24 | HDPE | 75 | J643 | J570 | 45.5 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
25 | HDPE | 63 | j642a | j647 | 45.5 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 25 | HDPE | 63 | J570 | J440 | 36.5 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
26 | HDPE | 63 | j681 | j631 | 60 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 26 | HDPE | 63 | J570 | J536 | 50 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
27 | HDPE | 110 | j619 | j556 | 80 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 27 | HDPE | 160 | J751 | 659 | 649.4 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  |  |  | 5796
28 | HDPE | 63 | j556 | j651 | 64.3 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 28 | HDPE | 160 | J659 | J307 | 175.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  |  |  | 4927.5
29 | HDPE | 110 | j556 | j573 | 37.5 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 29 | HDPE | 160 | J751 | J660 | 97 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  |  |  | 653.4
30 | HDPE | 63 | j573 | j458 | 63.9 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 30 | HDPE | 63 | J660 | J349 | 90 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
31 | HDPE | 110 | j573 | j599a | 27 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 31 | HDPE | 160 | J660 | J698 | 183 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
32 | HDPE | 63 | j599a | j599b | 32 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 32 | HDPE | 140 | J690 | J143 | 57 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
33 | HDPE | 110 | j599a | j599a | 26 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 33 | HDPE | 63 | J143 | J306 | 86.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
34 | HDPE | 63 | j599 | j9 | 33 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 34 | HDPE | 140 | J143 | J203 | 96.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
35 | HDPE | 110 | j599 | j738 | 33.8 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 35 | HDPE | 63 | J203 | J459 | 21.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
36 | HDPE | 90 | j738 | j757 | 44.6 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 36 | HDPE | 140 | J203 | J227 | 13 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
37 | HDPE | 90 | j757 | j754 | 133 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 37 | HDPE | 63 | J227 | J227A | 113.5 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
38 | HDPE | 9 | j757 | j269 | 180 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 38 | HDPE | 140 | J227 | J310 | 65.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
39 | HDPE | 75 | j269 | j316 | 46.5 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 39 | HDPE | 140 | J310 | J368 | 27 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
40 | HDPE | 75 | j299 | j316 | 81 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 40 | HDPE | 63 | J368 | J368A | 57.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
41 | HDPE | 75 | j299 | j362 | 76 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 41 | HDPE | 110 | J689 | J465 | 57 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
42 | HDPE | 90 | j299 | j318 | 12 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 42 | HDPE | 110 | J465 | J682 | 64 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
43 | HDPE | 63 | j318 | j323 | 32.5 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 43 | HDPE | 110 | J465 | J682 | 85 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
44 | HDPE | 63 | j318 | j380 | 67 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 44 | HDPE | 110 | J742 | J695 | 40 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
45 | HDPE | 90 | j318 | j733 | 102 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 45 | HDPE | 110 | J210 | J181 | 30 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
46 | HDPE | 75 | j733 | j717 | 199 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 46 | HDPE | 110 | J695 | J594 | 375 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
|  | POWER MECH |  |  |  | MEDHAJ |  |  | JAL NIGAM U.P. |  |  | 47 | HDPE | 110 | J594 | J517 | 65 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
Name: |  | SHASHIRANJAN | [9 empty] | 48 | HDPE | 110 | J517 | J684 | 204 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
Designation: |  | ENGINEER | [9 empty] | 49 | HDPE | 110 | J684 | J703 | 454 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
Signature: | [11 empty] | 50 | HDPE | 63 | J751 | J716 | 252 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
Date: | [11 empty] | 51 | HDPE | 90 | J684 | J454 | 60.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
[12 empty] | 52 | HDPE | 63 | J454 | J219 | 32.8 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
[12 empty] | 53 | HDPE | 63 | J219 | J191 | 21.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
[12 empty] | 54 | HDPE | 63 | J219 | J628 | 40 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
[12 empty] | 55 | HDPE | 90 | J454 | J549 | 72.7 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
[12 empty] | 56 | HDPE | 63 | J219A | J219B | 52 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
[12 empty] | 57 | HDPE | 63 | J549 | J246 | 146.5 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
[12 empty] | 58 | HDPE | 63 | J246A | J246B | 61 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
[12 empty] | 59 | HDPE | 63 | J246A | J262 | 181 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
[14 empty] | POWER MECH |  |  |  | MEDHAJ |  |  | JAL NIGAM U.P.
[12 empty] | Name: |  | SHASHIRANJAN
[12 empty] | Designation: |  | ENGINEER
Signature:
Date:

## ATTARSAND -AGS
| HYDROSTATIC TEST FOR PRESSURE PIPES | [11 empty] | HYDROSTATIC TEST FOR PRESSURE PIPES | [11 empty] | HYDROSTATIC TEST FOR PRESSURE PIPES | [11 empty] | HYDROSTATIC TEST FOR PRESSURE PIPES | [11 empty] | HYDROSTATIC TEST FOR PRESSURE PIPES
Project:- |  | Rural water supply project Under JJM , Pratapgarh , Utter Pradesh | [9 empty] | Project:- |  | Rural water supply project Under JJM , Pratapgarh , Utter Pradesh | [9 empty] | Project:- |  | Rural water supply project Under JJM , Pratapgarh , Utter Pradesh | [9 empty] | Project:- |  | Rural water supply project Under JJM , Pratapgarh , Utter Pradesh | [9 empty] | Project:- |  | Rural water supply project Under JJM , Pratapgarh , Utter Pradesh
Client : - |  | State Water & Sanitation Mission Govt of Uttar Pradesh | [9 empty] | Client : - |  | State Water & Sanitation Mission Govt of Uttar Pradesh | [9 empty] | Client : - |  | State Water & Sanitation Mission Govt of Uttar Pradesh | [9 empty] | Client : - |  | State Water & Sanitation Mission Govt of Uttar Pradesh | [9 empty] | Client : - |  | State Water & Sanitation Mission Govt of Uttar Pradesh
TPI :- |  | Medhaj Techno Concept Pvt . Ltd. | [9 empty] | TPI :- |  | Medhaj Techno Concept Pvt . Ltd. | [9 empty] | TPI :- |  | Medhaj Techno Concept Pvt . Ltd. | [9 empty] | TPI :- |  | Medhaj Techno Concept Pvt . Ltd. | [9 empty] | TPI :- |  | Medhaj Techno Concept Pvt . Ltd.
Contractor :- |  | Power Mech Project Ltd. | [9 empty] | Contractor :- |  | Power Mech Project Ltd. | [9 empty] | Contractor :- |  | Power Mech Project Ltd. | [9 empty] | Contractor :- |  | Power Mech Project Ltd. | [9 empty] | Contractor :- |  | Power Mech Project Ltd.
Block: MANGRAURA, G.P:ATTARSAND AND PARASPUR | [11 empty] | Block: MANGRAURA, G.P:ATTARSAND AND PARASPUR | [11 empty] | Block: MANGRAURA, G.P:ATTARSAND AND PARASPUR | [11 empty] | Block: MANGRAURA, G.P:ATTARSAND AND PARASPUR | [11 empty] | Block: MANGRAURA, G.P:ATTARSAND AND PARASPUR
Dail Log Ref. …………………. | [5 empty] | Tested as per CPHEEO …………………….. | [5 empty] | Dail Log Ref. …………………. | [5 empty] | Tested as per CPHEEO …………………….. | [5 empty] | Dail Log Ref. …………………. | [5 empty] | Tested as per CPHEEO …………………….. | [5 empty] | Dail Log Ref. …………………. | [5 empty] | Tested as per CPHEEO …………………….. | [5 empty] | Dail Log Ref. …………………. | [5 empty] | Tested as per CPHEEO ……………………..
Date 28-02-2023 | [5 empty] | Date of Testing …………………………………. | 2023-02-28 |  |  |  |  | Date | [5 empty] | Date of Testing …………………………………. | [5 empty] | Date | [5 empty] | Date of Testing …………………………………. | [5 empty] | Date | [5 empty] | Date of Testing …………………………………. | [5 empty] | Date | [5 empty] | Date of Testing ………………………………….
SL. No. | Material of Pipe | ID (MM) | Start Node | End Node | Length | Applied test pressure (kg/cm'2) | Time in Hrs |  |  | Observation | Remark | SL. No. | Material of Pipe | ID (MM) | Start Node | End Node | Length | Applied test pressure (kg/cm'2) | Time in Hrs |  |  | Observation | Remark | SL. No. | Material of Pipe | ID (MM) | Start Node | End Node | Length | Applied test pressure (kg/cm'2) | Time in Hrs |  |  | Observation | Remark | SL. No. | Material of Pipe | ID (MM) | Start Node | End Node | Length | Applied test pressure (kg/cm'2) | Time in Hrs |  |  | Observation | Remark | SL. No. | Material of Pipe | ID (MM) | Start Node | End Node | Length | Applied test pressure (kg/cm'2) | Time in Hrs |  |  | Observation | Remark
[7 empty] | Pressure rising time (Hrs) | Pressure Released time (Hrs) | Total Duration Hrs | [9 empty] | Pressure rising time (Hrs) | Pressure Released time (Hrs) | Total Duration Hrs | [9 empty] | Pressure rising time (Hrs) | Pressure Released time (Hrs) | Total Duration Hrs | [9 empty] | Pressure rising time (Hrs) | Pressure Released time (Hrs) | Total Duration Hrs | [9 empty] | Pressure rising time (Hrs) | Pressure Released time (Hrs) | Total Duration Hrs |  |  | 99
1 | HDPE | 144.4 | j-75 | j-6 | 900MTR | 5.5KG/CM2 | 27-2-2023(03:09pm) | 27-02-2023(06:45pm) | 03:36min |  |  | 1 | HDPE | 56.7 | j-41 | j-14 | 68.4 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 1 | HDPE | 144.4 | J75 | J99 | 255.8 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 1 | HDPE | 180.6 | j456 | j655 | 351.8 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 1 | HDPE | 99.1 | J158 | J170 | 146 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO
[12 empty] | 2 | HDPE | 56.7 | J-14 | J4 | 95.8 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 2 | HDPE | 144.4 | J99 | J115 | 69 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 2 | HDPE | 180.6 | j655 | j723 | 633.9 | 5.5kg/cm3 | 3 | 1 | 04:00hrs | NO |  | 2 | HDPE | 81.1 | J170 | J252 | 47 | 5.5kg/cm3 | 3 | 1 | 04:00hrs | NO
|  | POWER MECH |  |  |  | MEDHAJ |  |  | JAL NIGAM U.P. |  |  | 3 | HDPE | 81.1 | J14 | J21 | 156.8 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 3 | HDPE | 99.3 | J20 | J115 | 111.2 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 3 | HDPE | 180.6 | j723 | j748 | 344.9 | 5.5kg/cm4 | 3 | 1 | 04:00hrs | NO |  | 3 | HDPE | 81.1 | J252 | J753 | 423 | 5.5kg/cm4 | 3 | 1 | 04:00hrs | NO
Name: |  | K.ANWESH KUMAR REDDY | [9 empty] | 4 | HDPE | 56.7 | J21 | J18 | 108.9 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 4 | HDPE | 56.7 | J115 | J57 | 107 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 4 | HDPE | 180.6 | j748 | j0 | 432.9 | 5.5kg/cm5 | 3 | 1 | 04:00hrs | NO |  | 4 | HDPE | 56.7 | J735 | J708 | 98 | 5.5kg/cm5 | 3 | 1 | 04:00hrs | NO
Designation: |  | SR.ENGINEER | [9 empty] | 5 | HDPE | 81.1 | J21 | J48 | 109.1 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 5 | HDPE | 56.7 | J20 | J59 | 19 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 5 | HDPE | 180.6 | j723 | j373 | 68 | 5.5kg/cm6 | 3 | 1 | 04:00hrs | NO |  | POWER MECH | [5 empty] | MEDHAJ |  |  | JAL NIGAM U.P.
Signature: | [11 empty] | 6 | HDPE | 144.4 | J48 | J77 | 134.2 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 6 | HDPE | 99.3 | J20 | J32 | 40 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 6 | HDPE | 144.4 | j373 | j474 | 50 | 5.5kg/cm7 | 3 | 1 | 04:00hrs | NO |  | Name: | K.ANWESH KUMAR REDDY
Date: |  | 2023-02-28 | [9 empty] | 7 | HDPE | 144.4 | J77 | J72 | 136.8 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 7 | HDPE | 56.7 | J28 | J13 | 43 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 7 | HDPE | 144.4 | j373 | j505 | 47 | 5.5kg/cm8 | 3 | 1 | 04:00hrs | NO |  | Designation: | SR.ENGINEER
[12 empty] | 8 | HDPE | 144.4 | J72 | J22 | 173 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 8 | HDPE | 56.7 | J149 | J176 | 84.9 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 8 | HDPE | 99.3 | j474 | j499 | 39 | 5.5kg/cm9 | 3 | 1 | 04:00hrs | NO |  | Signature:
[12 empty] | 9 | HDPE | 144.4 | J22 | J214 | 196 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 9 | HDPE | 99.3 | J149 | J158 | 13.8 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 9 | HDPE | 99.3 | j499 | j731 | 32 | 5.5kg/cm10 | 3 | 1 | 04:00hrs | NO |  | Date:
[12 empty] | 10 | HDPE | 56.7 | J214 | J118 | 23.7 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 10 | HDPE | 180.6 | J158 | J456 | 362.9 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 10 | HDPE | 99.3 | j731 | j575 | 28 | 5.5kg/cm11 | 3 | 1 | 04:00hrs | NO
[12 empty] | 11 | HDPE | 144.4 | J214 | J195 | 47 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 11 | HDPE | 180.6 | J456 | J228 | 541.1 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 11 | HDPE | 64.7 | j474 | j471 | 64 | 5.5kg/cm12 | 3 | 1 | 04:00hrs | NO
[12 empty] | 12 | HDPE | 56.7 | J195 | J100 | 93.3 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 12 | HDPE | 56.7 | J101 | J18 | 115.2 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 12 | HDPE | 64.7 | j384 | j471 | 70 | 5.5kg/cm13 | 3 | 1 | 04:00hrs | NO
[12 empty] | 13 | HDPE | 144.4 | J195 | J112 | 437 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 13 | HDPE | 67.4 | J188 | J265 | 60.2 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 13 | HDPE | 64.7 | j505 | j604 | 64 | 5.5kg/cm14 | 3 | 1 | 04:00hrs | NO
[12 empty] | 14 | HDPE | 144.4 | J112 | J111 | 26.2 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 14 | HDPE | 56.7 | J188 | J27 | 37 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 14 | HDPE | 64.7 | j604 | j700 | 35.6 | 5.5kg/cm15 | 3 | 1 | 04:00hrs | NO
[12 empty] | 15 | HDPE | 56.7 | J111 | J152 | 22 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 15 | HDPE | 56.7 | J265 | J52 | 45.4 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 15 | HDPE | 64.7 | j700 | j301 | 16 | 5.5kg/cm16 | 3 | 1 | 04:00hrs | NO
[12 empty] | 16 | HDPE | 144.4 | J111 | J122 | 67.5 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 16 | HDPE | 81.1 | J265 | J534 | 178.7 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 16 | HDPE | 64.7 | j694 | j700 | 41.1 | 5.5kg/cm17 | 3 | 1 | 04:00hrs | NO
[12 empty] | 17 | HDPE | 56.7 | J122 | J86 | 50.1 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 17 | HDPE | 81.1 | J534 | J137 | 27.8 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 17 | HDPE | 56.7 | j471 | j575 | 81 | 5.5kg/cm18 | 3 | 1 | 04:00hrs | NO
[12 empty] | 18 | HDPE | 144.4 | J122 | J81 | 33.1 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 18 | HDPE | 144.4 | J137 | J145 | 341.2 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 18 | HDPE | 56.7 | j731 | j747 | 22.5 | 5.5kg/cm19 | 3 | 1 | 04:00hrs | NO
[12 empty] | 19 | HDPE | 56.7 | J81 | J62 | 35.2 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 19 | HDPE | 144.4 | J145 | J79 | 283.9 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 19 | HDPE | 56.7 | j655 | j634 | 167.2 | 5.5kg/cm20 | 3 | 1 | 04:00hrs | NO
[12 empty] | 20 | HDPE | 144.4 | J81 | J67 | 31.7 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 20 | HDPE | 81.1 | J79 | J47 | 142.1 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 20 | HDPE | 56.7 | j575 | j399 | 96 | 5.5kg/cm21 | 3 | 1 | 04:00hrs | NO
[12 empty] | 21 | HDPE | 56.7 | J67 | J63 | 33.7 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 21 | HDPE | 81.1 | J47 | J49 | 131.9 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 21 | HDPE | 81.1 | j499 | j604 | 47 | 5.5kg/cm22 | 3 | 1 | 04:00hrs | NO
[12 empty] | 22 | HDPE | 99.3 | J22 | J33 | 118.5 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 22 | HDPE | 81.1 | J47 | J93 | 193.2 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 22 | HDPE | 81.1 | j725 | j340 | 74 | 5.5kg/cm23 | 3 | 1 | 04:00hrs | NO
[12 empty] | 23 | HDPE | 144.4 | J67 | J29 | 65.3 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 23 | HDPE | 81.1 | J93 | J85 | 96 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 23 | HDPE | 99.3 | j505 | j488 | 40 | 5.5kg/cm24 | 3 | 1 | 04:00hrs | NO
[12 empty] | 24 | HDPE | 56.7 | J29 | J31 | 33 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 24 | HDPE | 144.4 | J79 | J89 | 55 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | POWER MECH | [5 empty] | MEDHAJ |  |  | JAL NIGAM U.P.
[12 empty] | 25 | HDPE | 56.7 | J29 | J34 | 68.8 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 25 | HDPE | 56.7 | J89 | J139 | 80.2 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | Name: | K.ANWESH KUMAR REDDY
[12 empty] | 26 | HDPE | 144.4 | J29 | J35 | 62 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 26 | HDPE | 144.4 | J82 | J102 | 91.1 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | Designation: | SR.ENGINEER
[12 empty] | 27 | HDPE | 99.3 | J72 | J39 | 67.4 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 27 | HDPE | 144.4 | J102 | J48 | 258 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | Signature:
[12 empty] | 28 | HDPE | 56.7 | J77 | J65 | 144.5 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 28 | HDPE | 144.4 | J179 | J145 | 123 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | Date:
[12 empty] | 29 | HDPE | 81.1 | J65 | J195 | 160 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 29 | HDPE | 56.7 | J82 | J114 | 76.4 | 5.5kg/cm3 | 3 | 1 | 04:00hrs | NO
[12 empty] | 30 | HDPE | 81.1 | J65 | J66 | 282.9 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 30 | HDPE | 56.7 | J102 | J174 | 105.9 | 5.5kg/cm4 | 3 | 1 | 04:00hrs | NO
[12 empty] | 31 | HDPE | 81.1 | J66 | J10 | 418.9 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 31 | HDPE | 56.7 | J117 | J202 | 36.1 | 5.5kg/cm5 | 3 | 1 | 04:00hrs | NO
[12 empty] | 32 | HDPE | 81.1 | J66 | J92 | 46 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 32 | HDPE | 56.7 | J93 | J64 | 42 | 5.5kg/cm6 | 3 | 1 | 04:00hrs | NO
[12 empty] | 33 | HDPE | 81.1 | J92 | J58 | 175.2 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 33 | HDPE | 56.7 | J85 | J241 | 29 | 5.5kg/cm7 | 3 | 1 | 04:00hrs | NO
[12 empty] | 34 | HDPE | 81.1 | J58 | J112 | 78 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 34 | HDPE | 64.7 | J80 | J117 | 25.1 | 5.5kg/cm8 | 3 | 1 | 04:00hrs | NO
[12 empty] | 35 | HDPE | 81.1 | J10 | J7 | 7 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 35 | HDPE | 64.7 | J117 | J97 | 19.4 | 5.5kg/cm9 | 3 | 1 | 04:00hrs | NO
[12 empty] | 36 | HDPE | 56.7 | J10 | J17 | 35 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 36 | HDPE | 64.7 | J97 | J76 | 21.8 | 5.5kg/cm10 | 3 | 1 | 04:00hrs | NO
[12 empty] | 37 | HDPE | 81.1 | J10 | J16 | 103.5 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 37 | HDPE | 64.7 | J97 | J274 | 126.5 | 5.5kg/cm11 | 3 | 1 | 04:00hrs | NO
[12 empty] | 38 | HDPE | 81.1 | J16 | J58 | 403.8 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 38 | HDPE | 64.7 | J274 | J378 | 55 | 5.5kg/cm12 | 3 | 1 | 04:00hrs | NO
[12 empty] | 39 | HDPE | 81.1 | J35 | J16 | 228.9 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | POWER MECH | [5 empty] | MEDHAJ |  |  | JAL NIGAM U.P.
[12 empty] | 40 | HDPE | 81.1 | J7 | J11 | 143.7 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | Name: | K.ANWESH KUMAR REDDY
[12 empty] | 41 | HDPE | 67.4 | J11 | J2 | 230.4 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | Designation: | SR.ENGINEER
[12 empty] | 42 | HDPE | 67.4 | J11 | J23 | 304.2 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | Signature:
[12 empty] | 43 | HDPE | 56.7 | J23 | J53 | 84.4 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | Date:
[12 empty] | 44 | HDPE | 56.7 | J23 | J42 | 61.8 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO
[12 empty] | 45 | HDPE | 56.7 | J42 | J70 | 22.3 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO
[12 empty] | 46 | HDPE | 56.7 | J42 | J53 | 15 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO
[12 empty] | 47 | HDPE | 56.7 | J53 | J36 | 35.8 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO
[12 empty] | 48 | HDPE | 56.7 | J23 | J19 | 140.3 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO
[12 empty] | POWER MECH | [5 empty] | MEDHAJ |  |  | JAL NIGAM U.P.
[12 empty] | Name: | K.ANWESH KUMAR REDDY
[12 empty] | Designation: | SR.ENGINEER
Signature:
Date: