## hydro testing
| HYDROSTATIC TEST FOR PRESSURE PIPES | [12 empty] | HYDROSTATIC TEST FOR PRESSURE PIPES | [11 empty] | HYDROSTATIC TEST FOR PRESSURE PIPES
Project:- |  | Rural water supply project Under JJM , Pratapgarh , Utter Pradesh | [10 empty] | Project:- |  | Rural water supply project Under JJM , Pratapgarh , Utter Pradesh | [9 empty] | Project:- |  | Rural water supply project Under JJM , Pratapgarh , Utter Pradesh
Client : - |  | State Water & Sanitation Mission Govt of Uttar Pradesh | [10 empty] | Client : - |  | State Water & Sanitation Mission Govt of Uttar Pradesh | [9 empty] | Client : - |  | State Water & Sanitation Mission Govt of Uttar Pradesh
TPI :- |  | Medhaj Techno Concept Pvt . Ltd. | [10 empty] | TPI :- |  | Medhaj Techno Concept Pvt . Ltd. | [9 empty] | TPI :- |  | Medhaj Techno Concept Pvt . Ltd.
Contractor :- |  | Power Mech Project Ltd. | [10 empty] | Contractor :- |  | Power Mech Project Ltd. | [9 empty] | Contractor :- |  | Power Mech Project Ltd.
Block: MANGRAURA, G.P-sekhpur adharganj | [12 empty] | Block: MANGRAURA, G.P-sekhpur adharganj | [11 empty] | Block: MANGRAURA, G.P-sekhpur adharganj
Dail Log Ref. …………………. | [5 empty] | Tested as per CPHEEO …………………….. | [6 empty] | Dail Log Ref. …………………. | [5 empty] | Tested as per CPHEEO …………………….. | [5 empty] | Dail Log Ref. …………………. | [5 empty] | Tested as per CPHEEO ……………………..
Date | 2023-04-28 |  |  |  |  | Date of Testing | 2023-04-28 | [5 empty] | Date | 2023-05-30 |  |  |  |  | Date of Testing | 2023-05-30 |  |  |  |  | Date | 2023-05-02 |  |  |  |  | Date of Testing |  | 2023-05-02
SL. No. | Material of Pipe | ID (MM) | Start Node | End Node | Length | Applied test pressure (kg/cm'2) | Time in Hrs |  |  | Observation | Remark |  | SL. No. | Material of Pipe | ID (MM) | Start Node | End Node | Length | Applied test pressure (kg/cm'2) | Time in Hrs |  |  | Observation | Remark | SL. No. | Material of Pipe | ID (MM) | Start Node | End Node | Length | Applied test pressure (kg/cm'2) | Time in Hrs |  |  | Observation | Remark |  | start node | end node
[7 empty] | Pressure rising time (Hrs) | Pressure Released time (Hrs) | Total Duration Hrs | [10 empty] | Pressure rising time (Hrs) | Pressure Released time (Hrs) | Total Duration Hrs | [9 empty] | Pressure rising time (Hrs) | Pressure Released time (Hrs) | Total Duration Hrs |  |  |  | J116 | J77 | KACHA |  | 63 | 32
1 | HDPE | 67.4 | j-3 | j-1 | 452.5 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  |  | 1 | HDPE | 126.3 | j60 | j63 | 95.8 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 1 | HDPE | 99.3 | j70 | j26 | 1474 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  |  | J77 | J145 | B.T ROAD | 0.39 | 63 | 3.5
2 | HDPE | 126.3 | J1 | J-8 | 125.5 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  |  | 2 | HDPE | 67.4 | j63 | j69 | 46 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 2 | HDPE | 81.1 | j26 | j14 | 138.3 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  |  | J77 | J145 | KACHA |  | 63 | 49
3 | HDPE | 56.7 | J8 | J115 | 37.4 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  |  | 3 | HDPE | 56.7 | j9 | j64 | 50 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 3 | HDPE | 81.1 | j14 | j23 | 124.1 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  |  | J23 | J129 | KACHA |  | 63 | 17.2
4 | HDPE | 126.3 | J8 | J4 | 225.4 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  |  | 4 | HDPE | 67.4 | j9 | j6 | 231.5 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 4 | HDPE | 56.7 | j23 | j129 | 17.2 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  |  | J27 | J43 | KACHA |  | 63 | 210
5 | HDPE | 56.7 | J4 | J59 | 9 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  |  | 5 | HDPE | 56.7 | j6 | j42 | 106.9 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 5 | HDPE | 81.1 | j14 | j27 | 90 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  |  | J17 | J13 | KACHA |  | 63 | 62
6 | HDPE | 126.3 | J4 | J28 | 90.8 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  |  | 6 | HDPE | 126.3 | j63 | j91 | 88.9 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 6 | HDPE | 67.4 | j27 | j48 | 24.3 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 535 | J13 | J57 | KACHA |  | 63 | 68
7 | HDPE | 126.3 | j34 | j24 | 44.9 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  |  | 7 | HDPE | 126.3 | j91 | j124 | 181.6 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 7 | HDPE | 67.4 | j48 | j38 | 23.6 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  |  | J113 | J119 | KACHA |  | 63 | 6.2
8 | HDPE | 126.3 | j24 | j16 | 100.3 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  |  | 8 | HDPE | 99.3 | j91 | j99 | 19 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 8 | HDPE | 56.7 | j27 | j43 | 210 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  |  | J113 | J119 | KACHA |  | 63 | 120
9 | HDPE | 56.7 | j16 | j24 | 83 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  |  | 9 | HDPE | 99.3 | j99 | j104 | 58 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 9 | HDPE | 81.1 | j26 | j21 | 89.5 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  |  | J77 | J54 | KACHA |  | 63 | 227.7
10 | HDPE | 126.3 | j16 | j18 | 31 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  |  | 10 | HDPE | 56.7 | j104 | j153 | 55 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 10 | HDPE | 67.4 | j21 | j17 | 74 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  |  | J113(1) | J113(2) | KACHA |  | 63 | 11
11 | HDPE | 126.3 | j18 | j10 | 314.8 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  |  | 11 | HDPE | 56.7 | j104(a) | j104(b) | 28.7 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 11 | HDPE | 56.7 | j17 | j13 | 62 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  |  | J62 | J51 | KACHA |  | 63 | 84.6
12 | HDPE | 67.4 | j10 | j22 | 68.2 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  |  | 12 | HDPE | 99.3 | j104 | j88 | 75 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 12 | HDPE | 67.4 | j21 | j32 | 74.5 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  |  | J75(1) | J75(2) | KACHA |  | 63 | 47.4
13 | HDPE | 67.4 | j22 | J11 | 183.2 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  |  | 13 | HDPE | 99.3 | j88 | j114 | 57.3 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 13 | HDPE | 67.4 | j32 | j13 | 41.2 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  |  | J5 | J7 | KACHA | 0.39 | 63 | 196.2
14 | HDPE | 56.7 | j11 | j85 | 60.4 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 17.2 | 14 | HDPE | 99.3 | j114 | j124 | 72 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 14 | HDPE | 56.7 | j13 | j57 | 68 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 12159.1 | J5 | J7 | BRICK ROAD | 0.39 | 63 | 100.2
15 | HDPE | 56.7 | j11 | j19 | 151.2 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 68.2 | 15 | HDPE | 99.3 | j99 | j134 | 94 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 15 | HDPE | 56.7 | j60 | j141 | 13 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  |  | J67 | J109 | KACHA |  | 63 | 3.2
16 | HDPE | 56.7 | j19 | j40 | 203 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 36.5 | 16 | HDPE | 126.3 | j124 | j157 | 76 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 16 | HDPE | 56.7 | j141 | j105 | 42.4 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  |  | J67 | J109 | BRICK ROAD | 0.39 | 63 | 51.2
17 | HDPE | 126.3 | j1 | j2 | 146.1 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 21.8 | 17 | HDPE | 99.3 | j88 | j84 | 127.5 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 17 | HDPE | 56.7 | j78 | j148 | 27.5 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  |  | J60 | J80 | KACHA |  | 63 | 12.5
18 | HDPE | 126.3 | j2 | j62 | 272 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 30 | 18 | HDPE | 99.3 | j84 | j92 | 145.5 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 18 | HDPE | 56.7 | j67 | j109 | 3.5 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  |  | J80 | J141 | KACHA |  | 63 | 21
19 | HDPE | 56.7 | j62 | j51 | 84.6 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 70.7 | 19 | HDPE | 56.7 | j92 | j158 | 46.8 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 19 | HDPE | 56.7 | j67 | 109 | 43.4 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  |  | J80 | J105 | KACHA |  | 63 | 42
20 | HDPE | 56.7 | j51 | j75 | 17.6 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 57 | 20 | HDPE | 56.7 | j92 | j92(a) | 68.7 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 20 | HDPE | 56.7 | j67 | j109 | 9 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  |  | J120 | J102 | B.T ROAD | 0.39 | 63 | 3.5
21 | HDPE | 126.3 | j62 | j157 | 53.7 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  |  | 21 | HDPE | 56.7 | j92(a) | j92(b) | 45 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 21 | HDPE | 67.4 | j78 | j94 | 50 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  |  | J120 | J102 | BRICK ROAD | 0.39 | 63 | 41.3
22 | HDPE | 144.4 | j157 | OHT | 66.8 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  |  | 22 | HDPE | 56.7 | j92(a) | j102 | 25.1 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 22 | HDPE | 67.4 | j103 | j37 | 155 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  |  | J102 | J144 | BRICK ROAD | 0.39 | 63 | 16.1
23 | HDPE | 56.7 | j19 | j87 | 149.2 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  |  | 23 | HDPE | 56.7 | j102 | j144 | 16.1 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 23 | HDPE | 56.7 | j75(1) | j75(2) | 47.4 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  |  | J102 | J92(A) | BRICK ROAD | 0.39 | 63 | 25.1
24 | HDPE | 56.7 | j2 | j12 | 137.9 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  |  | 24 | HDPE | 56.7 | j102 | j120 | 44.8 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 24 | HDPE | 56.7 | j67 | j109 | 55.9 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  |  | J92(B) | J92(A) | KACHA |  | 63 | 45
25 | HDPE | 56.7 | j12 | j39 | 189.2 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  |  | 25 | HDPE | 126.3 | j63 | j120 | 43.3 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 25 | HDPE | 56.7 | j28 | j34 | 67 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  |  | J92(A) | J92 | BRICK ROAD | 0.39 | 63 | 68.7
26 | HDPE | 56.7 | j12 | j71 | 162.6 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  |  | 26 | HDPE | 126.3 | j120 | j111 | 50.5 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 26 | HDPE | 56.7 | J16 | J89 | 39.7 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  |  | J92 | J158 | KACHA |  | 63 | 46.8
27 | HDPE | 126.3 | j2 | j5 | 208 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  |  | 27 | HDPE | 67.4 | j111 | j94 | 41 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 27 | HDPE | 56.7 | J65 | J142 | 18.7 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  |  | J104 | J153 | KACHA |  | 63 | 55
28 | HDPE | 126.3 | j5 | j67 | 32 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  |  | 28 | HDPE | 126.3 | j111 | j72 | 46.2 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | 28 | HDPE | 56.7 | J165(A) | J165(B) | 12.6 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  |  | j104(a) | j104(b) | KACHA |  | 63 | 28.7
29 | HDPE | 126.3 | j67 | j60 | 286 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  |  | 29 | HDPE | 56.7 | j72 | j123 | 137.5 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO | [14 empty] | j72 | j123 | B.T ROAD | 0.36 | 63 | 3.5
30 | HDPE | 56.7 | j60 | j80 | 12.5 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  |  | 30 | HDPE | 56.7 | j72 | j146 | 27.3 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO | [14 empty] | j72 | j123 | KACHA |  | 63 | 113
31 | HDPE | 56.7 | j80 | j141 | 21 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  |  | 31 | HDPE | 126.3 | j72 | j112 | 170.4 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  |  |  | POWER MECH |  |  |  | MEDHAJ |  |  | JAL NIGAM U.P. |  |  |  | j72 | j123 | BRICK ROAD | 0.39 | 63 | 21
32 | HDPE | 56.7 | j80 | j105 | 42 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  |  | 32 | HDPE | 56.7 | j53 | j65 | 467.6 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | Name: |  | K.ANWESH KUMAR REDDY | [10 empty] | j72 | j146 | KACHA |  | 63 | 21.3
33 | HDPE | 56.7 | j5 | j7 | 296.4 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  |  | 33 | HDPE | 67.4 | j112 | j98 | 65 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | Designation: |  | SR.ENGINEER | [10 empty] | j72 | j146 | INTERLOCKING | 0.39 | 63 | 6
34 | HDPE | 56.7 | j75 | j139 | 47.4 | 5.5kg/cm3 | 3 | 1 | 04:00hrs | NO |  |  | 34 | HDPE | 56.7 | j98 | j149 | 30 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | Signature: | [12 empty] | j53 | j65 | KACHA |  | 63 | 26.9
35 | HDPE | 144.4 | j157 | OHT | 100 | 5.5kg/cm4 | 3 | 1 | 04:00hrs | NO |  |  | 35 | HDPE | 67.4 | j98 | j78 | 111 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO |  | Date: | [12 empty] | j53 | j65 | B.T ROAD | 0.39 | 63 | 3.5
[13 empty] | 36 | HDPE | 67.4 | j78 | j94 | 98.4 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO | [14 empty] | j53 | j65 | INTERLOCKING | 0.39 | 63 | 100.2
[13 empty] | 37 | HDPE | 126.3 | j112 | j70 | 119 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO | [14 empty] | j53 | j65 | KACHA |  | 63 | 337
|  | POWER MECH |  |  |  | MEDHAJ |  |  | JAL NIGAM U.P. |  |  |  | 38 | HDPE |  | j70 | j49 | 273.6 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO | [14 empty] | j65 | j142 | KACHA |  | 63 | 18.7
Name: |  | K.ANWESH KUMAR REDDY | [10 empty] | 39 | HDPE | 67.4 | j49 | j54 | 255.1 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO | [14 empty] | j165A | j165B | KACHA |  | 63 | 12.6
Designation: |  | SR.ENGINEER | [10 empty] | 40 | HDPE | 67.4 | j49 | j68 | 92 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO | [14 empty] | j6 | j42 | KACHA |  | 63 | 106.9
Signature: | [12 empty] | 41 | HDPE | 67.4 | j68 | j68(a) | 126.1 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO | [14 empty] | j2 | j12 | KACHA |  | 63 | 57.3
Date: |  | 2023-02-28 | [10 empty] | 42 | HDPE | 67.4 | j68(a) | j97 | 113 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO | [14 empty] | j2 | j12 | KACHA |  | 63 | 80.6
[13 empty] | 43 | HDPE | 67.4 | j68 | j116 | 79.7 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO | [14 empty] | j12 | j71 | KACHA |  | 63 | 70.7
[13 empty] | 44 | HDPE | 56.7 | j116 | j147 | 36.5 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO | [14 empty] | j16 | J89 | KACHA |  | 63 | 39.7
[13 empty] | 45 | HDPE | 56.7 | j116 | j77 | 32 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO | [14 empty] | J16 | J24 | KACHA |  | 63 | 83
[13 empty] | 46 | HDPE | 56.7 | j77 | j145 | 52.5 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO | [14 empty] | J4 | J59 | KACHA |  | 63 | 9
[13 empty] | 47 | HDPE | 56.7 | j77 | j54 | 227.7 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO | [14 empty] | J10 | J22 | BRICK ROAD | 0.39 | 75 | 68.2
[13 empty] | 48 | HDPE | 56.7 | j113(1) | j113(2) | 11 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO | [14 empty] | J8 | J115 | BRICK ROAD | 0.39 | 63 | 12.2
[13 empty] | 49 | HDPE | 56.7 | j113 | j119 | 126.2 | 5.5kg/cm2 | 3 | 1 | 04:00hrs | NO | [14 empty] | J8 | J115 | KACHA |  | 63 | 25.2
[13 empty] | 50 | HDPE | 56.7 | j23 | j129 | 17.2 | 5.5kg/cm3 | 3 | 1 | 04:00hrs | NO | [14 empty] | J19 | J87 | KACHA |  | 63 | 59.6
[13 empty] | 51 | HDPE | 56.7 | j141 | j80 | 21.8 | 5.5kg/cm4 | 3 | 1 | 04:00hrs | NO
[13 empty] | 52 | HDPE | 56.7 | j98 | j149 | 30 | 5.5kg/cm5 | 3 | 1 | 04:00hrs | NO
[13 empty] | 53 | HDPE | 56.7 | j10 | j22 | 68.2 | 5.5kg/cm6 | 3 | 1 | 04:00hrs | NO
[38 empty] | J19 | J87 | BRICK ROAD |  | 63 | 89.6
[15 empty] | POWER MECH |  |  |  | MEDHAJ |  |  | JAL NIGAM U.P. | [15 empty] | J19 | J40 | INTERLOCKING | 0.44 | 63 | 203
[13 empty] | Name: |  | K.ANWESH KUMAR REDDY | [22 empty] | J11 | J85 | KACHA |  | 63 | 60.4
[13 empty] | Designation: |  | SR.ENGINEER | [22 empty] | J11 | J19 | KACHA |  | 63 | 94.2
[13 empty] | Signature: | [24 empty] | J12(1) | J39(1) | KACHA |  | 63 | 36.5
[13 empty] | Date: | [24 empty] | J11 | J19 | INTERLOCKING | 0.44 | 63 | 57
[38 empty] | J62 | J125 | BRICK ROAD | 0.39 | 63 | 84.6
[38 empty] | J51 | J75 | KACHA |  | 63 | 17.6
[38 empty] | J75 | J139 | KACHA |  | 63 | 47.4
[38 empty] | J12 | J71 | INTERLOCKING | 0.39 | 63 | 12.5
[38 empty] | J12 | J71 | KACHA |  | 63 | 79.4
[38 empty] | J12 | J39 | BRICK ROAD | 0.39 | 63 | 18
[38 empty] | J12 | J39 | KACHA |  | 63 | 171.2
[38 empty] | J60 | J141 | BRICK ROAD | 0.39 | 63 | 13
[38 empty] | J141 | J80 | KACHA |  | 63 | 21.8
[38 empty] | J141 | J105 | KACHA |  | 63 | 42.4
[38 empty] | J9 | J64 | KACHA |  | 63 | 50
[38 empty] | J98 | J149 | KACHA |  | 63 | 30
[38 empty] | J78 | J148 | KACHA |  | 63 | 27.5
[38 empty] | J67 | J109 | B.T ROAD | 0.39 | 63 | 3.5
[38 empty] | J67 | J109 | BRICK ROAD | 0.39 | 63 | 43.4
[38 empty] | J67 | J109 | KACHA |  | 63 | 9
[38 empty] | J116 | J147 | B.T ROAD | 0.39 | 63 | 3.5
[38 empty] | J116 | J147 | KACHA |  | 63 | 33

## road restoration
BLOCK-MANGRAURA G.P-SESHPUR ADHARGANJ (RESTORATION JMR)
Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | DI/HDPE | Pipe Length (M) | (SQM) | RESTORATION | Remarks
1 | J77 | J145 | B.T ROAD | 0.39 | 63 | 3.5 | 1.365 | DONE
2 | J5 | J7 | BRICK ROAD | 0.39 | 63 | 100.2 | 39.078 | DONE
3 | J67 | J109 | BRICK ROAD | 0.39 | 63 | 51.2 | 19.968 | DONE
4 | J120 | J102 | B.T ROAD | 0.39 | 63 | 3.5 | 1.365 | DONE
5 | J120 | J102 | BRICK ROAD | 0.39 | 63 | 41.3 | 16.107 | DONE
6 | J102 | J144 | BRICK ROAD | 0.39 | 63 | 16.1 | 6.279 | DONE
7 | J102 | J92(A) | BRICK ROAD | 0.39 | 63 | 25.1 | 9.789 | DONE
8 | J92(A) | J92 | BRICK ROAD | 0.39 | 63 | 68.7 | 26.793 | DONE
9 | j72 | j123 | B.T ROAD | 0.36 | 63 | 3.5 | 1.26 | DONE
10 | j72 | j123 | BRICK ROAD | 0.39 | 63 | 21 | 8.19 | DONE
11 | j72 | j146 | INTERLOCKING | 0.39 | 63 | 6 | 2.34 | DONE
12 | j53 | j65 | B.T ROAD | 0.39 | 63 | 3.5 | 1.365 | DONE
13 | j53 | j65 | INTERLOCKING | 0.44 | 63 | 100.2 | 44.088 | DONE
14 | J10 | J22 | BRICK ROAD | 0.39 | 75 | 68.2 | 26.598 | DONE
15 | J8 | J115 | BRICK ROAD | 0.39 | 63 | 12.2 | 4.758 | DONE
16 | J19 | J87 | BRICK ROAD | 0.36 | 63 | 89.6 | 32.256 | DONE
17 | J19 | J40 | INTERLOCKING | 0.44 | 63 | 203 | 89.32 | DONE
18 | J11 | J19 | INTERLOCKING | 0.44 | 63 | 57 | 25.08 | DONE
19 | J22 | J11 | BRICK ROAD | 0.39 | 75 | 183.2 | 71.448 | DONE
20 | J49 | J54 | BRICK ROAD | 0.39 | 75 | 50 | 19.5 | DONE
21 | J26 | J14 | BRICK ROAD | 0.39 | 90 | 96 | 37.44 | DONE
22 | J14 | J23 | BRICK ROAD | 0.39 | 90 | 4 | 1.56 | DONE
23 | J26 | J46 | B.T ROAD | 0.39 | 90 | 3.5 | 1.365 | DONE
24 | J62 | J125 | BRICK ROAD | 0.39 | 63 | 84.6 | 32.994 | DONE
25 | J12 | J71 | INTERLOCKING | 0.39 | 63 | 12.5 | 4.875 | DONE
26 | J12 | J39 | BRICK ROAD | 0.39 | 63 | 18 | 7.02 | DONE
27 | J60 | J141 | BRICK ROAD | 0.39 | 63 | 13 | 5.07 | DONE
28 | J67 | J109 | B.T ROAD | 0.39 | 63 | 3.5 | 1.365 | DONE
29 | J67 | J109 | BRICK ROAD | 0.39 | 63 | 43.4 | 16.926 | DONE
30 | J116 | J147 | B.T ROAD | 0.39 | 63 | 3.5 | 1.365 | DONE
31 | J63 | J9 | BRICK ROAD | 0.39 | 75 | 46 | 17.94 | DONE
32 | J9 | J6 | BRICK ROAD | 0.39 | 75 | 231.5 | 90.285 | DONE
33 | J98 | J78 | BRICK ROAD | 0.39 | 75 | 50 | 19.5 | DONE
34 | J78 | J94 | BRICK ROAD | 0.39 | 75 | 50 | 19.5 | DONE
35 | J68 | J68(1) | B.T ROAD | 0.39 | 75 | 3.5 | 1.365 | DONE
36 | J68(1) | J97 | BRICK ROAD | 0.39 | 75 | 113 | 44.07 | DONE
37 | J103 | J37 | BRICK ROAD | 0.39 | 75 | 155 | 60.45 | DONE
38 | J91 | J99 | BRICK ROAD | 0.44 | 110 | 19 | 8.36 | DONE
39 | J99 | J134 | BRICK ROAD | 0.44 | 110 | 11 | 4.84 | DONE
40 | J99 | J104 | BRICK ROAD | 0.44 | 110 | 24.2 | 10.648 | DONE
41 | J84 | J92 | BRICK ROAD | 0.44 | 110 | 108 | 47.52 | DONE
42 | J124 | J114 | BRICK ROAD | 0.44 | 110 | 72 | 31.68 | DONE
43 | J114 | J88 | BRICK ROAD | 0.44 | 110 | 57.3 | 25.212 | DONE
44 | J2 | J62 | B.T ROAD | 0.44 | 140 | 6 | 2.64 | DONE
45 | J2 | J62 | BRICK ROAD | 0.44 | 140 | 225 | 99 | DONE
46 | J2 | J62 | BRICK ROAD | 0.44 | 140 | 41 | 18.04 | DONE
47 | J62 | J157 | BRICK ROAD | 0.44 | 140 | 53.7 | 23.628 | DONE
48 | J2 | J5 | INTERLOCKING | 0.44 | 140 | 3.5 | 1.54 | DONE
49 | J2(A) | J5(B) | B.T ROAD | 0.44 | 140 | 4 | 1.76 | DONE
50 | J5 | J60 | B.T ROAD | 0.44 | 140 | 4.7 | 2.068 | DONE
51 | J120 | J111 | BRICK ROAD | 0.44 | 140 | 4 | 1.76 | DONE
52 | J63 | J91 | BRICK ROAD | 0.44 | 140 | 88.9 | 39.116 | DONE
53 | J91 | J124 | BRICK ROAD | 0.44 | 140 | 181.6 | 79.904 | DONE
54 | J124 | J157 | BRICK ROAD | 0.44 | 140 | 76 | 33.44 | DONE
55 | J1 | J8 | BRICK ROAD | 0.44 | 140 | 125.5 | 55.22 | DONE
56 | J18 | J10 | BRICK ROAD | 0.44 | 140 | 314.8 | 138.512 | DONE
57 | J157 | OHT | BRICK ROAD | 0.44 | 160 | 100 | 44 | DONE
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  | SIGN.with date