## SESHPUR ADHARGANJ
seshpur adharganj | [17 empty] | seshpur adharganj
Sl.No | Date | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | DIA/HDPE | Pipe Length (M) | [5 empty] | CUMMULATIVE | SITE ENGINEER | Remarks | RESTORATION |  | Sl.No | Date | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | DIA/HDPE | Pipe Length (M) |  |  |  |  | CUMMULATIVE
1 | 2023-03-14 | J116 | J77 | KACHA |  | 63 | 32 | [5 empty] | 32 |  |  |  |  | Road restoration | [11 empty] | #REF!
2 | 2023-03-14 | J77 | J145 | B.T ROAD | 0.39 | 63 | 3.5 | [5 empty] | 35.5 |  |  |  | 1.365 | 1 | 2023-03-14 | J77U5:V26U5:V31U5:V36N86U5:V22U5:V41N86U5:V22U5:V46N86U5:V22U5:V51N86U5:V22U5:V56N86U5:V22U5:V61N86U5:V22U5:V66N86U5:V22U5:V69N86U5:V22 | J145 | B.T ROAD | 0.39 | 63 | 3.5 |  |  |  |  | #REF!
3 | 2023-03-14 | J77 | J145 | KACHA |  | 63 | 49 | [5 empty] | 84.5 |  |  |  | 0 | 2 |  | J5 | J7 | BRICK ROAD | 0.39 | 63 | 100.2 |  |  |  |  | #REF!
4 | 2023-03-14 | J23 | J129 | KACHA |  | 63 | 17.2 | [5 empty] | 101.7 |  |  |  | 0 | 3 |  | J67 | J109 | BRICK ROAD | 0.39 | 63 | 51.2 |  |  |  |  | #REF!
5 | 2023-03-14 | J27 | J43 | KACHA |  | 63 | 210 | [5 empty] | 311.7 |  |  |  | 0 | 4 |  | J120 | J102 | B.T ROAD | 0.39 | 63 | 3.5 |  |  |  |  | #REF!
6 | 2023-03-14 | J17 | J13 | KACHA |  | 63 | 62 | [5 empty] | 373.7 |  |  |  | 0 | 5 |  | J120 | J102 | BRICK ROAD | 0.39 | 63 | 41.3 |  |  |  |  | #REF!
7 | 2023-03-14 | J13 | J57 | KACHA |  | 63 | 68 | [5 empty] | 441.7 |  |  |  | 0 | 6 |  | J102 | J144 | BRICK ROAD | 0.39 | 63 | 16.1 |  |  |  |  | #REF!
8 | 2023-03-14 | J113 | J119 | KACHA |  | 63 | 6.2 | [5 empty] | 447.9 |  |  |  | 0 | 7 |  | J102 | J92(A) | BRICK ROAD | 0.39 | 63 | 25.1 |  |  |  |  | #REF!
9 | 2023-03-14 | J113 | J119 | KACHA |  | 63 | 120 | [5 empty] | 567.9 |  |  |  | 0 | 8 |  | J92(A) | J92 | BRICK ROAD | 0.39 | 63 | 68.7 |  |  |  |  | #REF!
10 | 2023-03-14 | J77 | J54 | KACHA |  | 63 | 227.7 | [5 empty] | 795.6 |  |  |  | 0 | 9 |  | j72 | j123 | B.T ROAD | 0.36 | 63 | 3.5 |  |  |  |  | #REF!
11 | 2023-03-14 | J113(1) | J113(2) | KACHA |  | 63 | 11 | [5 empty] | 806.6 |  |  |  | 0 | 10 |  | j72 | j123 | BRICK ROAD | 0.39 | 63 | 21 |  |  |  |  | #REF!
12 | 2023-03-14 | J62 | J51 | KACHA |  | 63 | 84.6 | [5 empty] | 891.2 |  |  | 84.6 | 0 | 11 |  | j72 | j146 | INTERLOCKING | 0.39 | 63 | 6 |  |  |  |  | #REF!
13 | 2023-03-14 | J75(1) | J75(2) | KACHA |  | 63 | 47.4 | [5 empty] | 938.6 |  |  |  | 0 | 12 |  | j53 | j65 | B.T ROAD | 0.39 | 63 | 3.5 |  |  |  |  | #REF!
14 | 2023-03-14 | J5 | J7 | KACHA | 0.39 | 63 | 196.2 | [5 empty] | 1134.8 |  |  | 296 | 76.518 | 13 |  | j53 | j65 | INTERLOCKING | 0.44 | 63 | 100.2 |  |  |  |  | #REF!
15 |  | J5 | J7 | BRICK ROAD | 0.39 | 63 | 100.2 | [5 empty] | 1235 |  |  |  | 39.078 | 14 |  | J10 | J22 | BRICK ROAD | 0.39 | 75 | 68.2 |  |  |  |  | #REF!
16 | 2023-03-14 | J67 | J109 | KACHA |  | 63 | 3.2 | [5 empty] | 1238.2 |  |  |  | 0 | 15 |  | J8 | J115 | BRICK ROAD | 0.39 | 63 | 12.2 |  |  |  |  | #REF!
17 | 2023-03-14 | J67 | J109 | BRICK ROAD | 0.39 | 63 | 51.2 | [5 empty] | 1289.4 |  |  | 51.2 | 19.968 | 16 | 2023-03-14 | J19 | J87 | BRICK ROAD | 0.39 | 63 | 89.6 |  |  |  |  | #REF!
18 | 2023-03-14 | J60 | J80 | KACHA |  | 63 | 12.5 | [5 empty] | 1301.9 |  |  |  | 0 | 17 | 2023-03-14 | J19 | J40 | INTERLOCKING | 0.44 | 63 | 203 |  |  |  |  | #REF!
19 | 2023-03-14 | J80 | J141 | KACHA |  | 63 | 21 | [5 empty] | 1322.9 |  |  |  | 0 | 18 | 2023-03-14 | J11 | J19 | INTERLOCKING | 0.44 | 63 | 57 |  |  |  |  | #REF!
20 | 2023-03-14 | J80 | J105 | KACHA |  | 63 | 42 | [5 empty] | 1364.9 |  |  |  | 0 | 19 | 2023-03-14 | J22 | J11 | BRICK ROAD | 0.39 | 75 | 183.2 |  |  |  |  | #REF!
21 | 2023-03-14 | J120 | J102 | B.T ROAD | 0.39 | 63 | 3.5 | [5 empty] | 1368.4 |  |  | 3.5 | 1.365 | 20 | 2023-03-14 | J49 | J54 | BRICK ROAD | 0.39 | 75 | 50 |  |  |  |  | #REF!
22 | 2023-03-14 | J120 | J102 | BRICK ROAD | 0.39 | 63 | 41.3 | [5 empty] | 1409.7 |  |  | 41.3 | 16.107 | 21 | 2023-03-14 | J26 | J14 | BRICK ROAD | 0.39 | 90 | 96 |  |  |  |  | #REF!
23 | 2023-03-14 | J102 | J144 | BRICK ROAD | 0.39 | 63 | 16.1 | [5 empty] | 1425.8 |  |  | 16.1 | 6.279 | 22 | 2023-03-14 | J14 | J23 | BRICK ROAD | 0.39 | 90 | 4 |  |  |  |  | #REF!
24 | 2023-03-14 | J102 | J92(A) | BRICK ROAD | 0.39 | 63 | 25.1 | [5 empty] | 1450.9 |  |  | 25.1 | 9.789 | 23 | 2023-03-14 | J26 | J46 | B.T ROAD | 0.39 | 90 | 3.5 |  |  |  |  | #REF!
25 | 2023-03-14 | J92(B) | J92(A) | KACHA |  | 63 | 45 | [5 empty] | 1495.9 |  |  |  | 0 | 24 | 2023-03-14 | J62 | J125 | BRICK ROAD | 0.39 | 63 | 84.6 |  |  |  |  | #REF!
26 | 2023-03-14 | J92(A) | J92 | BRICK ROAD | 0.39 | 63 | 68.7 | [5 empty] | 1564.6 |  |  | 68.7 | 26.793 | 25 | 2023-03-14 | J12 | J71 | INTERLOCKING | 0.39 | 63 | 12.5 |  |  |  |  | #REF!
27 | 2023-03-14 | J92 | J158 | KACHA |  | 63 | 46.8 | [5 empty] | 1611.4 |  |  |  | 0 | 26 | 2023-03-14 | J12 | J39 | BRICK ROAD | 0.39 | 63 | 18 |  |  |  |  | #REF!
28 | 2023-03-14 | J104 | J153 | KACHA |  | 63 | 55 | [5 empty] | 1666.4 |  |  |  | 0 | 27 | 2023-03-14 | J60 | J141 | BRICK ROAD | 0.39 | 63 | 13 |  |  |  |  | #REF!
29 | 2023-03-14 | j104(a) | j104(b) | KACHA |  | 63 | 28.7 | [5 empty] | 1695.1 |  |  |  | 0 | 28 | 2023-03-14 | J67 | J109 | B.T ROAD | 0.39 | 63 | 3.5 |  |  |  |  | #REF!
30 | 2023-03-14 | j72 | j123 | B.T ROAD | 0.36 | 63 | 3.5 | [5 empty] | 1698.6 |  |  | 3.5 | 1.26 | 29 | 2023-03-14 | J67 | J109 | BRICK ROAD | 0.39 | 63 | 43.4 |  |  |  |  | #REF!
31 | 2023-03-14 | j72 | j123 | KACHA |  | 63 | 113 | [5 empty] | 1811.6 |  |  |  | 0 | 30 | 2023-03-14 | J116 | J147 | B.T ROAD | 0.39 | 63 | 3.5 |  |  |  |  | #REF!
32 |  | j72 | j123 | BRICK ROAD | 0.39 | 63 | 21 | [5 empty] | 1832.6 |  |  | 21 | 8.19 | 31 |  | J63 | J9 | BRICK ROAD | 0.39 | 75 | 46 |  |  |  |  | #REF!
33 | 2023-03-14 | j72 | j146 | KACHA |  | 63 | 21.3 | [5 empty] | 1853.9 |  |  |  | 0 | 32 | 2023-03-14 | J9 | J6 | BRICK ROAD | 0.39 | 75 | 231.5 |  |  |  |  | #REF!
34 |  | j72 | j146 | INTERLOCKING | 0.39 | 63 | 6 | [5 empty] | 1859.9 |  |  | 6 | 2.34 | 33 |  | J98 | J78 | BRICK ROAD | 0.39 | 75 | 50 |  |  |  |  | #REF!
35 | 2023-03-14 | j53 | j65 | KACHA |  | 63 | 26.9 | [5 empty] | 1886.8 |  |  |  | 0 | 34 | 2023-03-14 | J78 | J94 | BRICK ROAD | 0.39 | 75 | 50 |  |  |  |  | #REF!
36 |  | j53 | j65 | B.T ROAD | 0.39 | 63 | 3.5 | [5 empty] | 1890.3 |  |  | 3.5 | 1.365 | 35 |  | J68 | J68(1) | B.T ROAD | 0.39 | 75 | 3.5 |  |  |  |  | #REF!
37 | 2023-03-14 | j53 | j65 | INTERLOCKING | 0.44 | 63 | 100.2 | [5 empty] | 1990.5 |  |  | 100.2 | 44.088 | 36 | 2023-03-14 | J68(1) | J97 | BRICK ROAD | 0.39 | 75 | 113 |  |  |  |  | #REF!
38 | 2023-03-14 | j53 | j65 | KACHA |  | 63 | 337 | [5 empty] | 2327.5 |  |  |  | 0 | 37 | 2023-03-14 | J103 | J37 | BRICK ROAD | 0.39 | 75 | 155 |  |  |  |  | #REF!
39 | 2023-03-14 | j65 | j142 | KACHA |  | 63 | 18.7 | [5 empty] | 2346.2 |  |  |  | 0 | 38 | 2023-03-14 | J91 | J99 | BRICK ROAD | 0.44 | 110 | 19 |  |  |  |  | #REF!
40 | 2023-03-14 | j165A | j165B | KACHA |  | 63 | 12.6 | [5 empty] | 2358.8 |  |  |  | 0 | 39 | 2023-03-14 | J99 | J134 | BRICK ROAD | 0.44 | 110 | 11 |  |  |  |  | #REF!
41 | 2023-03-14 | j6 | j42 | KACHA |  | 63 | 106.9 | [5 empty] | 2465.7 |  |  |  | 0 | 40 | 2023-03-14 | J99 | J134 | BRICK ROAD | 0.44 | 110 | 11 |  |  |  |  | #REF!
42 | 2023-03-14 | j2 | j12 | KACHA |  | 63 | 57.3 | [5 empty] | 2523 |  |  |  | 0 | 41 | 2023-03-14 | J99 | J104 | BRICK ROAD | 0.44 | 110 | 24.2 |  |  |  |  | #REF!
43 | 2023-03-14 | j2 | j12 | KACHA |  | 63 | 80.6 | [5 empty] | 2603.6 |  |  |  | 0 | 42 | 2023-03-14 | J84 | J92 | BRICK ROAD | 0.44 | 110 | 108 |  |  |  |  | #REF!
44 | 2023-03-14 | j12 | j71 | KACHA |  | 63 | 70.7 | [5 empty] | 2674.3 |  |  |  | 0 | 43 |  | J124 | J114 | BRICK ROAD | 0.44 | 110 | 72 |  |  |  |  | #REF!
45 |  | j16 | J89 | KACHA |  | 63 | 39.7 | [5 empty] | 2714 |  |  |  | 0 | 44 |  | J114 | J88 | BRICK ROAD | 0.44 | 110 | 57.3 |  |  |  |  | #REF!
46 |  | J16 | J24 | KACHA |  | 63 | 83 | [5 empty] | 2797 |  |  |  | 0 | 45 |  | J2 | J62 | B.T ROAD | 0.44 | 140 | 6 |  |  |  |  | #REF!
47 |  | J4 | J59 | KACHA |  | 63 | 9 | [5 empty] | 2806 |  |  |  | 0 | 46 |  | J2 | J62 | BRICK ROAD | 0.44 | 140 | 225 |  |  |  |  | #REF!
48 |  | J10 | J22 | BRICK ROAD | 0.39 | 75 | 68.2 | [5 empty] | 2874.2 |  |  |  | 26.598 | 47 |  | J2 | J62 | BRICK ROAD | 0.44 | 140 | 41 |  |  |  |  | #REF!
49 |  | J8 | J115 | BRICK ROAD | 0.39 | 63 | 12.2 | [5 empty] | 2886.4 |  |  |  | 4.758 | 48 |  | J62 | J157 | BRICK ROAD | 0.44 | 140 | 53.7 |  |  |  |  | #REF!
50 |  | J8 | J115 | KACHA |  | 63 | 25.2 | [5 empty] | 2911.6 |  |  |  | 0 | 49 |  | J2 | J5 | INTERLOCKING | 0.44 | 140 | 3.5 |  |  |  |  | #REF!
51 |  | J19 | J87 | KACHA |  | 63 | 59.6 | [5 empty] | 2971.2 |  |  |  | 0 | 50 |  | J2(A) | J5(B) | B.T ROAD | 0.44 | 140 | 4 |  |  |  |  | #REF!
52 |  | J19 | J87 | BRICK ROAD |  | 63 | 89.6 | [5 empty] | 3060.8 |  |  |  | 0 | 51 |  | J5 | J60 | B.T ROAD | 0.44 | 140 | 4.7 |  |  |  |  | #REF!
53 |  | J19 | J40 | INTERLOCKING | 0.44 | 63 | 203 | [5 empty] | 3263.8 |  |  |  | 89.32 | 52 |  | J120 | J111 | BRICK ROAD | 0.44 | 140 | 4 |  |  |  |  | #REF!
54 |  | J11 | J85 | KACHA |  | 63 | 60.4 | [5 empty] | 3324.2 |  |  |  | 0 | 53 |  | J63 | J91 | BRICK ROAD | 0.44 | 140 | 88.9 |  |  |  |  | #REF!
55 |  | J11 | J19 | KACHA |  | 63 | 94.2 | [5 empty] | 3418.4 |  |  |  | 0 | 54 |  | J91 | J124 | BRICK ROAD | 0.44 | 140 | 181.6 |  |  |  |  | #REF!
56 |  | J12(1) | J39(1) | KACHA |  | 63 | 36.5 | [5 empty] | 3454.9 |  |  |  | 0 | 55 |  | J124 | J157 | BRICK ROAD | 0.44 | 140 | 76 |  |  |  |  | #REF!
57 |  | J11 | J19 | INTERLOCKING | 0.44 | 63 | 57 | [5 empty] | 3511.9 |  |  |  | 25.08 | 56 |  | J1 | J8 | BRICK ROAD | 0.44 | 140 | 125.5 |  |  |  |  | #REF!
58 |  | J22 | J11 | BRICK ROAD | 0.39 | 75 | 183.2 | [5 empty] | 3695.1 |  |  |  | 71.448 | 57 | 2023-03-14 | J18 | J10 | BRICK ROAD | 0.44 | 140 | 314.8 |  |  |  |  | #REF!
59 | 2023-03-14 | J27 | J48 | KACHA |  | 75 | 24.3 | 24.3 |  |  |  |  | 3719.4 |  |  |  | 0 | 58 | 2023-03-14 | J157 | OHT | BRICK ROAD | 0.44 | 160 | 100 |  |  |  |  | #REF!
60 | 2023-03-14 | J48 | J38 | KACHA |  | 75 | 23.6 | 23.6 |  |  |  |  | 3743 |  |  |  | 0 | [12 empty] | #REF!
61 | 2023-03-14 | J21 | J17 | KACHA |  | 75 | 74 | 74 |  |  |  |  | 3817 |  |  |  | 0 |  | 2023-03-14 | 63 | 75 | 110 | 140 | 160 | [5 empty] | #REF!
62 | 2023-03-14 | J13 | J32 | KACHA |  | 75 | 41.2 | 41.2 |  |  |  |  | 3858.2 |  |  |  | 0 |  | 2023-03-14 | 984.1 | 950.4 | 302.5 | 1128.7 | 100 | 3465.7 |  |  |  |  | #REF!
63 | 2023-03-14 | J32 | J21 | KACHA |  | 75 | 74.5 | 74.5 |  |  |  |  | 3932.7 |  |  |  | 0 |  | 2023-03-14 | [10 empty] | #REF!
64 | 2023-03-14 | J49 | J54 | KACHA |  | 75 | 205.1 | 205.1 |  |  |  |  | 4137.8 |  |  |  | 0 |  | 2023-03-14 | [10 empty] | #REF!
65 | 2023-03-14 | J49 | J54 | BRICK ROAD | 0.39 | 75 | 50 | 50 |  |  |  |  | 4187.8 |  |  | 50 | 19.5 |  | 2023-03-14 | [10 empty] | #REF!
66 | 2023-03-14 | J26 | J14 | KACHA |  | 90 | 42.3 |  | 42.3 |  |  |  | 4230.1 |  |  |  | 0 |  | 2023-03-14 | [10 empty] | #REF!
67 | 2023-03-14 | J26 | J14 | BRICK ROAD | 0.39 | 90 | 96 |  | 96 |  |  |  | 4326.1 |  |  | 96 | 37.44 |  | 2023-03-14 | [10 empty] | #REF!
68 | 2023-03-14 | J14 | J23 | BRICK ROAD | 0.39 | 90 | 4 |  | 4 |  |  |  | 4330.1 |  |  | 4 | 1.56 |  | 2023-03-14 | [10 empty] | #REF!
69 | 2023-03-14 | J14 | J23 | KACHA |  | 90 | 120.1 |  | 102 |  |  |  | 4450.2 |  |  |  | 0 |  | 2023-03-14 | [10 empty] | #REF!
70 | 2023-03-14 | J14 | J27 | KACHA |  | 90 | 90 |  | 101 |  |  |  | 4540.2 |  |  |  | 0 |  | 2023-03-14 | [10 empty] | #REF!
71 | 2023-03-14 | J26 | J46 | B.T ROAD | 0.39 | 90 | 3.5 |  | 3.5 |  |  |  | 4543.7 |  |  | 3.5 | 1.365 |  | 2023-03-14 | [10 empty] | #REF!
72 | 2023-03-14 | J26 | J46 | KACHA |  | 90 | 86 |  | 86 |  |  |  | 4629.7 |  |  | 86 | 0 |  | 2023-03-14 | [10 empty] | #REF!
73 | 2023-03-14 | J70 | J49 | KACHA |  | 90 | 273.6 |  | 273.6 |  |  |  | 4903.3 |  |  |  | 0 |  | 2023-03-14 | [10 empty] | #REF!
74 | 2023-03-14 | J70 | J26 | KACHA |  | 110 | 1474 |  |  | 1362 |  |  | 6377.3 |  |  |  | 0 |  | 2023-03-14 | [10 empty] | #REF!
75 | 2023-03-14 | J70 | J112 | KACHA |  | 140 | 119 |  |  |  | 119 |  | 6496.3 |  |  |  | 0 |  | 2023-03-14 | [10 empty] | #REF!
76 | 2023-03-14 | J157 | J62 | KACHA |  | 140 | 53.6 |  |  |  | 53.6 |  | 6549.9 |  |  |  | 0 |  | 2023-03-14 | [10 empty] | #REF!
dia of pipe |  | 63 | 75 | 90 | 110 | 140 | 160
|  | 3443.7 | 744.1 | 715.5 | 1474 | 172.6 | 0 | [5 empty] | 6549.9 | [6 empty] | 12231.5
|  | 4871 | 2635 | 985 | 2015 | 2689 | 179 | [5 empty] | 13374
MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT. |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  |  | NAME |  |  |  | NAME | [10 empty] | 63 | 75 | 90 | 110 | 140 | 160
SIGN.with date |  |  |  |  | SIGN.with date |  |  |  | SIGN.with date | [10 empty] | 3443.7 | 744.1 | 715.5 | 1474 | 172.6 | 0
[20 empty] | 707.8 | 1661.2 | 0 | 648.3 | 2497.5 | 166.8
12231.5
avg width-0.390
|  | TYPE OF ROAD |  | 63 | 75 | 90 | 110 | 111 | 112 | 113 | 114 | 115 | 140 | 141 | 142 | 143 | Cummilative | sqm | rupees
|  | BRICK ROAD |  | 425.4 | 301.4 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 287.508 | 355 | 404991 | 826.8 | 322.452 | 72551.7
|  | B.T ROAD |  | 14 | 0 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.72 | 85 | 179996 | 17.5 | 6.825 | 5562.375
|  | INTERLOCKING |  | 366.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160.828 | 177 | 44999 | 366.2 | 142.818 | 87547.434
[19 empty] | 165661.509 |  | 245440
1.0826
0
seshpur adharganj
Sl.No | Date | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | DIA/HDPE | Pipe Length (M) | [5 empty] | CUMMULATIVE |  |  | RESTORATION
[8 empty] | 75mm | 90mm | 110mm | 140mm | 160mm
1 | 2023-03-14 | J62 | J125 | BRICK ROAD | 0.39 | 63 | 84.6 | [5 empty] | 84.6 |  |  | 84.6 | 32.994 |  |  |  | 2122.3
2 | 2023-03-14 | J51 | J75 | KACHA |  | 63 | 17.6 | [5 empty] | 102.2 |  |  |  | 0
3 | 2023-03-14 | J75 | J139 | KACHA |  | 63 | 47.4 | [5 empty] | 149.6 |  |  |  | 0 |  |  | 1 | 2023-03-14 | J62 | J125 | BRICK ROAD | 0.39 | 63 | 84.6 |  |  |  |  | 84.6
4 | 2023-03-14 | J12 | J71 | INTERLOCKING | 0.39 | 63 | 12.5 | [5 empty] | 162.1 |  |  | 12.5 | 4.875
5 | 2023-03-14 | J12 | J71 | KACHA |  | 63 | 79.4 | [5 empty] | 241.5 |  |  | 79.4 | 0
6 |  | J12 | J39 | BRICK ROAD | 0.39 | 63 | 18 | [5 empty] | 259.5 |  |  |  | 7.02 |  |  | 1 | 2023-03-14 | J12 | J71 | INTERLOCKING | 0.39 | 63 | 12.5 |  |  |  |  | 12.5
7 |  | J12 | J39 | KACHA |  | 63 | 171.2 | [5 empty] | 430.7 |  |  |  | 0
8 | 2023-03-14 | J60 | J141 | BRICK ROAD | 0.39 | 63 | 13 | [5 empty] | 443.7 |  |  | 13 | 5.07 |  |  | 1 |  | J12 | J39 | BRICK ROAD | 0.39 | 63 | 18 |  |  |  |  | 18
9 | 2023-03-14 | J141 | J80 | KACHA |  | 63 | 21.8 | [5 empty] | 465.5 |  |  |  | 0
10 | 2023-03-14 | J141 | J105 | KACHA |  | 63 | 42.4 | [5 empty] | 507.9 |  |  |  | 0 |  |  | 1 | 2023-03-14 | J60 | J141 | BRICK ROAD | 0.39 | 63 | 13 |  |  |  |  | 13
11 | 2023-03-14 | J9 | J64 | KACHA |  | 63 | 50 | [5 empty] | 557.9 |  |  |  | 0
12 | 2023-03-14 | J98 | J149 | KACHA |  | 63 | 30 | [5 empty] | 587.9 |  |  |  | 0
13 | 2023-03-14 | J78 | J148 | KACHA |  | 63 | 27.5 | [5 empty] | 615.4 |  |  |  | 0
14 | 2023-03-14 | J67 | J109 | B.T ROAD | 0.39 | 63 | 3.5 | [5 empty] | 618.9 |  |  | 3.5 | 1.365
15 | 2023-03-14 | J67 | J109 | BRICK ROAD | 0.39 | 63 | 43.4 | [5 empty] | 662.3 |  |  | 43.4 | 16.926
16 | 2023-03-14 | J67 | J109 | KACHA |  | 63 | 9 | [5 empty] | 671.3 |  |  |  | 0 |  |  | 1 | 2023-03-14 | J67 | J109 | B.T ROAD | 0.39 | 63 | 3.5 |  |  |  |  | 3.5
17 | 2023-03-14 | J116 | J147 | B.T ROAD | 0.39 | 63 | 3.5 | [5 empty] | 674.8 |  |  | 3.5 | 1.365 |  |  | 2 | 2023-03-14 | J67 | J109 | BRICK ROAD | 0.39 | 63 | 43.4 |  |  |  |  | 46.9
18 | 2023-03-14 | J116 | J147 | KACHA |  | 63 | 33 | [5 empty] | 707.8 |  |  |  | 0 |  |  | 3 | 2023-03-14 | J67 | J109 | KACHA |  | 63 | 9 |  |  |  |  | 55.9
19 | 2023-03-14 | J3 | J1 | KACHA |  | 75 | 452.5 | 452.5 |  |  |  |  | 1160.3 |  |  |  | 0 |  |  | 4 | 2023-03-14 | J116 | J147 | B.T ROAD | 0.39 | 63 | 3.5 |  |  |  |  | 59.4
20 | 2023-03-14 | J63 | J9 | BRICK ROAD | 0.39 | 75 | 46 | 46 |  |  |  |  | 1206.3 |  |  | 46 | 17.94 |  |  | 5 | 2023-03-14 | J116 | J147 | KACHA |  | 63 | 33 |  |  |  |  | 92.4
21 | 2023-03-14 | J9 | J6 | BRICK ROAD | 0.39 | 75 | 231.5 | 231.5 |  |  |  |  | 1437.8 |  |  | 231.5 | 90.285 |  |  | 6 | 2023-03-14 | J3 | J1 | KACHA |  | 75 | 452.5 | 452.5 |  |  |  | 544.9
22 | 2023-03-14 | J111 | J94 | KACHA |  | 75 | 41 | 41 |  |  |  |  | 1478.8 |  |  |  | 0 |  |  | 7 | 2023-03-14 | J63 | J9 | BRICK ROAD | 0.39 | 75 | 46 | 46 |  |  |  | 590.9
23 | 2023-03-14 | J112 | J98 | KACHA |  | 75 | 65 | 65 |  |  |  |  | 1543.8 |  |  |  | 0 |  |  | 8 | 2023-03-14 | J9 | J6 | BRICK ROAD | 0.39 | 75 | 231.5 | 231.5 |  |  |  | 822.4
24 |  | J98 | J78 | KACHA |  | 75 | 61 | 61 |  |  |  |  | 1604.8 |  |  |  | 0 |  |  | 9 | 2023-03-14 | J111 | J94 | KACHA |  | 75 | 41 | 41 |  |  |  | 863.4
25 | 2023-03-14 | J98 | J78 | BRICK ROAD | 0.39 | 75 | 50 | 50 |  |  |  |  | 1654.8 |  |  | 50 | 19.5 |  |  | 10 | 2023-03-14 | J112 | J98 | KACHA |  | 75 | 65 | 65 |  |  |  | 928.4
26 | 2023-03-14 | J78 | J94 | KACHA |  | 75 | 98.4 | 98.4 |  |  |  |  | 1753.2 |  |  |  | 0 |  |  | 11 |  | J98 | J78 | KACHA |  | 75 | 61 | 61 |  |  |  | 989.4
27 | 2023-03-14 | J78 | J94 | BRICK ROAD | 0.39 | 75 | 50 | 50 |  |  |  |  | 1803.2 |  |  | 50 | 19.5 |  |  | 12 | 2023-03-14 | J98 | J78 | BRICK ROAD | 0.39 | 75 | 50 | 50 |  |  |  | 1039.4
28 | 2023-03-14 | J49 | J68 | KACHA |  | 75 | 92 | 92 |  |  |  |  | 1895.2 |  |  |  | 0 |  |  | 13 | 2023-03-14 | J78 | J94 | KACHA |  | 75 | 98.4 | 98.4 |  |  |  | 1137.8
29 | 2023-03-14 | J68 | J68(1) | B.T ROAD | 0.39 | 75 | 3.5 | 3.5 |  |  |  |  | 1898.7 |  |  | 3.5 | 1.365 |  |  | 14 | 2023-03-14 | J78 | J94 | BRICK ROAD | 0.39 | 75 | 50 | 50 |  |  |  | 1187.8
30 | 2023-03-14 | J68 | J68(1) | KACHA |  | 75 | 122.6 | 122.6 |  |  |  |  | 2021.3 |  |  |  | 0 |  |  | 15 | 2023-03-14 | J49 | J68 | KACHA |  | 75 | 92 | 92 |  |  |  | 1279.8
31 | 2023-03-14 | J68(1) | J97 | BRICK ROAD | 0.39 | 75 | 113 | 113 |  |  |  |  | 2134.3 |  |  | 113 | 44.07 |  |  | 16 | 2023-03-14 | J68 | J68(1) | B.T ROAD | 0.39 | 75 | 3.5 | 3.5 |  |  |  | 1283.3
32 | 2023-03-14 | J68 | J116 | KACHA |  | 75 | 79.7 | 79.7 |  |  |  |  | 2214 |  |  |  | 0 |  |  | 17 | 2023-03-14 | J68 | J68(1) | KACHA |  | 75 | 122.6 | 122.6 |  |  |  | 1405.9
33 |  | J103 | J37 | BRICK ROAD | 0.39 | 75 | 155 | [5 empty] | 2369 |  |  |  | 60.45 |  |  | 18 | 2023-03-14 | J68(1) | J97 | BRICK ROAD | 0.39 | 75 | 113 | 113 |  |  |  | 1518.9
34 | 2023-03-14 | J91 | J99 | BRICK ROAD | 0.44 | 110 | 19 |  |  | 19 |  |  | 2388 |  |  | 19 | 8.36 |  |  | 19 | 2023-03-14 | J68 | J116 | KACHA |  | 75 | 79.7 | 79.7 |  |  |  | 1598.6
35 | 2023-03-14 | J99 | J134 | KACHA |  | 110 | 83 |  |  | 83 |  |  | 2471 |  |  |  | 0 |  |  | 20 |  | J103 | J37 | BRICK ROAD | 0.39 | 75 | 155 |  |  |  |  | 1753.6
36 |  | J99 | J134 | BRICK ROAD | 0.44 | 110 | 11 |  |  | 11 |  |  | 2482 |  |  | 11 | 4.84 |  |  | 21 | 2023-03-14 | J91 | J99 | BRICK ROAD | 0.44 | 110 | 19 |  | 19 |  |  | 1772.6
37 | 2023-03-14 | J99 | J104 | KACHA |  | 110 | 33.8 |  |  | 33.8 |  |  | 2515.8 |  |  |  | 0 |  |  | 22 | 2023-03-14 | J99 | J134 | KACHA |  | 110 | 83 |  | 83 |  |  | 1855.6
38 |  | J99 | J104 | BRICK ROAD | 0.44 | 110 | 24.2 |  |  | 24.2 |  |  | 2540 |  |  | 24.2 | 10.648 |  |  | 23 |  | J99 | J134 | BRICK ROAD | 0.44 | 110 | 11 |  | 11 |  |  | 1866.6
39 | 2023-03-14 | J104 | J88 | KACHA |  | 110 | 75 |  |  | 62 |  |  | 2615 |  |  |  | 0 |  |  | 24 | 2023-03-14 | J99 | J104 | KACHA |  | 110 | 33.8 |  | 33.8 |  |  | 1900.4
40 | 2023-03-14 | J88 | J84 | KACHA |  | 110 | 127.5 |  |  | 127.5 |  |  | 2742.5 |  |  |  | 0 |  |  | 25 |  | J99 | J104 | BRICK ROAD | 0.44 | 110 | 24.2 |  | 24.2 |  |  | 1924.6
41 | 2023-03-14 | J84 | J92 | KACHA |  | 110 | 37.5 |  |  | 37.5 |  |  | 2780 |  |  |  | 0 |  |  | 26 | 2023-03-14 | J104 | J88 | KACHA |  | 110 | 75 |  | 62 |  |  | 1999.6
42 | 2023-03-14 | J84 | J92 | BRICK ROAD | 0.44 | 110 | 108 |  |  | 108 |  |  | 2888 |  |  | 108 | 47.52 |  |  | 27 | 2023-03-14 | J88 | J84 | KACHA |  | 110 | 127.5 |  | 127.5 |  |  | 2127.1
43 | 2023-03-14 | J124 | J114 | BRICK ROAD | 0.44 | 110 | 72 |  |  | 72 |  |  | 2960 |  |  | 72 | 31.68 |  |  | 28 | 2023-03-14 | J84 | J92 | KACHA |  | 110 | 37.5 |  | 37.5 |  |  | 2164.6
44 | 2023-03-14 | J114 | J88 | BRICK ROAD | 0.44 | 110 | 57.3 |  |  | 57.3 |  |  | 3017.3 |  |  | 57.3 | 25.212 |  |  | 29 | 2023-03-14 | J84 | J92 | BRICK ROAD | 0.44 | 110 | 108 |  | 108 |  |  | 2272.6
45 | 2023-03-14 | J2 | J62 | B.T ROAD | 0.44 | 140 | 6 |  |  |  | 6 |  | 3023.3 |  |  | 6 | 2.64 |  |  | 30 | 2023-03-14 | J124 | J114 | BRICK ROAD | 0.44 | 110 | 72 |  | 72 |  |  | 2344.6
46 |  | J2 | J62 | BRICK ROAD | 0.44 | 140 | 225 |  |  |  | 225 |  | 3248.3 |  |  |  | 99 |  |  | 31 | 2023-03-14 | J114 | J88 | BRICK ROAD | 0.44 | 110 | 57.3 |  | 57.3 |  |  | 2401.9
47 | 2023-03-14 | J2 | J62 | BRICK ROAD | 0.44 | 140 | 41 |  |  |  | 41 |  | 3289.3 |  |  | 41 | 18.04 |  |  | 32 | 2023-03-14 | J2 | J62 | B.T ROAD | 0.44 | 140 | 6 |  |  | 6 |  | 2407.9
48 | 2023-03-14 | J62 | J157 | BRICK ROAD | 0.44 | 140 | 53.7 |  |  |  | 53.7 |  | 3343 |  |  | 53.7 | 23.628 |  |  | 33 |  | J2 | J62 | BRICK ROAD | 0.44 | 140 | 225 |  |  | 225 |  | 2632.9
49 | 2023-03-14 | J2 | J1 | KACHA |  | 140 | 146.1 |  |  |  | 146.1 |  | 3489.1 |  |  |  | 0 |  |  | 34 | 2023-03-14 | J2 | J62 | BRICK ROAD | 0.44 | 140 | 41 |  |  | 41 |  | 2673.9
50 | 2023-03-14 | J2 | J5 | INTERLOCKING | 0.44 | 140 | 3.5 |  |  |  | 3.5 |  | 3492.6 |  |  | 3.5 | 1.54 |  |  | 35 | 2023-03-14 | J62 | J157 | BRICK ROAD | 0.44 | 140 | 53.7 |  |  | 53.7 |  | 2727.6
51 | 2023-03-14 | J2(A) | J5(B) | B.T ROAD | 0.44 | 140 | 4 |  |  |  | 4 |  | 3496.6 |  |  | 4 | 1.76 |  |  | 36 | 2023-03-14 | J2 | J1 | KACHA |  | 140 | 146.1 |  |  | 146.1 |  | 2873.7
52 | 2023-03-14 | J2 | J5 | KACHA |  | 140 | 200.5 |  |  |  | 204.5 |  | 3697.1 |  |  |  | 0 |  |  | 37 | 2023-03-14 | J2 | J5 | INTERLOCKING | 0.44 | 140 | 3.5 |  |  | 3.5 |  | 2877.2
53 | 2023-03-14 | J5 | J60 | B.T ROAD | 0.44 | 140 | 4.7 |  |  |  | 4.7 |  | 3701.8 |  |  | 4.7 | 2.068 |  |  | 38 | 2023-03-14 | J2(A) | J5(B) | B.T ROAD | 0.44 | 140 | 4 |  |  | 4 |  | 2881.2
54 |  | J5 | J67 | KACHA |  | 140 | 32 |  |  |  | 32 |  | 3733.8 |  |  |  | 0 |  |  | 39 | 2023-03-14 | J2 | J5 | KACHA |  | 140 | 200.5 |  |  | 204.5 |  | 3081.7
55 | 2023-03-14 | J67 | J60 | KACHA |  | 140 | 28.6 |  |  |  | 28.6 |  | 3762.4 |  |  |  | 0 |  |  | 40 | 2023-03-14 | J5 | J60 | B.T ROAD | 0.44 | 140 | 4.7 |  |  | 4.7 |  | 3086.4
56 | 2023-03-14 | J60 | J63 | KACHA |  | 140 | 95.8 |  |  |  | 96 |  | 3858.2 |  |  |  | 0 |  |  | 41 |  | J5 | J67 | KACHA |  | 140 | 32 |  |  | 32 |  | 3118.4
57 | 2023-03-14 | J63 | J120 | KACHA |  | 140 | 43.3 |  |  |  | 43.3 |  | 3901.5 |  |  |  | 0 |  |  | 42 | 2023-03-14 | J67 | J60 | KACHA |  | 140 | 28.6 |  |  | 28.6 |  | 3147
58 | 2023-03-14 | J120 | J111 | BRICK ROAD | 0.44 | 140 | 4 |  |  |  | 4 |  | 3905.5 |  |  | 4 | 1.76 |  |  | 43 | 2023-03-14 | J60 | J63 | KACHA |  | 140 | 95.8 |  |  | 96 |  | 3242.8
59 | 2023-03-14 | J120 | J111 | KACHA |  | 140 | 46.5 |  |  |  | 49 |  | 3952 |  |  |  | 0 |  |  | 44 | 2023-03-14 | J63 | J120 | KACHA |  | 140 | 43.3 |  |  | 43.3 |  | 3286.1
60 | 2023-03-14 | J111 | J72 | KACHA |  | 140 | 46.2 |  |  |  | 47.2 |  | 3998.2 |  |  |  | 0 |  |  | 45 | 2023-03-14 | J120 | J111 | BRICK ROAD | 0.44 | 140 | 4 |  |  | 4 |  | 3290.1
61 | 2023-03-14 | J72 | J112 | KACHA |  | 140 | 170.4 |  |  |  | 170.4 |  | 4168.6 |  |  |  | 0 |  |  | 46 | 2023-03-14 | J120 | J111 | KACHA |  | 140 | 46.5 |  |  | 49 |  | 3336.6
62 | 2023-03-14 | J63 | J91 | BRICK ROAD | 0.44 | 140 | 88.9 |  |  |  | 92 |  | 4257.5 |  |  | 92 | 39.116 |  |  | 47 | 2023-03-14 | J111 | J72 | KACHA |  | 140 | 46.2 |  |  | 47.2 |  | 3382.8
63 | 2023-03-14 | J91 | J124 | BRICK ROAD | 0.44 | 140 | 181.6 |  |  |  | 181.6 |  | 4439.1 |  |  | 181.6 | 79.904 |  |  | 48 | 2023-03-14 | J72 | J112 | KACHA |  | 140 | 170.4 |  |  | 170.4 |  | 3553.2
64 | 2023-03-14 | J124 | J157 | BRICK ROAD | 0.44 | 140 | 76 |  |  |  | 82 |  | 4515.1 |  |  | 82 | 33.44 |  |  | 49 | 2023-03-14 | J63 | J91 | BRICK ROAD | 0.44 | 140 | 88.9 |  |  | 92 |  | 3642.1
65 | 2023-03-14 | J1 | J8 | BRICK ROAD | 0.44 | 140 | 125.5 | [5 empty] | 4640.6 |  |  | 100 | 55.22 |  |  | 50 | 2023-03-14 | J91 | J124 | BRICK ROAD | 0.44 | 140 | 181.6 |  |  | 181.6 |  | 3823.7
66 |  | J8 | J4 | KACHA |  | 140 | 225.4 | [5 empty] | 4866 |  |  |  | 0 |  |  | 51 | 2023-03-14 | J124 | J157 | BRICK ROAD | 0.44 | 140 | 76 |  |  | 82 |  | 3899.7
67 |  | J4 | J28 | KACHA |  | 140 | 90.8 | [5 empty] | 4956.8 |  |  |  | 0 |  |  | 52 | 2023-03-14 | J1 | J8 | BRICK ROAD | 0.44 | 140 | 125.5 |  |  |  |  | 4025.2
68 |  | J28 | J34 | KACHA |  | 140 | 67 | [5 empty] | 5023.8 |  |  |  | 0 |  |  | 53 |  | J8 | J4 | KACHA |  | 140 | 225.4 |  |  |  |  | 4250.6
69 |  | J34 | J24 | KACHA |  | 140 | 44.9 | [5 empty] | 5068.7 |  |  |  | 0 |  | 2603.1 | 54 |  | J4 | J28 | KACHA |  | 140 | 90.8 |  |  |  |  | 4341.4
70 |  | J24 | J16 | KACHA |  | 140 | 100.3 | [5 empty] | 5169 |  |  |  | 0 |  |  | 55 |  | J28 | J34 | KACHA |  | 140 | 67 |  |  |  |  | 4408.4
71 |  | J16 | J18 | KACHA |  | 140 | 31 | [5 empty] | 5200 |  |  |  | 0 |  |  | 56 |  | J34 | J24 | KACHA |  | 140 | 44.9 |  |  |  |  | 4453.3
72 |  | J18 | J10 | BRICK ROAD | 0.44 | 140 | 314.8 | [5 empty] | 5514.8 |  |  |  | 138.512 |  |  | 57 |  | J24 | J16 | KACHA |  | 140 | 100.3 |  |  |  |  | 4553.6
73 |  | J157 | OHT | BRICK ROAD | 0.44 | 160 | 100 |  |  |  |  | 100 | 5614.8 |  |  |  | 44 |  |  | 58 |  | J16 | J18 | KACHA |  | 140 | 31 |  |  |  |  | 4584.6
74 |  | J157 | OHT | KACHA |  | 160 | 66.8 |  |  |  |  | 66.8 | 5681.6 |  |  |  | 0 |  |  | 59 |  | J18 | J10 | BRICK ROAD | 0.44 | 140 | 314.8 |  |  |  |  | 4899.4
[20 empty] | 60 |  | J157 | OHT | BRICK ROAD | 0.44 | 160 | 100 |  |  |  | 100 | 4999.4
|  | 63 | 75 | 90 | 110 | 140 | 160 | [12 empty] | 61 |  | J157 | OHT | KACHA |  | 160 | 66.8 |  |  |  | 66.8 | 5066.2
|  | 707.8 | 1661.2 | 0 | 648.3 | 2497.5 | 166.8 | [5 empty] | 5681.6
|  | 4871 | 2635 | 985 | 2015 | 2689 | 179 | [5 empty] | 13374
|  | 4151.5 | 2405.3 | 715.5 | 2122.3 | 2670.1 | 166.8
[6 empty] | 2670.1 | [13 empty] | 2405.2
MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT. |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  |  | SIGN.with date |  |  |  | SIGN.with date
average width-0.419
TYPE OF ROAD |  | 63 | 75 | 90 | 110 | 140 | 160 | 113 | 114 | 115 | 140 | 141 | Cummilative | 143 | Cummilative |  | sqm
BRICK ROAD |  | 159 | 645.5 | 0 | 291.5 | 1110.5 | 100 | 0 | 0 | 0 | 0 | 0 | 2306.5 | 0 | 2306.5 |  | 966.4235
B.T ROAD |  | 7 | 3.5 | 0 | 0 | 14.7 | 0 | 0 | 0 | 0 | 0 | 0 | 25.2 | 0 | 25.2 |  | 10.5588
INTERLOCKING |  | 12.5 | 0 | 0 | 0 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 16 |  | 6.704
0
2347.7
total rupees
[5 empty] | BRICK ROAD | 966.4235 | 322.452 | [5 empty] | 1288.8755
[5 empty] | B.T ROAD | 10.5588 | 6.825 | [5 empty] | 17.3838
[5 empty] | INTERLOCKING | 6.704 | 142.818 | [5 empty] | 149.522
seshpur adharganj
sqm
|  | TYPE OF ROAD |  | 63mm |  | 75mm | 90mm | 110mm | 140mm | 160mm | Cumulative
|  | BRICK ROAD |  | 2306.5 |  | 490.5 | 0 | 291.5 | 679.3 | 100 | 3867.8
|  | B.T ROAD |  | 25.2 |  | 3.5 | 0 | 0 | 14.7 | 0 | 43.4
|  | INTERLOCKING |  | 16 |  | 0 | 0 | 0 | 3.5 | 0 | 19.5
|  | BRICK ROAD | 1262.135
|  | B.T ROAD | 17.283
|  | INTERLOCKING | 257.215
0.81
0.405

## seshpur adharganj 2
seshpur adharganj
Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | DIA/HDPE | Pipe Length (M) | CUMMULATIVE
1 | j43 | j43(1) |  | 0.363 | 63 | 700 | 700
2 | j128 | j128(1) |  | 0.363 | 63 | 380 | 1080
MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  |  | DESIGNATION
NAME |  |  |  |  | NAME
SIGN.with date |  |  |  |  | SIGN.with date