## hardoi jmr sheet
HARDOI
Sl.No | Date | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | DI/HDPE | Pipe Length (M) |  |  |  |  | Cumulative Length (M) | LHS/RHS | Distance from Road C/L | Site Engineer Sign | RESTORATION | Remarks |  | TYPE OF ROAD | 63mm | 75mm | 90mm | 110mm | 140mm | Cumulative
[7 empty] | 63mm | 75mm | 90mm | 110mm | 140mm | [7 empty] | BRICK ROAD | 296.5 | 116.1 | 278.6 | 196.8 | 220.4 | 1108.4
1 |  | J101 | 91 | KACHA |  | HDPE | 162 |  |  |  |  | 162 | RHS |  | SHASHIRANJAN |  |  |  | B.T ROAD | 15.5 | 3 | 4 | 3.5 | 3.5 | 29.5
2 |  | J91 | 20 | KACHA |  | HDPE | 34 |  |  |  |  | 196 | LHS |  | SHASHIRANJAN |  |  |  | INTERLOCKING | 119 | 0 | 0 | 0 | 0 | 119
3 |  | J91 | 89 | KACHA |  | HDPE | 76 |  |  |  |  | 272 | RHS |  | SHASHIRANJAN
4 |  | J89 | 29 | KACHA |  | HDPE | 29 |  |  |  |  | 301 | RHS |  | SHASHIRANJAN
5 |  | J29(A) | 36 | KACHA |  | HDPE |  | 340 |  |  |  | 641 | RHS |  | SHASHIRANJAN
6 |  | J29 | 36 | KACHA |  | HDPE | 60 |  |  |  |  | 701 |  |  | SHASHIRANJAN
7 |  | J36 | 47 | KACHA |  | HDPE | 60 |  |  |  |  | 761 | RHS |  | SHASHIRANJAN
8 |  | J47 | 84 | KACHA |  | HDPE | 58 |  |  |  |  | 819 | RHS |  | SHASHIRANJAN |  |  | 363
9 |  | J84 | 96 | KACHA |  | HDPE |  | 30 |  |  |  | 849 | RHS |  | SHASHIRANJAN |  |  | 36
10 |  | J96 | 95 | BRICK ROAD | 0.45 | HDPE |  |  |  |  | 58 | 907 | RHS |  | SHASHIRANJAN | 58 | 26.1
11 |  | J47(A) | 84(A) | BRICK ROAD | 0.36 | HDPE | 3 |  |  |  |  | 910 | RHS |  | SHASHIRANJAN | 3 | 9
12 |  | J96(A) | 95(A) | BRICK ROAD | 0.45 | HDPE |  |  |  |  | 44 | 954 | RHS |  | SHASHIRANJAN | 44 | 0
13 |  | J95 | J75 | BRICK ROAD | 0.45 | HDPE |  |  |  |  | 118.4 | 1072.4 | RHS |  | SHASHIRANJAN | 118.4 | 26.1
14 |  | J75 | 104 | KACHA |  | HDPE |  |  |  |  | 196 | 1268.4 | RHS |  | SHASHIRANJAN
15 |  | J103 | 93 | KACHA |  | HDPE |  |  |  | 112 |  | 1380.4 | RHS |  | SHASHIRANJAN
16 |  | J93 | 106 | KACHA |  | HDPE |  |  | 50 |  |  | 1430.4 | RHS |  | SHASHIRANJAN
17 |  | J106 | 77 | KACHA |  | HDPE |  |  | 252.1 |  |  | 1682.5 | RHS |  | SHASHIRANJAN
18 |  | J76 | 99 | KACHA |  | HDPE | 165 |  |  |  |  | 1847.5 | RHS |  | SHASHIRANJAN
19 |  | J99 | 92 | KACHA |  | HDPE | 62.8 |  |  |  |  | 1910.3 | RHS |  | SHASHIRANJAN
20 |  | J92 | 100 | KACHA |  | HDPE | 20.2 |  |  |  |  | 1930.5 | RHS |  | SHASHIRANJAN
21 |  | J99(A) | 92(A) | KACHA |  | HDPE | 3.5 |  |  |  |  | 1934 | RHS |  | SHASHIRANJAN
22 |  | J99 | 86 | KACHA |  | HDPE | 9.5 |  |  |  |  | 1943.5 | LHS |  | SHASHIRANJAN
23 |  | J92 | 90 | KACHA |  | HDPE | 19 |  |  |  |  | 1962.5 | LHS |  | SHASHIRANJAN
24 |  | J92 | 90 | B.T ROAD | 0.363 | HDPE | 4 |  |  |  |  | 1966.5 |  |  | SHASHIRANJAN | 4
25 |  | J92 | J100 | KACHA |  | HDPE | 32 |  |  |  |  | 1998.5 | RHS |  | SHASHIRANJAN
26 |  | J100 | 102 | KACHA |  | HDPE | 20 |  |  |  |  | 2018.5 | RHS |  | SHASHIRANJAN
27 |  | J102 | 94 | KACHA |  | HDPE | 12 |  |  |  |  | 2030.5 | RHS |  | SHASHIRANJAN
28 |  | J94 | 82 | KACHA |  | HDPE |  |  | 125.4 |  |  | 2155.9 | LHS |  | SHASHIRANJAN
29 |  | J82 | 52 | KACHA |  | HDPE | 182 |  |  |  |  | 2337.9 | LHS |  | SHASHIRANJAN
30 |  | J82 | 63 | KACHA |  | HDPE |  | 58.5 |  |  |  | 2396.4 | LHS |  | SHASHIRANJAN
31 |  | J82(A) | 63(A) | KACHA |  | HDPE | 3.5 |  |  |  |  | 2399.9 | LHS |  | SHASHIRANJAN
32 |  | J63 | 26 | KACHA |  | HDPE | 10.5 |  |  |  |  | 2410.4 | LHS |  | SHASHIRANJAN
33 |  | J63 | 26 | B.T ROAD | 0.363 | HDPE | 4 |  |  |  |  | 2414.4 |  |  | SHASHIRANJAN | 4
34 |  | J63 | 19 | KACHA |  | HDPE | 33 |  |  |  |  | 2447.4 | LHS |  | SHASHIRANJAN
35 |  | J19 | 25 | KACHA |  | HDPE | 67 |  |  |  |  | 2514.4 | LHS |  | SHASHIRANJAN
36 |  | J103 | 69 | BRICK ROAD | 0.39 | HDPE |  |  | 150.2 |  |  | 2664.6 | LHS |  | SHASHIRANJAN | 150.2 | 26.1
37 |  | J69 | 76 | BRICK ROAD | 0.363 | HDPE | 52 |  |  |  |  | 2716.6 | LHS |  | SHASHIRANJAN | 52 | 26.1
38 |  | J76 | 128 | KACHA |  | HDPE | 38.6 |  |  |  |  | 2755.2 | LHS |  | SHASHIRANJAN
39 |  | J76 | J47 | KACHA |  | HDPE | 36.8 |  |  |  |  | 2792 | LHS |  | SHASHIRANJAN
40 |  | J69 | J36 | KACHA |  | HDPE |  |  | 117 |  |  | 2909 | LHS |  | SHASHIRANJAN
41 |  | J96 | J55 | KACHA |  | HDPE |  |  |  |  | 321.8 | 3230.8 | RHS |  | SHASHIRANJAN
42 |  | J55 | 112 | KACHA |  | HDPE |  |  |  | 119.8 |  | 3350.6 | RHS |  | SHASHIRANJAN
43 |  | J112 | 33 | KACHA |  | HDPE |  |  |  | 61.5 |  | 3412.1 | LHS |  | SHASHIRANJAN
44 |  | J33 | 51 | KACHA |  | HDPE | 6.4 |  |  |  |  | 3418.5 | RHS |  | SHASHIRANJAN
45 |  | J33 | 38 | KACHA |  | HDPE | 15.6 |  |  |  |  | 3434.1 | LHS |  | SHASHIRANJAN
46 |  | J38 | 44 | KACHA |  | HDPE | 34 |  |  |  |  | 3468.1 | LHS |  | SHASHIRANJAN
47 |  | J38 | 61 | KACHA |  | HDPE | 15 |  |  |  |  | 3483.1 | LHS |  | SHASHIRANJAN
48 |  | J61 | 80 | KACHA |  | HDPE | 92 |  |  |  |  | 3575.1 | LHS |  | SHASHIRANJAN
49 |  | J61 | 88 | KACHA |  | HDPE | 133.5 |  |  |  |  | 3708.6 | RHS |  | SHASHIRANJAN
50 |  | J88 | 100 | KACHA |  | HDPE | 112.3 |  |  |  |  | 3820.9 | LHS |  | SHASHIRANJAN
51 |  | J110 | 78 | KACHA |  | HDPE | 87 |  |  |  |  | 3907.9 | LHS |  | SHASHIRANJAN
52 |  | J110 | 64 | KACHA |  | HDPE | 151.6 |  |  |  |  | 4059.5 | LHS |  | SHASHIRANJAN
53 |  | J110 | 64 | B.T ROAD | 0.363 | HDPE | 4 |  |  |  |  | 4063.5 |  |  | SHASHIRANJAN | 4
54 |  | J64 | 68 | KACHA |  | HDPE | 91.9 |  |  |  |  | 4155.4 | LHS |  | SHASHIRANJAN
55 |  | J88 | 59 | KACHA |  | HDPE | 128 |  |  |  |  | 4283.4 | LHS |  | SHASHIRANJAN
56 |  | J59 | 46 | KACHA |  | HDPE | 106 |  |  |  |  | 4389.4 | LHS |  | SHASHIRANJAN
57 |  | J46 | 54 | KACHA |  | HDPE | 30 |  |  |  |  | 4419.4 | LHS |  | SHASHIRANJAN
58 |  | J46 | 50 | KACHA |  | HDPE | 20 |  |  |  |  | 4439.4 | LHS |  | SHASHIRANJAN
59 |  | J50 | 55 | KACHA |  | HDPE |  |  |  | 108 |  | 4547.4 | LHS |  | SHASHIRANJAN
60 |  | J112 | 107 | BRICK ROAD | 0.41 | HDPE |  |  |  | 118.5 |  | 4665.9 | RHS |  | SHASHIRANJAN | 118.5 | 26.1
61 |  | J107 | J116 | BRICK ROAD | 0.41 | HDPE |  |  |  | 53.3 |  | 4719.2 | LHS |  | SHASHIRANJAN | 53.3 | 26.1
62 |  | J107 | J116 | BRICK ROAD | 0.41 | HDPE |  |  |  | 25 |  | 4744.2 |  |  | SHASHIRANJAN | 25 | 26.1
63 |  | J97 | 74 | KACHA |  | HDPE |  |  | 155.8 |  |  | 4900 | RHS |  | SHASHIRANJAN
64 |  | J74 | 60 | KACHA |  | HDPE |  | 32 |  |  |  | 4932 | RHS |  | SHASHIRANJAN
65 |  | J60 | 31 | KACHA |  | HDPE |  | 42.3 |  |  |  | 4974.3 | RHS |  | SHASHIRANJAN
66 |  | J60 | 71 | KACHA |  | HDPE |  | 75 |  |  |  | 5049.3 | RHS |  | SHASHIRANJAN
67 |  | J71 | 17 | KACHA |  | HDPE | 37.4 |  |  |  |  | 5086.7 | LHS |  | SHASHIRANJAN
68 |  | J17 | 23 | KACHA |  | HDPE | 32.6 |  |  |  |  | 5119.3 | LHS |  | SHASHIRANJAN
69 |  | J17 | 41 | KACHA |  | HDPE | 25 |  |  |  |  | 5144.3 | LHS |  | SHASHIRANJAN
70 |  | J41 | 53 | KACHA |  | HDPE | 26.8 |  |  |  |  | 5171.1 | LHS |  | SHASHIRANJAN
71 |  | J41 | 6 | KACHA |  | HDPE | 73 |  |  |  |  | 5244.1 | LHS |  | SHASHIRANJAN
72 |  | J6 | 5 | BRICK ROAD | 0.363 | HDPE | 40 |  |  |  |  | 5284.1 | LHS |  | SHASHIRANJAN | 40 | 26.1
73 |  | J6 | 13 | KACHA |  | HDPE | 41.5 |  |  |  |  | 5325.6 | LHS |  | SHASHIRANJAN
74 |  | J70 | 71 | KACHA |  | HDPE |  | 16 |  |  |  | 5341.6 | LHS |  | SHASHIRANJAN
75 |  | J70 | 79 | KACHA |  | HDPE |  | 67.2 |  |  |  | 5408.8 | RHS |  | SHASHIRANJAN
76 |  | J79 | 81 | KACHA |  | HDPE |  |  | 60.8 |  |  | 5469.6 | RHS |  | SHASHIRANJAN
77 |  | J81 | 2 | KACHA |  | HDPE | 30 |  |  |  |  | 5499.6 | RHS |  | SHASHIRANJAN
78 |  | J81 | 88 | KACHA |  | HDPE |  | 170.3 |  |  |  | 5669.9 | RHS |  | SHASHIRANJAN
79 |  | J79 | 111 | KACHA |  | HDPE |  |  | 55 |  |  | 5724.9 | RHS |  | SHASHIRANJAN
80 |  | J79 | 111 | B.T ROAD | 0.39 | HDPE |  |  | 4 |  |  | 5728.9 |  |  | SHASHIRANJAN | 4
81 |  | J111 | 114 | KACHA |  | HDPE | 34 |  |  |  |  | 5762.9 | RHS |  | SHASHIRANJAN
82 |  | J111 | 115 | KACHA |  | HDPE | 4.5 |  |  |  |  | 5767.4 | RHS |  | SHASHIRANJAN
83 |  | J111 | 116 | BRICK ROAD | 0.39 | HDPE |  |  | 128.4 |  |  | 5895.8 | RHS |  | SHASHIRANJAN | 128.4 | 26.1
84 |  | J116 | 70 | KACHA |  | HDPE |  |  | 109.7 |  |  | 6005.5 | RHS |  | SHASHIRANJAN
85 |  | J116 | 107 | KACHA |  | HDPE |  |  |  | 64.4 |  | 6069.9 | LHS |  | SHASHIRANJAN
86 |  | J97 | 35 | KACHA |  | HDPE |  |  |  | 62.8 |  | 6132.7 | LHS |  | SHASHIRANJAN
87 |  | J35 | 14 | KACHA |  | HDPE |  |  |  |  | 62 | 6194.7 | LHS |  | SHASHIRANJAN
88 |  | J14 | 15 | KACHA |  | HDPE |  |  |  |  | 8 | 6202.7 | LHS |  | SHASHIRANJAN
89 |  | J15 | 75 | KACHA |  | HDPE |  |  |  |  | 274.2 | 6476.9 | LHS |  | SHASHIRANJAN
90 |  | J84 | 45 | BRICK ROAD | 0.375 | HDPE |  | 116.1 |  |  |  | 6593 | RHS |  | SHASHIRANJAN | 116.1 | 26.1
91 |  | J45 | 7 | KACHA |  | HDPE | 53.5 |  |  |  |  | 6646.5 | RHS |  | SHASHIRANJAN
92 |  | J45 | 10 | KACHA |  | HDPE |  | 99.6 |  |  |  | 6746.1 | RHS |  | SHASHIRANJAN | 3
93 |  | J45 | 10 | B.T ROAD | 0.375 | HDPE |  | 3 |  |  |  | 6749.1 |  |  | SHASHIRANJAN
94 |  | J10 | 22 | KACHA |  | HDPE | 80.5 |  |  |  |  | 6829.6 | LHS |  | SHASHIRANJAN
95 |  | J22 | 21 | KACHA |  | HDPE | 36 |  |  |  |  | 6865.6 | LHS |  | SHASHIRANJAN
96 |  | J22 | 34 | KACHA |  | HDPE | 296 |  |  |  |  | 7161.6 | LHS |  | SHASHIRANJAN
97 |  | J34 | 18 | INTERLOCKING | 0.363 | HDPE | 119 |  |  |  |  | 7280.6 | LHS |  | SHASHIRANJAN | 119
98 |  | J18 | 12 | KACHA |  | HDPE | 22 |  |  |  |  | 7302.6 | LHS |  | SHASHIRANJAN
99 |  | J18 | 58 | KACHA |  | HDPE | 109.8 |  |  |  |  | 7412.4 | RHS |  | SHASHIRANJAN
100 |  | J58 | 3 | KACHA |  | HDPE | 34.1 |  |  |  |  | 7446.5 | RHS |  | SHASHIRANJAN
101 |  | J58 | 73 | KACHA |  | HDPE | 55 |  |  |  |  | 7501.5 | RHS |  | SHASHIRANJAN
102 |  | J34 | 37 | KACHA |  | HDPE | 29.8 |  |  |  |  | 7531.3 | RHS |  | SHASHIRANJAN
103 |  | J37 | 85 | KACHA |  | HDPE | 14 |  |  |  |  | 7545.3 | RHS |  | SHASHIRANJAN
104 |  | J37 | 56 | KACHA |  | HDPE | 25.6 |  |  |  |  | 7570.9 | RHS |  | SHASHIRANJAN
105 |  | J83 | 65 | BRICK ROAD | 0.363 | HDPE | 35 |  |  |  |  | 7605.9 |  |  | SHASHIRANJAN | 35 | 26.1
106 |  | J14 | 11 | BRICK ROAD | 0.363 | HDPE | 166.5 |  |  |  |  | 7772.4 |  |  | SHASHIRANJAN | 166.5 | 26.1
107 |  | J14 | 11 | B.T ROAD |  | HDPE | 3.5 |  |  |  |  | 7775.9 |  |  | SHASHIRANJAN
108 |  | J103 | j104 | KACHA |  | HDPE |  |  |  |  | 38 | 7813.9 |  |  | SHASHIRANJAN
109 |  | J104 | OHT | KACHA |  | HDPE |  |  |  |  | 46.5 | 7860.4 |  |  | SHASHIRANJAN
110 |  | J104 | OHT | B.T ROAD | 0.41 | HDPE |  |  |  |  | 3.5 | 7863.9 |  |  | SHASHIRANJAN | 3.5
111 |  | J104 | J94 | B.T ROAD | 0.41 | HDPE |  |  |  | 3.5 |  | 7867.4 |  |  | SHASHIRANJAN | 3.5
112 |  | j94 | j104 | KACHA |  | HDPE |  |  |  | 187 |  | 8054.4 |  |  | SHASHIRANJAN
[7 empty] | 3709.8 | 1050 | 1208.4 | 915.8 | 1170.4 | 8054.4
[7 empty] | 4079 | 1233 | 1154 | 874 | 1186 | 8526
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  |  | SIGN.with date
TYPE OF ROAD |  |  | 63mm | 75mm | 90mm | 110mm | 140mm | Cumulative
BRICK ROAD |  |  | 296.5 | 116.1 | 278.6 | 196.8 | 220.4 | 1108.4
B.T ROAD |  |  | 15.5 | 3 | 4 | 3.5 | 3.5 | 29.5
INTERLOCKING |  |  | 119 | 0 | 0 | 0 | 0 | 119
|  |  | 107.6295 | 43.5375 | 108.654 | 80.688 | 99.18
|  |  | 5.6265 | 1.125 | 1.56 | 1.435 | 1.435
43.197

## Sheet1
HARDOI(road restoration)
Sl.No | Date | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | DI/HDPE | Pipe Length (M) |  |  |  |  | sqmeter | RESTORATION | Remarks
[7 empty] | 63mm | 75mm | 90mm | 110mm | 140mm
1 |  | J96 | 95 | BRICK ROAD | 0.45 | HDPE |  |  |  |  | 58 | 26.1
2 |  | J47(A) | 84(A) | BRICK ROAD | 0.36 | HDPE | 3 |  |  |  |  | 1.08
3 |  | J96(A) | 95(A) | BRICK ROAD | 0.45 | HDPE |  |  |  |  | 44 | 19.8
4 |  | J95 | J75 | BRICK ROAD | 0.45 | HDPE |  |  |  |  | 118.4 | 53.28
5 |  | J92 | 90 | B.T ROAD | 0.363 | HDPE | 4 |  |  |  |  | 1.452
6 |  | J63 | 26 | B.T ROAD | 0.363 | HDPE | 4 |  |  |  |  | 1.452
7 |  | J103 | 69 | BRICK ROAD | 0.39 | HDPE |  |  | 150.2 |  |  | 58.578
8 |  | J69 | 76 | BRICK ROAD | 0.363 | HDPE | 52 |  |  |  |  | 18.876
9 |  | J110 | 64 | B.T ROAD | 0.363 | HDPE | 4 |  |  |  |  | 1.452
10 |  | J112 | 107 | BRICK ROAD | 0.41 | HDPE |  |  |  | 118.5 |  | 48.585
11 |  | J107 | J116 | BRICK ROAD | 0.41 | HDPE |  |  |  | 53.3 |  | 21.853
12 |  | J107 | J116 | BRICK ROAD | 0.41 | HDPE |  |  |  | 25 |  | 10.25
13 |  | J6 | 5 | BRICK ROAD | 0.363 | HDPE | 40 |  |  |  |  | 14.52
14 |  | J79 | 111 | B.T ROAD | 0.39 | HDPE |  |  | 4 |  |  | 1.56
15 |  | J111 | 116 | BRICK ROAD | 0.39 | HDPE |  |  | 128.4 |  |  | 50.076
16 |  | J84 | 45 | BRICK ROAD | 0.375 | HDPE |  | 116.1 |  |  |  | 43.5375
17 |  | J45 | 10 | B.T ROAD | 0.375 | HDPE |  | 3 |  |  |  | 1.125
18 |  | J34 | 18 | INTERLOCKING | 0.363 | HDPE | 119 |  |  |  |  | 43.197
19 |  | J83 | 65 | BRICK ROAD | 0.363 | HDPE | 35 |  |  |  |  | 12.705
20 |  | J14 | 11 | BRICK ROAD | 0.363 | HDPE | 166.5 |  |  |  |  | 60.4395
21 |  | J14 | 11 | B.T ROAD | 0.363 | HDPE | 3.5 |  |  |  |  | 1.2705
22 |  | J104 | OHT | B.T ROAD | 0.41 | HDPE |  |  |  |  | 3.5 | 1.435
23 |  | J104 | J94 | B.T ROAD | 0.41 | HDPE |  |  |  | 3.5 |  | 1.435