## Purebhika and Raigarh
PUREBHIKA AND RAIGARH(RESTORATION)
Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | Dia of pipe | Pipe Length (M) AS PER SITE
1 | J171 | J235 | INTERLOCKING | 0.36 | 63 | 39.8
2 | J218 | J208 | INTERLOCKING | 0.36 | 63 | 33.2
3 | J208 | J171 | INTERLOCKING | 0.36 | 63 | 33.2
4 | J196 | J303 | INTERLOCKING | 0.36 | 63 | 120.4
5 | J303 | J285 | INTERLOCKING | 0.36 | 63 | 117.1
6 | J299 | J293 | INTERLOCKING | 0.36 | 63 | 17.4
7 | j253 | j248 | INTERLOCKING | 0.36 | 63 | 40
8 | j248 | j270 | INTERLOCKING | 0.36 | 63 | 34
9 | J270 | J278 | INTERLOCKING | 0.36 | 63 | 21.3
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  | SIGN.with date

## Dharouli
DHAROULI(RESTORATION)
Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | Dia of pipe | Pipe Length (M) AS PER SITE
1 | J184 | 183 | INTERLOCKING | 0.46 | 63 | 63.4
2 | 147 | 117 | INTERLOCKING | 0.46 | 63 | 135
3 | 199 | 165 | INTERLOCKING | 0.46 | 63 | 175
4 | 165 | 201 | INTERLOCKING | 0.46 | 63 | 60
5 | 201 | 131 | INTERLOCKING | 0.46 | 63 | 87.5
6 | 131 | 140 | INTERLOCKING | 0.46 | 63 | 75
7 | 140 | 148 | INTERLOCKING | 0.46 | 63 | 63
8 | 131 | 143 | INTERLOCKING | 0.46 | 63 | 74.6
9 | 143 | 149 | INTERLOCKING | 0.46 | 63 | 78.8
10 | J169 | J149 | INTERLOCKING | 0.46 | 63 | 74
11 | J220 | J229 | INTERLOCKING | 0.46 | 63 | 66
12 | J218 | J229 | INTERLOCKING | 0.46 | 63 | 52
13 | 179 | 184 | INTERLOCKING | 0.46 | 63 | 16.7
14 | 218 | 238 | INTERLOCKING | 0.46 | 63 | 4
15 | J220 | J196 | INTERLOCKING | 0.46 | 63 | 171.6
16 | J165 | J161 | INTERLOCKING | 0.46 | 63 | 21
17 | J161 | J201 | INTERLOCKING | 0.46 | 63 | 30.3
18 | 204 | 179 | INTERLOCKING | 0.46 | 90 | 55
19 | J204 | J230 | INTERLOCKING | 0.46 | 90 | 4
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  | SIGN.with date

## HARDOI
BLOCK -MANGRAUARA G.P- HARDOI
Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | DI/HDPE | Pipe Length (M) |  |  |  |  | RESTORATION | Remarks
[6 empty] | 63mm | 75mm | 90mm | 110mm | 140mm
1 | J96 | 95 | BRICK ROAD | 0.45 | HDPE |  |  |  |  | 58 | 26.1
2 | J47(A) | 84(A) | BRICK ROAD | 0.363 | HDPE | 3 |  |  |  |  | 3
3 | J96(A) | 95(A) | BRICK ROAD | 0.45 | HDPE |  |  |  |  | 44 | 19.8
4 | J95 | J75 | BRICK ROAD | 0.45 | HDPE |  |  |  |  | 118.4 | 53.28
5 | J92 | 90 | B.T ROAD | 0.363 | HDPE | 4 |  |  |  |  | 4
6 | J63 | 26 | B.T ROAD | 0.363 | HDPE | 4 |  |  |  |  | 4
7 | J103 | 69 | BRICK ROAD | 0.39 | HDPE |  |  | 150.2 |  |  | 150.2
8 | J69 | 76 | BRICK ROAD | 0.363 | HDPE | 52 |  |  |  |  | 52
9 | J110 | 64 | B.T ROAD | 0.363 | HDPE | 4 |  |  |  |  | 4
10 | J112 | 107 | BRICK ROAD | 0.41 | HDPE |  |  |  | 118.5 |  | 118.5
11 | J107 | J116 | BRICK ROAD | 0.41 | HDPE |  |  |  | 53.3 |  | 53.3
12 | J107 | J116 | BRICK ROAD | 0.41 | HDPE |  |  |  | 25 |  | 25
13 | J6 | 5 | BRICK ROAD | 0.363 | HDPE | 40 |  |  |  |  | 40
14 | J79 | 111 | B.T ROAD | 0.39 | HDPE |  |  | 4 |  |  | 4
15 | J111 | 116 | BRICK ROAD | 0.39 | HDPE |  |  | 128.4 |  |  | 128.4
16 | J84 | 45 | BRICK ROAD | 0.375 | HDPE |  | 116.1 |  |  |  | 116.1
17 | J45 | 10 | B.T ROAD | 0.375 | HDPE |  | 3 |  |  |  | 3
18 | J34 | 18 | INTERLOCKING | 0.363 | HDPE | 119 |  |  |  |  | 119
19 | J83 | 65 | BRICK ROAD | 0.363 | HDPE | 35 |  |  |  |  | 35
20 | J14 | 11 | BRICK ROAD | 0.363 | HDPE | 166.5 |  |  |  |  | 166.5
21 | J14 | 11 | B.T ROAD | 0.363 | HDPE | 3.5 |  |  |  |  | 3.5
22 | J104 | OHT | B.T ROAD | 0.41 | HDPE |  |  |  |  | 3.5 | 1.435
23 | J104 | J94 | B.T ROAD | 0.41 | HDPE |  |  |  | 3.5 |  | 3.5
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  |  | SIGN.with date

## SESHPUR ADHARGANJ
BLOCK -MANGRAURA G.P-SESHPUR ADHARGANJ
Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | DI/HDPE | Pipe Length (M) |  | RESTORATION(SQM) | Remarks
1 | J77 | J145 | B.T ROAD | 0.39 | 63 | 3.5 |  | 1.365
2 | J5 | J7 | BRICK ROAD | 0.39 | 63 | 100.2 |  | 39.078
3 | J67 | J109 | BRICK ROAD | 0.39 | 63 | 51.2 |  | 19.968
4 | J120 | J102 | B.T ROAD | 0.39 | 63 | 3.5 |  | 1.365
5 | J120 | J102 | BRICK ROAD | 0.39 | 63 | 41.3 |  | 16.107
6 | J102 | J144 | BRICK ROAD | 0.39 | 63 | 16.1 |  | 6.279
7 | J102 | J92(A) | BRICK ROAD | 0.39 | 63 | 25.1 |  | 9.789
8 | J92(A) | J92 | BRICK ROAD | 0.39 | 63 | 68.7 |  | 26.793
9 | j72 | j123 | B.T ROAD | 0.36 | 63 | 3.5 |  | 1.26
10 | j72 | j123 | BRICK ROAD | 0.39 | 63 | 21 |  | 8.19
11 | j72 | j146 | INTERLOCKING | 0.39 | 63 | 6 |  | 2.34
12 | j53 | j65 | B.T ROAD | 0.39 | 63 | 3.5 |  | 1.365
13 | j53 | j65 | INTERLOCKING | 0.44 | 63 | 100.2 |  | 44.088
14 | J10 | J22 | BRICK ROAD | 0.39 | 75 | 68.2 |  | 26.598
15 | J8 | J115 | BRICK ROAD | 0.39 | 63 | 12.2 |  | 4.758
16 | J19 | J87 | BRICK ROAD | 0.363 | 63 | 89.6 |  | 32.5248
17 | J19 | J40 | INTERLOCKING | 0.44 | 63 | 203 |  | 89.32
18 | J11 | J19 | INTERLOCKING | 0.44 | 63 | 57 |  | 25.08
19 | J22 | J11 | BRICK ROAD | 0.39 | 75 | 183.2 |  | 71.448
20 | J49 | J54 | BRICK ROAD | 0.39 | 75 | 50 |  | 19.5
21 | J26 | J14 | BRICK ROAD | 0.39 | 90 | 96 |  | 37.44
22 | J14 | J23 | BRICK ROAD | 0.39 | 90 | 4 |  | 1.56
23 | J26 | J46 | B.T ROAD | 0.39 | 90 | 3.5 |  | 1.365
24 | J62 | J125 | BRICK ROAD | 0.39 | 63 | 84.6 |  | 32.994
25 | J12 | J71 | INTERLOCKING | 0.39 | 63 | 12.5 |  | 4.875
26 | J12 | J39 | BRICK ROAD | 0.39 | 63 | 18 |  | 7.02
27 | J60 | J141 | BRICK ROAD | 0.39 | 63 | 13 |  | 5.07
28 | J67 | J109 | B.T ROAD | 0.39 | 63 | 3.5 |  | 1.365
29 | J67 | J109 | BRICK ROAD | 0.39 | 63 | 43.4 |  | 16.926
30 | J116 | J147 | B.T ROAD | 0.39 | 63 | 3.5 |  | 1.365
31 | J63 | J9 | BRICK ROAD | 0.39 | 75 | 46 |  | 17.94
32 | J9 | J6 | BRICK ROAD | 0.39 | 75 | 231.5 |  | 90.285
33 | J98 | J78 | BRICK ROAD | 0.39 | 75 | 50 |  | 19.5
34 | J78 | J94 | BRICK ROAD | 0.39 | 75 | 50 |  | 19.5
35 | J68 | J68(1) | B.T ROAD | 0.39 | 75 | 3.5 |  | 1.365
36 | J68(1) | J97 | BRICK ROAD | 0.39 | 75 | 113 |  | 44.07
37 | J103 | J37 | BRICK ROAD | 0.39 | 75 | 155 |  | 60.45
38 | J91 | J99 | BRICK ROAD | 0.44 | 110 | 19 |  | 8.36
39 | J99 | J134 | BRICK ROAD | 0.44 | 110 | 11 |  | 4.84
40 | J99 | J104 | BRICK ROAD | 0.44 | 110 | 24.2 |  | 10.648
41 | J84 | J92 | BRICK ROAD | 0.44 | 110 | 108 |  | 47.52
42 | J124 | J114 | BRICK ROAD | 0.44 | 110 | 72 |  | 31.68
43 | J114 | J88 | BRICK ROAD | 0.44 | 110 | 57.3 |  | 25.212
44 | J2 | J62 | B.T ROAD | 0.44 | 140 | 6 |  | 2.64
45 | J2 | J62 | BRICK ROAD | 0.44 | 140 | 225 |  | 99
46 | J2 | J62 | BRICK ROAD | 0.44 | 140 | 41 |  | 18.04
47 | J62 | J157 | BRICK ROAD | 0.44 | 140 | 53.7 |  | 23.628
48 | J2 | J5 | INTERLOCKING | 0.44 | 140 | 3.5 |  | 1.54
49 | J2(A) | J5(B) | B.T ROAD | 0.44 | 140 | 4 |  | 1.76
50 | J5 | J60 | B.T ROAD | 0.44 | 140 | 4.7 |  | 2.068
51 | J120 | J111 | BRICK ROAD | 0.44 | 140 | 4 |  | 1.76
52 | J63 | J91 | BRICK ROAD | 0.44 | 140 | 88.9 |  | 39.116
53 | J91 | J124 | BRICK ROAD | 0.44 | 140 | 181.6 |  | 79.904
54 | J124 | J157 | BRICK ROAD | 0.44 | 140 | 76 |  | 33.44
55 | J1 | J8 | BRICK ROAD | 0.44 | 140 | 125.5 |  | 55.22
56 | J18 | J10 | BRICK ROAD | 0.44 | 140 | 314.8 |  | 138.512
57 | J157 | OHT | BRICK ROAD | 0.44 | 160 | 100 |  | 44
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  | SIGN.with date

## utras
UTRAS(JMR) BLOCK-MANGRAURA
s.no | Start Node | End Node | Type of Road | WIDTH OF EXCAVATION | Dia of pipe (MM) | Pipe Length (M) | restoration(sqm) | REMARK
1 | J291 | J289 | BRICK ROAD | 0.363 | 63 | 2.8 | 1.0164
2 | J298 | J304 | BRICK ROAD | 0.363 | 63 | 6.2 | 2.2506
3 | J230 | J221 | BRICK ROAD | 0.363 | 63 | 25.3 | 9.1839
4 | J230 | J221(1) | BRICK ROAD | 0.363 | 63 | 72.9 | 26.4627
5 | J199 | J201 | BRICK ROAD | 0.363 | 63 | 3 | 1.089
6 | J236 | J226 | BRICK ROAD | 0.363 | 63 | 3.4 | 1.2342
7 | J88 | J93 | BRICK ROAD | 0.363 | 63 | 6 | 2.178
8 | J198 | J197 | BRICK ROAD | 0.363 | 63 | 15.4 | 5.5902
9 | J191 | J193 | BRICK ROAD | 0.363 | 63 | 26.4 | 9.5832
10 | J197 | J207 | BRICK ROAD | 0.363 | 63 | 23.5 | 8.5305
11 | J207 | J209 | BRICK ROAD | 0.363 | 63 | 27.2 | 9.8736
12 | J222 | J225 | BRICK ROAD | 0.363 | 63 | 171.2 | 62.1456
13 | J225 | J223 | BRICK ROAD | 0.363 | 63 | 69.3 | 25.1559
14 | J150 | J114 | BRICK ROAD | 0.363 | 63 | 148.9 | 54.0507
15 | J114 | J83 | BRICK ROAD | 0.363 | 63 | 162.3 | 58.9149
16 | J289 | J294 | BRICK ROAD | 0.375 | 75 | 66.1 | 24.7875
17 | J297 | J294 | BRICK ROAD | 0.375 | 75 | 46.8 | 17.55
18 | J308 | J310 | BRICK ROAD | 0.375 | 75 | 4 | 1.5
19 | J139 | J142 | BRICK ROAD | 0.39 | 90 | 55.8 | 21.762
20 | J142 | J146 | BRICK ROAD | 0.39 | 90 | 45.4 | 17.706
21 | J146 | J150 | BRICK ROAD | 0.39 | 90 | 67.2 | 26.208
22 | J130 | J139 | BRICK ROAD | 0.41 | 110 | 46.7 | 19.147
23 | j261 | j259 | BRICK ROAD | 0.41 | 110 | 4.5 | 1.845
24 | j261 | j259 | CC road | 0.41 | 110 | 4.5 | 1.845
25 | j265 | j277 | BRICK ROAD | 0.375 | 75 | 64 | 24
26 | j265 | j269 | BRICK ROAD | 0.363 | 63 | 41.6 | 15.1008
27 | j257 | j257 | CC road | 0.363 | 63 | 4 | 1.452
28 | j321 | j313 | BRICK ROAD | 0.363 | 63 | 120 | 43.56
29 | j245 | j245 | CC road | 0.363 | 63 | 5 | 1.815
30 | j242 | j244 | BRICK ROAD | 0.363 | 63 | 40 | 14.52
31 | j242 | j242 | CC road | 0.363 | 63 | 3 | 1.089
32 | j298 | j301 | BRICK ROAD | 0.363 | 63 | 52.1 | 18.9123
33 | j289 | j283 | BRICK ROAD | 0.39 | 90 | 27 | 10.53
34 | j283 | j287 | BRICK ROAD | 0.41 | 110 | 19.4 | 7.954
35 | j287 | j299 | BRICK ROAD | 0.41 | 110 | 33 | 13.53
36 | j310 | j311 | BRICK ROAD | 0.363 | 63 | 17.8 | 6.4614
37 | j308 | j309 | BRICK ROAD | 0.363 | 63 | 33 | 11.979
38 | j20 | j38 | BRICK ROAD | 0.363 | 63 | 25 | 9.075
39 | j54 | j55 | interlock | 0.363 | 63 | 95.9 | 34.8117
40 | j24 | j29 | BRICK ROAD | 0.363 | 63 | 39.6 | 14.3748
41 | j21 | j18 | interlock | 0.46 | 160 | 4 | 1.84
42 | j73 | j57 | BRICK ROAD | 0.363 | 63 | 93.9 | 34.0857
43 | j57 | j58 | BRICK ROAD | 0.363 | 63 | 19.7 | 7.1511
44 | j88 | j102 | BRICK ROAD | 0.363 | 63 | 4 | 1.452
45 | j97 | j102 | BRICK ROAD | 0.46 | 160 | 70 | 32.2
46 | j102 | j107 | BRICK ROAD | 0.46 | 160 | 56 | 25.76
47 | j107 | j130 | BRICK ROAD | 0.46 | 160 | 278.6 | 128.156
48 | j130 | j149 | BRICK ROAD | 0.46 | 160 | 217.9 | 100.234
49 | j149 | j151 | BRICK ROAD | 0.363 | 63 | 57.3 | 20.7999
50 | j151 | j165 | BRICK ROAD | 0.363 | 63 | 76.7 | 27.8421
51 | j111 | j120 | BRICK ROAD | 0.375 | 75 | 115.2 | 43.2
52 | j12 | j11 | BRICK ROAD | 0.46 | 160 | 26 | 11.96
53 | j11 | j9 | interlock | 0.46 | 160 | 47 | 21.62
54 | j9 | j7 | interlock | 0.46 | 160 | 27 | 12.42
55 | j34 | j32 | BRICK ROAD | 0.363 | 63 | 51.9 | 18.8397
56 | j7 | j2 | interlock | 0.46 | 160 | 80.1 | 36.846
57 | j2 | j40 | BRICK ROAD | 0.39 | 90 | 312 | 121.68
58 | j40 | j63 | BRICK ROAD | 0.375 | 75 | 218 | 81.75
59 | j63 | j69 | BRICK ROAD | 0.363 | 63 | 104.7 | 38.0061
60 | j176 | j196 | BRICK ROAD | 0.363 | 63 | 282.7 | 102.6201
61 | j158 | j192 | BRICK ROAD | 0.375 | 75 | 50 | 18.75
62 | j150 | j199 | BRICK ROAD | 0.39 | 90 | 198 | 77.22
63 | j210 | j226 | BRICK ROAD | 0.39 | 90 | 110 | 42.9
64 | j226 | j222 | BRICK ROAD | 0.375 | 75 | 150 | 56.25
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  | SIGN.with date