## Sheet2
ATTARSAND AND PRASPUR(ROAD RESTORATION)
Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | Dia of pipe | Pipe Length (M) AS PER SITE
1 | J23 | J61 | B.T ROAD |  | 110 | 129.3
2 | J61 | J43 | B.T ROAD |  | 110 | 58.6
3 | J43 | 68 | B.T ROAD |  | 110 | 94
4 | J68 | J57 | B.T ROAD |  | 110 | 30.6
5 | J57 | J30 | B.T ROAD |  | 110 | 87.3
6 | J30 | J79 | B.T ROAD |  | 110 | 6.5
7 | J79 | J35 | B.T ROAD |  | 110 | 49.2
8 | J35 | J28 | B.T ROAD |  | 110 | 49.5
9 | J26 | J5 | B.T ROAD |  | 63 | 161.2
10 | J29 | J228 | B.T ROAD |  | 140 | 865.6
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  | SIGN.with date