## aurangabad
GOVERNMENT OF UTTAR PRADESH
STATE WATER & SANITATION MISSION ( SWSM )
Joint Measurement Report of Pipe Line
Name of the Work :- Survey , Design Preparation of DPR , Construction , Commissioning and O&M for 10 Years of Various Rural Water Supply Projects in the state of Uttar Pradesh as Per Request for Proposal for Division " Prayagraj "
Name of the Agency : POWER MECH PROJECTS LIMITED – BHOORATHNOM CONSTRUCTIONS COMPANY PRIVATE LIMITED (JV), Hyderabad.
Name OF Scheme |  | :aurangabad
Block |  | : Mangraura
Total Scope |  | :
JMR No. |  | : 1
Date of JMR |  | :
Sr. No. | Start Node | End Node | Dia | Pipe Length (as per Drawing) | Pipe Length (as per Site) | Width | Depth | Quantity | Type OF Road | Dismantling Length | Dismantling Width | Dismantling Quantity | Restoration Length | Restoration Width | Restoration Quantity | Restoration Status | Remark
1 | 137 | 138 | 63 | 86 | 92.2 | 0.36 | 1.06
2 | 137 | 128 | 75 | 145 | 142.8 | 0.375 | 1.07
3 | 137 | 128 | 75 |  | 11.7 | 0.375 | 1.07 |  | interlocking | 11.7 | 0.46 | 5.382 | 11.7 | 0.46 | 5.382
4 | 128 | 135 | 63 | 206 | 121.9 | 0.36 | 1.06 |  | interlocking | 121.9 | 0.46 | 56.074 | 121.9 | 0.46 | 56.074
5 | 128 | 135 | 63 |  | 37 | 0.36 | 1.06
6 | 135a | 135b | 63 |  | 55.4 | 0.36 | 1.06
7 | 135a | 135b | 63 |  | 6 | 0.36 | 1.06 |  | interlocking | 6 | 0.46 | 2.76 | 6 | 0.46 | 2.76
8 | 136 | 135 | 63 | 41 | 134 | 0.36 | 1.06
9 | 135 | 130 | 63 | 40 | 40.1 | 0.36 | 1.06
10 | 130 | 132 | 63 | 66 | 84.5 | 0.36 | 1.06
11 | 130a | 130b | 63 |  | 61.4 | 0.36 | 1.06
12 | 130 | 126 | 63 | 247 | 50.2 | 0.36 | 1.06 |  | brick road | 50.2 | 0.36 | 18.072 | 50.2 | 0.36 | 18.072
13 | 130 | 126 | 63 |  | 28.1 | 0.36 | 1.06
14 | 130 | 126 | 63 |  | 148.1 | 0.36 | 1.06
15 | 128 | 126 | 75 | 133 | 20 | 0.375 | 1.07 |  | interlocking | 20 | 0.46 | 9.2 | 20 | 0.46 | 9.2
16 | 128 | 126 | 75 |  | 19.7 | 0.375 | 1.07 |  | culvert
17 | 128 | 126 | 75 |  | 88.4 | 0.375 | 1.07
18 | 126 | 56 | 75 | 198 | 2.1 | 0.375 | 1.07
19 | 126 | 56 | 75 |  | 128.5 | 0.375 | 1.07 |  | b.t road | 128.5 | 0.375 | 48.1875 | 128.5 | 0.375 | 48.1875
20 | 126 | 56 | 75 |  | 7 | 0.375 | 1.07 |  | b.t road crossing | 7 | 0.375 | 2.625 | 7 | 0.375 | 2.625
21 | 56 | 38 | 160 | 299 | 298.2 | 0.46 | 1.16
22 | 56 | 122 | 160 | 223 | 91.1 | 0.46 | 1.16
23 | 56 | 122 | 160 |  | 56.9 | 0.46 | 1.16 |  | interlocking | 56.9 | 0.46 | 26.174 | 56.9 | 0.46 | 26.174
24 | 56 | 122 | 160 |  | 76.4 | 0.46 | 1.16
25 | 56 | 122 | 160 |  | 4.2 | 0.46 | 1.16 |  | brick road | 4.2 | 0.46 | 1.932 | 4.2 | 0.46 | 1.932
26 | 122 | 124 | 160 | 129 | 6 | 0.46 | 1.16 |  | b.t road crossing | 6 | 0.46 | 2.76 | 6 | 0.46 | 2.76
27 | 122 | 124 | 160 |  | 170 | 0.46 | 1.16
28 | 124 | 125 | 63 | 13 | 92.6 | 0.36 | 1.06
29 | 124 | 124a | 160 | 162 | 14.9 | 0.46 | 1.16
30 | 124a | 143 | 160 |  | 174.3 | 0.46 | 1.16
31 | 124a | 124b | 63 |  | 39.1 | 0.36 | 1.06
32 | 143 | 142 | 63 | 9 | 200.5 | 0.36 | 1.06
33 | 143 | 145 | 160 | 182 | 113 | 0.46 | 1.16
34 | 143 | 145 | 160 |  | 5.9 | 0.46 | 1.16 |  | b.t crossing | 5.9 | 0.46 | 2.714 | 5.9 | 0.46 | 2.714
35 | 146 | 145 | 160 | 9 | 7.6 | 0.46 | 1.16
36 | 145 | 144 | 75 | 235 | 230.6 | 0.375 | 1.07
37 | 145 | 144 | 75 |  | 9.8 | 0.375 | 1.07 |  | b.t crossing | 9.8 | 0.375 | 3.675 | 9.8 | 0.375 | 3.675
38 | 144 | 149 | 140 | 345 | 298.6 | 0.44 | 1.14
39 | 144 | 149 | 140 |  | 63.2 | 0.44 | 1.14 |  | interlocking | 63.2 | 0.46 | 29.072 | 63.2 | 0.46 | 29.072
40 | 149 | 154 | 140 | 351 | 6 | 0.44 | 1.14 |  | b.t crossing | 6 | 0.44 | 2.64 | 6 | 0.44 | 2.64
41 | 149 | 154 | 140 |  | 152.1 | 0.44 | 1.14 |  | brick road | 152.1 | 0.44 | 66.924 | 152.1 | 0.44 | 66.924
42 | 149 | 154 | 140 |  | 14.7 | 0.44 | 1.14 |  | brick road | 14.7 | 0.44 | 6.468 | 14.7 | 0.44 | 6.468
43 | 154 | 164 | 110 | 232 | 91.6 | 0.41 | 1.1 |  | brick road | 91.6 | 0.41 | 37.556 | 91.6 | 0.41 | 37.556
44 | 154 | 164 | 110 |  | 140 | 0.41 | 1.1
45 | 164 | 166 | 160 | 92 | 68.6 | 0.46 | 1.14
46 | 164 | 166 | 160 |  | 31 | 0.46 | 1.14 |  | brick road | 31 | 0.46 | 14.26 | 31 | 0.46 | 14.26
47 | 166 | 166a | 75 |  | 20 | 0.375 | 1.07
48 | 166a | 170 | 75 |  | 276 | 0.375 | 1.07
49 | 170 | 172 | 75 | 88 | 92.3 | 0.375 | 1.07
50 | 172 | 166 | 160 | 129 | 128.7 | 0.46 | 1.14 |  | brick road | 128.7 | 0.46 | 59.202 | 128.7 | 0.46 | 59.202
51 | 166a | 167 | 75 |  | 29.1 | 0.375 | 1.07
52 | 164 | 160 | 160 | 84 | 100.9 | 0.46 | 1.14
53 | 154 | 160 | 63 | 198 | 110.1 | 0.36 | 1.06
54 | 154 | 160 | 63 |  | 92.2 | 0.36 | 1.06 |  | brick road | 92.2 | 0.36 | 33.192 | 92.2 | 0.36 | 33.192
55 | 154 | 153 | 140 | 50 | 51 | 0.44 | 1.14
56 | 153 | 158 | 160 | 301 | 292.9 | 0.46 | 1.16
57 | 153 | 146 | 160 | 216 | 214.9 | 0.46 | 1.16
58 | 144 | 122 | 140 | 325 | 47 | 0.44 | 1.14
59 | 144 | 122 | 140 |  | 6.8 | 0.44 | 1.14 |  | culvert
60 | 144 | 122 | 140 |  | 192 | 0.44 | 1.14 |  | interlocking | 192 | 0.46 | 88.32 | 192 | 0.46 | 88.32
61 | 144 | 122 | 140 |  | 8 | 0.44 | 1.14 |  | culvert
62 | 144 | 122 | 140 |  | 80.6 | 0.44 | 1.14
63 | 224 | 228 | 90 | 55 | 53.2 | 0.39 | 1.09 |  | brick road | 53.2 | 0.39 | 20.748 | 53.2 | 0.39 | 20.748
64 | 228 | 231 | 90 | 10 | 10.8 | 0.39 | 1.09 |  | brick road | 10.8 | 0.39 | 4.212 | 10.8 | 0.39 | 4.212
65 | 228 | 225 | 63 | 98 | 3.1 | 0.36 | 1.06 |  | brick road | 3.1 | 0.36 | 1.116 | 3.1 | 0.36 | 1.116
66 | 228 | 225 | 63 |  | 89.4 | 0.36 | 1.06
67 | 231 | 232 | 63 | 162 | 59.5 | 0.36 | 1.06
68 | 231 | 233 | 63 | 155 | 162.5 | 0.36 | 1.06
69 | 225 | 228 | 90 | 47 | 5.6 | 0.39 | 1.09 |  | b.t road crossing | 5.6 | 0.39 | 2.184 | 5.6 | 0.39 | 2.184
70 | 224 | 227 | 90 |  | 51.7 | 0.39 | 1.09
71 | 227 | 227a | 63 |  | 22.3 | 0.36 | 1.06
72 | 227 | 230 | 90 | 27 | 103.4 | 0.39 | 1.09
73 | 230 | 230a | 90 |  | 45.2 | 0.39 | 1.09
74 | 230 | 226 | 90 | 101 | 62.1 | 0.39 | 1.09
75 | 226 | 229 | 63 | 124 | 175.9 | 0.36 | 1.06
76 | 230 | 236 | 90 | 259 | 177.4 | 0.39 | 1.09 |  | brick road | 177.4 | 0.39 | 69.186 | 177.4 | 0.39 | 69.186
77 | 236 | 239 | 63 | 216 | 204.7 | 0.36 | 1.06
78 | 236 | 223a | 90 | 398 | 225.4 | 0.39 | 1.09
79 | 223a | 223b | 90 |  | 68.7 | 0.39 | 1.09
80 | 223a | 223 | 90 |  | 172.4 | 0.39 | 1.09
81 | 223 | 234a | 90 | 234 | 182.9 | 0.39 | 1.09
82 | 234a | 234b | 75 |  | 205.8 | 0.375 | 1.07
83 | 234 | 234c | 75 |  | 27.3 | 0.375 | 1.07
84 | 234 | 234d | 75 |  | 70.1 | 0.375 | 1.07
85 | 237 | 234 | 63 | 231 | 45.5 | 0.36 | 1.06
86 | 234 | 234a | 75 |  | 55.3 | 0.375 | 1.07
87 | 223 | 193 | 90 | 444 | 447.9 | 0.39 | 1.09
88 | 223 | 193 | 90 |  | 7 | 0.39 | 1.09 |  | b.t crossing | 7 | 0.39 | 2.73 | 7 | 0.39 | 2.73 |  |  | 203.2
89 | 193 | 195 | 140 | 93 | 7.4 | 0.44 | 1.14 |  | culvert | [8 empty] | 89.6
90 | 193 | 195 | 140 |  | 88.9 | 0.44 | 1.14 | [10 empty] | 112.3
91 | 195 | 196 | 140 | 31 | 29.1 | 0.44 | 1.14 | [10 empty] | 107.5
92 | 196 | 197 | 63 | 17 | 54.4 | 0.36 | 1.06 | [10 empty] | 75.1
93 | 192 | 195 | 140 | 98 | 98.4 | 0.44 | 1.14 | [10 empty] | 41.1
94 | 192 | 193 | 90 | 61 | 65.6 | 0.39 | 1.09
95 | 192 | 192a | 140 |  | 45.8 | 0.44 | 1.14
96 | 192a | 192b | 63 |  | 24.3 | 0.36 | 1.06
97 | 192a | 181 | 140 |  | 172.5 | 0.44 | 1.14
98 | 181 | 187 | 140 | 113 | 44.7 | 0.44 | 1.14 |  | interlockng | 44.7 | 0.46 | 20.562 | 44.7 | 0.46 | 20.562
99 | 187 | 193 | 140 | 134 | 171.1 | 0.44 | 1.14
100 | 187 | 193 | 140 |  | 5 | 0.44 | 1.14 |  | b.t crossing | 5 | 0.44 | 2.2 | 5 | 0.44 | 2.2
101 | 181 | 179 | 160 | 55 | 29.7 | 0.46 | 1.16 |  | interlocking | 29.7 | 0.46 | 13.662 | 29.7 | 0.46 | 13.662
102 | 181 | 179 | 160 |  | 55.3 | 0.46 | 1.16 |  | cc road | 55.3 | 0.46 | 25.438 | 55.3 | 0.46 | 25.438
103 | 179 | 180 | 75 | 142 | 160.3 | 0.375 | 1.07
104 | 179 | 178 | 160 | 148 | 151.5 | 0.46 | 1.16 |  | cc road | 151.5 | 0.46 | 69.69 | 151.5 | 0.46 | 69.69
105 | 178 | 206 | 160 | 361 | 373.2 | 0.46 | 1.16 |  | cc road | 373.2 | 0.46 | 171.672 | 373.2 | 0.46 | 171.672
106 | 206 | 213 | 160 | 130 | 184.5 | 0.46 | 1.16 |  | b.t road | 184.5 | 0.46 | 84.87 | 184.5 | 0.46 | 84.87
107 | 213 | 214 | 90 | 57 | 52.2 | 0.39 | 1.09
108 | 214 | 215 | 63 | 82 | 114.5 | 0.36 | 1.06
109 | 214 | 215 | 63 | 36 | 61.2 | 0.36 | 1.06
110 | 213 | 218 | 140 | 179 | 31 | 0.44 | 1.14 |  | b.t road | 31 | 0.44 | 13.64 | 31 | 0.44 | 13.64
111 | 213 | 218 | 140 |  | 139.3 | 0.44 | 1.14
112 | 224 | 218 | 110 | 156 | 206.1 | 0.41 | 1.1
113 | 172 | 178 | 160 | 424 | 423.2 | 0.46 | 1.16 |  | cc road | 423.2 | 0.46 | 194.672 | 423.2 | 0.46 | 194.672
114 | 217 | 223 | 90 | 362 | 366.3 | 0.39 | 1.09
115 | 196 | 198 | 140 | 216 | 252.2 | 0.44 | 1.14
116 | 198 | 199 | 140 | 138 | 141.5 | 0.44 | 1.14 |  | brick road | 141.5 | 0.44 | 62.26 | 141.5 | 0.44 | 62.26
117 | 199 | 207 | 75 | 148 | 29 | 0.375 | 1.07 |  | brick road | 29 | 0.375 | 10.875 | 29 | 0.375 | 10.875
118 | 199 | 207 | 75 |  | 5 | 0.375 | 1.07 |  | interlocking | 5 | 0.46 | 2.3 | 5 | 0.46 | 2.3
119 | 199 | 207 | 75 |  | 95 | 0.375 | 1.07
120 | 199 | 207 | 75 |  | 41 | 0.375 | 1.07 |  | brick road | 41 | 0.375 | 15.375 | 41 | 0.375 | 15.375
121 | 199 | 207 | 75 |  | 29 | 0.375 | 1.07
122 | 210 | 204 | 75 |  | 56 | 0.375 | 1.07
123 | 19 | 11 | 63 | 184 | 61.7 | 0.36 | 1.06
124 | 11 | 12 | 63 | 83 | 95.3 | 0.36 | 1.06
125 | 11 | 14 | 63 | 12 | 93.2 | 0.36 | 1.06
126 | 5 | 6 | 63 | 54 | 183.4 | 0.36 | 1.06
127 | 9 | 17 | 200 | 103 | 228.3 | 0.5 | 1.2
128 | 17 | 23 | 63 | 200 | 101.2 | 0.36 | 1.06
129 | 23 | 22 | 200 | 108 | 40.2 | 0.5 | 1.2
130 | 22 | 20 | 200 | 40 | 35.4 | 0.5 | 1.2
131 | 20 | 21 | 63 | 36 | 50.5 | 0.36 | 1.06
132 | 20 | 17 | 200 | 51 | 42.4 | 0.5 | 1.2
133 | 22 | 38 | 160 | 56 | 177.2 | 0.46 | 1.16
134 | 22 | 38 | 160 |  | 5 | 0.46 | 1.16 |  | b.t crossing | 5 | 0.46 | 2.3 | 5 | 0.46 | 2.3
135 | 1 | 3 | 63 | 167 | 67.2 | 0.36 | 1.06
136 | 1 | 3 | 63 |  | 82.2 | 0.36 | 1.06 |  | brick road | 82.2 | 0.36 | 29.592 | 82.2 | 0.36 | 29.592
137 | 23 | 27 | 200 | 152 | 158.8 | 0.46 | 1.2 |  | b.t road | 158.8 | 0.46 | 73.048 | 158.8 | 0.46 | 73.048
138 | 27 | 30 | 63 | 322 | 5 | 0.36 | 1.06 |  | b.t crossing | 5 | 0.36 | 1.8 | 5 | 0.36 | 1.8
139 | 27 | 30 | 63 |  | 273.3 | 0.36 | 1.06
140 | 27 | 37 | 200 | 168 | 172.3 | 0.46 | 1.2 |  | b.t road | 172.3 | 0.46 | 79.258 | 172.3 | 0.46 | 79.258
141 | 37 | 39 | 63 | 146 | 34.1 | 0.36 | 1.06
142 | 37 | 37a | 63 |  | 115.6 | 0.36 | 1.06
143 | 37a | 37b | 63 |  | 106.8 | 0.36 | 1.06
144 | 37 | 42 | 200 | 472 | 481.1 | 0.46 | 1.2 |  | b.t road | 481.1 | 0.46 | 221.306 | 481.1 | 0.46 | 221.306
145 | 42 | 43 | 200 | 14 | 98 | 0.46 | 1.2 |  | interlocking | 98 | 0.46 | 45.08 | 98 | 0.46 | 45.08
146 | 42 | 43 | 200 |  | 88.1 | 0.46 | 1.2
147 | 43 | 43a | 63 |  | 136.4 | 0.36 | 1.06
148 | 43 | 41 | 200 | 305 | 303.2 | 0.46 | 1.2
149 | 41 | 36 | 75 | 138 | 137 | 0.375 | 1.07
150 | 36 | 34 | 63 | 42 | 67.2 | 0.36 | 1.06
151 | 36 | 28 | 63 | 175 | 207.8 | 0.36 | 1.06
152 | 41 | 122 | 140 | 453 | 472 | 0.44 | 1.14 |  | brick road | 472 | 0.44 | 207.68 | 472 | 0.44 | 207.68
153 | 42 | 48 | 140 | 203 | 211.8 | 0.44 | 1.14 |  | b.t road | 211.8 | 0.44 | 93.192 | 211.8 | 0.44 | 93.192
154 | 48 | 49 | 63 | 160 | 156.5 | 0.36 | 1.06
155 | 48 | 57 | 140 | 136 | 110.5 | 0.44 | 1.14 |  | b.t road | 110.5 | 0.44 | 48.62 | 110.5 | 0.44 | 48.62
156 | 48 | 57 | 140 |  | 25.6 | 0.44 | 1.14 |  | interlocking | 25.6 | 0.46 | 11.776 | 25.6 | 0.46 | 11.776
157 | 57 | 58 | 63 | 115 | 55.8 | 0.36 | 1.06 |  | brick road | 55.8 | 0.36 | 20.088 | 55.8 | 0.36 | 20.088
158 | 63 | 68 | 75 | 194 | 114.9 | 0.375 | 1.07
159 | 68 | 69 | 75 | 40 | 33.4 | 0.375 | 1.07
160 | 67 | 69 | 63 | 121 | 185 | 0.36 | 1.06
161 | 82 | 71 | 75 | 69 | 62 | 0.375 | 1.07 |  | brick road | 62 | 0.375 | 23.25 | 62 | 0.375 | 23.25
162 | 66 | 67 | 75 | 46 | 81.2 | 0.375 | 1.07 | [11 empty] | 477
163 | 57 | 62 | 140 | 142 | 139.1 | 0.44 | 1.07 |  | interlocking | 139.1 | 0.46 | 63.986 | 139.1 | 0.46 | 63.986
164 | 62 | 90 | 63 | 242 | 310 | 0.36 | 1.06
165 | 62 | 92 | 140 | 213 | 220 | 0.44 | 1.14 |  | b.t road | 220 | 0.44 | 96.8 | 220 | 0.44 | 96.8
166 | 92 | 95 | 75 | 93 | 93.6 | 0.375 | 1.07 | [11 empty] | 1520
167 | 95 | 98 | 63 | 116 | 135.9 | 0.36 | 1.06
168 | 95 | 96 | 63 | 48 | 5 | 0.36 | 1.06 |  | b.t crossing | 5 | 0.36 | 1.8 | 5 | 0.36 | 1.8
169 | 95 | 96 | 63 |  | 39 | 0.36 | 1.06
170 | 92 | 94 | 110 | 197 | 201.7 | 0.41 | 1.1
171 | 92 | 101 | 110 | 138 | 142.2 | 0.41 | 1.1 |  | brick road | 142.2 | 0.41 | 58.302 | 142.2 | 0.41 | 58.302
172 | 101 | 104 | 110 | 68 | 70.2 | 0.41 | 1.1
173 | 104 | 106 | 110 | 116 | 119.6 | 0.41 | 1.1 |  | brick road | 119.6 | 0.41 | 49.036 | 119.6 | 0.41 | 49.036
174 | 106 | 107 | 110 | 12 | 15.6 | 0.41 | 1.1
175 | 107 | 109 | 63 | 75 | 20.7 | 0.36 | 1.06
176 | 107 | 112 | 63 | 89 | 88.9 | 0.36 | 1.06
177 | 116 | 119 | 63 | 35 | 3 | 0.36 | 1.06 |  | brick road | 3 | 0.36 | 1.08 | 3 | 0.36 | 1.08
178 | 116 | 119 | 63 |  | 69 | 0.36 | 1.06
179 | 116 | 113 | 63 | 95 | 89 | 0.36 | 1.06
180 | 116 | 108 | 63 | 39 | 41.6 | 0.36 | 1.06
181 | 108 | 109 | 75 | 45 | 48 | 0.375 | 1.07 |  | brick road | 48 | 0.375 | 18 | 48 | 0.375 | 18
182 | 109 | 115 | 63 | 41 | 20.8 | 0.36 | 1.06
183 | 109 | 106 | 75 | 75 | 39.6 | 0.375 | 1.07
184 | 108 | 103 | 75 | 112 | 111 | 0.375 | 1.07
185 | 108 | 103 | 75 |  | 6 | 0.375 | 1.07 |  | culvert
186 | 105 | 104 | 75 | 197 | 203.2 | 0.375 | 1.07
187 | 163 | 161 | 75 | 92 | 89.6 | 0.375 | 1.07
188 | 161 | 162 | 63 | 76 | 112.3 | 0.36 | 1.06
189 | 173 | 174 | 63 | 83 | 107.5 | 0.36 | 1.06 |  | interlocking | 107.5 | 0.46 | 49.45 | 107.5 | 0.46 | 49.45
190 | 59 | 61 | 140 | 40 | 75.1 | 0.44 | 1.14 |  | interlocking | 75.1 | 0.46 | 34.546 | 75.1 | 0.46 | 34.546
191 | 85 | 86 | 63 | 44 | 41.1 | 0.36 | 1.06
[5 empty] | 19832.7 | [6 empty] | 2534.5715 |  |  | 2534.5715
Representative PMPL - BRCCPL (JV) Pratapgarh | [6 empty] | Representative Medhaj Techno Concept Pvt Ltd (TPI) Pratapgarh |  |  |  |  | Representative UP Jal Nigam (Rural) Pratapgarh
|  | 63 | 75 | 90 | 110 | 140 | 160 | 200 | 250
|  | 5572.7 | 2871.3 | 2097.8 | 987 | 3401 | 3255.1 | 1647.8 | 0 | 19832.7

## aurangabad 2
GOVERNMENT OF UTTAR PRADESH
STATE WATER & SANITATION MISSION ( SWSM )
Joint Measurement Report of Pipe Line
Name of the Work :- Survey , Design Preparation of DPR , Construction , Commissioning and O&M for 10 Years of Various Rural Water Supply Projects in the state of Uttar Pradesh as Per Request for Proposal for Division " Prayagraj "
Name of the Agency : POWER MECH PROJECTS LIMITED – BHOORATHNOM CONSTRUCTIONS COMPANY PRIVATE LIMITED (JV), Hyderabad.
Name OF Scheme |  | :aurangabad
Block |  | : Mangraura
Total Scope |  | :
JMR No. |  | : 2
Date of JMR |  | :
Sr. No. | Start Node | End Node | Dia | Pipe Length (as per Drawing) | Pipe Length (as per Site) | Width | Depth | Quantity | Type OF Road | Dismantling Length | Dismantling Width | Dismantling Quantity | Restoration Length | Restoration Width | Restoration Quantity | Restoration Status | Remark
1 | j4 | j5 | 250 | 274 | 274 | 0.55 | 1.25 | [10 empty] | 55
2 | j5 | j7 | 250 | 54 | 54 | 0.55 | 1.25 | [10 empty] | 66
3 | j7 | j9 | 250 | 159 | 159 | 0.55 | 1.25 | [10 empty] | 44
4 | j91 | j91(1) | 63 |  | 200 | 0.363 | 1.06 | [10 empty] | 33
5 | 176 | 177 | 63 | 82 | 143.2 | 0.363 | 1.06 | [10 empty] | 55
Representative PMPL - BRCCPL (JV) Pratapgarh | [6 empty] | Representative Medhaj Techno Concept Pvt Ltd (TPI) Pratapgarh |  |  |  |  | Representative UP Jal Nigam (Rural) Pratapgarh | [5 empty] | 60.5
54
33
44
444.5
5762.4

## MADHURA RANI GANJ
MADHURA RANI GANJ AND SARAOULI(JMR) BLOCK-MANGRAURA | [9 empty] | MADHURA RANI GANJ AND SARAOULI(JMR) BLOCK-MANGRAURA
Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | Dia of pipe(MM) | Pipe Length (M) | CUMMULATIVE | Depth(M) | REMARK | Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | Dia of pipe(MM) | Pipe Length (M) | CUMMULATIVE | Depth(M) | REMARK
1 | J137 | J132 |  |  | 63 | 27 | 27 | 1.06 |  | 1 | j542 | j491 | brick road | 0.36 | 63 | 100.7 | 100.7 | 1.06
2 | J142 | J143 |  |  | 63 | 86.1 | 113.1 | 1.06 |  | 2 | j380 | j399 | interlocking | 0.46 | 63 | 125.8 | 226.5 | 1.06
3 | J147 | J148 |  |  | 63 | 48.1 | 161.2 | 1.06 |  | 3 | j399 | j403 | interlocking | 0.46 | 63 | 25.2 | 251.7 | 1.06
4 | J147 | J148 | BRICK ROAD | 0.36 | 63 | 33.6 | 194.8 | 1.06 |  | 4 | j403 | j411 | interlocking | 0.46 | 63 | 30.1 | 281.8 | 1.06
5 | J148A | J148 |  |  | 63 | 9.3 | 204.1 | 1.06 |  | 5 | j411 | j418 | interlocking | 0.46 | 63 | 57.2 | 339 | 1.06
6 | J148 | J148B |  |  | 63 | 53.2 | 257.3 | 1.06 |  | 6 | j411 | j418 |  |  | 63 | 23.2 | 362.2 | 1.06
7 | J180 | J149 |  |  | 63 | 91.3 | 348.6 | 1.06 |  | 7 | j380 | j399 | culvert |  | 63 | 2 | 364.2 | 1.06
8 | J147 | J187 |  |  | 63 | 146.1 | 494.7 | 1.06 |  | 8 | j380 | j399 | b.t road | 0.36 | 63 | 6.7 | 370.9 | 1.06
9 | J187 | J196 |  |  | 63 | 175.8 | 670.5 | 1.06 |  | 9 | j447a | j447b |  |  | 63 | 10.2 | 381.1 | 1.06
10 | J196 | J197 |  |  | 63 | 37.1 | 707.6 | 1.06 |  | 10 | j129 | j130 | brickroad | 0.36 | 63 | 25.1 | 406.2 | 1.06
11 | J192 | J193 |  |  | 63 | 25 | 732.6 | 1.06 |  | 11 | j34 | j35 | b.t road | 0.36 | 63 | 5 | 411.2 | 1.06
12 | J192 | J187 |  |  | 63 | 24.7 | 757.3 | 1.06 |  | 12 | j34 | j35 | cc | 0.36 | 63 | 103.1 | 514.3 | 1.06
13 | J192 | J198 |  |  | 63 | 129.2 | 886.5 | 1.06 |  | 13 | j133 | j134 | cc | 0.36 | 63 | 113.2 | 627.5 | 1.06
14 | J198 | J196 |  |  | 63 | 34.5 | 921 | 1.06 |  | 14 | j134 | j136 | cc | 0.36 | 63 | 54 | 681.5 | 1.06
15 | J198 | J228 |  |  | 63 | 536.8 | 1457.8 | 1.06 |  | 15 | j134 | j135 | cc | 0.36 | 63 | 24.8 | 706.3 | 1.06
16 | J3 | J10 | B.T ROAD | 0.36 | 63 | 45.7 | 1503.5 | 1.06 |  | 16 | j133 | j138 | interlocking | 0.46 | 63 | 85.1 | 791.4 | 1.06
17 | J3 | J11 |  |  | 63 | 119.2 | 1622.7 | 1.06 |  | 17 | j138 | j160 | cc | 0.36 | 63 | 47.1 | 838.5 | 1.06
18 | J27 | J26 |  |  | 63 | 85.5 | 1708.2 | 1.06 |  | 18 | j138 | j139 | cc | 0.36 | 63 | 78.3 | 916.8 | 1.06
19 | J28 | 41 |  |  | 63 | 155 | 1863.2 | 1.06 |  | 19 | j25 | j38 | b.t road | 0.36 | 63 | 4 | 920.8 | 1.06
20 | J91A | J91B |  |  | 63 | 18.6 | 1881.8 | 1.06 |  | 20 | j25 | j38 |  |  | 63 | 15.3 | 936.1 | 1.06
21 | J91 | J91A | B.T ROAD | 0.36 | 63 | 27 | 1908.8 | 1.06 |  | 21 | j25 | j38 | interlocking | 0.46 | 63 | 33.1 | 969.2 | 1.06
22 | J91A | J90 |  |  | 63 | 18.1 | 1926.9 | 1.06 |  | 22 | j25 | j38 | cc | 0.36 | 63 | 93.5 | 1062.7 | 1.06
23 | J90 | J94 |  |  | 63 | 39.6 | 1966.5 | 1.06 |  | 23 | j39 | j38 | cc | 0.36 | 63 | 47.6 | 1110.3 | 1.06
24 | J90 | J86 |  |  | 63 | 31.8 | 1998.3 | 1.06 |  | 24 | j38 | j79 | cc | 0.36 | 63 | 80.8 | 1191.1 | 1.06
25 | J86 | J97 |  |  | 63 | 71 | 2069.3 | 1.06 |  | 25 | j27 | j27a |  |  | 63 | 37.2 | 1228.3 | 1.06
26 | J97 | J94 |  |  | 63 | 42.7 | 2112 | 1.06 |  | 26 | j27 | j27a | b.t road | 0.36 | 63 | 3 | 1231.3 | 1.06
27 | J97 | J98 |  |  | 63 | 63.6 | 2175.6 | 1.06 |  | 27 | j30 | j31 | cc | 0.36 | 63 | 73.1 | 1304.4 | 1.06
28 | J98 | J99 |  |  | 63 | 20 | 2195.6 | 1.06 |  | 28 | j55 | j50 |  |  | 90 | 77.6 | 1382 | 1.09
29 | J98 | J106 |  |  | 63 | 44.1 | 2239.7 | 1.06 |  | 29 | j63 | j74 |  |  | 90 | 101.3 | 1483.3 | 1.09
30 | J100 | J101 |  |  | 63 | 45.7 | 2285.4 | 1.06 |  | 30 | j126 | j129 | brick road | 0.41 | 110 | 30.2 | 1513.5 | 1.1
31 | J100 | J103 |  |  | 63 | 28.4 | 2313.8 | 1.06 |  | 31 | j2 | j3 |  |  | 110 | 195.6 | 1709.1 | 1.1
32 | J103 | J105 |  |  | 63 | 35.3 | 2349.1 | 1.06 |  | 32 | j2 | j3 | b.t road | 0.41 | 110 | 5 | 1714.1 | 1.1
33 | J103 | J103A |  |  | 63 | 46.3 | 2395.4 | 1.06 |  | 33 | j441 | j459 |  |  | 110 | 140.9 | 1855 | 1.1
34 | J84 | J100 |  |  | 63 | 64.7 | 2460.1 | 1.06 |  | 34 | j448 | j454 |  |  | 140 | 118.6 | 1973.6 | 1.14
35 | J105 | J92 |  |  | 63 | 64.1 | 2524.2 | 1.06 |  | 35 | j425 | j437 |  |  | 140 | 91.3 | 2064.9 | 1.14
36 | J128 | J76 |  |  | 63 | 59.4 | 2583.6 | 1.06 |  | 36 | j437 | j441 |  |  | 140 | 110.1 | 2175 | 1.14
37 | J123 | J122 |  |  | 63 | 37.2 | 2620.8 | 1.06 |  | 37 | j451 | j447 |  |  | 140 | 44.2 | 2219.2 | 1.14
38 | J61 | J49 |  |  | 63 | 318.2 | 2939 | 1.06 |  | 38 | j50 | j49 |  |  | 140 | 189.7 | 2408.9 | 1.14
39 | J47 | J48 |  |  | 63 | 72.4 | 3011.4 | 1.06 |  | 39 | j45 | j63 |  |  | 140 | 291.1 | 2700 | 1.14
40 | J49 | J51 |  |  | 63 | 104 | 3115.4 | 1.06 |  | 40 | j120 | j123 | brick road | 0.44 | 140 | 26.2 | 2726.2 | 1.14
41 | J51 | J52 |  |  | 63 | 19.6 | 3135 | 1.06 |  | 41 | j123 | j126 | brick road | 0.44 | 140 | 48.1 | 2774.3 | 1.14
42 | J51 | J50 |  |  | 63 | 223 | 3358 | 1.06 |  | 42 | j77 | j72 | b.t road | 0.44 | 140 | 206.2 | 2980.5 | 1.14
43 | J55 | J58 |  |  | 63 | 190.2 | 3548.2 | 1.06 |  | 43 | j442 | j448 |  |  | 160 | 167.5 | 3148 | 1.16
44 | J63 | J66 |  |  | 63 | 130.2 | 3678.4 | 1.06 |  | 44 | j49 | j47 |  |  | 160 | 215 | 3363 | 1.16
45 | J32 | J33 |  |  | 63 | 37.1 | 3715.5 | 1.06 |  | 45 | j47 | j45 |  |  | 160 | 701.1 | 4064.1 | 1.16
46 | J32 | J32A |  |  | 63 | 56.4 | 3771.9 | 1.06 |  | 46 | j47 | j45 | culvert |  | 160 | 3 | 4067.1 | 1.16
47 | J32 | J32B |  |  | 63 | 21.3 | 3793.2 | 1.06 |  | 47 | j45 | j34 |  |  | 160 | 206 | 4273.1 | 1.16
48 | J32A | J40 |  |  | 63 | 187.7 | 3980.9 | 1.06 |  | 48 | j34 | j30 |  |  | 160 | 90 | 4363.1 | 1.16
49 | J29 | J21 |  |  | 63 | 187.3 | 4168.2 | 1.06 |  | 49 | j30 | j29 |  |  | 160 | 15 | 4378.1 | 1.16
50 | J21 | J22 |  |  | 63 | 174.6 | 4342.8 | 1.06 |  | 50 | j29 | j25 |  |  | 160 | 168 | 4546.1 | 1.16
51 | J21A | J21 |  |  | 63 | 9.1 | 4351.9 | 1.06 |  | 51 | j25 | j24 |  |  | 160 | 54.9 | 4601 | 1.16
52 | J21A | J21B |  |  | 63 | 32.1 | 4384 | 1.06 |  | 52 | j24 | j23 |  |  | 160 | 88.8 | 4689.8 | 1.16
53 | J21A | J20 |  |  | 63 | 37.1 | 4421.1 | 1.06 |  | 53 | j24 | j23 | b.t road | 0.46 | 160 | 7.2 | 4697 | 1.16
54 | J20 | J19 |  |  | 63 | 46.3 | 4467.4 | 1.06 |  | 54 | j23 | j26 |  |  | 160 | 127.2 | 4824.2 | 1.16
55 | J20 | J17 |  |  | 63 | 51.1 | 4518.5 | 1.06 |  | 55 | j26 | j28 |  |  | 160 | 7.7 | 4831.9 | 1.16
56 | J17 | J19 |  |  | 63 | 10.6 | 4529.1 | 1.06 |  | 56 | j28 | j46 |  |  | 160 | 195.7 | 5027.6 | 1.16
57 | J17 | J15 |  |  | 63 | 46.2 | 4575.3 | 1.06 |  | 57 | j46 | j72 |  |  | 160 | 234.1 | 5261.7 | 1.16
58 | J15 | J15A |  |  | 63 | 27.3 | 4602.6 | 1.06 |  | 58 | j72 | j110 |  |  | 160 | 165.3 | 5427 | 1.16
59 | J15 | J16 |  |  | 63 | 26.8 | 4629.4 | 1.06 |  | 59 | j72 | j110 | b.t road | 0.46 | 160 | 4.6 | 5431.6 | 1.16
60 | J13 | J14 |  |  | 63 | 39.2 | 4668.6 | 1.06 |  | 60 | j113 | j115 |  |  | 160 | 60 | 5491.6 | 1.16
61 | J590 | J618 |  |  | 63 | 101.3 | 4769.9 | 1.06 |  | 61 | j115 | j120 | brick road | 0.46 | 160 | 338.3 | 5829.9 | 1.16
62 | J618 | J628 |  |  | 63 | 29 | 4798.9 | 1.06 |  | 62 | j216 | j215 |  |  | 160 | 263.1 | 6093 | 1.16
63 | J628 | J630 |  |  | 63 | 53.7 | 4852.6 | 1.06 |  | 63 | j167 | j182 |  |  | 160 | 152.1 | 6245.1 | 1.16
64 | J618 | J627 |  |  | 63 | 194.7 | 5047.3 | 1.06 |  | 64 | j310 | j309 | b.t road | 0.5 | 200 | 270.7 | 6515.8 | 1.2
65 | J627 | J644 |  |  | 63 | 63.4 | 5110.7 | 1.06 |  | 65 | j310 | j283 | b.t road | 0.5 | 200 | 119.7 | 6635.5 | 1.2
66 | J628 | J644 |  |  | 63 | 218.7 | 5329.4 | 1.06 |  | 66 | j283 | j228 | b.t road | 0.5 | 200 | 223.2 | 6858.7 | 1.2
67 | J576 | J627 |  |  | 63 | 214 | 5543.4 | 1.06 |  | 67 | j228 | j216 | b.t road | 0.5 | 200 | 248.5 | 7107.2 | 1.2
68 | J644 | J658 |  |  | 63 | 469.6 | 6013 | 1.06 |  | 68 | j216 | j170 | b.t road | 0.5 | 200 | 357.2 | 7464.4 | 1.2
69 | J658 | J657 |  |  | 63 | 153.4 | 6166.4 | 1.06 |  | 69 | j216 | j170 |  |  | 200 | 76.8 | 7541.2 | 1.2
70 | J657 | J624 |  |  | 63 | 388 | 6554.4 | 1.06 |  | 70 | j170 | j169 |  |  | 200 | 68.5 | 7609.7 | 1.2
71 | J624 | J620 |  |  | 63 | 185 | 6739.4 | 1.06 |  | 71 | j169 | j167 |  |  | 200 | 191.2 | 7800.9 | 1.2
72 | J624 | J595 | B.T ROAD | 0.36 | 63 | 3.3 | 6742.7 | 1.06 |  | 72 | j169 | j167 | b.t road | 0.5 | 200 | 5 | 7805.9 | 1.2
73 | J624 | J595 |  |  | 63 | 113.6 | 6856.3 | 1.06 |  | 73 | j167 | j166 | b.t road | 0.5 | 200 | 25.1 | 7831 | 1.2
74 | J595 | J596 |  |  | 63 | 74.5 | 6930.8 | 1.06 |  | 74 | j166 | j159 | b.t road | 0.5 | 200 | 92.7 | 7923.7 | 1.2
75 | J595 | J587 |  |  | 63 | 47.1 | 6977.9 | 1.06 |  | 75 | j159 | j146 | b.t road | 0.5 | 200 | 119.5 | 8043.2 | 1.2
76 | J587 | J525A |  |  | 63 | 36 | 7013.9 | 1.06 |  | 76 | j159 | j141 | b.t road | 0.5 | 200 | 85.1 | 8128.3 | 1.2
77 | J525A | J525B |  |  | 63 | 29.2 | 7043.1 | 1.06 |  | 77 | j141 | j113 | b.t road | 0.5 | 200 | 133.5 | 8261.8 | 1.2
78 | J525A | J511 |  |  | 63 | 162.1 | 7205.2 | 1.06 |  | 78 | j113 | j27 | b.t road | 0.5 | 200 | 212.3 | 8474.1 | 1.2
79 | J511A | J511B |  |  | 63 | 41.2 | 7246.4 | 1.06 |  | 79 | j27 | j23 | b.t road | 0.5 | 200 | 61 | 8535.1 | 1.2
80 | J587 | J639 | B.T ROAD | 0.36 | 63 | 2.5 | 7248.9 | 1.06 |  | 80 | j27 | j23 | culvert |  | 200 | 4.7 | 8539.8 | 1.2
81 | J587 | J639 |  |  | 63 | 421.6 | 7670.5 | 1.06 |  | 81 | j27 | j23 | b.t road | 0.5 | 200 | 12.3 | 8552.1 | 1.2
82 | J639 | J638 |  |  | 63 | 2.1 | 7672.6 | 1.06 |  | 82 | j502 | j493 | brick road | 0.5 | 200 | 19.2 | 8571.3 | 1.2
83 | J638 | J657 |  |  | 63 | 237 | 7909.6 | 1.06 |  | 83 | j493 | j491 | brick road | 0.5 | 200 | 101 | 8672.3 | 1.2
84 | J658 | J648 |  |  | 63 | 218.4 | 8128 | 1.06 |  | 84 | j491 | j489 | brick road | 0.5 | 200 | 29.3 | 8701.6 | 1.2
85 | J648 | J638 |  |  | 63 | 142.6 | 8270.6 | 1.06 |  | 85 | j489 | j485 |  | 0.5 | 200 | 45 | 8746.6 | 1.2
86 | J648 | J640 |  |  | 63 | 51.4 | 8322 | 1.06 |  | 86 | j485 | j481 | brick road | 0.5 | 200 | 46.4 | 8793 | 1.2
87 | J640 | J616 |  |  | 63 | 128 | 8450 | 1.06 |  | 87 | j487 | j486 | b.t road | 0.5 | 200 | 65.8 | 8858.8 | 1.2
88 | J616 | J617 |  |  | 63 | 38 | 8488 | 1.06 |  | 88 | j486 | j482 | b.t road | 0.5 | 200 | 75.6 | 8934.4 | 1.2
89 | J616 | J537 |  |  | 63 | 3.9 | 8491.9 | 1.06 |  | 89 | j481 | j483 | b.t road | 0.5 | 200 | 57.3 | 8991.7 | 1.2
90 | J616 | J537 | BRICK ROAD | 0.36 | 63 | 5.4 | 8497.3 | 1.06 |  | 90 | j480 | j477 |  | 0.5 | 200 | 70.6 | 9062.3 | 1.2
91 | J616 | J537 |  |  | 63 | 258.1 | 8755.4 | 1.06 |  | 91 | j477 | j379 |  | 0.5 | 200 | 98.8 | 9161.1 | 1.2
92 | J544 | J545 |  |  | 63 | 103.1 | 8858.5 | 1.06 |  | 92 | j379 | j376 |  | 0.5 | 200 | 45.6 | 9206.7 | 1.2
93 | J567 | J633 |  |  | 63 | 386.2 | 9244.7 | 1.06 |  | 93 | j495 | j487 |  | 0.46 | 160 | 87.8 | 9294.5 | 1.16
94 | J633 | J640 |  |  | 63 | 73.4 | 9318.1 | 1.06 |  | 94 | j433 | j492 |  | 0.46 | 160 | 167.8 | 9462.3 | 1.16
95 | J633 | J634 |  |  | 63 | 35.2 | 9353.3 | 1.06 |  | 95 | j433 | j442 | brick road | 0.46 | 160 | 27.1 | 9489.4 | 1.16
96 | J639 | J601 |  |  | 63 | 163.7 | 9517 | 1.06 |  | 96 | j511 | j514 |  | 0.44 | 140 | 25.1 | 9514.5 | 1.14
97 | J601 | J593 |  |  | 63 | 109.1 | 9626.1 | 1.06 |  | 97 | j511 | j514 | interlocking | 0.46 | 140 | 152.8 | 9667.3 | 1.14
98 | J593 | J568 |  |  | 63 | 90.7 | 9716.8 | 1.06 |  | 98 | j447 | j442 |  |  | 140 | 20 | 9687.3 | 1.14
99 | J568 | J569 |  |  | 63 | 49.2 | 9766 | 1.06 |  | 99 | j447 | j442 | brick road | 0.44 | 140 | 52 | 9739.3 | 1.14
100 | J568 | J562 |  |  | 63 | 52.1 | 9818.1 | 1.06 |  | 100 | j24 | j12 |  |  | 110 | 122.7 | 9862 | 1.1
101 | J562 | J563 |  |  | 63 | 38.2 | 9856.3 | 1.06 |  | 101 | j12 | j1 |  |  | 110 | 105.3 | 9967.3 | 1.1
102 | J562 | J557 |  |  | 63 | 20.6 | 9876.9 | 1.06 |  | 102 | j77 | j92 |  |  | 110 | 77.8 | 10045.1 | 1.1
103 | J557 | J529 |  |  | 63 | 68.2 | 9945.1 | 1.06 |  | 103 | j77 | j84 |  |  | 110 | 74.8 | 10119.9 | 1.1
104 | J557 | J543 |  |  | 63 | 120.2 | 10065.3 | 1.06 |  | 104 | j570 | j590 |  |  | 110 | 106.4 | 10226.3 | 1.1
105 | J543 | J509 |  |  | 63 | 153.6 | 10218.9 | 1.06 |  | 105 | j84 | j86 |  |  | 90 | 79.2 | 10305.5 | 1.09
106 | J509 | J529 |  |  | 63 | 51.3 | 10270.2 | 1.06 |  | 106 | j489 | j490 |  |  | 63 | 32 | 10337.5 | 1.06
107 | J543 | J546 |  |  | 63 | 28.3 | 10298.5 | 1.06 |  | 107 | j447a | j447b |  |  | 63 | 31 | 10368.5 | 1.06
108 | J546 | J552 |  |  | 63 | 89.3 | 10387.8 | 1.06 |  | 108 | j456 | j457 |  |  | 63 | 21.1 | 10389.6 | 1.06
109 | J546 | J547 |  |  | 63 | 45.2 | 10433 | 1.06 |  | 109 | j74 | j75 | interlocking | 0.46 | 63 | 97 | 10486.6 | 1.06
110 | j546 | j558 |  |  | 63 | 94.1 | 10527.1 | 1.06 |  | 110 | j162 | j165 | brick road | 0.36 | 63 | 298.7 | 10785.3 | 1.06
111 | j558 | j542 |  |  | 63 | 63.3 | 10590.4 | 1.06 |  | 111 | j45 | j133 | interlocking | 0.46 | 63 | 133 | 10918.3 | 1.06
112 | j558 | j542 | BRICK ROAD | 0.36 | 63 | 76.3 | 10666.7 | 1.06 |  | 112 | j111 | j128 | brick road | 0.36 | 63 | 238.4 | 11156.7 | 1.06
113 | j542 | j559 |  |  | 63 | 64.5 | 10731.2 | 1.06 |  | 113 | j128 | j130 | brick road | 0.36 | 63 | 11.2 | 11167.9 | 1.06
114 | j559 | j558 |  |  | 63 | 90.6 | 10821.8 | 1.06 |  | 114 | j130 | j137 | brick road | 0.36 | 63 | 44.5 | 11212.4 | 1.06
115 | j559 | j593 |  |  | 63 | 152.5 | 10974.3 | 1.06 |  | 115 | j137 | j142 | brick road | 0.36 | 63 | 45.5 | 11257.9 | 1.06
116 | j601 | j530 |  |  | 63 | 5.8 | 10980.1 | 1.06 |  | 116 | j142 | j147 | brick road | 0.36 | 63 | 22.3 | 11280.2 | 1.06
117 | j601 | j530 | BRICK ROAD | 0.36 | 63 | 210.7 | 11190.8 | 1.06 |  | 117 | j381 | j382 | b.t road | 0.44 | 140 | 6.2 | 11286.4 | 1.14
118 | j504 | j506 |  |  | 63 | 225.7 | 11416.5 | 1.06 |  | 118 | j381 | j382 |  |  | 140 | 29.7 | 11316.1 | 1.14
119 | j590a | j585 |  |  | 63 | 34.8 | 11451.3 | 1.06 |  | 119 | j382 | j386 |  |  | 140 | 34.3 | 11350.4 | 1.14
120 | j585 | j574 |  |  | 63 | 52.3 | 11503.6 | 1.06 |  | 120 | j398 | j393 | brickroad | 0.44 | 140 | 50.6 | 11401 | 1.14
121 | j574 | j570a |  |  | 63 | 44.9 | 11548.5 | 1.06 |  | 121 | j401 | j414 | brickroad | 0.36 | 63 | 6.5 | 11407.5 | 1.06
122 | j570a | j570b |  |  | 63 | 18.1 | 11566.6 | 1.06 |  | 122 | j310 | j376 | b.t road | 0.5 | 200 | 6.9 | 11414.4 | 1.2
123 | j570a | j570c |  |  | 63 | 29.7 | 11596.3 | 1.06 |  | 123 | j587 | j639 | b.t road | 0.36 | 63 | 3.5 | 11417.9 | 1.06
124 | j578 | j575 |  |  | 63 | 51.6 | 11647.9 | 1.06 |  | 124 | j504 | j506 | b.t road | 0.36 | 63 | 7 | 11424.9 | 1.06
125 | j575 | j574 |  |  | 63 | 10.1 | 11658 | 1.06 |  | 125 | j536 | j538 | b.t road | 0.36 | 63 | 6.5 | 11431.4 | 1.06
126 | j575 | j580 |  |  | 63 | 29.7 | 11687.7 | 1.06 |  | 126 | j574 | j575 | b.t road | 0.36 | 63 | 6.9 | 11438.3 | 1.06
127 | j585 | j581 |  |  | 63 | 141.1 | 11828.8 | 1.06 |  | 127 | j7 | j7a |  |  | 63 | 302 | 11740.3 | 1.06
128 | j379 | j502 |  |  | 63 | 292 | 12120.8 | 1.06 |  |  |  |  | 63 | 90 | 110 | 140 | 160 | 200
129 | j514 | j619 |  |  | 63 | 134.2 | 12255 | 1.06 |  |  |  |  | 2611.5 | 258.1 | 858.7 | 1496.2 | 3547.3 | 2968.5 | 11740.3
130 | j514 | j619 | BRICK ROAD | 0.36 | 63 | 323 | 12578 | 1.06 |  | POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
131 | j401 | j414 |  |  | 63 | 182 | 12760 | 1.06 |  | DESIGNATION |  |  |  | DESIGNATION |  |  | DESIGNATION
132 | j414 | j419 |  |  | 63 | 52.8 | 12812.8 | 1.06 |  | NAME |  |  |  | NAME |  |  | NAME
133 | j419 | j422 |  |  | 63 | 30 | 12842.8 | 1.06 |  | SIGN.with date |  |  |  | SIGN.with date |  |  | SIGN.with date
134 | j416 | j419 |  |  | 63 | 5.2 | 12848 | 1.06
135 | j416 | j417 |  |  | 63 | 24 | 12872 | 1.06 | [9 empty] | 33727.7
136 | j416 | j418 |  |  | 63 | 47 | 12919 | 1.06 | [9 empty] | 34187.8
137 | j418 | j423 |  |  | 63 | 56 | 12975 | 1.06
138 | j382 | j383 |  |  | 63 | 49.8 | 13024.8 | 1.06
139 | j386 | j387 |  |  | 63 | 23.6 | 13048.4 | 1.06
140 | j386 | j388 |  |  | 63 | 28.3 | 13076.7 | 1.06
141 | j414 | j407 |  |  | 63 | 15 | 13091.7 | 1.06 | [5 empty] | 398.556
142 | j414 | j407 | BRICK ROAD | 0.36 | 63 | 3.9 | 13095.6 | 1.06 | [5 empty] | 93.242 |  | 1048
143 | j407 | j408 |  |  | 63 | 40 | 13135.6 | 1.06 | [5 empty] | 30.06 |  | 433.27
144 | j451 | j455a |  |  | 63 | 82.4 | 13218 | 1.06 | [5 empty] | 649.5008 |  |  | 1139.272
145 | j455a | j455b |  |  | 63 | 49 | 13267 | 1.06 | [5 empty] | 340.078
146 | j455a | j455c |  |  | 63 | 80 | 13347 | 1.06 | [5 empty] | 1109.2128
147 | j455c | j462 |  |  | 63 | 63.6 | 13410.6 | 1.06 | [5 empty] | 257.58
148 | j455c | j466 |  |  | 63 | 54.5 | 13465.1 | 1.06
149 | j466 | j471 |  |  | 63 | 64 | 13529.1 | 1.06
150 | j466 | j464 |  |  | 63 | 30.6 | 13559.7 | 1.06
151 | j464 | j468 |  |  | 63 | 59.2 | 13618.9 | 1.06
152 | j468 | j471 |  |  | 63 | 20.4 | 13639.3 | 1.06
153 | j468 | j469 |  |  | 63 | 28 | 13667.3 | 1.06
154 | j464 | j459 |  |  | 63 | 186 | 13853.3 | 1.06
155 | j459 | j440 |  |  | 63 | 175 | 14028.3 | 1.06
156 | j440 | j440a |  |  | 63 | 28.2 | 14056.5 | 1.06
157 | j440a | j440b |  |  | 63 | 27.1 | 14083.6 | 1.06
158 | j440a | j440c |  |  | 63 | 26.6 | 14110.2 | 1.06
159 | j487 | j488 |  |  | 63 | 42.3 | 14152.5 | 1.06
160 | j487 | j476 |  |  | 63 | 197 | 14349.5 | 1.06
161 | j476 | j478 |  |  | 63 | 46.5 | 14396 | 1.06
162 | j478 | j479a | BRICK ROAD | 0.36 | 63 | 12.2 | 14408.2 | 1.06
163 | j479a | j479 | BRICK ROAD | 0.36 | 63 | 6.5 | 14414.7 | 1.06
164 | j479a | j479 |  |  | 63 | 14.2 | 14428.9 | 1.06
165 | j479a | j479b |  |  | 63 | 30.6 | 14459.5 | 1.06
166 | j478 | j480 |  |  | 63 | 40.9 | 14500.4 | 1.06
167 | j476 | j476a |  |  | 63 | 95.2 | 14595.6 | 1.06
168 | j476a | j398 |  |  | 63 | 94.4 | 14690 | 1.06
169 | j477 | j485 |  |  | 63 | 80.2 | 14770.2 | 1.06
170 | j485 | j477 |  |  | 63 | 51.2 | 14821.4 | 1.06
171 | j482 | j486 |  |  | 63 | 89.8 | 14911.2 | 1.06
172 | j495 | j499 |  |  | 63 | 46.3 | 14957.5 | 1.06
173 | j499 | j500 |  |  | 63 | 53.7 | 15011.2 | 1.06
174 | j499 | j501 |  |  | 63 | 71.2 | 15082.4 | 1.06
175 | j495 | j498 |  |  | 63 | 45.2 | 15127.6 | 1.06
176 | j496 | j498 |  |  | 63 | 40.3 | 15167.9 | 1.06
177 | j552a | j552b |  |  | 63 | 28.2 | 15196.1 | 1.06
178 | j519 | j523 |  |  | 63 | 65.3 | 15261.4 | 1.06
179 | j523 | j521 |  |  | 63 | 14 | 15275.4 | 1.06
180 | j523 | j525 |  |  | 63 | 51.2 | 15326.6 | 1.06
181 | j523 | j521 |  |  | 63 | 23.4 | 15350 | 1.06
182 | j594 | j598 | BRICK ROAD | 0.36 | 63 | 3.3 | 15353.3 | 1.06
183 | j594 | j598 |  |  | 63 | 173 | 15526.3 | 1.06
184 | j608 | j609 |  |  | 63 | 118 | 15644.3 | 1.06
185 | j608 | j609 |  |  | 63 | 2.5 | 15646.8 | 1.06
186 | j527 | j513 |  |  | 63 | 55.4 | 15702.2 | 1.06
187 | j553 | j554 |  |  | 63 | 35.7 | 15737.9 | 1.06
188 | j553a | j553b |  |  | 63 | 35.1 | 15773 | 1.06
189 | j520 | j522 |  |  | 63 | 21 | 15794 | 1.06
190 | j531a | j531b |  |  | 63 | 80.5 | 15874.5 | 1.06
191 | j493 | j494 |  |  | 63 | 68.9 | 15943.4 | 1.06
192 | j526 | j530 | interlocking | 0.46 | 63 | 21.7 | 15965.1 | 1.06
193 | j530 | j600 | interlocking | 0.46 | 63 | 181 | 16146.1 | 1.06
194 | j530 | j600 |  |  | 63 | 161.5 | 16307.6 | 1.06
194 | j600 | j601 | BRICK ROAD | 0.36 | 63 | 51.2 | 16358.8 | 1.06
195 | j600 | j602 | BRICK ROAD | 0.36 | 63 | 53.2 | 16412 | 1.06
196 | j602 | j603 |  |  | 63 | 62.8 | 16474.8 | 1.06
197 | j602 | j616 | BRICK ROAD | 0.36 | 63 | 21.7 | 16496.5 | 1.06
198 | j645 | j635 |  |  | 63 | 76.3 | 16572.8 | 1.06
199 | j604 | j606 |  |  | 63 | 59.2 | 16632 | 1.06
200 | j604 | j605 |  |  | 63 | 89.2 | 16721.2 | 1.06
201 | j626 | j625 |  |  | 63 | 30.2 | 16751.4 | 1.06
202 | j570 | j572 |  |  | 63 | 38 | 16789.4 | 1.06
203 | j576a | j576b |  |  | 63 | 41.5 | 16830.9 | 1.06
204 | j381 | j391 | B.T ROAD | 0.36 | 63 | 5 | 16835.9 | 1.06
205 | j435 | j439 |  |  | 63 | 32.2 | 16868.1 | 1.06
206 | j428 | j438 | culvert |  | 63 | 2.4 | 16870.5 | 1.06
207 | j428 | j438 | BRICK ROAD | 0.36 | 63 | 95.5 | 16966 | 1.06
208 | j438 | j443 | BRICK ROAD | 0.36 | 63 | 50.9 | 17016.9 | 1.06
209 | j443 | j444 | BRICK ROAD | 0.36 | 63 | 2.3 | 17019.2 | 1.06
210 | j443 | j444 |  |  | 63 | 33.3 | 17052.5 | 1.06
211 | j438 | j429 | BRICK ROAD | 0.36 | 63 | 2.7 | 17055.2 | 1.06
212 | j438 | j429 |  |  | 63 | 63.3 | 17118.5 | 1.06
213 | j427a | j427b | BRICK ROAD | 0.36 | 63 | 37.1 | 17155.6 | 1.06
214 | j427 | j428 | BRICK ROAD | 0.36 | 63 | 32.2 | 17187.8 | 1.06
215 | j427a | j429 | BRICK ROAD | 0.36 | 63 | 8.1 | 17195.9 | 1.06
216 | j429 | j430 | BRICK ROAD | 0.36 | 63 | 23.7 | 17219.6 | 1.06
217 | j429 | j424 |  |  | 63 | 47.9 | 17267.5 | 1.06
218 | j424 | j426 |  |  | 63 | 3.9 | 17271.4 | 1.06
219 | j424 | j426 | BRICK ROAD | 0.36 | 63 | 53.6 | 17325 | 1.06
220 | j424 | j426 |  |  | 63 | 24 | 17349 | 1.06
221 | j424 | j409 |  |  | 63 | 76.6 | 17425.6 | 1.06
222 | j409 | j510 |  |  | 63 | 99.4 | 17525 | 1.06
223 | j536 | j538 |  |  | 63 | 89.7 | 17614.7 | 1.06
224 | j506 | j508 |  |  | 63 | 29.2 | 17643.9 | 1.06
225 | j487 | j495 |  |  | 63 | 27 | 17670.9 | 1.06
226 | j570 | j567 |  |  | 140 | 149 | 17819.9 | 1.14
227 | j567 | j544 |  |  | 140 | 197.6 | 18017.5 | 1.14
228 | j425 | j450 |  |  | 140 | 243.6 | 18261.1 | 1.14
229 | j450 | j456 |  |  | 140 | 50.5 | 18311.6 | 1.14
230 | j450 | j451 |  |  | 140 | 73 | 18384.6 | 1.14
231 | j451 | j447 |  |  | 140 | 260 | 18644.6 | 1.14
232 | j451 | j448 |  |  | 140 | 444 | 19088.6 | 1.14
233 | j544 | j537 |  |  | 160 | 164 | 19252.6 | 1.16
234 | j537 | j526 |  |  | 160 | 190 | 19442.6 | 1.16
235 | j526 | j502 |  |  | 160 | 100.2 | 19542.8 | 1.16
236 | j381 | j391 |  |  | 160 | 16.1 | 19558.9 | 1.16
237 | j391 | j425 |  |  | 160 | 324.3 | 19883.2 | 1.16
238 | j431 | j428 |  |  | 160 | 18.3 | 19901.5 | 1.16
239 | j427a | j427 |  |  | 160 | 41.6 | 19943.1 | 1.16
240 | j409 | j406 |  |  | 160 | 205.2 | 20148.3 | 1.16
241 | j406 | j427 |  |  | 160 | 188.6 | 20336.9 | 1.16
242 | j406 | j401 |  |  | 160 | 12.1 | 20349 | 1.16
243 | j401 | j391 |  |  | 160 | 133.6 | 20482.6 | 1.16
244 | j495 | j505 |  |  | 160 | 105.3 | 20587.9 | 1.16
245 | j505 | j511 |  |  | 160 | 79.7 | 20667.6 | 1.16
246 | j376 | j371 |  |  | 200 | 188.4 | 20856 | 1.2
247 | j376 | j371 | culvert |  | 200 | 14.3 | 20870.3 | 1.2
248 | j376 | j371 |  |  | 200 | 754 | 21624.3 | 1.2
249 | j371 | j316 |  |  | 200 | 503.7 | 22128 | 1.2
250 | j376 | j380 |  |  | 200 | 190.3 | 22318.3 | 1.2
251 | j380 | j381 |  |  | 200 | 129.2 | 22447.5 | 1.2
|  |  | 63 | 140 | 160 | 200
|  |  | 17670.9 | 1417.7 | 1579 | 1779.9 | 22447.5
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  | SIGN.with date |  |  |  | 20282.4
2913.9
5126.3
|  |  | ROAD RESTORATION | [7 empty] | 4748.4
TYPE OF ROAD | 63 | 75 | 90 | 110 | 140 | 160 | 200 | AVG WIDTH | Cummilative |  | 258.1
BRICK ROAD | 1107.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0.36 | 398.556 | 1047 | 858.7
B.T ROAD | 83.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.36 | 30.06
interlocking | 202.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0.46 | 93.242
cc | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  | SIGN.with date
3824.4
2311.5
875

## MADHURA RANI GANJ(TANISH-2)
MADHURA RANI GANJ AND SARAOULI(JMR) BLOCK-MANGRAURA
Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | Dia of pipe(MM) | Pipe Length (M) | CUMMULATIVE | Depth(M) | REMARK
1 | j542 | j491 | brick road | 0.36 | 63 | 100.7 | 100.7 | 1.06
2 | j380 | j399 | interlocking | 0.46 | 63 | 125.8 | 226.5 | 1.06
3 | j399 | j403 | interlocking | 0.46 | 63 | 25.2 | 251.7 | 1.06
4 | j403 | j411 | interlocking | 0.46 | 63 | 30.1 | 281.8 | 1.06
5 | j411 | j418 | interlocking | 0.46 | 63 | 57.2 | 339 | 1.06
6 | j411 | j418 |  |  | 63 | 23.2 | 362.2 | 1.06
7 | j380 | j399 | culvert |  | 63 | 2 | 364.2 | 1.06
8 | j380 | j399 | b.t road | 0.36 | 63 | 6.7 | 370.9 | 1.06
9 | j447a | j447b |  |  | 63 | 10.2 | 381.1 | 1.06
10 | j129 | j130 | brick road | 0.36 | 63 | 25.1 | 406.2 | 1.06
11 | j34 | j35 | b.t road | 0.36 | 63 | 5 | 411.2 | 1.06
12 | j34 | j35 | cc | 0.36 | 63 | 103.1 | 514.3 | 1.06
13 | j133 | j134 | cc | 0.36 | 63 | 113.2 | 627.5 | 1.06
14 | j134 | j136 | cc | 0.36 | 63 | 54 | 681.5 | 1.06
15 | j134 | j135 | cc | 0.36 | 63 | 24.8 | 706.3 | 1.06
16 | j133 | j138 | interlocking | 0.46 | 63 | 85.1 | 791.4 | 1.06
17 | j138 | j160 | cc | 0.36 | 63 | 47.1 | 838.5 | 1.06
18 | j138 | j139 | cc | 0.36 | 63 | 78.3 | 916.8 | 1.06
19 | j25 | j38 | b.t road | 0.36 | 63 | 4 | 920.8 | 1.06
20 | j25 | j38 |  |  | 63 | 15.3 | 936.1 | 1.06
21 | j25 | j38 | interlocking | 0.46 | 63 | 33.1 | 969.2 | 1.06
22 | j25 | j38 | cc | 0.36 | 63 | 93.5 | 1062.7 | 1.06
23 | j39 | j38 | cc | 0.36 | 63 | 47.6 | 1110.3 | 1.06
24 | j38 | j79 | cc | 0.36 | 63 | 80.8 | 1191.1 | 1.06
25 | j27 | j27a |  |  | 63 | 37.2 | 1228.3 | 1.06
26 | j27 | j27a | b.t road | 0.36 | 63 | 3 | 1231.3 | 1.06
27 | j30 | j31 | cc | 0.36 | 63 | 73.1 | 1304.4 | 1.06
28 | j55 | j50 |  |  | 90 | 77.6 | 1382 | 1.09
29 | j63 | j74 |  |  | 90 | 101.3 | 1483.3 | 1.09
30 | j126 | j129 | brick road | 0.41 | 110 | 30.2 | 1513.5 | 1.1
31 | j2 | j3 |  |  | 110 | 195.6 | 1709.1 | 1.1
32 | j2 | j3 | b.t road | 0.41 | 110 | 5 | 1714.1 | 1.1
33 | j441 | j459 |  |  | 110 | 140.9 | 1855 | 1.1
34 | j448 | j454 |  |  | 140 | 118.6 | 1973.6 | 1.14
35 | j425 | j437 |  |  | 140 | 91.3 | 2064.9 | 1.14
36 | j437 | j441 |  |  | 140 | 110.1 | 2175 | 1.14
37 | j451 | j447 |  |  | 140 | 44.2 | 2219.2 | 1.14
38 | j50 | j49 |  |  | 140 | 189.7 | 2408.9 | 1.14
39 | j45 | j63 |  |  | 140 | 291.1 | 2700 | 1.14
40 | j120 | j123 | brick road | 0.44 | 140 | 26.2 | 2726.2 | 1.14
41 | j123 | j126 | brick road | 0.44 | 140 | 48.1 | 2774.3 | 1.14
42 | j77 | j72 | b.t road | 0.44 | 140 | 206.2 | 2980.5 | 1.14
43 | j442 | j448 |  |  | 160 | 167.5 | 3148 | 1.16
44 | j49 | j47 |  |  | 160 | 215 | 3363 | 1.16
45 | j47 | j45 |  |  | 160 | 701.1 | 4064.1 | 1.16
46 | j47 | j45 | culvert |  | 160 | 3 | 4067.1 | 1.16
47 | j45 | j34 |  |  | 160 | 206 | 4273.1 | 1.16
48 | j34 | j30 |  |  | 160 | 90 | 4363.1 | 1.16
49 | j30 | j29 |  |  | 160 | 15 | 4378.1 | 1.16
50 | j29 | j25 |  |  | 160 | 168 | 4546.1 | 1.16
51 | j25 | j24 |  |  | 160 | 54.9 | 4601 | 1.16
52 | j24 | j23 |  |  | 160 | 88.8 | 4689.8 | 1.16
53 | j24 | j23 | b.t road | 0.46 | 160 | 7.2 | 4697 | 1.16
54 | j23 | j26 |  |  | 160 | 127.2 | 4824.2 | 1.16
55 | j26 | j28 |  |  | 160 | 7.7 | 4831.9 | 1.16
56 | j28 | j46 |  |  | 160 | 195.7 | 5027.6 | 1.16
57 | j46 | j72 |  |  | 160 | 234.1 | 5261.7 | 1.16
58 | j72 | j110 |  |  | 160 | 165.3 | 5427 | 1.16
59 | j72 | j110 | b.t road | 0.46 | 160 | 4.6 | 5431.6 | 1.16
60 | j113 | j115 |  |  | 160 | 60 | 5491.6 | 1.16
61 | j115 | j120 | brick road | 0.46 | 160 | 338.3 | 5829.9 | 1.16
62 | j216 | j215 |  |  | 160 | 263.1 | 6093 | 1.16
63 | j167 | j182 |  |  | 160 | 152.1 | 6245.1 | 1.16
64 | j310 | j309 | b.t road | 0.5 | 200 | 270.7 | 6515.8 | 1.2
65 | j310 | j283 | b.t road | 0.5 | 200 | 119.7 | 6635.5 | 1.2
66 | j283 | j228 | b.t road | 0.5 | 200 | 223.2 | 6858.7 | 1.2
67 | j228 | j216 | b.t road | 0.5 | 200 | 248.5 | 7107.2 | 1.2
68 | j216 | j170 | b.t road | 0.5 | 200 | 357.2 | 7464.4 | 1.2
69 | j216 | j170 | b.t road | 0.5 | 200 | 76.8 | 7541.2 | 1.2
70 | j170 | j169 | b.t road | 0.5 | 200 | 68.5 | 7609.7 | 1.2
71 | j169 | j167 | b.t road | 0.5 | 200 | 191.2 | 7800.9 | 1.2
72 | j169 | j167 | b.t road | 0.5 | 200 | 5 | 7805.9 | 1.2
73 | j167 | j166 | b.t road | 0.5 | 200 | 25.1 | 7831 | 1.2
74 | j166 | j159 | b.t road | 0.5 | 200 | 92.7 | 7923.7 | 1.2
75 | j159 | j146 | b.t road | 0.5 | 200 | 119.5 | 8043.2 | 1.2
76 | j159 | j141 | b.t road | 0.5 | 200 | 85.1 | 8128.3 | 1.2
77 | j141 | j113 | b.t road | 0.5 | 200 | 133.5 | 8261.8 | 1.2 |  |  | 1253.95
78 | j113 | j27 | b.t road | 0.5 | 200 | 212.3 | 8474.1 | 1.2 |  |  | 140.01
79 | j27 | j23 | b.t road | 0.5 | 200 | 61 | 8535.1 | 1.2
80 | j27 | j23 | culvert |  | 200 | 4.7 | 8539.8 | 1.2
81 | j27 | j23 | b.t road | 0.5 | 200 | 12.3 | 8552.1 | 1.2
82 | j502 | j493 | brick road | 0.5 | 200 | 19.2 | 8571.3 | 1.2
83 | j493 | j491 | brick road | 0.5 | 200 | 101 | 8672.3 | 1.2
84 | j491 | j489 | brick road | 0.5 | 200 | 29.3 | 8701.6 | 1.2
85 | j489 | j485 |  |  | 200 | 45 | 8746.6 | 1.2
86 | j485 | j481 | brick road | 0.5 | 200 | 46.4 | 8793 | 1.2
87 | j487 | j486 | b.t road | 0.5 | 200 | 65.8 | 8858.8 | 1.2
88 | j486 | j482 | b.t road | 0.5 | 200 | 75.6 | 8934.4 | 1.2 |  | 1313.315
89 | j481 | j483 | b.t road | 0.5 | 200 | 57.3 | 8991.7 | 1.2
90 | j480 | j477 |  | 0.5 | 200 | 70.6 | 9062.3 | 1.2
91 | j477 | j379 |  | 0.5 | 200 | 98.8 | 9161.1 | 1.2
92 | j379 | j376 |  | 0.5 | 200 | 45.6 | 9206.7 | 1.2
93 | j495 | j487 | b.t road | 0.46 | 160 | 87.8 | 9294.5 | 1.16
94 | j433 | j492 |  |  | 160 | 167.8 | 9462.3 | 1.16
95 | j433 | j442 | brick road | 0.46 | 160 | 27.1 | 9489.4 | 1.16
96 | j511 | j514 |  | 0.44 | 140 | 25.1 | 9514.5 | 1.14
97 | j511 | j514 | interlocking | 0.46 | 140 | 152.8 | 9667.3 | 1.14
98 | j447 | j442 |  |  | 140 | 20 | 9687.3 | 1.14
99 | j447 | j442 | brick road | 0.44 | 140 | 52 | 9739.3 | 1.14
100 | j24 | j12 |  |  | 110 | 122.7 | 9862 | 1.1
101 | j12 | j1 |  |  | 110 | 105.3 | 9967.3 | 1.1
102 | j77 | j92 |  |  | 110 | 77.8 | 10045.1 | 1.1
103 | j77 | j84 |  |  | 110 | 74.8 | 10119.9 | 1.1
104 | j570 | j590 |  |  | 110 | 106.4 | 10226.3 | 1.1
105 | j84 | j86 |  |  | 90 | 79.2 | 10305.5 | 1.09
106 | j489 | j490 |  |  | 63 | 32 | 10337.5 | 1.06
107 | j447a | j447b |  |  | 63 | 31 | 10368.5 | 1.06
108 | j456 | j457 |  |  | 63 | 21.1 | 10389.6 | 1.06
109 | j74 | j75 | interlocking | 0.46 | 63 | 97 | 10486.6 | 1.06
110 | j162 | j165 | b.t road | 0.36 | 63 | 298.7 | 10785.3 | 1.06
111 | j45 | j133 | b.t road | 0.36 | 63 | 133 | 10918.3 | 1.06
112 | j111 | j128 | b.t road | 0.36 | 63 | 238.4 | 11156.7 | 1.06
113 | j128 | j130 | b.t road | 0.36 | 63 | 11.2 | 11167.9 | 1.06
114 | j130 | j137 | b.t road | 0.36 | 63 | 44.5 | 11212.4 | 1.06
115 | j137 | j142 | b.t road | 0.36 | 63 | 45.5 | 11257.9 | 1.06
116 | j142 | j147 | b.t road | 0.36 | 63 | 22.3 | 11280.2 | 1.06
117 | j381 | j382 | b.t road | 0.44 | 140 | 6.2 | 11286.4 | 1.14
118 | j381 | j382 |  |  | 140 | 29.7 | 11316.1 | 1.14
119 | j382 | j386 |  |  | 140 | 34.3 | 11350.4 | 1.14
120 | j398 | j393 | brick road | 0.44 | 140 | 50.6 | 11401 | 1.14
121 | j401 | j414 | brick road | 0.36 | 63 | 6.5 | 11407.5 | 1.06
122 | j310 | j376 | b.t road | 0.5 | 200 | 6.9 | 11414.4 | 1.2
123 | j587 | j639 | b.t road | 0.36 | 63 | 3.5 | 11417.9 | 1.06
124 | j504 | j506 | b.t road | 0.36 | 63 | 7 | 11424.9 | 1.06
125 | j536 | j538 | b.t road | 0.36 | 63 | 6.5 | 11431.4 | 1.06
126 | j574 | j575 | culvert | 0.36 | 63 | 6.9 | 11438.3 | 1.06
127 | j7 | j7a |  |  | 63 | 302 | 11740.3 | 1.06
|  |  | 63 | 90 | 110 | 140 | 160 | 200
|  |  | 2611.5 | 258.1 | 858.7 | 1496.2 | 3547.3 | 2968.5 | 11740.3
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  | SIGN.with date
ROAD RESTORATION
TYPE OF ROAD | 63 | 75 | 90 | 110 | 140 | 160 | 200 | AVG WIDTH | Cummilative
brick road | 132.3 | 0 | 0 | 30.2 | 176.9 | 365.4 | 195.9 | 0.416 | 374.6912
b.t road | 829.3 | 0 | 0 | 5 | 212.4 | 99.6 | 2507.9 | 0.461 | 1684.5862
interlocking | 453.5 | 0 | 0 | 0 | 152.8 | 0 | 0 | 0.36 | 218.268
cc | 715.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.466 | 333.423
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  | SIGN.with date

## madhura arani ganj 4
GOVERNMENT OF UTTAR PRADESH
STATE WATER & SANITATION MISSION ( SWSM )
Joint Measurement Report of Pipe Line
Name of the Work :- Survey , Design Preparation of DPR , Construction , Commissioning and O&M for 10 Years of Various Rural Water Supply Projects in the state of Uttar Pradesh as Per Request for Proposal for Division " Prayagraj "
Name of the Agency : POWER MECH PROJECTS LIMITED – BHOORATHNOM CONSTRUCTIONS COMPANY PRIVATE LIMITED (JV), Hyderabad.
Name OF Scheme |  | :madhura rani ganj
Block |  | : Mangraura
Total Scope |  | :
JMR No. |  | : 1
Date of JMR |  | :
Sr. No. | Start Node | End Node | Dia | Pipe Length (as per Drawing) | Pipe Length (as per Site) | Width | Depth | Quantity | Type OF Road | Dismantling Length | Dismantling Width | Dismantling Quantity | Restoration Length | Restoration Width | Restoration Quantity | Restoration Status | Remark
1 | OHT | j1(1) | 250 |  | 368 | 0.55 | 1.25
2 | j1(1) | j1 | 200 |  | 272 | 0.5 | 1.2
3 | j1(1) | j2 | 200 |  | 26 | 0.5 | 1.2 |  | brick road | 0.5 | 26 | 13 | 0.5 | 26 | 13 | done
4 | j2 | j23 | 200 |  | 106 | 0.5 | 1.2
5 | j590 | j592 | 63 |  | 219 | 0.36 | 1.06
6 | j162 | j230 | 63 |  | 525 | 0.36 | 1.06
7 | j38 | j138 | 63 |  | 325.4 | 0.36 | 1.06
8 | j21 | j22 | 63 |  | 300 | 0.36 | 1.06 | [11 empty] | 22411
9 | j44 | j44(1) | 63 |  | 156.2 | 0.36 | 1.06 | [10 empty] | 22447.5
10 | j112 | j112(1) | 63 |  | 205.3 | 0.36 | 1.06 | [10 empty] | 11740.3 | 36545.2
[5 empty] | 2502.9 | [12 empty] | 2502.9
Representative PMPL - BRCCPL (JV) Pratapgarh | [6 empty] | Representative Medhaj Techno Concept Pvt Ltd (TPI) Pratapgarh |  |  |  |  | Representative UP Jal Nigam (Rural) Pratapgarh | [5 empty] | 36690.7