## UTRAS
UTRAS(JMR) BLOCK-MANGRAURA AGENCY-RAMPRABAV CONTRACTOR
s.no | Start Node | End Node | Type of Road | WIDTH OF EXCAVATION | Dia of pipe (MM) | Pipe Length (M) | CUMMULATIVE
1 | J86 | J87 |  |  | 63 | 42.6 | 42.6
2 | J86 | J87 | B.T ROAD | 0.363 | 63 | 3 | 45.6
3 | J106 | J116 |  |  | 63 | 157.7 | 203.3
4 | J116 | J127 |  |  | 63 | 184.8 | 388.1
5 | J127 | J136 |  |  | 63 | 61.9 | 450
6 | J116 | J117 |  |  | 63 | 226.7 | 676.7
7 | J117 | J156 |  |  | 63 | 236.9 | 913.6
8 | J117 | J156 | B.T ROAD | 0.363 | 63 | 3.1 | 916.7
9 | J156 | J290 | B.T ROAD | 0.363 | 63 | 4.8 | 921.5
10 | J156 | J290 |  |  | 63 | 185.5 | 1107
11 | J156 | J290 | CULVERT |  | 63 | 7 | 1114
12 | J156 | J290 |  |  | 63 | 122 | 1236
13 | J291 | J292 |  |  | 63 | 155 | 1391
14 | J291 | J289 | BRICK ROAD | 0.363 | 63 | 2.8 | 1393.8
15 | J291 | J289 |  |  | 63 | 235 | 1628.8
16 | J305 | J297 |  |  | 63 | 25.7 | 1654.5
17 | J297 | J298 |  |  | 63 | 20 | 1674.5
18 | J298 | J304 | BRICK ROAD | 0.363 | 63 | 6.2 | 1680.7
19 | J298 | J272 |  |  | 63 | 97.5 | 1778.2
20 | J298 | J272 | CULVERT |  | 63 | 3.4 | 1781.6
21 | J298 | J272 |  |  | 63 | 104 | 1885.6
22 | J310 | J320 |  |  | 63 | 104.5 | 1990.1
23 | J322 | J324 | B.T ROAD | 0.363 | 63 | 7 | 1997.1
24 | J322 | J324 |  |  | 63 | 59.1 | 2056.2
25 | J324 | J323 |  |  | 63 | 420.9 | 2477.1
26 | J324 | J323 | B.T ROAD | 0.363 | 63 | 7.7 | 2484.8
27 | J324 | J323 |  |  | 63 | 33 | 2517.8
28 | J320 | J307 |  |  | 63 | 272 | 2789.8
29 | J130 | J126 |  |  | 63 | 271.4 | 3061.2
30 | J199 | J221 |  |  | 63 | 124.1 | 3185.3
31 | J230 | J221 |  |  | 63 | 25.7 | 3211
32 | J230 | J221 | BRICK ROAD | 0.363 | 63 | 25.3 | 3236.3
33 | J230 | J221(1) | BRICK ROAD | 0.363 | 63 | 72.9 | 3309.2
34 | J221 | J228 |  |  | 63 | 47.3 | 3356.5
35 | J199 | J201 | BRICK ROAD | 0.363 | 63 | 3 | 3359.5
36 | J199 | J201 |  |  | 63 | 99 | 3458.5
37 | J201 | J204 |  |  | 63 | 36.9 | 3495.4
38 | J239 | J237 |  |  | 63 | 33.3 | 3528.7
39 | J237 | J238 |  |  | 63 | 22.3 | 3551
40 | J237 | J236 |  |  | 63 | 128.8 | 3679.8
41 | J236 | J226 |  |  | 63 | 161.3 | 3841.1
42 | J236 | J226 | BRICK ROAD | 0.363 | 63 | 3.4 | 3844.5
43 | J117 | J101 |  |  | 63 | 131.3 | 3975.8
44 | J101 | J100 |  |  | 63 | 26.7 | 4002.5
45 | J101 | J92 |  |  | 63 | 51 | 4053.5
46 | J92 | J79 | B.T ROAD | 0.363 | 63 | 3 | 4056.5
47 | J92 | J79 |  |  | 63 | 209 | 4265.5
48 | J79 | J80 | B.T ROAD | 0.363 | 63 | 3.4 | 4268.9
49 | J79 | J80 |  |  | 63 | 307.6 | 4576.5
50 | J80 | J82 |  |  | 63 | 222.3 | 4798.8
51 | J80 | J52 |  |  | 63 | 378.6 | 5177.4
52 | J52 | J53 |  |  | 63 | 343.2 | 5520.6
53 | J52 | J40 |  |  | 63 | 478.1 | 5998.7
54 | J41 | J81 |  |  | 63 | 340.9 | 6339.6
55 | J81 | J103 |  |  | 63 | 624 | 6963.6
56 | J103(1) | J103(2) |  |  | 63 | 129.8 | 7093.4
57 | J103 | J104 |  |  | 63 | 181.8 | 7275.2
58 | J124 | J125 |  |  | 63 | 131 | 7406.2
59 | J72 | J51 |  |  | 63 | 53 | 7459.2
60 | J51 | J37 |  |  | 63 | 11 | 7470.2
61 | J37 | J73 |  |  | 63 | 25 | 7495.2
62 | J73 | J84 |  |  | 63 | 14 | 7509.2
63 | J84 | J88 |  |  | 63 | 7.6 | 7516.8
64 | J88 | J93 |  |  | 63 | 141.4 | 7658.2
65 | J88 | J93 | BRICK ROAD | 0.363 | 63 | 6 | 7664.2
66 | J179 | J183 |  |  | 63 | 60 | 7724.2
67 | J183 | J185 |  |  | 63 | 90 | 7814.2
68 | J185 | J187 |  |  | 63 | 80 | 7894.2
69 | J183 | J184 |  |  | 63 | 35 | 7929.2
70 | J183 | J184 | B.T ROAD | 0.363 | 63 | 4 | 7933.2
71 | J183 | J181 |  |  | 63 | 191 | 8124.2
72 | J198 | J202 |  |  | 63 | 21 | 8145.2
73 | J202 | J209 |  |  | 63 | 42 | 8187.2
74 | J198 | J197 | BRICK ROAD | 0.363 | 63 | 15.4 | 8202.6
75 | J198 | J197 |  |  | 63 | 100 | 8302.6
76 | J198(1) | J197(1) |  |  | 63 | 17 | 8319.6
77 | J191 | J193 | BRICK ROAD | 0.363 | 63 | 26.4 | 8346
78 | J197 | J207 | BRICK ROAD | 0.363 | 63 | 23.5 | 8369.5
79 | J197 | J207 |  |  | 63 | 10 | 8379.5
80 | J207 | J209 | BRICK ROAD | 0.363 | 63 | 27.2 | 8406.7
81 | J209 | J213 |  |  | 63 | 52.9 | 8459.6
82 | J213 | J212 |  |  | 63 |  | 8459.6
83 | J212 | J220 |  |  | 63 |  | 8459.6
84 | J220 | J222 |  |  | 63 |  | 8459.6
85 | J222 | J225 | BRICK ROAD | 0.363 | 63 | 171.2 | 8630.8
86 | J225 | J223 | BRICK ROAD | 0.363 | 63 | 69.3 | 8700.1
87 | J150 | J114 | BRICK ROAD | 0.363 | 63 | 148.9 | 8849
88 | J114 | J83 | BRICK ROAD | 0.363 | 63 | 162.3 | 9011.3
89 | J33 | J68 |  |  | 63 | 13.4 | 9024.7
90 | J68 | J64 |  |  | 63 | 36 | 9060.7
91 | J64 | J41 |  |  | 63 | 144 | 9204.7
92 | J41 | J104 |  |  | 63 | 173 | 9377.7
93 | J92 | J86 |  |  | 75 | 263.2 | 9640.9
94 | J86 | J78 |  |  | 75 | 119.9 | 9760.8
95 | J106 | J111 |  |  | 75 | 77 | 9837.8
96 | J136 | J126 |  |  | 75 | 147.5 | 9985.3
97 | J111 | J106 |  |  | 75 | 80.4 | 10065.7
98 | J289 | J294 | BRICK ROAD | 0.375 | 75 | 66.1 | 10131.8
99 | J297 | J294 | BRICK ROAD | 0.375 | 75 | 46.8 | 10178.6
100 | J305 | J308 |  |  | 75 | 38.2 | 10216.8
101 | J308 | J310 | BRICK ROAD | 0.375 | 75 | 4 | 10220.8
102 | J308 | J310 |  |  | 75 | 33.2 | 10254
103 | J136 | J156 |  |  | 75 | 268 | 10522
104 | J104 | J124 |  |  | 75 | 65 | 10587
105 | J104 | J124 |  |  | 75 | 266 | 10853
106 | J124 | J138 |  |  | 75 | 195.8 | 11048.8
107 | J158 | J169 |  |  | 75 | 74.3 | 11123.1
108 | J169 | J176 |  |  | 75 | 64 | 11187.1
109 | J176 | J177 |  |  | 75 | 33.4 | 11220.5
110 | J177 | J179 |  |  | 75 | 58 | 11278.5
111 | J125 | J83 |  |  | 90 | 536.9 | 11815.4
112 | J83 | J26 |  |  | 90 | 111.8 | 11927.2
113 | J78 | J106 |  |  | 90 | 166.3 | 12093.5
114 | J289 | J294 |  |  | 90 | 70 | 12163.5
115 | J139 | J142 | BRICK ROAD | 0.39 | 90 | 55.8 | 12219.3
116 | J142 | J146 | BRICK ROAD | 0.39 | 90 | 45.4 | 12264.7
117 | J146 | J150 | BRICK ROAD | 0.39 | 90 | 67.2 | 12331.9
118 | J150 | J114 |  |  | 90 | 190 | 12521.9
119 | J104 | J41 |  |  | 90 | 137.1 | 12659
120 | J130 | J139 |  |  | 110 | 282.3 | 12941.3
121 | J130 | J139 | BRICK ROAD | 0.41 | 110 | 46.7 | 12988
122 | j266 | j261 |  | 0.41 | 110 | 33 | 13021
123 | j261 | j259 |  | 0.41 | 110 | 63.9 | 13084.9
124 | j261 | j259 | BOE road | 0.41 | 110 | 4.5 | 13089.4
125 | j261 | j259 | CC road | 0.41 | 110 | 4.5 | 13093.9
126 | j259 | j260 |  | 0.41 | 110 | 141.5 | 13235.4
127 | j260 | j265 |  | 0.41 | 110 | 17 | 13252.4
128 | j265 | j277 |  | 0.375 | 75 | 64 | 13316.4
129 | j265 | j277 | BOE | 0.375 | 75 | 64 | 13380.4
130 | j277 | j280 |  | 0.363 | 63 | 31.6 | 13412
131 | j280 | j285 |  | 0.363 | 63 | 165 | 13577
132 | j285 | j286 |  | 0.363 | 63 | 133 | 13710
133 | j265 | j269 | BOE | 0.363 | 63 | 41.6 | 13751.6
134 | j269 | j295 |  | 0.363 | 63 | 150 | 13901.6
135 | j259 | j257 |  | 0.41 | 110 | 53 | 13954.6
136 | j257 | j257 | CC road | 0.363 | 63 | 4 | 13958.6
137 | j257 | j258 |  | 0.363 | 63 | 110.2 | 14068.8
138 | j258 | j274 |  | 0.363 | 63 | 154.1 | 14222.9
139 | j274 | j666 |  | 0.41 | 110 | 154 | 14376.9
140 | j257 | j245 |  | 0.41 | 110 | 125.6 | 14502.5
141 | j245 | j240 |  | 0.44 | 140 | 16.5 | 14519
142 | j240 | j246 |  | 0.363 | 63 | 85 | 14604
143 | j246 | j247 |  | 0.363 | 63 | 160 | 14764
144 | j246 | j249 |  | 0.363 | 63 | 60 | 14824
145 | j249 | j251 |  | 0.363 | 63 | 55 | 14879
146 | j326 | j328 |  | 0.363 | 63 | 105 | 14984
147 | j331 | j332 |  | 0.363 | 63 | 100 | 15084
148 | j331 | j333 |  | 0.363 | 63 | 17 | 15101
149 | j333 | j335 |  | 0.363 | 63 | 17 | 15118
150 | j335 | j337 |  | 0.363 | 63 | 240 | 15358
151 | j331 | j329 |  | 0.363 | 63 | 60 | 15418
152 | j329 | j326 |  | 0.363 | 63 | 103 | 15521
153 | j326 | j324 |  | 0.363 | 63 | 71.4 | 15592.4
154 | j326 | j324 | BT road | 0.363 | 63 | 7 | 15599.4
155 | j307 | j316 |  | 0.363 | 63 | 240 | 15839.4
156 | j307 | j316 | BT raod | 0.363 | 63 | 6.9 | 15846.3
157 | j322 | j295 |  | 0.363 | 63 | 200 | 16046.3
158 | j321 | j313 | BOE | 0.363 | 63 | 120 | 16166.3
159 | j321 | j313 |  | 0.363 | 63 | 195 | 16361.3
160 | j313 | j313 | BT road | 0.363 | 63 | 3 | 16364.3
161 | j304 | j272 |  | 0.363 | 63 | 208 | 16572.3
162 | j272 | j270 |  | 0.375 | 75 | 35 | 16607.3
163 | j220 | j267 |  | 0.375 | 75 | 33 | 16640.3
164 | j267 | j266 |  | 0.375 | 75 | 18 | 16658.3
165 | j241 | j242 |  | 0.363 | 63 | 29.4 | 16687.7
166 | j298 | j301 | BOE | 0.363 | 63 | 52.1 | 16739.8
167 | j298 | j301 |  | 0.363 | 63 | 30.2 | 16770
168 | j301 | j302 |  | 0.363 | 63 | 13.3 | 16783.3
169 | j297 | j296 |  | 0.363 | 63 | 32.2 | 16815.5
170 | j296 | j279 |  | 0.363 | 63 | 60.5 | 16876
171 | j296 | j286 |  | 0.363 | 63 | 20 | 16896
172 | j289 | j283 | BOE | 0.39 | 90 | 27 | 16923
173 | j283 | j287 | BOE | 0.41 | 110 | 19.4 | 16942.4
174 | j287 | j299 | BOE | 0.41 | 110 | 33 | 16975.4
175 | j310 | j311 | BOE | 0.363 | 63 | 17.8 | 16993.2
176 | j308 | j309 | BOE | 0.363 | 63 | 33 | 17026.2
177 | j308 | j309 |  | 0.363 | 63 | 27 | 17053.2
178 | j52 | j3 |  | 0.375 | 75 | 319.2 | 17372.4
179 | j79 | j56 |  | 0.363 | 63 | 46 | 17418.4
180 | j56 | j3 |  | 0.375 | 75 | 330 | 17748.4
181 | j78 | j3 |  | 0.46 | 160 | 231 | 17979.4
182 | j3 | j3 | BT road | 0.46 | 160 | 3.7 | 17983.1
183 | j3 | j1 |  | 0.46 | 160 | 250 | 18233.1
184 | j1 | j2 |  | 0.46 | 160 | 230.3 | 18463.4
185 | j2 | j4 | BT road | 0.46 | 160 | 5.5 | 18468.9
186 | j2 | j4 |  | 0.46 | 160 | 93.8 | 18562.7
187 | j4 | j6 |  | 0.41 | 110 | 39 | 18601.7
188 | j6 | j20 |  | 0.41 | 110 | 96 | 18697.7
189 | j20 | j41 |  | 0.41 | 110 | 62.5 | 18760.2
190 | j20 | j38 | BOE | 0.363 | 63 | 25 | 18785.2
191 | j20 | j38 |  | 0.363 | 63 | 23 | 18808.2
192 | j38 | j39 |  | 0.363 | 63 | 25 | 18833.2
193 | j38 | j54 |  | 0.363 | 63 | 40 | 18873.2
194 | j41 | j41 | BT road | 0.41 | 110 | 4 | 18877.2
195 | j41 | j81 |  | 0.363 | 63 | 342 | 19219.2
196 | j64 | j61 |  | 0.363 | 63 | 52.7 | 19271.9
197 | j54 | j55 | interlock | 0.363 | 63 | 95.9 | 19367.8
198 | j33 | j32 |  | 0.363 | 63 | 71.4 | 19439.2
199 | j32 | j30 |  | 0.363 | 63 | 112.6 | 19551.8
200 | j28a | j28b |  | 0.363 | 63 | 69 | 19620.8
201 | j28b | j28b | BT road | 0.363 | 63 | 3 | 19623.8
202 | j26 | j21 |  | 0.46 | 160 | 41.5 | 19665.3
203 | j21 | j24 |  | 0.363 | 63 | 35.3 | 19700.6
204 | j24 | j29 | BOE | 0.363 | 63 | 39.6 | 19740.2
205 | j29 | j31 |  | 0.363 | 63 | 31.4 | 19771.6
206 | j24 | j24 | BT road | 0.363 | 63 | 4.2 | 19775.8
207 | j24a | j24b |  | 0.363 | 63 | 145.7 | 19921.5
208 | j21 | j18 |  | 0.46 | 160 | 47 | 19968.5
209 | j18 | j17 |  | 0.46 | 160 | 32 | 20000.5
210 | j17 | j12 |  | 0.46 | 160 | 59.1 | 20059.6
211 | j21 | j18 | interlock | 0.46 | 160 | 4 | 20063.6
212 | j18 | j19 |  | 0.363 | 63 | 28.9 | 20092.5
213 | j12 | j51 |  | 0.363 | 63 | 51 | 20143.5
214 | j51 | j22 |  | 0.363 | 63 | 50 | 20193.5
215 | j51 | j51 | BT road | 0.363 | 63 | 4 | 20197.5
216 | j22 | j23 |  | 0.363 | 63 | 31 | 20228.5
217 | j22 | j16 |  | 0.363 | 63 | 19.9 | 20248.4
218 | j16a | j16b |  | 0.363 | 63 | 17 | 20265.4
219 | j16 | j14 |  | 0.363 | 63 | 39.1 | 20304.5
220 | j14 | j13 |  | 0.363 | 63 | 15.9 | 20320.4
221 | j14 | j15 |  | 0.363 | 63 | 66 | 20386.4
222 | j37 | j48 |  | 0.363 | 63 | 72.5 | 20458.9
223 | j48 | j44 |  | 0.363 | 63 | 208 | 20666.9
224 | j44 | j47 |  | 0.363 | 63 | 65 | 20731.9
225 | j42 | j43 |  | 0.363 | 63 | 73 | 20804.9
226 | j43a | j43b |  | 0.363 | 63 | 136 | 20940.9
227 | j73 | j57 | BOE | 0.363 | 63 | 93.9 | 21034.8
228 | j57 | j58 | BOE | 0.363 | 63 | 19.7 | 21054.5
229 | j57 | j58 |  | 0.363 | 63 | 7 | 21061.5
230 | j58 | j59 |  | 0.363 | 63 | 15.4 | 21076.9
231 | j88 | j102 |  | 0.363 | 63 | 85.4 | 21162.3
232 | j88 | j102 | BOE | 0.363 | 63 | 4 | 21166.3
233 | j97 | j102 | BOE | 0.46 | 160 | 70 | 21236.3
234 | j102 | j107 | BOE | 0.46 | 160 | 56 | 21292.3
235 | j107 | j108 |  | 0.363 | 63 | 53.9 | 21346.2
236 | j108 | j110 |  | 0.363 | 63 | 55 | 21401.2
237 | j108 | j109 |  | 0.363 | 63 | 42.9 | 21444.1
238 | j107 | j130 | BOE | 0.46 | 160 | 278.6 | 21722.7
239 | j130 | j149 | BOE | 0.46 | 160 | 217.9 | 21940.6
240 | j149 | j155 |  | 0.363 | 63 | 80 | 22020.6
241 | j149 | j151 | BOE | 0.363 | 63 | 57.3 | 22077.9
242 | j151 | j165 | BOE | 0.363 | 63 | 76.7 | 22154.6
243 | j151 | j165 |  | 0.363 | 63 | 115.3 | 22269.9
244 | j154 | j170 |  | 63.44 | 63 | 115.2 | 22385.1
245 | j170 | j175 |  | 63.44 | 63 | 60 | 22445.1
246 | j175 | j206 |  | 63.44 | 63 | 96 | 22541.1
247 | j206 | j214 |  | 0.44 | 140 | 33 | 22574.1
248 | j214 | j234 |  | 0.44 | 140 | 56.3 | 22630.4
249 | j234 | j235 |  | 0.44 | 140 | 180.3 | 22810.7
250 | j111 | j112 |  | 0.363 | 63 | 35.2 | 22845.9
251 | j111 | j120 | BOE | 0.375 | 75 | 115.2 | 22961.1
252 | j120 | j126 |  | 0.375 | 75 | 60 | 23021.1
253 | j126 | j132 |  | 0.363 | 63 | 38.5 | 23059.6
254 | j126 | j132 | BT road | 0.363 | 63 | 4 | 23063.6
255 | j126 | j129 |  | 0.363 | 63 | 282 | 23345.6
256 | j129 | j130 |  | 0.363 | 63 | 282 | 23627.6
257 | j78 | j89 |  | 0.46 | 160 | 226.3 | 23853.9
#REF! | j12 | j11 | BOE | 0.46 | 160 | 26 | 23879.9
#REF! | j11 | j9 | interlock | 0.46 | 160 | 47 | 23926.9
#REF! | j9 | j7 | interlock | 0.46 | 160 | 27 | 23953.9
#REF! | j7 | j8 |  | 0.363 | 63 | 145 | 24098.9
#REF! | j34 | j32 | BOE | 0.363 | 63 | 51.9 | 24150.8
#REF! | j7 | j2 | interlock | 0.46 | 160 | 80.1 | 24230.9
#REF! | j7 | j2 |  | 0.46 | 160 | 63.6 | 24294.5
#REF! | j2 | j2 | BT road | 0.46 | 160 | 4.2 | 24298.7
#REF! | j2 | j40 | BOE | 0.39 | 90 | 312 | 24610.7
#REF! | j40 | j63 | BOE | 0.375 | 75 | 218 | 24828.7
#REF! | j63 | j65 |  | 0.363 | 63 | 59.6 | 24888.3
#REF! | j63 | j69 | BOE | 0.363 | 63 | 104.7 | 24993
#REF! | j69 | j71 |  | 0.363 | 63 | 76.8 | 25069.8
#REF! | j71 | j75 |  | 0.363 | 63 | 82.3 | 25152.1
#REF! | j69 | j70 |  | 0.363 | 63 | 44.6 | 25196.7
#REF! | j176 | j196 | BOE | 0.363 | 63 | 282.7 | 25479.4
#REF! | j158 | j192 |  | 0.375 | 75 | 99 | 25578.4
#REF! | j158 | j192 | BOE | 0.375 | 75 | 50 | 25628.4
#REF! | j158 | j125 |  | 0.39 | 90 | 196.5 | 25824.9
#REF! | j150 | j199 | BOE | 0.39 | 90 | 198 | 26022.9
#REF! | j199 | j210 |  | 0.39 | 90 | 113.4 | 26136.3
#REF! | j210 | j226 | BOE | 0.39 | 90 | 110 | 26246.3
#REF! | j226 | j222 | BOE | 0.375 | 75 | 150 | 26396.3
#REF! | j226 | j222 |  | 0.375 | 75 | 155 | 26551.3
#REF! | j223 | j224 |  | 0.363 | 63 | 80 | 26631.3
#REF! | j223 | j217 |  | 0.363 | 63 | 28.7 | 26660
#REF! | j139 | j144 |  | 0.363 | 63 | 119.8 | 26779.8
#REF! | j144 | j145 |  | 0.363 | 63 | 98.5 | 26878.3
#REF! | j146 | j144 |  | 0.363 | 63 | 71.2 | 26949.5
#REF! | j236 | j254 |  | 0.363 | 63 | 623 | 27572.5
| 63 | 75 | 90 | 110 | 140 | 160
| 18063.3 | 3611.2 | 2337.4 | 1179.9 | 286.1 | 2094.6 |  | 27572.5
Abstract (Bill Breakup)
1 | Dia of Pipe | WO/DPR Qty's | Laying, Jointing, Backfilling - 60% |  |  |  | Gap Closing- 5% |  |  |  | Hydro Test - 15% |  |  |  | FHTC Stretch - 10%
|  |  | Laying Up to Date | Laying Qty Billed up to Date | Qty Billed Up to Previous | This Bill Qty (Laying) | WO/DPR Qty's | GAP Closing Billed Qty up to Date | GAP Closing Qty Up to Previous | This Bill Qty (GAP Closing) | WO/DPR Qty's | Hydro Test Qty Billed up to Date | Hydro Test Qty Up to Previous | This Bill Qty (Hydro Test ) | FHTC Stretch Qty Billed up to Date | FHTC Stretch Qty Billed Up to Previous | This Bill Qty (FHTC Stretch Billed )
1.1 | 63 mm HDPE |  | 18063.3 | 18063.3 | 15653 | 2410.3
1.2 | 75 mm HDPE |  | 3611.2 | 3611.2 | 2991 | 620.2
1.3 | 90 mm HDPE |  | 2337.4 | 2337.4 | 2286 | 51.4
1.4 | 110mm HDPE |  | 1179.9 | 1179.9 | 1098 | 81.9
1.5 | 125mm HDPE |  |  | 0 |  | 0
1.6 | 140mm HDPE |  | 286.1 | 286.1 |  | 286.1
1.7 | 160mm HDPE |  | 2094.6 | 2094.6 | 1560 | 534.6
1.8 | 180mm HDPE
1.9 | 200mm HDPE
Sub Total = |  |  | 27572.5 | 27572.5 | 23588 | 3984.5
Sub-Contractor Site Engineer (Sr.Eng/ DY.M-SMX ) (Dy.M-PMX ) AGM Project Incharge

## Recon Sheet
POWER MECH PROJECTS.LIMITED | [11 empty] | FHTC
RURAL WATER SUPPLY PROJECT UNDER JJM, UP - PRAYAGRAJ
Reconciliation Statement - Issued Vs Certification Qty.
| Contractor Name-RAMPRAV CONSTRUCTION |  | MONTH: | sept | Block: | mangraura
| ABC Limited |  | BILL NO: |  | GP: | UTRAS
Sl NO | Description | Units |  |  |  |  | Balance Qty | SAP Entry | Remarks | Upto date Consumption
|  |  | Total Issued Qty | Cumulative Consumption | Upto Pre Consumed Qty | This Bill Consumed Qty |  |  |  | GP | GP | GP | GP | Total Consumption upto This Bill |  | Entry Qty
A | HDPE Pipe :- | [8 empty] | BLOCK | BLOCK | BLOCK | BLOCK
1 | HDPE PIPE-63MM,PN-6,CLASS:PE-100,IS:4984 | Rmt | 18081 | 18063.3 | 15653 | 2410.3 |  | 4474 | [5 empty] | 0 | 1200000251 | #REF! | -17.7
2 | HDPE PIPE-75MM,PN-6,CLASS:PE-100 | Rmt | 3850 | 3611.2 | 2991 | 620.2 | [7 empty] | 0 | 1200000332 | #REF!
3 | HDPE PIPE-90MM,PN-6,CLASS:PE-100 | Rmt | 2490 | 2337.4 | 2286 | 51.4 | [7 empty] | 0 | 1200000333 | #REF!
4 | HDPE PIPE-110MM,PN-6,CLASS:PE-100 | Rmt | 1185 | 1179.9 | 1098 | 81.9 | [7 empty] | 0 | 1200000334 | -1098
5 | HDPE PIPE-125MM,PN-6,CLASS:PE-100,IS4984 | Rmt |  | 0 |  | 0 | [7 empty] | 0 | 1200000252 | 0
6 | HDPE PIPE-140MM,PN-6,CLASS:PE-100,IS4984 | Rmt | 540 | 286.1 |  | 286.1 | [7 empty] | 0 | 1200000253 | 0
7 | HDPE PIPE-160MM,PN-6,CLASS:PE-100 | Rmt | 2100 | 2094.6 | 1560 | 534.6 | [7 empty] | 0 | 1200000335 | -1560 | -5.4
8 | HDPE PIPE-200MM,PN-6,CLASS:PE-100,IS4984 | Rmt | 84 |  |  | 0 | [7 empty] | 0 | 1200000255 | 0
9 | DI PIPE-Ø200MM , K7,IS:8329 | Rmt |  |  |  | 0 | [7 empty] | 0 | 900007097 | 0
10 | HDPE PIPE-250MM,PN-6,CLASS:PE-100,IS4984 | Rmt |  |  |  | 0 | [7 empty] | 0 | 1200000256 | 0
| Total Qty In ( Rmt ) = |  | 28330 | 27572.5 | 23588 | 3984.5
B | Specials :-
| Equal Tee | [12 empty] | 0 |  | 0
1 | HDPE-63X63X63MM,PN-6,R-TEE,CLASS:PE-100 | Nos | 50 | 49 |  | 31 |  | 4474 | [5 empty] | 0 | 200030286 | 0
2 | HDPE-75X75X75MM,PN-6,R-TEE,CLASS:PE-100 | Nos | 30 | 10 |  | 9 | [7 empty] | 0 | 200030287 | 0
3 | HDPE-90X90X90MM,PN-6,R-TEE,CLASS:PE-100 | Nos | 25 | 3 |  | 3 | [7 empty] | 0 | 200030288 | 0
4 | HDPE-110X110X110MM,PN-6,R-TEE,CL:PE-100 | Nos | 10 | 4 |  | 4 | [7 empty] | 0 | 200030289 | 0
5 | HDPE 125mm X 125mm X 125mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032212 | 0
6 | HDPE-140X140X140MM,PN-6,R-TEE,CL:PE-100 | Nos | 1 | [10 empty] | 0 | 200030291 | 0
7 | HDPE-160X160X160MM,PN-6,R-TEE,CL:PE-100 | Nos | 2 | 2 |  | 2 | [7 empty] | 0 | 200030293 | 0
8 | HDPE 200X200X200 MM, PN-6, R-TEE, CLASS: | Nos | [11 empty] | 0 | 200030300 | 0
| Total Qty In ( Rmt ) = |  | 118
C | Branch TEE | [14 empty] | 0
1 | HDPE BRANCH TEE 63MM X 63MM X 50MM | Nos | 4 |  |  |  |  | 4474 | [5 empty] | 0 | 200032593 | 0
2 | HDPE 75MM X 75MM X 50MM PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032575 | 0
3 | HDPE 75mm X 75mm X 63mm PN6 TEE PE100 | Nos | 5 | 3 |  | 3 | [7 empty] | 0 | 200032202 | 0
4 | HDPE 90mm X 90mm X 50mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032233 | 0
5 | HDPE 90mm X 90mm X 63mm, PN6 TEE PE100 | Nos | 20 | 7 |  | 7 | [7 empty] | 0 | 200032203 | 0
6 | HDPE 90mm X 90mm X 75mm PN6 TEE PE100 | Nos | 5 | 2 |  | 2 | [7 empty] | 0 | 200032204 | 0
7 | HDPE 110mm X 110mm X 50mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032234 | 0
8 | HDPE 110mm X 110mm X 63mm PN6 TEE PE100 | Nos | 10 | [10 empty] | 0 | 200032205 | 0
9 | HDPE 110mm X 110mm X 75mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032206 | 0
10 | HDPE 110mm X 110mm X 90mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032207 | 0
11 | HDPE 125mm X 125mm X 50mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032235 | 0
12 | HDPE 125mm X 125mm X 63mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032208 | 0
13 | HDPE 125mm X 125mm X 75mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032209 | 0
14 | HDPE 125mm X 125mm X 90mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032210 | 0
15 | HDPE 125mm X 125mm X 110mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032211 | 0
16 | HDPE Branch TEE 140mm X 140mm X 50mm | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032236 | 0
17 | HDPE 140mm X 140mm X 63mm PN6 TEE PE100 | Nos | 2 | [10 empty] | 0 | 200032213 | 0
18 | HDPE 140mm X 140mm X 75mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032214 | 0
19 | HDPE 140mm X 140mm X 110mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032215 | 0
20 | HDPE Branch TEE 140mm X 140mm X 125mm | Nos | [11 empty] | 0 | 200032216 | 0
21 | HDPE-140X90X140MM,PN-6,R-TEE,CL:PE-100 | Nos | [11 empty] | 0 | 200030290 | 0
22 | HDPE 160mm X 160mm X 50mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032237 | 0
23 | HDPE 160mm X 160mm X 63mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032217 | 0
24 | HDPE 160mm X 160mm X 75mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032218 | 0
25 | HDPE 160mm X 160mm X 90mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032219 | 0
26 | HDPE-160X110X160MM,PN-6,R-TEE,CL:PE-100 | Nos | [11 empty] | 0 | 200030292 | 0
27 | HDPE 160mm X 160mm X 125mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032220 | 0
28 | HDPE 200mm X 200mm X 63mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032222 | 0
29 | HDPE 200X75X200 MM, PN-6, R-TEE, CLASS:P | Nos | [11 empty] | 0 | 200030297 | 0
30 | HDPE 200X90X200 MM, PN-6, R-TEE, CLASS:P | Nos | [11 empty] | 0 | 200030298 | 0
31 | HDPE 200mm X 200mm X 110mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032223 | 0
32 | HDPE 200mm X 200mm X 160mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032225 | 0
33 | HDPE 250mm X 250mm X 90mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032228 | 0
| Total Qty In ( Rmt ) = |  | 46
D | 4 Way Tee | [14 empty] | 0
1 | HDPE 63MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | 5 |  |  |  |  | 4474 | [5 empty] | 0 | 200030301 | 0
2 | HDPE 75MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | 5 | 3 |  | 3 | [7 empty] | 0 | 200030302 | 0
3 | HDPE 90MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030303 | 0
4 | HDPE 110MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [11 empty] | 0 | 200030304 | 0
5 | HDPE125MM,PN6,4WAY CROSS FITTING,CLPE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032584 | 0
6 | HDPE 140MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [11 empty] | 0 | 200030305 | 0
7 | HDPE 160MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030306 | 0
8 | HDPE200MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [11 empty] | 0 | 200030308 | 0
Total Qty In ( No's ) =
E | Reducers
1 | HDPE-75MM,PN6, 63MM,ENLARGER,CLASS:PE100 | Nos | 15 | 3 |  | 3 |  | 4474 | [5 empty] | 0 | 200030309 | 0
2 | HDPE-90MM,PN6, 63MM,ENLARGER,CLASS:PE100 | Nos | 10 | [10 empty] | 0 | 200030311 | 0
3 | HDPE-90MM,PN6, 75MM,ENLARGER,CLASS:PE100 | Nos | [11 empty] | 0 | 200030310 | 0
4 | HDPE-110MM,PN6,63MM,ENLARGER,CLASS:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030314 | 0
5 | HDPE-110MM,PN6,75MM,ENLARGER,CLASS:PE100 | Nos | 5 | [10 empty] | 0 | 200030312 | 0
6 | HDPE-110MM,PN6,90MM,ENLARGER,CLASS:PE100 | Nos | [11 empty] | 0 | 200030313 | 0
7 | HDPE-125MM,PN6, 63MM Reducer PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032241 | 0
8 | HDPE-125MM,PN6, 75MM Reducer PE100 | Nos | [11 empty] | 0 | 200032239 | 0
9 | HDPE-125MM,PN6, 90MM Reducer PE100 | Nos | [11 empty] | 0 | 200032240 | 0
10 | HDPE-125MM,PN6, 110MM Reducer PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032242 | 0
11 | HDPE-140MM,PN6,63MM,ENLARGER,CL:PE100 | Nos | [11 empty] | 0 | 200030320 | 0
12 | HDPE-140MM,PN6, 75MM Reducer PE100 | Nos | [11 empty] | 0 | 200032243 | 0
13 | HDPE-140MM,PN6,90MM,ENLARGER,CL:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030317 | 0
14 | HDPE-140MM,PN6,110MM,ENLARGER,CL:PE100 | Nos | [11 empty] | 0 | 200030315 | 0
15 | HDPE-140MM,PN6,125MM,ENLARGER,CL:PE100 | Nos | [11 empty] | 0 | 200030316 | 0
16 | HDPE-160MM,PN6,63MM Reducer PE100 | Nos | 10 |  |  |  |  | 4474 | [5 empty] | 0 | 200032247 | 0
17 | HDPE-160MM,PN6,75MM Reducer PE100 | Nos | [11 empty] | 0 | 200032246 | 0
18 | HDPE-160MM,PN6,90MM Reducer PE100 | Nos | [11 empty] | 0 | 200032245 | 0
19 | HDPE-160MM,PN6,110MM,ENLARGER,CL:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030319 | 0
20 | HDPE-160MM,PN6, 125MM Reducer PE100 | Nos | [11 empty] | 0 | 200032244 | 0
21 | HDPE-160MM,PN6,140MM,ENLARGER,CL:PE100 | Nos | [11 empty] | 0 | 200030318 | 0
22 | HDPE-200MM,PN6,75MM Reducer PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032249 | 0
23 | HDPE-200MM,PN6,90MM,ENLARGER,CLASS:PE100 | Nos | [11 empty] | 0 | 200030326 | 0
24 | HDPE-200MM,PN6,110MM Reducer PE100 | Nos | [11 empty] | 0 | 200032248 | 0
25 | HDPE-200MM,PN6,140MM,ENLARGER,CL:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030325 | 0
26 | HDPE-200MM,PN6,160MM,ENLARGER,CL:PE100 | Nos | [11 empty] | 0 | 200030328 | 0
27 | HDPE-200MM,PN6,63MM,ENLARGER,CLASS:PE100 | Nos | [11 empty] | 0 | 200030327 | 0
28 | HDPE Reducer 200mm X 125mm | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200034192 | 0
Total Qty In ( No's ) =
F | Bends 45 Degree
1 | HDPE BEND-63MM,PN6 45DEG PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032193 | 0
2 | HDPE BEND-90MM, PN6 45DEG PE100 | Nos | [11 empty] | 0 | 200032195 | 0
3 | HDPE BEND-110MM, PN6 45DEG PE100 | Nos | [11 empty] | 0 | 200032196 | 0
4 | HDPE BEND-75MM,PN6 45DEG PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032194 | 0
5 | HDPE BEND-125MM,PN-6,90DEG,CLASS:PE-100 | Nos | [11 empty] | 0 | 200030270 | 0
6 | HDPE BEND-125MM, PN6 45DEG PE100 | Nos | [11 empty] | 0 | 200032197 | 0
7 | HDPE BEND-140MM,PN-6,45DEG,CLASS:PE-100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030275 | 0
8 | HDPE BEND-160MM,PN-6,45DEG,CLASS:PE-100 | Nos | [11 empty] | 0 | 200030276 | 0
Total Qty In ( No's ) =
G | Bends 90Degree
1 | HDPE BEND-63MM,PN-6,90DEG,CLASS:PE-100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030266 | 0
2 | HDPE BEND-75MM,PN-6,90DEG,CLASS:PE-100 | Nos | [11 empty] | 0 | 200030267 | 0
3 | HDPE BEND-90MM,PN-6,90DEG,CLASS:PE-100 | Nos | [11 empty] | 0 | 200030268 | 0
4 | HDPE BEND-110MM,PN-6,90DEG,CLASS:PE-100 | Nos | 5 |  |  |  |  | 4474 | [5 empty] | 0 | 200030269 | 0
5 | HDPE BEND-140MM,PN-6,90DEG,CLASS:PE-100 | Nos | [11 empty] | 0 | 200030271 | 0
6 | HDPE BEND-160MM,PN-6,90DEG,CLASS:PE-100 | Nos | [11 empty] | 0 | 200030272 | 0
7 | HDPE BEND-200MM,PN-6,90DEG,CLASS:PE-100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030274 | 0
Total Qty In ( No's ) =
H | End Caps
1 | HDPE-63MM,PN6,END CAP,CLASS:PE100 | Nos | 20 | 19 |  | 19 |  | 4474 | [5 empty] | 0 | 200030277 | 0
2 | HDPE-75MM,PN6,END CAP,CLASS:PE100 | Nos | [11 empty] | 0 | 200030278 | 0
3 | HDPE-90MM,PN6,END CAP,CLASS:PE100 | Nos | [11 empty] | 0 | 200030279 | 0
4 | HDPE-110MM,PN6,END CAP,CLASS:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030280 | 0
5 | HDPE-140MM,PN6,END CAP,CLASS:PE100 | Nos | [11 empty] | 0 | 200030282 | 0
Total Qty In ( No's ) =
1 | FHTC
1 | GI PIPE-15MM | Rmt | [5 empty] | 4474 |  | 0 | 0 |  |  | 0 | 1200000409 | 0
2 | MDPE PIPE-20MM | Rmt | [7 empty] | 0 | 0 |  |  | 0 | 1200000408 | 0
3 | BRASS TAP | Nos | [5 empty] | 4474 |  | 0 | 0 |  |  | 0 | 1200000231 | 0
4 | PP CLAMP SADLLE-63MM | Nos | [7 empty] | 0 |  |  |  | 0 | 1200000410 | 0
5 | PP CLAMP SADDLE-75MM | Nos | [11 empty] | 0 | 1200000425 | 0
6 | PP CLAMP SADLLE-90MM | Nos | [5 empty] | 4474 | [5 empty] | 0 | 1200000411 | 0
7 | PP CLAMP SADDLE-140MM | Nos | [11 empty] | 0 | 900008156 | 0
8 | PP CLAMP SADDLE-160MM | Nos | [11 empty] | 0 | 900008157 | 0
9 | PP CLAMP SADDLE-200MM | Nos | [5 empty] | 4474 | [5 empty] | 0 | 900008159 | 0
10 | PP CLAMP SADDLE 125MM WITH M8 FASTNERS | Nos | [11 empty] | 0 | 900008617 | 0
11 | PP CLAMP SADLLE-110MM | Nos | [11 empty] | 0 | 900007416 | 0
12 | G.I ELBOW 15 MM | Nos | [7 empty] | 0 | 0 |  |  | 0 | 1200000419 | 0
13 | GI SOCKET-15MM | Nos | [7 empty] | 0 | 0 |  |  | 0 | 1200000416 | 0
14 | WALL MOUNT SADDLE GI PIPE-15MM | Nos | [5 empty] | 4474 | [5 empty] | 0 | 1200000418 | 0
15 | 15MM GI NIPPLE - 0.3MTR LENGTH | Nos | [7 empty] | 0 | 0 |  |  | 0 | 1200000450 | 0
16 | 15MM GI NIPPLE - 0.5MTR LENGTH | Nos | [7 empty] | 0 | 0 |  |  | 0 | 1200000451 | 0
17 | 20MM MDPE COMPRESSION ELBOW | Nos | [7 empty] | 0 | 0 |  |  | 0 | 1200000448 | 0
18 | SS FLOW CONTROL VAlVE | Nos | [5 empty] | 4474 |  | 0 | 0 |  |  | 0 | 1200000417 | 0
19 | MDPE FEMLE THREADED ASSEMBLY-20MM | Nos | [7 empty] | 0 | 0 |  |  | 0 | 1200000414 | 0
20 | MDPE ELBOW-20MM | Nos | [11 empty] | 0 | 1200000415 | 0
21 | TEFLAN TAPE | Nos |  |  |  | 0 | 0 | [6 empty] | 0 | 200001364 | 0
22 | [6 empty] | 0 | [6 empty] | 0 | #N/A | 0
Total Qty In ( No's ) =
Sub Contractor Site Engineer Block incharge AGM DM PMX Project Incharge
ENTRY NO:

## Details
POWER MECH PROJECTS.LIMITED | [10 empty] | FHTC
RURAL WATER SUPPLY PROJECT UNDER JJM, UP - PRAYAGRAJ
Reconciliation Statement - Issued Vs Certification Qty.
| Contractor Name-RAMPRAV CONTRACTOR |  | MONTH: | sep | Block: | MANGRAURA
| ABC Limited |  | BILL NO: |  | GP: | UTRAS
Sl NO | Description | Units | Consumption Details (Node/Junction) |  |  |  | Total Consumed upto Date | Remarks | Upto date Consumption
[9 empty] | GP | GP | GP | GP | Total Consumption upto This Bill |  | Entry Qty
B | Specials :-
| Equal Tee | [11 empty] | 0 |  | 0
1 | HDPE-63X63X63MM,PN-6,R-TEE,CLASS:PE-100 | Nos | j80,79,101,117,122,290,291,320,321,322,299,301,304,296,71,69,65,81,64,38,68,32,29,24,30,36,49,57,58,22,13,14,93,95,108,103,160,159,163,185,197,207,196,207,209,217,219,223 |  |  |  | 49 | [5 empty] | 0 | 200030286 | 0
2 | HDPE-75X75X75MM,PN-6,R-TEE,CLASS:PE-100 | Nos | j111,118,120,136,156,308,305,297,52,126, |  |  |  | 10 | [5 empty] | 0 | 200030287 | 0
3 | HDPE-90X90X90MM,PN-6,R-TEE,CLASS:PE-100 | Nos | j158,104,226 |  |  |  | 3 | [5 empty] | 0 | 200030288 | 0
4 | HDPE-110X110X110MM,PN-6,R-TEE,CL:PE-100 | Nos | j259,j266,j274,j139 |  |  |  | 4 | [5 empty] | 0 | 200030289 | 0
5 | HDPE 125mm X 125mm X 125mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032212 | 0
6 | HDPE-140X140X140MM,PN-6,R-TEE,CL:PE-100 | Nos | [10 empty] | 0 | 200030291 | 0
7 | HDPE-160X160X160MM,PN-6,R-TEE,CL:PE-100 | Nos | j78,j3 |  |  |  | 2 | [5 empty] | 0 | 200030293 | 0
8 | HDPE 200X200X200 MM, PN-6, R-TEE, CLASS: | Nos | [10 empty] | 0 | 200030300 | 0
C | Branch TEE | [13 empty] | 0
1 | HDPE BRANCH TEE 63MM X 63MM X 50MM | Nos | [10 empty] | 0 | 200032593 | 0
2 | HDPE 75MM X 75MM X 50MM PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032575 | 0
3 | HDPE 75mm X 75mm X 63mm PN6 TEE PE100 | Nos | j86,136,63 |  |  |  | 3 | [5 empty] | 0 | 200032202 | 0
4 | HDPE 90mm X 90mm X 50mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032233 | 0
5 | HDPE 90mm X 90mm X 63mm, PN6 TEE PE100 | Nos | j140,142,146,150,199,199(1),210 |  |  |  | 7 | [5 empty] | 0 | 200032203 | 0
6 | HDPE 90mm X 90mm X 75mm PN6 TEE PE100 | Nos | j158,j104 |  |  |  | 2 | [5 empty] | 0 | 200032204 | 0
7 | HDPE 110mm X 110mm X 50mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032234 | 0
8 | HDPE 110mm X 110mm X 63mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032205 | 0
9 | HDPE 110mm X 110mm X 75mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032206 | 0
10 | HDPE 110mm X 110mm X 90mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032207 | 0
11 | HDPE 125mm X 125mm X 50mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032235 | 0
12 | HDPE 125mm X 125mm X 63mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032208 | 0
13 | HDPE 125mm X 125mm X 75mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032209 | 0
14 | HDPE 125mm X 125mm X 90mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032210 | 0
15 | HDPE 125mm X 125mm X 110mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032211 | 0
16 | HDPE Branch TEE 140mm X 140mm X 50mm | Nos | [10 empty] | 0 | 200032236 | 0
17 | HDPE 140mm X 140mm X 63mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032213 | 0
18 | HDPE 140mm X 140mm X 75mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032214 | 0
19 | HDPE 140mm X 140mm X 110mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032215 | 0
20 | HDPE Branch TEE 140mm X 140mm X 125mm | Nos | [10 empty] | 0 | 200032216 | 0
21 | HDPE-140X90X140MM,PN-6,R-TEE,CL:PE-100 | Nos | [10 empty] | 0 | 200030290 | 0
22 | HDPE 160mm X 160mm X 50mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032237 | 0
23 | HDPE 160mm X 160mm X 63mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032217 | 0
24 | HDPE 160mm X 160mm X 75mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032218 | 0
25 | HDPE 160mm X 160mm X 90mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032219 | 0
26 | HDPE-160X110X160MM,PN-6,R-TEE,CL:PE-100 | Nos | [10 empty] | 0 | 200030292 | 0
27 | HDPE 160mm X 160mm X 125mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032220 | 0
28 | HDPE 200mm X 200mm X 63mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032222 | 0
29 | HDPE 200X75X200 MM, PN-6, R-TEE, CLASS:P | Nos | [10 empty] | 0 | 200030297 | 0
30 | HDPE 200X90X200 MM, PN-6, R-TEE, CLASS:P | Nos | [10 empty] | 0 | 200030298 | 0
31 | HDPE 200mm X 200mm X 110mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032223 | 0
32 | HDPE 200mm X 200mm X 160mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032225 | 0
33 | HDPE 250mm X 250mm X 90mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032228 | 0
D | 4 Way Tee | [13 empty] | 0
1 | HDPE 63MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [10 empty] | 0 | 200030301 | 0
2 | HDPE 75MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | j52,56,126 |  |  |  | 3 | [5 empty] | 0 | 200030302 | 0
3 | HDPE 90MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [10 empty] | 0 | 200030303 | 0
4 | HDPE 110MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [10 empty] | 0 | 200030304 | 0
5 | HDPE125MM,PN6,4WAY CROSS FITTING,CLPE100 | Nos | [10 empty] | 0 | 200032584 | 0
6 | HDPE 140MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [10 empty] | 0 | 200030305 | 0
7 | HDPE 160MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [10 empty] | 0 | 200030306 | 0
8 | HDPE200MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [10 empty] | 0 | 200030308 | 0
E | Reducers
1 | HDPE-75MM,PN6, 63MM,ENLARGER,CLASS:PE100 | Nos | j56,56,63 |  |  |  | 3 | [5 empty] | 0 | 200030309 | 0
2 | HDPE-90MM,PN6, 63MM,ENLARGER,CLASS:PE100 | Nos | [10 empty] | 0 | 200030311 | 0
3 | HDPE-90MM,PN6, 75MM,ENLARGER,CLASS:PE100 | Nos | [10 empty] | 0 | 200030310 | 0
4 | HDPE-110MM,PN6,63MM,ENLARGER,CLASS:PE100 | Nos | [10 empty] | 0 | 200030314 | 0
5 | HDPE-110MM,PN6,75MM,ENLARGER,CLASS:PE100 | Nos | [10 empty] | 0 | 200030312 | 0
6 | HDPE-110MM,PN6,90MM,ENLARGER,CLASS:PE100 | Nos | [10 empty] | 0 | 200030313 | 0
7 | HDPE-125MM,PN6, 63MM Reducer PE100 | Nos | [10 empty] | 0 | 200032241 | 0
8 | HDPE-125MM,PN6, 75MM Reducer PE100 | Nos | [10 empty] | 0 | 200032239 | 0
9 | HDPE-125MM,PN6, 90MM Reducer PE100 | Nos | [10 empty] | 0 | 200032240 | 0
10 | HDPE-125MM,PN6, 110MM Reducer PE100 | Nos | [10 empty] | 0 | 200032242 | 0
11 | HDPE-140MM,PN6,63MM,ENLARGER,CL:PE100 | Nos | [10 empty] | 0 | 200030320 | 0
12 | HDPE-140MM,PN6, 75MM Reducer PE100 | Nos | [10 empty] | 0 | 200032243 | 0
13 | HDPE-140MM,PN6,90MM,ENLARGER,CL:PE100 | Nos | [10 empty] | 0 | 200030317 | 0
14 | HDPE-140MM,PN6,110MM,ENLARGER,CL:PE100 | Nos | [10 empty] | 0 | 200030315 | 0
15 | HDPE-140MM,PN6,125MM,ENLARGER,CL:PE100 | Nos | [10 empty] | 0 | 200030316 | 0
16 | HDPE-160MM,PN6,63MM Reducer PE100 | Nos | [10 empty] | 0 | 200032247 | 0
17 | HDPE-160MM,PN6,75MM Reducer PE100 | Nos | [10 empty] | 0 | 200032246 | 0
18 | HDPE-160MM,PN6,90MM Reducer PE100 | Nos | [10 empty] | 0 | 200032245 | 0
19 | HDPE-160MM,PN6,110MM,ENLARGER,CL:PE100 | Nos | [10 empty] | 0 | 200030319 | 0
20 | HDPE-160MM,PN6, 125MM Reducer PE100 | Nos | [10 empty] | 0 | 200032244 | 0
21 | HDPE-160MM,PN6,140MM,ENLARGER,CL:PE100 | Nos | [10 empty] | 0 | 200030318 | 0
22 | HDPE-200MM,PN6,75MM Reducer PE100 | Nos | [10 empty] | 0 | 200032249 | 0
23 | HDPE-200MM,PN6,90MM,ENLARGER,CLASS:PE100 | Nos | [10 empty] | 0 | 200030326 | 0
24 | HDPE-200MM,PN6,110MM Reducer PE100 | Nos | [10 empty] | 0 | 200032248 | 0
25 | HDPE-200MM,PN6,140MM,ENLARGER,CL:PE100 | Nos | [10 empty] | 0 | 200030325 | 0
26 | HDPE-200MM,PN6,160MM,ENLARGER,CL:PE100 | Nos | [10 empty] | 0 | 200030328 | 0
27 | HDPE-200MM,PN6,63MM,ENLARGER,CLASS:PE100 | Nos | [10 empty] | 0 | 200030327 | 0
28 | HDPE Reducer 200mm X 125mm | Nos | [10 empty] | 0 | 200034192 | 0
F | Bends 45 Degree
1 | HDPE BEND-63MM,PN6 45DEG PE100 | Nos | [10 empty] | 0 | 200032193 | 0
2 | HDPE BEND-90MM, PN6 45DEG PE100 | Nos | [10 empty] | 0 | 200032195 | 0
3 | HDPE BEND-110MM, PN6 45DEG PE100 | Nos | [10 empty] | 0 | 200032196 | 0
4 | HDPE BEND-75MM,PN6 45DEG PE100 | Nos | [10 empty] | 0 | 200032194 | 0
5 | HDPE BEND-125MM,PN-6,90DEG,CLASS:PE-100 | Nos | [10 empty] | 0 | 200030270 | 0
6 | HDPE BEND-125MM, PN6 45DEG PE100 | Nos | [10 empty] | 0 | 200032197 | 0
7 | HDPE BEND-140MM,PN-6,45DEG,CLASS:PE-100 | Nos | [10 empty] | 0 | 200030275 | 0
8 | HDPE BEND-160MM,PN-6,45DEG,CLASS:PE-100 | Nos | [10 empty] | 0 | 200030276 | 0
G | Bends 90Degree
1 | HDPE BEND-63MM,PN-6,90DEG,CLASS:PE-100 | Nos | [10 empty] | 0 | 200030266 | 0
2 | HDPE BEND-75MM,PN-6,90DEG,CLASS:PE-100 | Nos | [10 empty] | 0 | 200030267 | 0
3 | HDPE BEND-90MM,PN-6,90DEG,CLASS:PE-100 | Nos | [10 empty] | 0 | 200030268 | 0
4 | HDPE BEND-110MM,PN-6,90DEG,CLASS:PE-100 | Nos | [10 empty] | 0 | 200030269 | 0
5 | HDPE BEND-140MM,PN-6,90DEG,CLASS:PE-100 | Nos | [10 empty] | 0 | 200030271 | 0
6 | HDPE BEND-160MM,PN-6,90DEG,CLASS:PE-100 | Nos | [10 empty] | 0 | 200030272 | 0
7 | HDPE BEND-200MM,PN-6,90DEG,CLASS:PE-100 | Nos | [10 empty] | 0 | 200030274 | 0
H | End Caps
1 | HDPE-63MM,PN6,END CAP,CLASS:PE100 | Nos | 82,100,292,311,309,306,312,323,302,300,279,282,314,53,76,72,70,67,66 |  |  |  | 19 | [5 empty] | 0 | 200030277 | 0
2 | HDPE-75MM,PN6,END CAP,CLASS:PE100 | Nos | [10 empty] | 0 | 200030278 | 0
3 | HDPE-90MM,PN6,END CAP,CLASS:PE100 | Nos | [10 empty] | 0 | 200030279 | 0
4 | HDPE-110MM,PN6,END CAP,CLASS:PE100 | Nos | [10 empty] | 0 | 200030280 | 0
5 | HDPE-140MM,PN6,END CAP,CLASS:PE100 | Nos | [10 empty] | 0 | 200030282 | 0
Sub Contractor Site Engineer Block incharge AGM DM PMX Project Incharge
ENTRY NO: