## Sheet1
Block | Name of Scheme | Department | Type of OHT(PMPL comments) | Date | Observations | Category of Defect (Critical/ Major/ Minor) | TPI Engineer Name | NC Compliances by TKC | NC Compliance date | Rectified/Not Recrtified
4 | 5 | 6 |  | 8 | 9 | 10 | 11 | 17 | 18 | 19
Mangraura | Atrasand & Parsupur | Civil - Backfilling |  | 8: 2023-08-25; 9: Area Should Be Barricaded For Unauthorized Access.; 10: Critical; 11: Sumit Kumar
Mangraura | Atrasand & Parsupur | Civil - Pipe Laying | Cast in site(Pipe line) | 2023-07-04 | End Caps Has Not Been Used To Prevent The Entry Of Foreign Material Like Insects At Node -193 To 26. | Major | Lalan Sharma | YES |  | Not Rectified
Mangraura | Atrasand & Parsupur | Civil - Pipe Laying |  | 8: 2023-05-16; 9: End Cap Has Not Been Provided & Pipe Mouth Is Left Open To Prevent The Entry Of Foreign Material Like Insects At Node J1 To J3. As Per Is - 8360 Part 1 To 3.; 10: Major; 11: Sumit Kumar
Mangraura | Atrasand & Parsupur | Civil - Pipe Laying |  | 8: 2023-05-16; 9: Backfilling And Soil Compaction Not Done Properly Between Node J1 To J3. Refer Is 7634 Part 2 Clause 6.4.3; 10: Major; 11: Sumit Kumar
Mangraura | Atrasand & Parsupur | Civil - Pipe Laying |  | 8: 2023-05-16; 9: It Has Been Observed That Stacking Of Pea- Gravel On Directly Contact Of Surface At Work Site.; 10: Major; 11: Sumit Kumar
Mangraura | Atrasand & Parsupur | Civil - Pipe Laying |  | 8: 2023-05-16; 9: Stand Post Has Not Been Provided. J1 To J3.; 10: Major; 11: Sumit Kumar
Mangraura | Atrasand & Parsupur | Civil - Pipe Laying |  | 8: 2023-05-16; 9: Backfilling And Soil Compaction Not Done Properly Between Node J3 To J5. Refer Is 7634 Part 2 Clause 6.4.3; 10: Major; 11: Sumit Kumar
Mangraura | Atrasand & Parsupur | Civil - Pipe Laying |  | 8: 2023-05-16; 9: Logsheet Not Available, And Not Maintained At Working Site.; 10: Major; 11: Sumit Kumar
Mangraura | Atrasand & Parsupur | Civil - Pipe Laying |  | 8: 2023-05-16; 9: Signage Board Not Available At Work Site.; 10: Major; 11: Sumit Kumar
Mangraura | Atrasand & Parsupur | Civil - Pipe Laying |  | 8: 2023-07-04; 9: End Cap Has Not Been Provided & Pipe Mouth Is Left Open To Prevent The Entry Of Foreign Material Like Insects. As Per Is-8360 Part 1 To 3.; 10: Major; 11: Vindhesh Kumar
Mangraura | Atrasand & Parsupur | Civil - Pipe Laying |  | 8: 2023-07-04; 9: Mdpe Pipe Has Not Laid 600 Mm Below The Ground As Per Approved Drawing And Was Found Lying On The Ground.; 10: Major; 11: Vindhesh Kumar
Mangraura | Atrasand & Parsupur | Civil - Pipe Laying |  | 8: 2023-09-02; 9: End Cap Of The Hdpe Pipe Has Been Not Provided At Node - 51 Which Is Wrong Practice Refer Is 8001.; 10: Critical; 11: Lalan Sharma
Mangraura | Aurangabad | Civil - Backfilling |  | 8: 2024-06-13; 9: Backfilling Not Completed After Pipe Laying At Junction 15 To 72; 10: Major; 11: Vilash Dubey
Mangraura | Barasarai | Civil - Pipe Laying |  | 8: 2023-07-24; 9: Width Of The Trench Observed Is 200Mm At (Node No. J158- J164) Whereas As Per Dpr The Width Should Be At Least 300Mm+ Of Pipe.; 10: Major; 11: Vindhesh Kumar
Mangraura | Barasarai | Civil - Pipe Laying |  | 8: 2023-07-24; 9: Pipe Laying Work Is Complete. Trench Is Backfilled Haphazardly Without Any Proper Layering Watering And Compaction.; 10: Major; 11: Vindhesh Kumar
Mangraura | Barasarai | Civil - Pipe Laying |  | 8: 2023-07-24; 9: End Cap Was Not Provided At The Ends Of The Pipe To Prevent Ingress Of Material.; 10: Major; 11: Vindhesh Kumar
Mangraura | Barasarai | Civil - Pipe Laying |  | 8: 2023-08-04; 9: Backfilling And Compaction Have Not Been Done Properly.J14 To J15.; 10: Critical; 11: Lalan Sharma
Mangraura | Barhupur | Civil - Pipe Laying |  | 8: 2023-12-05; 9: Width Of The Trench Has Been Observed 200Mm At Work Site At J102 To J259.; 10: Major; 11: Vindhesh Kumar
Mangraura | Choumari | Civil - Backfilling |  | 8: 2024-02-26; 9: Backfilling Of Soil Has Not Been Done Properly. At Node 96-99.; 10: Major; 11: Vilash Dubey
Mangraura | Choumari | Civil - Pipe Laying |  | 8: 2024-02-26; 9: The Pipe Has Been Laid On The Canal Bridge Without Casing. J96 To J99; 10: Critical; 11: Vilash Dubey
Mangraura | Dehridigar | Civil - Road Restoration |  | 8: 2023-12-22; 9: Reinstatement Of Boe Road Has Not Been Done Properly. J246 To J254.; 10: Critical; 11: Vindhesh Kumar
Mangraura | Gehrauli | Civil - Pipe Laying |  | 8: 2023-09-20; 9: Depth Of The Trench For Laying Of Pipe At Node 86-99 Has Been Found 900 Mm Where As It Should Be (1000 Mm + Dia. Of Pipe).; 10: Major; 11: Sanjay Kumar
Mangraura | Koni & Salahipur Kanjas | Civil - Backfilling |  | 8: 2024-08-14; 9: During Site Visit, There Is A Need For Re - Backfilling At Many Places In The Village. Please Do This Asap.; 10: Major; 11: Vilash Dubey
Mangraura | Lauli Pokhatakham | Civil - Pipe Laying |  | 8: 2023-08-17; 9: Pipe Laying Work Is Complete. Trench Is Not Backfilled Haphazardly Without Any Proper Layering And Compaction According To Indian Standard 7634:2012(Part-2).; 10: Major; 11: Lalan Sharma
Mangraura | Lauli Pokhatakham | Civil - Pipe Laying |  | 8: 2023-08-17; 9: Stacking Of Pipe Was In Open Space Exposed To Direct Sunlight Which Is Not Proper.; 10: Major; 11: Lalan Sharma
Mangraura | Lauli Pokhatakham | Civil - Pipe Laying |  | 8: 2023-08-18; 9: As Per Visual Observation And Site Test, The Quality Of Brick Has Been Found Very Poor. Test Report Also Not Available. It Should Removed From Site Immediately.; 10: Critical; 11: Vilash Dubey
Mangraura | Mangraura | Civil - Pipe Laying |  | 8: 2023-07-10; 9: End Cap Has Not Been Fitted On The Mouth Of The Pipe To Prevent The Blockage Of The Pipe.; 10: Major; 11: Lalan Sharma
Mangraura | Mangraura | Civil - Pipe Laying |  | 8: 2023-08-23; 9: Htc Connection Is Given Without Hydro Test And End Cap Is Not Provided.; 10: Critical; 11: Lalan Sharma
Mangraura | Mangraura | Civil - Pipe Laying |  | 8: 2023-08-23; 9: Initial Backfilling Of 150 Mm From Crown Of Laid Pipe Had Not In Practice At Node 6A To 6B.; 10: Critical; 11: Lalan Sharma
Mangraura | Mangraura | Civil - Pipe Laying |  | 8: 2023-08-23; 9: Backfilling In Pipeline Trench Has Been Not Done In Layer By Layer And Also Compaction Is Not Done At Node - 5 To 10; 10: Critical; 11: Lalan Sharma
Mangraura | Mangraura | Civil - Pipe Laying |  | 8: 2023-08-23; 9: Backfilling And Compaction Of Soil Have Not Been Done Appropriately At Node 8A To 8B; 10: Critical; 11: Lalan Sharma
Mangraura | Mangraura | Civil - Pipe Laying |  | 8: 2023-08-23; 9: Backfilling Work Has Not Been Done Along Node 8 - 9. Accident May Occur Due To This.; 10: Critical; 11: Lalan Sharma
Mangraura | Mangraura | Civil - Pipe Laying |  | 8: 2023-08-23; 9: Pipe Jointing Work Has Not Been Done And End Cap Also Not Provided Along Node 5 To 10.; 10: Critical; 11: Lalan Sharma
Mangraura | Mangraura | Civil - Pipe Laying |  | 8: 2023-08-23; 9: Backfilling And Compaction Of Soil Have Not Been Appropriately Done At Node No Esr To 71.; 10: Critical; 11: Lalan Sharma
Mangraura | Sakra | Civil - Pipe Laying |  | 8: 2023-05-16; 9: It Has Been Observed That Power Distribution Board Should Be Maintained Properly At Work Site.; 10: Major; 11: Sumit Kumar
Mangraura | Sakra | Civil - Pipe Laying |  | 8: 2023-05-16; 9: It Is Observed That There Are Bare Electric Wires Which May Cause Accident, It Should Use Industrial Plug And Wire Proper Taping.; 10: Major; 11: Sumit Kumar
Mangraura | Sakra | Civil - Pipe Laying |  | 8: 2023-05-16; 9: Honeycomb Has Been Observed On The Coping Of Boundary Wall.; 10: Major; 11: Sumit Kumar
Mangraura | Sakra | Civil - Pipe Laying |  | 8: 2023-05-16; 9: Plaster Of Coping Not Completed.; 10: Major; 11: Sumit Kumar
Mangraura | Sakra | Civil - Pipe Laying |  | 8: 2023-05-16; 9: Hdpe Pipe Should Be Stacked Under Cover, Left Out Directly Contact Of Direct Sunlight Which May Causes Quality Issue Of The Pipe. J1A To J1B; 10: Major; 11: Sumit Kumar
Mangraura | Sakra | Civil - Pipe Laying |  | 8: 2023-05-16; 9: It Has Been Observed That Fine Aggregate Directly Stacked On Contact Of Surface.; 10: Major; 11: Sumit Kumar
Mangraura | Sakra | Civil - Pipe Laying |  | 8: 2023-05-16; 9: End Cap Has Not Been Provided & Pipe Mouth Is Left Open To Prevent The Entry Of Foreign Material Like Insects At Node J10 To J25. As Per Is - 8360 Part 1 To 3.; 10: Major; 11: Sumit Kumar
Mangraura | Sakra | Civil - Pipe Laying |  | 8: 2023-05-16; 9: Backfilling And Compaction Not Done Properly Between Node 1A To Jb. Refer Is 7634 Part 2 Clause 6.4.3; 10: Major; 11: Sumit Kumar
Mangraura | Sarayjmuvari | Civil - Fhtc |  | 8: 2023-07-12; 9: End Cap Was Not Provided At The Ends Of The Pipe To Prevent Ingress Of Material.; 10: Major; 11: Vindhesh Kumar
Mangraura | Sarayjmuvari | Civil - Fhtc |  | 8: 2023-07-12; 9: Mdpe Pipe Has Not Laid 600 Mm Below The Ground As Per Approved Drawing And Was Found Lying On The Ground.; 10: Major; 11: Vindhesh Kumar
Mangraura | Sarayjmuvari | Civil - Fhtc |  | 8: 2023-07-12; 9: Mdpe Pipe Has Not Laid 600 Mm Below The Ground As Per Approved Drawing And Was Found Lying On The Ground.; 10: Major; 11: Vindhesh Kumar
Mangraura | Sarayjmuvari | Civil - Fhtc |  | 8: 2023-07-12; 9: Backfilling And Compaction Has Not Been Done Properly.; 10: Major; 11: Vindhesh Kumar
Mangraura | Sarayjmuvari | Civil - Fhtc |  | 8: 2023-07-12; 9: Fhtc Done Without Clamping, Grouting And Plastic Tap Used Instead Of Brass Tap .; 10: Major; 11: Vindhesh Kumar
Mangraura | Sarayjmuvari | Civil - Fhtc |  | 8: 2023-07-12; 9: Fhtc Done Without Clamping, Grouting And Plastic Tap Used Instead Of Brass Tap .; 10: Major; 11: Vindhesh Kumar
Mangraura | Sarayjmuvari | Civil - Road Restoration |  | 8: 2023-07-17; 9: G.I. Pipe Grouting Work Not Done At J45 To 48; 10: Major; 11: Sumit Kumar
Mangraura | Sarayjmuvari | Civil - Road Restoration |  | 8: 2023-07-17; 9: Restoration Has Not Been Completed At Site. J45 To J48.; 10: Major; 11: Sumit Kumar
Mangraura | Sarayjmuvari | Civil - Road Restoration |  | 8: 2023-07-17; 9: Bituminous Road Restoration Has Not Been Completed At J45 To J48.; 10: Major; 11: Sumit Kumar
Mangraura | Sarayjmuvari | Civil - Road Restoration |  | 8: 2023-07-17; 9: Cashing-Pipe Has Not Been Provided At Nala- Crossing.; 10: Major; 11: Sumit Kumar
Mangraura | Sarayjmuvari | Civil - Road Restoration |  | 8: 2023-07-17; 9: Restoration Has Not Been Completed At Site J48 To J50.; 10: Major; 11: Sumit Kumar
Mangraura | Sarayjmuvari | Civil - Road Restoration |  | 8: 2023-07-17; 9: Hdpe Pipe Not Laid Properly Kept Out Near Road Side.; 10: Major; 11: Sumit Kumar
Mangraura | Sarayjmuvari | Civil - Road Restoration |  | 8: 2023-07-17; 9: Endcap Has Been Not Provided On The Edge Of Hdpe Pipe Left Mouth Open May Get Entry Foreign Material Like Insects. J50 To J55.; 10: Major; 11: Sumit Kumar
Mangraura | Sarayjmuvari | Civil - Road Restoration |  | 8: 2023-07-17; 9: Bituminous Road Restoration Has Not Been Completed At Site. J 55 To J 58.; 10: Major; 11: Sumit Kumar
Mangraura | Sarayjmuvari | Civil - Road Restoration |  | 8: 2023-07-17; 9: Endcap Has Been Not Provided On The Edge Of The 63Mm Dia Pipe May Get Entry Foreign Material Like Insects. J70 To J74.; 10: Major; 11: Sumit Kumar
Mangraura | Shivpur Khurd | Civil - Pipe Laying |  | 8: 2023-10-05; 9: Width Of The Trench Observed Is 250Mm At Node No. (Node No-10 To 11) Whereas As Per Dpr The Width Should Be At Least 300Mm+ Of Pipe.; 10: Major; 11: Vindhesh Kumar
Mangraura | Shivpur Khurd | Civil - Pipe Laying |  | 8: 2023-10-05; 9: End Cap Has Been Not Provided On The Edge Hdpe Pipe. J45 To 47.; 10: Major; 11: Sumit Kumar
Mangraura | Suryagarhjagannath | Civil - Pipe Laying |  | 8: 2023-07-24; 9: Depth Of The Trench Observed Is 950Mm At The Top Of The 63Mm Hdpe Pipe (Node No-J 158 - J 164) Whereas As Per Dpr The Depth Should Be At Least 1000Mm+ Of Pipe.; 10: Major; 11: Vindhesh Kumar