## utras 2
GOVERNMENT OF UTTAR PRADESH
STATE WATER & SANITATION MISSION ( SWSM )
Joint Measurement Report of Pipe Line
Name of the Work :- Survey , Design Preparation of DPR , Construction , Commissioning and O&M for 10 Years of Various Rural Water Supply Projects in the state of Uttar Pradesh as Per Request for Proposal for Division " Prayagraj "
Name of the Agency : POWER MECH PROJECTS LIMITED – BHOORATHNOM CONSTRUCTIONS COMPANY PRIVATE LIMITED (JV), Hyderabad.
Name OF Scheme |  | : utras 2
Block |  | : MANGRAURA
Total Scope |  | :
JMR No. |  | : 2
Date of JMR |  | :
Sr. No. | Start Node | End Node | Dia | Pipe Length (as per Drawing) | Pipe Length (as per Site) | Excavation Width | Depth | Quantity | Type OF Road | Dismantling Length | Dismantling Width | Dismantling Quantity | Restoration Length | Restoration Width | Restoration Quantity | Restoration Status | Remark
1 | j266 | j261 | 110 | 29 | 33 | 0.41 | 1.11
2 | j261 | j259 | 110 | 58 | 63.9 | 0.41 | 1.11
3 | j261 | j259 | 110 |  | 4.5 | 0.41 | 1.11 |  | BOE road | 4.5 | 0.41 | 1.845 | 4.5 | 0.41 | 1.845
4 | j261 | j259 | 110 |  | 4.5 | 0.41 | 1.11 |  | CC road | 4.5 | 0.41 | 1.845 | 4.5 | 0.41 | 1.845
5 | j259 | j260 | 110 | 125 | 141.5 | 0.41 | 1.11
6 | j260 | j265 | 110 |  | 17 | 0.41 | 1.11
7 | j265 | j277 | 75 | 132 | 64 | 0.375 | 1.075
8 | j265 | j277 | 75 |  | 64 | 0.375 | 1.075 |  | BOE | 64 | 0.375 | 24 | 64 | 0.375 | 24
9 | j277 | j280 | 63 | 31 | 31.6 | 0.363 | 1.063
10 | j280 | j285 | 63 | 166 | 165 | 0.363 | 1.063
11 | j285 | j286 | 63 | 133 | 133 | 0.363 | 1.063
12 | j265 | j269 | 63 | 40 | 41.6 | 0.363 | 1.063 |  | BOE | 41.6 | 0.363 | 15.1008 | 41.6 | 0.363 | 15.1008
13 | j269 | j295 | 63 | 252 | 150 | 0.363 | 1.063
14 | j259 | j257 | 110 | 50 | 53 | 0.41 | 1.11
15 | j257 | j257 | 63 |  | 4 | 0.363 | 1.063 |  | CC road | 4 | 0.363 | 1.452 | 4 | 0.363 | 1.452
16 | j257 | j258 | 63 |  | 110.2 | 0.363 | 1.063
17 | j258 | j274 | 63 | 147 | 154.1 | 0.363 | 1.063
18 | j274 | j666 | 110 | 148 | 154 | 0.41 | 1.11
19 | j257 | j245 | 110 |  | 125.6 | 0.41 | 1.11
20 | j245 | j240 | 140 |  | 16.5 | 0.44 | 1.14
21 | j240 | j246 | 63 |  | 85 | 0.363 | 1.063
22 | j246 | j247 | 63 |  | 160 | 0.363 | 1.063
23 | j246 | j249 | 63 |  | 60 | 0.363 | 1.063
24 | j249 | j251 | 63 |  | 55 | 0.363 | 1.063
25 | j326 | j328 | 63 | 120 | 105 | 0.363 | 1.063
26 | j331 | j332 | 63 | 89 | 100 | 0.363 | 1.063
27 | j331 | j333 | 63 | 18 | 17 | 0.363 | 1.063
28 | j333 | j335 | 63 | 17 | 17 | 0.363 | 1.063
29 | j335 | j337 | 63 | 274 | 240 | 0.363 | 1.063
30 | j331 | j329 | 63 | 57 | 60 | 0.363 | 1.063
31 | j329 | j326 | 63 | 50 | 103 | 0.363 | 1.063
32 | j326 | j324 | 63 | 94 | 71.4 | 0.363 | 1.063
33 | j326 | j324 | 63 |  | 7 | 0.363 | 1.063 |  | BT road | 7 | 0.363 | 2.541 | 7 | 0.363 | 2.541
34 | j307 | j316 | 63 | 387 | 240 | 0.363 | 1.063
35 | j307 | j316 | 63 |  | 6.9 | 0.363 | 1.063 |  | BT raod | 6.9 | 0.363 | 2.5047 | 6.9 | 0.363 | 2.5047
36 | j322 | j295 | 63 | 456 | 200 | 0.363 | 1.063
37 | j321 | j313 | 63 | 228 | 120 | 0.363 | 1.063 |  | BOE | 120 | 0.363 | 43.56 | 120 | 0.363 | 43.56
38 | j321 | j313 | 63 | 228 | 195 | 0.363 | 1.063
39 | j313 | j313 | 63 |  | 3 | 0.363 | 1.063 |  | BT road | 3 | 0.363 | 1.089 | 3 | 0.363 | 1.089
40 | j304 | j272 | 63 | 181 | 208 | 0.363 | 1.063
41 | j272 | j270 | 75 | 35 | 35 | 0.375 | 1.075
42 | j220 | j267 | 75 |  | 33 | 0.375 | 1.075
43 | j267 | j266 | 75 | 16 | 18 | 0.375 | 1.075
44 | j245 | j241 | 63 | 19 | 16.6 | 0.363 | 1.063
45 | j245 | j245 | 63 |  | 5 | 0.363 | 1.063 |  | CC road | 5 | 0.363 | 1.815 | 5 | 0.363 | 1.815
46 | j241 | j242 | 63 | 32 | 29.4 | 0.363 | 1.063
47 | j242 | j244 | 63 | 62 | 40 | 0.363 | 1.063 |  | BOE | 40 | 0.363 | 14.52 | 40 | 0.363 | 14.52
48 | j242 | j243 | 63 | 59 | 62 | 0.363 | 1.063
49 | j242 | j242 | 63 |  | 3 | 0.363 | 1.063 |  | CC road | 3 | 0.363 | 1.089 | 3 | 0.363 | 1.089
50 | j298 | j301 | 63 | 79 | 52.1 | 0.363 | 1.063 |  | BOE | 52.1 | 0.363 | 18.9123 | 52.1 | 0.363 | 18.9123
51 | j298 | j301 | 63 |  | 30.2 | 0.363 | 1.063
52 | j301 | j302 | 63 | 15 | 13.3 | 0.363 | 1.063
53 | j297 | j296 | 63 |  | 32.2 | 0.363 | 1.063
54 | j296 | j279 | 63 |  | 60.5 | 0.363 | 1.063
55 | j296 | j286 | 63 |  | 20 | 0.363 | 1.063
56 | j289 | j283 | 90 |  | 27 | 0.39 | 1.09 |  | BOE | 27 | 0.39 | 10.53 | 27 | 0.39 | 10.53
57 | j283 | j287 | 110 |  | 19.4 | 0.41 | 1.11 |  | BOE | 19.4 | 0.41 | 7.954 | 19.4 | 0.41 | 7.954
58 | j287 | j299 | 110 |  | 33 | 0.41 | 1.11 |  | BOE | 33 | 0.41 | 13.53 | 33 | 0.41 | 13.53
59 | j310 | j311 | 63 | 19 | 17.8 | 0.363 | 1.063 |  | BOE | 17.8 | 0.363 | 6.4614 | 17.8 | 0.363 | 6.4614
60 | j308 | j309 | 63 |  | 33 | 0.363 | 1.063 |  | BOE | 33 | 0.363 | 11.979 | 33 | 0.363 | 11.979
61 | j308 | j309 | 63 |  | 27 | 0.363 | 1.063
62 | j52 | j3 | 75 | 302 | 319.2 | 0.375 | 1.075
63 | j79 | j56 | 63 | 46 | 46 | 0.363 | 1.063
64 | j56 | j3 | 75 | 324 | 330 | 0.375 | 1.075
65 | j78 | j3 | 160 | 225 | 231 | 0.46 | 1.16
66 | j3 | j3 | 160 |  | 3.7 | 0.46 | 1.16 |  | BT road | 3.7 | 0.46 | 1.702 | 3.7 | 0.46 | 1.702
67 | j3 | j1 | 160 | 220 | 250 | 0.46 | 1.16
68 | j1 | tank | 200 | 84 | 82.4 | 0.5 | 1.2
69 | j1 | j2 | 160 | 246 | 230.3 | 0.46 | 1.16
70 | j2 | j4 | 160 |  | 5.5 | 0.46 | 1.16 |  | BT road | 5.5 | 0.46 | 2.53 | 5.5 | 0.46 | 2.53
71 | j2 | j4 | 160 | 80 | 93.8 | 0.46 | 1.16
72 | j4 | j6 | 110 | 54 | 39 | 0.41 | 1.11
73 | j6 | j20 | 110 | 86 | 96 | 0.41 | 1.11
74 | j20 | j41 | 110 | 65 | 62.5 | 0.41 | 1.11
75 | j20 | j38 | 63 | 49 | 25 | 0.363 | 1.063 |  | BOE | 25 | 0.363 | 9.075 | 25 | 0.363 | 9.075
76 | j20 | j38 | 63 |  | 23 | 0.363 | 1.063
77 | j38 | j39 | 63 | 35 | 25 | 0.363 | 1.063
78 | j38 | j54 | 63 | 91 | 40 | 0.363 | 1.063
79 | j41 | j41 | 110 |  | 4 | 0.41 | 1.11 |  | BT road | 4 | 0.41 | 1.64 | 4 | 0.41 | 1.64
80 | j41 | j81 | 63 | 292 | 342 | 0.363 | 1.063
81 | j64 | j61 | 63 | 51 | 52.7 | 0.363 | 1.063
82 | j54 | j55 | 63 |  | 95.9 | 0.363 | 1.063 |  | interlock | 95.9 | 0.363 | 34.8117 | 95.9 | 0.363 | 34.8117
83 | j33 | j32 | 63 | 26 | 71.4 | 0.363 | 1.063
84 | j32 | j30 | 63 | 51 | 112.6 | 0.363 | 1.063
85 | j30 | j33 | 63 |  |  | 0.363 | 1.063
86 | j28a | j28b | 63 |  | 69 | 0.363 | 1.063
87 | j28b | j28b | 63 |  | 3 | 0.363 | 1.063 |  | BT road | 3 | 0.363 | 1.089 | 3 | 0.363 | 1.089
88 | j26 | j21 | 160 | 40 | 41.5 | 0.46 | 1.16
89 | j21 | j24 | 63 | 39 | 35.3 | 0.363 | 1.063
90 | j24 | j29 | 63 | 33 | 39.6 | 0.363 | 1.063 |  | BOE | 39.6 | 0.363 | 14.3748 | 39.6 | 0.363 | 14.3748
91 | j29 | j31 | 63 | 118 | 31.4 | 0.363 | 1.063
92 | j24 | j24 | 63 |  | 4.2 | 0.363 | 1.063 |  | BT road | 4.2 | 0.363 | 1.5246 | 4.2 | 0.363 | 1.5246
93 | j24a | j24b | 63 |  | 145.7 | 0.363 | 1.063
94 | j21 | j18 | 160 | 53 | 47 | 0.46 | 1.16
95 | j18 | j17 | 160 | 29 | 32 | 0.46 | 1.16
96 | j17 | j12 | 160 | 57 | 59.1 | 0.46 | 1.16
97 | j21 | j18 | 160 |  | 4 | 0.46 | 1.16 |  | interlock | 4 | 0.46 | 1.84 | 4 | 0.46 | 1.84
98 | j18 | j19 | 63 | 20 | 28.9 | 0.363 | 1.063
99 | j12 | j51 | 63 | 53 | 51 | 0.363 | 1.063
100 | j51 | j22 | 63 | 51 | 50 | 0.363 | 1.063
101 | j51 | j51 | 63 |  | 4 | 0.363 | 1.063 |  | BT road | 4 | 0.363 | 1.452 | 4 | 0.363 | 1.452
102 | j22 | j23 | 63 | 42 | 31 | 0.363 | 1.063
103 | j22 | j16 | 63 | 28 | 19.9 | 0.363 | 1.063
104 | j16a | j16b | 63 | extra | 17 | 0.363 | 1.063
105 | j16 | j14 | 63 |  | 39.1 | 0.363 | 1.063
106 | j14 | j13 | 63 |  | 15.9 | 0.363 | 1.063
107 | j14 | j15 | 63 | 54 | 66 | 0.363 | 1.063
108 | j37 | j48 | 63 |  | 72.5 | 0.363 | 1.063
109 | j48 | j44 | 63 | 192 | 208 | 0.363 | 1.063
110 | j44 | j47 | 63 | 43 | 65 | 0.363 | 1.063
111 | j42 | j43 | 63 | 73 | 73 | 0.363 | 1.063
112 | j43a | j43b | 63 | extra | 176 | 0.363 | 1.063
113 | j73 | j57 | 63 | 94 | 93.9 | 0.363 | 1.063 |  | BOE | 93.9 | 0.363 | 34.0857 | 93.9 | 0.363 | 34.0857
114 | j57 | j58 | 63 | 22 | 19.7 | 0.363 | 1.063 |  | BOE | 19.7 | 0.363 | 7.1511 | 19.7 | 0.363 | 7.1511
115 | j57 | j58 | 63 |  | 7 | 0.363 | 1.063
116 | j58 | j59 | 63 | 28 | 15.4 | 0.363 | 1.063
117 | j88 | j102 | 63 | 88 | 85.4 | 0.363 | 1.063
118 | j88 | j102 | 63 |  | 4 | 0.363 | 1.063 |  | BOE | 4 | 0.363 | 1.452 | 4 | 0.363 | 1.452
119 | j97 | j102 | 160 | 72 | 70 | 0.46 | 1.16 |  | BOE | 70 | 0.46 | 32.2 | 70 | 0.46 | 32.2
120 | j102 | j107 | 160 | 48 | 56 | 0.46 | 1.16 |  | BOE | 56 | 0.46 | 25.76 | 56 | 0.46 | 25.76
121 | j107 | j108 | 63 | 57 | 53.9 | 0.363 | 1.063
122 | j108 | j110 | 63 | 31 | 55 | 0.363 | 1.063
123 | j108 | j109 | 63 | 15 | 42.9 | 0.363 | 1.063
124 | j107 | j130 | 160 | 269 | 278.6 | 0.46 | 1.16 |  | BOE | 278.6 | 0.46 | 128.156 | 278.6 | 0.46 | 128.156
125 | j130 | j149 | 160 | 203 | 217.9 | 0.46 | 1.16 |  | BOE | 217.9 | 0.46 | 100.234 | 217.9 | 0.46 | 100.234
126 | j149 | j155 | 63 | 42 | 80 | 0.363 | 1.063
127 | j149 | j151 | 63 | 54 | 57.3 | 0.363 | 1.063 |  | BOE | 57.3 | 0.363 | 20.7999 | 57.3 | 0.363 | 20.7999
128 | j151 | j165 | 63 | 266 | 76.7 | 0.363 | 1.063 |  | BOE | 76.7 | 0.363 | 27.8421 | 76.7 | 0.363 | 27.8421
129 | j151 | j165 | 63 |  | 115.3 | 0.363 | 1.063
130 | j154 | j170 | 63 | 107 | 115.2 | 0.363 | 1.063
131 | j170 | j175 | 63 | 52 | 60 | 0.363 | 1.063
132 | j175 | j206 | 63 | 94 | 96 | 0.363 | 1.063
133 | j206 | j214 | 140 | 37 | 33 | 0.44 | 1.14
134 | j214 | j234 | 140 | 54 | 56.3 | 0.44 | 1.14
135 | j234 | j235 | 140 | 137 | 180.3 | 0.44 | 1.14
136 | j111 | j112 | 63 | 32 | 35.2 | 0.363 | 1.063
137 | j111 | j120 | 75 | 105 | 115.2 | 0.375 | 1.075 |  | BOE | 115.2 | 0.375 | 43.2 | 115.2 | 0.375 | 43.2
138 | j120 | j126 | 75 |  | 60 | 0.375 | 1.075
139 | j126 | j132 | 63 |  | 38.5 | 0.363 | 1.063
140 | j126 | j132 | 63 |  | 4 | 0.363 | 1.063 |  | BT road | 4 | 0.363 | 1.452 | 4 | 0.363 | 1.452
141 | j126 | j129 | 63 | 147 | 282 | 0.363 | 1.063
142 | j129 | j130 | 63 | 157 | 282 | 0.363 | 1.063
143 | j78 | j89 | 160 | 192 | 266.3 | 0.46 | 1.16
144 | j89 | j97 | 160 | 69 | 266.3 | 0.46 | 1.16
145 | j12 | j11 | 160 |  | 26 | 0.46 | 1.16 |  | BOE | 26 | 0.46 | 11.96 | 26 | 0.46 | 11.96
146 | j11 | j9 | 160 |  | 47 | 0.46 | 1.16 |  | interlock | 47 | 0.46 | 21.62 | 47 | 0.46 | 21.62
147 | j9 | j7 | 160 |  | 27 | 0.46 | 1.16 |  | interlock | 27 | 0.46 | 12.42 | 27 | 0.46 | 12.42
148 | j7 | j8 | 63 | 73 | 145 | 0.363 | 1.063
149 | j34 | j32 | 63 |  | 51.9 | 0.363 | 1.063 |  | BOE | 51.9 | 0.363 | 18.8397 | 51.9 | 0.363 | 18.8397
150 | j7 | j2 | 160 | 142 | 80.1 | 0.46 | 1.16 |  | interlock | 80.1 | 0.46 | 36.846 | 80.1 | 0.46 | 36.846
151 | j7 | j2 | 160 |  | 63.6 | 0.46 | 1.16
152 | j2 | j2 | 160 |  | 4.2 | 0.46 | 1.16 |  | BT road | 4.2 | 0.46 | 1.932 | 4.2 | 0.46 | 1.932
153 | j2 | j40 | 90 | 302 | 312 | 0.39 | 1.09 |  | BOE | 312 | 0.39 | 121.68 | 312 | 0.39 | 121.68
154 | j40 | j63 | 75 | 211 | 218 | 0.375 | 1.075 |  | BOE | 218 | 0.375 | 81.75 | 218 | 0.375 | 81.75
155 | j63 | j65 | 63 | 57 | 59.6 | 0.363 | 1.063
156 | j63 | j69 | 63 | 93 | 104.7 | 0.363 | 1.063 |  | BOE | 104.7 | 0.363 | 38.0061 | 104.7 | 0.363 | 38.0061
157 | j69 | j71 | 63 | 76 | 76.8 | 0.363 | 1.063
158 | j71 | j75 | 63 | 87 | 82.3 | 0.363 | 1.063
159 | j69 | j70 | 63 | 20 | 44.6 | 0.363 | 1.063
160 | j40a | j40b | 63 | extra | 123.4 | 0.363 | 1.063
161 | j176 | j196 | 63 | 267 | 282.7 | 0.363 | 1.063 |  | BOE | 282.7 | 0.363 | 102.6201 | 282.7 | 0.363 | 102.6201
162 | j169a | j169b | 63 | extra | 119.7 | 0.363 | 1.063
163 | j158 | j192 | 75 | 138 | 99 | 0.375 | 1.075
164 | j192a | j192b | 63 | extra | 30 | 0.363 | 1.063
165 | j158 | j192 | 75 |  | 50 | 0.375 | 1.075 |  | BOE | 50 | 0.375 | 18.75 | 50 | 0.375 | 18.75
166 | j158 | j125 | 90 | 190 | 196.5 | 0.39 | 1.09
167 | j150 | j199 | 90 | 191 | 198 | 0.39 | 1.09 |  | BOE | 198 | 0.39 | 77.22 | 198 | 0.39 | 77.22
168 | j199 | j210 | 90 | 101 | 113.4 | 0.39 | 1.09
169 | j210 | j226 | 90 | 106 | 110 | 0.39 | 1.09 |  | BOE | 110 | 0.39 | 42.9 | 110 | 0.39 | 42.9
170 | j226 | j222 | 75 | 292 | 150 | 0.375 | 1.075 |  | BOE | 150 | 0.375 | 56.25 | 150 | 0.375 | 56.25
171 | j226 | j222 | 75 |  | 155 | 0.375 | 1.075
172 | j218a | j218b | 63 | extra | 42.9 | 0.363 | 1.063
173 | j223 | j224 | 63 | 44 | 80 | 0.363 | 1.063
174 | j223 | j217 | 63 |  | 28.7 | 0.363 | 1.063
175 | j223a | j223b | 63 | extra | 81 | 0.363 | 1.063
176 | j139 | j144 | 63 | 120 | 119.8 | 0.363 | 1.063
177 | j144 | j145 | 63 | 100 | 98.5 | 0.363 | 1.063
178 | j146 | j144 | 63 | 70 | 71.2 | 0.363 | 1.063
179 | j236 | j254 | 63 | 567 | 623 | 0.363 | 1.063
Representative PMPL - BRCCPL (JV) Pratapgarh | [6 empty] | Representative Medhaj Techno Concept Pvt Ltd (TPI) Pratapgarh |  |  |  |  | Representative UP Jal Nigam (Rural) Pratapgarh

## UTRAS
UTRAS(JMR) BLOCK-MANGRAURA
s.no | Start Node | End Node | Type of Road | WIDTH OF EXCAVATION | Dia of pipe (MM) | Pipe Length (M) | CUMMULATIVE | Depth(M) | REMARK
1 | J86 | J87 |  |  | 63 | 42.6 | 42.6 | 1.063
2 | J86 | J87 | B.T ROAD | 0.363 | 63 | 3 | 45.6 | 1.063
3 | J106 | J116 |  |  | 63 | 157.7 | 203.3 | 1.063
4 | J116 | J127 |  |  | 63 | 184.8 | 388.1 | 1.063
5 | J127 | J136 |  |  | 63 | 61.9 | 450 | 1.063
6 | J116 | J117 |  |  | 63 | 226.7 | 676.7 | 1.063
7 | J117 | J156 |  |  | 63 | 236.9 | 913.6 | 1.063
8 | J117 | J156 | B.T ROAD | 0.363 | 63 | 3.1 | 916.7 | 1.063
9 | J156 | J290 | B.T ROAD | 0.363 | 63 | 4.8 | 921.5 | 1.063
10 | J156 | J290 |  |  | 63 | 185.5 | 1107 | 1.063
11 | J156 | J290 | CULVERT |  | 63 | 7 | 1114
12 | J156 | J290 |  |  | 63 | 122 | 1236 | 1.063
13 | J291 | J292 |  |  | 63 | 155 | 1391 | 1.063
14 | J291 | J289 | BRICK ROAD | 0.363 | 63 | 2.8 | 1393.8 | 1.063
15 | J291 | J289 |  |  | 63 | 235 | 1628.8 | 1.063
16 | J305 | J297 |  |  | 63 | 25.7 | 1654.5 | 1.063
17 | J297 | J298 |  |  | 63 | 20 | 1674.5 | 1.063
18 | J298 | J304 | BRICK ROAD | 0.363 | 63 | 6.2 | 1680.7 | 1.063
19 | J298 | J272 |  |  | 63 | 97.5 | 1778.2 | 1.063
20 | J298 | J272 | CULVERT |  | 63 | 3.4 | 1781.6
21 | J298 | J272 |  |  | 63 | 104 | 1885.6 | 1.063
22 | J310 | J320 |  |  | 63 | 104.5 | 1990.1 | 1.063
23 | J322 | J324 | B.T ROAD | 0.363 | 63 | 7 | 1997.1 | 1.063
24 | J322 | J324 |  |  | 63 | 59.1 | 2056.2 | 1.063
25 | J324 | J323 |  |  | 63 | 420.9 | 2477.1 | 1.063
26 | J324 | J323 | B.T ROAD | 0.363 | 63 | 7.7 | 2484.8 | 1.063
27 | J324 | J323 |  |  | 63 | 33 | 2517.8 | 1.063
28 | J320 | J307 |  |  | 63 | 272 | 2789.8 | 1.063
29 | J130 | J126 |  |  | 63 | 271.4 | 3061.2 | 1.063
30 | J199 | J221 |  |  | 63 | 124.1 | 3185.3 | 1.063
31 | J230 | J221 |  |  | 63 | 25.7 | 3211 | 1.063
32 | J230 | J221 | BRICK ROAD | 0.363 | 63 | 25.3 | 3236.3 | 1.063
33 | J230 | J221(1) | BRICK ROAD | 0.363 | 63 | 72.9 | 3309.2 | 1.063
34 | J221 | J228 |  |  | 63 | 47.3 | 3356.5 | 1.063
35 | J199 | J201 | BRICK ROAD | 0.363 | 63 | 3 | 3359.5 | 1.063
36 | J199 | J201 |  |  | 63 | 99 | 3458.5 | 1.063
37 | J201 | J204 |  |  | 63 | 36.9 | 3495.4 | 1.063
38 | J239 | J237 |  |  | 63 | 33.3 | 3528.7 | 1.063
39 | J237 | J238 |  |  | 63 | 22.3 | 3551 | 1.063
40 | J237 | J236 |  |  | 63 | 128.8 | 3679.8 | 1.063
41 | J236 | J226 |  |  | 63 | 161.3 | 3841.1 | 1.063
42 | J236 | J226 | BRICK ROAD | 0.363 | 63 | 3.4 | 3844.5 | 1.063
43 | J117 | J101 |  |  | 63 | 131.3 | 3975.8 | 1.063
44 | J101 | J100 |  |  | 63 | 26.7 | 4002.5 | 1.063
45 | J101 | J92 |  |  | 63 | 51 | 4053.5 | 1.063
46 | J92 | J79 | B.T ROAD | 0.363 | 63 | 3 | 4056.5 | 1.063
47 | J92 | J79 |  |  | 63 | 209 | 4265.5 | 1.063
48 | J79 | J80 | B.T ROAD | 0.363 | 63 | 3.4 | 4268.9 | 1.063
49 | J79 | J80 |  |  | 63 | 307.6 | 4576.5 | 1.063
50 | J80 | J82 |  |  | 63 | 222.3 | 4798.8 | 1.063
51 | J80 | J52 |  |  | 63 | 378.6 | 5177.4 | 1.063
52 | J52 | J53 |  |  | 63 | 343.2 | 5520.6 | 1.063
53 | J52 | J40 |  |  | 63 | 478.1 | 5998.7 | 1.063
54 | J41 | J81 |  |  | 63 | 340.9 | 6339.6 | 1.063
55 | J81 | J103 |  |  | 63 | 624 | 6963.6 | 1.063
56 | J103(1) | J103(2) |  |  | 63 | 129.8 | 7093.4 | 1.063
57 | J103 | J104 |  |  | 63 | 181.8 | 7275.2 | 1.063
58 | J124 | J125 |  |  | 63 | 131 | 7406.2 | 1.063
59 | J72 | J51 |  |  | 63 | 53 | 7459.2 | 1.063
60 | J51 | J37 |  |  | 63 | 11 | 7470.2 | 1.063
61 | J37 | J73 |  |  | 63 | 25 | 7495.2 | 1.063
62 | J73 | J84 |  |  | 63 | 14 | 7509.2 | 1.063
63 | J84 | J88 |  |  | 63 | 7.6 | 7516.8 | 1.063
64 | J88 | J93 |  |  | 63 | 141.4 | 7658.2 | 1.063
65 | J88 | J93 | BRICK ROAD | 0.363 | 63 | 6 | 7664.2 | 1.063
66 | J179 | J183 |  |  | 63 | 60 | 7724.2 | 1.063
67 | J183 | J185 |  |  | 63 | 90 | 7814.2 | 1.063
68 | J185 | J187 |  |  | 63 | 80 | 7894.2 | 1.063
69 | J183 | J184 |  |  | 63 | 35 | 7929.2 | 1.063
70 | J183 | J184 | B.T ROAD | 0.363 | 63 | 4 | 7933.2 | 1.063
71 | J183 | J181 |  |  | 63 | 191 | 8124.2 | 1.063
72 | J198 | J202 |  |  | 63 | 21 | 8145.2 | 1.063
73 | J202 | J209 |  |  | 63 | 42 | 8187.2 | 1.063
74 | J198 | J197 | BRICK ROAD | 0.363 | 63 | 15.4 | 8202.6 | 1.063
75 | J198 | J197 |  |  | 63 | 100 | 8302.6 | 1.063
76 | J198(1) | J197(1) |  |  | 63 | 17 | 8319.6 | 1.063
77 | J191 | J193 | BRICK ROAD | 0.363 | 63 | 26.4 | 8346 | 1.063
78 | J197 | J207 | BRICK ROAD | 0.363 | 63 | 23.5 | 8369.5 | 1.063
79 | J197 | J207 |  |  | 63 | 10 | 8379.5 | 1.063
80 | J207 | J209 | BRICK ROAD | 0.363 | 63 | 27.2 | 8406.7 | 1.063
81 | J209 | J213 |  |  | 63 | 52.9 | 8459.6 | 1.063
82 | J213 | J212 |  |  | 63 |  | 8459.6 | 1.063
83 | J212 | J220 |  |  | 63 |  | 8459.6 | 1.063
84 | J220 | J222 |  |  | 63 |  | 8459.6 | 1.063
85 | J222 | J225 | BRICK ROAD | 0.363 | 63 | 171.2 | 8630.8 | 1.063
86 | J225 | J223 | BRICK ROAD | 0.363 | 63 | 69.3 | 8700.1 | 1.063
87 | J150 | J114 | BRICK ROAD | 0.363 | 63 | 148.9 | 8849 | 1.063
88 | J114 | J83 | BRICK ROAD | 0.363 | 63 | 162.3 | 9011.3 | 1.063
89 | J33 | J68 |  |  | 63 | 13.4 | 9024.7 | 1.063
90 | J68 | J64 |  |  | 63 | 36 | 9060.7 | 1.063
91 | J64 | J41 |  |  | 63 | 144 | 9204.7 | 1.063
92 | J41 | J104 |  |  | 63 | 173 | 9377.7 | 1.063
93 | J92 | J86 |  |  | 75 | 263.2 | 9640.9 | 1.075
94 | J86 | J78 |  |  | 75 | 119.9 | 9760.8 | 1.075
95 | J106 | J111 |  |  | 75 | 77 | 9837.8 | 1.075
96 | J136 | J126 |  |  | 75 | 147.5 | 9985.3 | 1.075
97 | J111 | J106 |  |  | 75 | 80.4 | 10065.7 | 1.075
98 | J289 | J294 | BRICK ROAD | 0.375 | 75 | 66.1 | 10131.8 | 1.075
99 | J297 | J294 | BRICK ROAD | 0.375 | 75 | 46.8 | 10178.6 | 1.075
100 | J305 | J308 |  |  | 75 | 38.2 | 10216.8 | 1.075
101 | J308 | J310 | BRICK ROAD | 0.375 | 75 | 4 | 10220.8 | 1.075
102 | J308 | J310 |  |  | 75 | 33.2 | 10254 | 1.075
103 | J136 | J156 |  |  | 75 | 268 | 10522 | 1.075
104 | J104 | J124 |  |  | 75 | 65 | 10587 | 1.075
105 | J104 | J124 |  |  | 75 | 266 | 10853 | 1.075
106 | J124 | J138 |  |  | 75 | 195.8 | 11048.8 | 1.075
107 | J158 | J169 |  |  | 75 | 74.3 | 11123.1 | 1.075
108 | J169 | J176 |  |  | 75 | 64 | 11187.1 | 1.075
109 | J176 | J177 |  |  | 75 | 33.4 | 11220.5 | 1.075
110 | J177 | J179 |  |  | 75 | 58 | 11278.5 | 1.075
111 | J125 | J83 |  |  | 90 | 536.9 | 11815.4 | 1.09
112 | J83 | J26 |  |  | 90 | 111.8 | 11927.2 | 1.09
113 | J78 | J106 |  |  | 90 | 166.3 | 12093.5 | 1.09
114 | J289 | J294 |  |  | 90 | 70 | 12163.5 | 1.09
115 | J139 | J142 | BRICK ROAD | 0.39 | 90 | 55.8 | 12219.3 | 1.09
116 | J142 | J146 | BRICK ROAD | 0.39 | 90 | 45.4 | 12264.7 | 1.09
117 | J146 | J150 | BRICK ROAD | 0.39 | 90 | 67.2 | 12331.9 | 1.09
118 | J150 | J114 |  |  | 90 | 190 | 12521.9 | 1.09
119 | J104 | J41 |  |  | 90 | 137.1 | 12659 | 1.09
120 | J130 | J139 |  |  | 110 | 282.3 | 12941.3 | 1.11
121 | J130 | J139 | BRICK ROAD | 0.41 | 110 | 46.7 | 12988 | 1.11
| 63 | 75 | 90 | 110
| 9377.7 | 1900.8 | 1380.5 | 329 |  |  | 12988
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  | SIGN.with date