## Barasarai
BARASARAI(JMR) | [6 empty] | CUMMULATIVE |  | Remark
Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | Dia of pipe | Pipe Length (M)
1 | J4 | J5 | B.T ROAD |  | 63 | 3.2 | 3.2
2 | J4 | J7 |  |  | 63 | 11.5 | 14.7
3 | J22 | J21 |  |  | 63 | 9 | 23.7
4 | J22 | J21 | BRICK ROAD |  | 63 | 14 | 37.7
5 | J24 | J23 |  |  | 63 | 105 | 142.7
6 | J25 | J39 |  |  | 63 | 78.5 | 221.2
7 | J23 | J39 | BRICK ROAD |  | 63 | 23.8 | 245
8 | J39 | J45 |  |  | 63 | 41.2 | 286.2 | [10 empty] | 0
9 | J45 | J53 |  |  | 63 | 74.8 | 361
10 | J72 | J71 |  |  | 63 | 24.5 | 385.5
11 | J71 | J70 |  |  | 63 | 18.5 | 404
12 | J70 | J68 |  |  | 63 | 60 | 464
13 | J68 | J52 |  |  | 63 | 29.5 | 493.5
14 | J52 | J68 | BRICK ROAD |  | 63 | 55.4 | 548.9
15 | J52 | J50 |  |  | 63 | 25.4 | 574.3
16 | J52 | J46 |  |  | 63 | 15.4 | 589.7
17 | J46 | J45 |  |  | 63 | 77.3 | 667
18 | J39 | J38 |  |  | 63 | 24.5 | 691.5
19 | J38 | J37 | BRICK ROAD |  | 63 | 22.1 | 713.6
20 | J38 | J43 | BRICK ROAD |  | 63 | 47.5 | 761.1
21 | J43 | J46 |  |  | 63 | 19 | 780.1
22 | J43 | J44 | BRICK ROAD |  | 63 | 39.9 | 820
23 | J68 | J69 | BRICK ROAD |  | 63 | 18.4 | 838.4
24 | J73 | J74 | BRICK ROAD |  | 63 | 123.5 | 961.9
25 | J76 | J75 | BRICK ROAD |  | 63 | 68.2 | 1030.1
26 | J76 | J71 |  |  | 63 | 95.7 | 1125.8
27 | J70 | J75 |  |  | 63 | 61.5 | 1187.3
28 | J89 | J90 | BRICK ROAD |  | 63 | 8.4 | 1195.7
29 | J89 | J90 |  |  | 63 | 157 | 1352.7
30 | J83 | J82 |  |  | 63 | 22.2 | 1374.9
31 | J82 | J88 |  |  | 63 | 69.8 | 1444.7
32 | J82 | J80 |  |  | 63 | 84.2 | 1528.9
33 | J80 | J79 |  |  | 63 | 28.5 | 1557.4
34 | J80 | J86 |  |  | 63 | 117.2 | 1674.6
35 | J80 | J86 | BRICK ROAD |  | 63 | 16 | 1690.6
36 | J86 | J81 | BRICK ROAD |  | 63 | 96.3 | 1786.9
37 | J92 | J93 |  |  | 63 | 288.8 | 2075.7
38 | J36 | J32 |  |  | 63 | 115.1 | 2190.8
39 | J32 | J33 | BRICK ROAD |  | 63 | 34.2 | 2225
40 | J32 | J30 | BRICK ROAD |  | 63 | 73.5 | 2298.5
41 | J30 | J27 |  |  | 63 | 47 | 2345.5
42 | J79 | J133 |  |  | 63 | 637 | 2982.5
43 | J133 | J140 |  |  | 63 | 7 | 2989.5 |  | culvert
44 | J133 | J140 |  |  | 63 | 275.6 | 3265.1
45 | J133 | J140 |  |  | 63 | 11 | 3276.1
46 | J133 | J140 | B.T ROAD |  | 63 | 3 | 3279.1
47 | J144 | J144A |  |  | 63 | 8 | 3287.1
48 | J144A | J144B |  |  | 63 | 113 | 3400.1
49 | J144A | J141 |  |  | 63 | 66.3 | 3466.4
50 | J141 | J141A |  |  | 63 | 73 | 3539.4
51 | J141 | J141B |  |  | 63 | 50 | 3589.4
52 | J127 | J128 |  |  | 63 | 168 | 3757.4
53 | J96 | J97 |  |  | 63 | 148.5 | 3905.9
54 | J54 | J57 | B.T ROAD |  | 63 | 3 | 3908.9
55 | J54 | J57 |  |  | 63 | 134 | 4042.9
56 | J57 | J61 | B.T ROAD |  | 63 | 3 | 4045.9
57 | J57 | J61 |  |  | 63 | 268.9 | 4314.8
58 | J57 | J62 |  |  | 63 | 140 | 4454.8
59 | J62 | J63 |  |  | 63 | 147 | 4601.8
60 | J62 | J63 | B.T ROAD |  | 63 | 3 | 4604.8
61 | J55 | J56 |  |  | 63 | 181.7 | 4786.5
62 | J67 | J49 |  |  | 63 | 216.5 | 5003
63 | J186 | J188 |  |  | 63 | 98 | 5101
64 | J213 | J219 |  |  | 63 | 164 | 5265
65 | J213 | J217 |  |  | 63 | 88 | 5353
66 | J213 | J217 | BRICK ROAD |  | 63 | 30 | 5383
67 | J217 | J226 | BRICK ROAD |  | 63 | 28 | 5411
68 | J217 | J226 |  |  | 63 | 17.2 | 5428.2
69 | J226 | J226A |  |  | 63 | 12.7 | 5440.9
70 | J226A | J226B |  |  | 63 | 12.2 | 5453.1
71 | J226A | J226C |  |  | 63 | 36.3 | 5489.4
72 | J209 | J207 |  |  | 63 | 12.4 | 5501.8
73 | J209 | J208 |  |  | 63 | 46 | 5547.8
74 | J209A | J209B |  |  | 63 | 17.7 | 5565.5
75 | j201 | j201A |  |  | 63 | 26.3 | 5591.8
76 | J210 | J210A | BRICK ROAD |  | 63 | 70 | 5661.8
77 | J210A | J210B |  |  | 63 | 46.7 | 5708.5
78 | J210A | J212 | BRICK ROAD |  | 63 | 27.5 | 5736
79 | J216 | J215 | B.T ROAD |  | 63 | 3 | 5739
80 | J216 | J215 | BRICK ROAD |  | 63 | 32 | 5771
81 | J218 | J223 | B.T ROAD |  | 63 | 3 | 5774
82 | J218 | J223 |  |  | 63 | 64.3 | 5838.3
83 | J200 | J199 |  |  | 63 | 125 | 5963.3
84 | J223 | J224 | B.T ROAD |  | 63 | 3 | 5966.3
85 | J223 | J224 | BRICK ROAD |  | 63 | 21 | 5987.3
86 | J232 | J233 |  |  | 63 | 59.6 | 6046.9
87 | J233 | J233A | B.T ROAD |  | 63 | 3 | 6049.9
88 | J233 | J233A |  |  | 63 | 26.6 | 6076.5
89 | J233A | J233B |  |  | 63 | 109.5 | 6186
90 | J233A | J226 |  |  | 63 | 63 | 6249
91 | J234 | J251 | INTERLOCKING |  | 63 | 107.3 | 6356.3
92 | J251 | J254 | INTERLOCKING |  | 63 | 1.5 | 6357.8
93 | J251 | J254 |  |  | 63 | 10 | 6367.8
94 | J254 | J255 | BRICK ROAD |  | 63 | 32.1 | 6399.9
95 | J254 | J255 |  |  | 63 | 87.2 | 6487.1
96 | J251 | J252 | INTERLOCKING |  | 63 | 17.8 | 6504.9
97 | J252 | J253 | INTERLOCKING |  | 63 | 4 | 6508.9
98 | J252 | J253 |  |  | 63 | 11 | 6519.9
99 | J252 | J249 | INTERLOCKING |  | 63 | 29 | 6548.9
100 | J252 | J249 |  |  | 63 | 165 | 6713.9
101 | J249 | J250 |  |  | 63 | 108.3 | 6822.2
102 | J249 | J232 |  |  | 63 | 162 | 6984.2
103 | J249 | J232 | BRICK ROAD |  | 63 | 23 | 7007.2
104 | J157 | J154 |  |  | 63 | 79 | 7086.2
105 | J157 | J155 |  |  | 63 | 10 | 7096.2
106 | J138 | J139 |  |  | 63 | 18 | 7114.2
107 | J1 | J3 |  |  | 63 | 305 | 7419.2
108 | J52 | J46 |  |  | 63 | 314.6 | 7733.8
109 | J114 | J117 | INTERLOCKING |  | 63 | 16.7 | 7750.5
110 | J114 | J117 |  |  | 63 | 79.6 | 7830.1
111 | J117 | J118 |  |  | 63 | 78 | 7908.1
112 | J117 | J120 |  |  | 63 | 12.5 | 7920.6
113 | J120 | J121 |  |  | 63 | 35.3 | 7955.9
114 | J120 | J122 |  |  | 63 | 75 | 8030.9
115 | J115 | J116 |  |  | 63 | 75 | 8105.9
116 | J158 | J159 |  |  | 63 | 69 | 8174.9
117 | J158 | J170 |  |  | 63 | 298.5 | 8473.4
118 | J170 | J177 |  |  | 63 | 115.2 | 8588.6
119 | J177 | J185 |  |  | 63 | 22.4 | 8611
120 | J177 | J185 | BRICK ROAD |  | 63 | 227 | 8838
121 | J177 | J171 |  |  | 63 | 107.3 | 8945.3
122 | J170 | J166 |  |  | 63 | 90.8 | 9036.1
123 | J166 | J169 |  |  | 63 | 70 | 9106.1
124 | J166 | J161 |  |  | 63 | 61.6 | 9167.7
125 | J161 | J162 |  |  | 63 | 70 | 9237.7
126 | J161 | j157 |  |  | 63 | 29.6 | 9267.3
127 | J112 | J111 |  |  | 63 | 23.9 | 9291.2
128 | J94 | J110 |  |  | 63 | 48.6 | 9339.8
129 | [6 empty] | 9339.8
130 | J91 | J98 | BRICK ROAD |  | 63 | 190.8 | 9530.6
131 | J91 | J98 |  |  | 63 | 11 | 9541.6
132 | J98 | J99 |  |  | 63 | 11 | 9552.6
133 | J99 | J105 |  |  | 63 | 70 | 9622.6
134 | J99 | J107 |  |  | 63 | 133.3 | 9755.9
135 | J107 | J108 |  |  | 63 | 58 | 9813.9
136 | J107 | J109 |  |  | 63 | 113.8 | 9927.7
137 | J98 | J100 |  |  | 63 | 58.4 | 9986.1
138 | [6 empty] | 9986.1
139 | J110 | J114 |  |  | 63 | 188 | 10174.1
140 | J114 | J113 |  |  | 63 | 21 | 10195.1
141 | J114 | J113 |  |  | 63 | 1.8 | 10196.9
142 | J82A | J82B |  |  | 63 | 31 | 10227.9
143 | J23 | J18 |  |  | 63 | 124 | 10351.9
144 | J209 | J209A |  |  | 75 | 33.3 | 10385.2
145 | J146 | J158 |  |  | 75 | 282.1 | 10667.3
146 | J155 | J151 |  |  | 75 | 185 | 10852.3
147 | J151 | J145 |  |  | 75 | 95.5 | 10947.8
148 | J151 | J154 |  |  | 75 | 129 | 11076.8
149 | J154 | J160 |  |  | 75 | 86.6 | 11163.4
150 | J10 | J22 | BRICK ROAD |  | 75 | 88 | 11251.4
151 | J10 | J22 |  |  | 75 | 69 | 11320.4
152 | J22 | J24 |  |  | 75 | 27.6 | 11348
153 | J24 | J25 |  |  | 75 | 37.5 | 11385.5
154 | J25 | J53 |  |  | 75 | 164.5 | 11550
155 | J53 | J72 |  |  | 75 | 136.1 | 11686.1
156 | J72 | J79 |  |  | 75 | 243 | 11929.1
157 | J217 | J209 | BRICK ROAD |  | 75 | 62.2 | 11991.3
158 | J209 | J198 |  |  | 75 | 151 | 12142.3
159 | J201 | J201A |  |  | 75 | 72 | 12214.3
160 | J216 | J218 |  |  | 75 | 30.2 | 12244.5
161 | J218 | J200 |  |  | 75 | 4 | 12248.5
162 | J200 | J223 |  |  | 75 | 55.8 | 12304.3
163 | J223 | J232 |  |  | 75 | 102 | 12406.3
164 | J192 | J193 |  |  | 90 | 42.5 | 12448.8
165 | J196 | J213 |  |  | 90 | 278.5 | 12727.3
166 | J196 | J198 |  |  | 90 | 48 | 12775.3
167 | J198 | J201 |  |  | 90 | 46.5 | 12821.8
168 | J198 | J201 | INTERLOCKING |  | 90 | 5 | 12826.8
169 | J201 | J204 |  |  | 90 | 117 | 12943.8
170 | J201 | J204 | B.T ROAD |  | 90 | 5 | 12948.8
171 | J204 | J210 |  |  | 90 | 43 | 12991.8
172 | J210 | J216 |  |  | 90 | 38.3 | 13030.1
173 | J204 | J197 |  |  | 90 | 113 | 13143.1
174 | J204 | J197 | B.T ROAD |  | 90 | 3 | 13146.1
175 | J197 | J145 |  |  | 90 | 663 | 13809.1
176 | J69 | J73 | BRICK ROAD |  | 110 | 50.9 | 13860
177 | J73 | J76 |  |  | 110 | 9 | 13869
178 | J73 | J76 | BRICK ROAD |  | 110 | 16.7 | 13885.7
179 | J76 | J81 |  |  | 110 | 151.6 | 14037.3
180 | J81 | J89 | BRICK ROAD |  | 110 | 20 | 14057.3
181 | J89 | J92 | culvert |  | 110 | 5 | 14062.3 |  | culvert
182 | J89 | J92 | B.T ROAD |  | 110 | 3 | 14065.3
183 | J89 | J92 | BRICK ROAD |  | 110 | 10 | 14075.3
184 | J144 | J140 |  |  | 110 | 42 | 14117.3
185 | J140 | J127 |  |  | 110 | 154.2 | 14271.5
186 | J127 | J96 |  |  | 110 | 350 | 14621.5
187 | J127 | J96 | B.T ROAD |  | 110 | 6 | 14627.5
188 | J96 | J92 |  |  | 110 | 28.7 | 14656.2
189 | J144 | J186 |  |  | 110 | 182.8 | 14839
190 | J186 | J192 |  |  | 110 | 152.7 | 14991.7
191 | J192 | J196 | B.T ROAD |  | 110 | 8 | 14999.7
192 | J192 | J196 |  |  | 110 | 177 | 15176.7
193 | J11 | J19 |  |  | 110 | 144 | 15320.7
194 | J19 | J50 |  |  | 110 | 141 | 15461.7
195 | J115 | J124 | BRICK ROAD |  | 110 | 31 | 15492.7
196 | J115 | J124 | culvert |  | 110 | 8 | 15500.7 |  | culvert
197 | J115 | J124 |  |  | 110 | 40 | 15540.7
198 | [6 empty] | 15540.7
199 | [6 empty] | 15540.7
200 | [6 empty] | 15540.7
201 | [6 empty] | 15540.7
202 | J26 | J51 |  |  | 110 | 19 | 15559.7
203 | J51 | J69 |  |  | 110 | 69 | 15628.7
204 | J113 | J112 |  |  | 125 | 65.1 | 15693.8
205 | J94 | J91 |  |  | 125 | 48 | 15741.8
206 | J91 | J67 |  |  | 125 | 327 | 16068.8
207 | J113 | J115 | BRICK ROAD |  | 125 | 87.9 | 16156.7
208 | J2 | J3 |  |  | 140 | 172.5 | 16329.2
209 | J3 | J11 |  |  | 140 | 80 | 16409.2
210 | J3 | J4 |  |  | 140 | 19.8 | 16429
211 | J4 | J10 |  |  | 140 | 29.2 | 16458.2
212 | J4 | J10 | B.T ROAD |  | 140 | 3 | 16461.2
213 | J10 | J49 | culvert |  | 140 | 3 | 16464.2 |  | culvert
214 | J10 | J49 |  |  | 140 | 403 | 16867.2
215 | J49 | J54 |  |  | 140 | 121 | 16988.2
216 | J54 | J55 |  |  | 140 | 29 | 17017.2
217 | J55 | J67 |  |  | 140 | 121.5 | 17138.7 |  |  |  |  | 262.5
218 | J1 | J2 |  |  | 160 | 228 | [5 empty] | 21.875
219
220
221
222
223
224
225
226
227
228
229
230
231
232 | j197 | j199 |  |  | 63 | 93
233 | j199 | j221 |  |  | 63 | 150
234 | j193 | j195 |  |  | 90 | 43
235 | j195 | j257 |  |  | 75 | 300 |  |  |  |  | 378
236 | j195(1) | j257(2) |  |  | 63 | 135
237 | j257 | j260 |  |  | 63 | 77
238 | j260 | j269 |  |  | 63 | 29
239 | j260 | j262 |  |  | 63 | 43
240 | j262 | j259 |  |  | 63 | 38
241 | j262 | j264 |  |  | 63 | 22
242 | j264 | j263 |  |  | 63 | 58
243 | j264 | j261 |  |  | 63 | 118
244 | j261 | j268 |  |  | 63 | 129
245 | j74(1) | j36(1) |  |  | 63 | 40
| 63 | 75 | 90 | 110 | 125 | 140 | 160
| 11283.9 | 2354.4 | 1445.8 | 1819.6 | 528 | 982 | 228 |  | 18641.7
Abstract (Bill Breakup)
1 | Dia of Pipe | WO/DPR Qty's | Laying, Jointing, Backfilling - 60% |  |  |  | Gap Closing- 5% |  |  |  | Hydro Test - 15% |  |  |  | FHTC Stretch - 10%
|  |  | Laying Up to Date | Laying Qty Billed up to Date | Qty Billed Up to Previous | This Bill Qty (Laying) | WO/DPR Qty's | GAP Closing Billed Qty up to Date | GAP Closing Qty Up to Previous | This Bill Qty (GAP Closing) | WO/DPR Qty's | Hydro Test Qty Billed up to Date | Hydro Test Qty Up to Previous | This Bill Qty (Hydro Test ) | FHTC Stretch Qty Billed up to Date | FHTC Stretch Qty Billed Up to Previous | This Bill Qty (FHTC Stretch Billed )
1.1 | 63 mm HDPE |  | 11283.9 | 11283.9 | 10411 | 872.9
1.2 | 75 mm HDPE |  | 2354.4 | 2354.4 | 2054 | 300.4
1.3 | 90 mm HDPE |  | 1445.8 | 1445.8 | 1402 | 43.8
1.4 | 110mm HDPE |  | 1819.6 | 1819.6 | 1819 | 0.6
1.5 | 125mm HDPE |  | 528 | 528 | 528 | 0
1.6 | 140mm HDPE |  | 982 | 982 | 982 | 0
1.7 | 160mm HDPE |  | 228 | 228 | 228 | 0
1.8 | 180mm HDPE
1.9 | 200mm HDPE
Sub Total = |  |  | 18641.7 | 19987 | 13010 | 1217.7
Sub-Contractor Site Engineer (Sr.Eng/ DY.M-SMX ) (Dy.M-PMX ) AGM Project Incharge

## BARASARAI (2)
Block |  | Mangraura
GP |  | BARASARAI
Agency Name/ Work Order No |  | AGS CONSTRUCTION
63MM
Sl.No | Date | Issue (M) | Laid (M) | Balance Against Issue (M) | indent | [8 empty] | DIA | TOTALSCOPE | Issue (M) | Laid (M) | Balance Against Issue (M) | return
1 | 2023-04-27 | 1950 |  |  | 2239 | Specials |  | Specification | Issue | Laid | Balance Against Issue | Remarks |  | 63 | 14448 | 11700 | 11283.9 | 416.1
2 | 2023-05-20 | 2450 |  |  | 503 | Equal TEE |  | 63mm | 20 |  |  |  |  | 75 | 2831 | 2400 | 2354.4 | 45.6
3 | 2023-05-29 | 400 |  |  | 4341 |  |  | 75mm | 2 |  |  |  |  | 90 | 1614 | 1000 | 1445.8 | -445.8
4 | 2023-06-04 | 2700 |  |  | 20452 |  |  | 90mm | [5 empty] | 110 | 2095 | 1875 | 1819.6 | 55.4
5 | 2023-06-17 | 3000 |  |  | 4342 |  |  | 110mm | [5 empty] | 125 | 751 | 744 | 528 | 216
6 |  | 900 |  |  | 14619 |  |  | 125mm | [5 empty] | 140 | 1022 | 1092 | 982 | 110 | 110
7 |  | 300 |  |  | 14618 |  |  | 140mm | [5 empty] | 160 | 287 | 288 | 228 | 60
[8 empty] | 160mm | [7 empty] | 19099
200mm
250mm
| TOTAL | 11700 |  |  |  | Branch TEE |  | 63mm X 50mm
75MM | [7 empty] | 75mm X 50mm
Sl.No | Date | Issue (M) | Laid (M) | Balance Against Issue (M) | Remarks |  |  | 90 mm X 50 mm
1 | 2023-05-07 | 800 |  |  | 4339 |  |  | 110mm X 50mm
2 | 2023-05-20 | 1200 |  |  | 503 |  |  | 125mm X 50mm
3 |  | 400 |  |  | 14618 |  |  | 140mm X 50mm
3 | [7 empty] | 160mm X 50mm
[8 empty] | 75 mm X 63 mm |  | 6 |  |  | 503
90 mm X 63 mm
90 mm X 75 mm
110mm X 63 mm
110mm X 75 mm
110mm X 90 mm
125mm X 63 mm
| TOTAL | 2400 | [5 empty] | 125mm X75 mm
90MM | [7 empty] | 125mm X90 mm
Sl.No | Date | Issue (M) | Laid (M) | Balance Against Issue (M) | Remarks |  |  | 125mm X 110mm
1 | 2023-04-27 | 400 |  |  | 2239 |  |  | 140mm X 63 mm
2 | 2023-06-17 | 600 |  |  | 4342 |  |  | 140mm X 75 mm
140mm X 90 mm
140mm X 110mm
140mm X 125 mm
160mm X 63 mm
160mm X 75 mm
160mm X 90 mm
160mm X 110 mm
160mm X 125 mm
| TOTAL | 1000 | [5 empty] | 160mm X 140 mm
110MM | [7 empty] | 200mm X 63 mm
Sl.No | Date | Issue (M) | Laid (M) | Balance Against Issue (M) | Remarks |  |  | 200mm X 75 mm
200mm X 90 mm
2 | 2023-06-29 | 875 |  |  | 4341 |  |  | 200mm X 110 mm
3 | 2023-07-10 | 1000 |  |  | 20460 |  |  | 200mm X 125 mm
4 | [7 empty] | 200mm X 140 mm
5 | [7 empty] | 200mm X 160 mm
6 | [7 empty] | 250mm X 63 mm
7 | [7 empty] | 250mm X 75 mm
8 | [7 empty] | 250mm X 90 mm
250mm X 110 mm
| TOTAL | 1875 | [5 empty] | 250mm X 140 mm
250mm X 160 mm
125MM | [5 empty] | 4-Way TEE |  | 63mm
Sl.No | Date | Issue (M) | Laid (M) | Balance Against Issue (M) | Remarks |  |  | 75mm
1 | 2023-07-28 | 744 |  |  | 20461 |  |  | 90mm
110mm
125mm
140mm
160mm
200mm
250mm
| TOTAL | 744 |  |  |  | Reducer |  | 75mm X 63 mm |  | 5
[8 empty] | 90mm X 63 mm |  | 2 |  |  | 20459
140MM | [7 empty] | 90mm X 75 mm |  | 2 |  |  | 20459
Sl.No | Date | Issue (M) | Laid (M) | Balance Against Issue (M) | Remarks |  |  | 110 mm X 63 mm |  | 8 |  |  | 20459
1 | 2023-07-28 | 1092 |  |  | 20461 |  |  | 110 mm X 75 mm |  | 2 |  |  | 20459
110 mm X 90 mm
125 mm X 63 mm
125 mm X 75 mm
125 mm X 90 mm
125 mm X 110 mm
140mm X 63 mm
| TOTAL | 1092 | [5 empty] | 140mm X 75 mm
140mm X 90 mm
160MM | [7 empty] | 140mm X 110mm
Sl.No | Date | Issue (M) | Laid (M) | Balance Against Issue (M) | Remarks |  |  | 140mm X 125mm
1 | 2023-07-28 | 288 |  |  | 20461 |  |  | 160mm X 63 mm
160mm X 75 mm
160mm X 90 mm
160mm X 110mm
160mm X 125mm
160mm X 140mm
200mm X 63mm
| TOTAL | 288 | [5 empty] | 200mm X 75mm
200mm X 90mm
200mm X 110mm
200mm X 125mm
200mm X 140mm
200mm X 160mm
250mm X 63mm
250mm X 75mm
250mm X 110mm
250mm X 140mm
250mm X 160mm
250mm X 200mm
[6 empty] | End Caps |  | 63mm | 20
75mm
90mm
110mm
125mm
140mm
160mm
[6 empty] | Bends | 63mm | 90 Deg
45 Deg
[7 empty] | 75mm | 90 Deg
45 Deg
[7 empty] | 90mm | 90 Deg
45 Deg
[7 empty] | 110mm | 90 Deg
45 Deg
[7 empty] | 125mm | 90 Deg
45 Deg
[7 empty] | 140mm | 90 Deg
45 Deg
[7 empty] | 160mm | 90 Deg
45 Deg
[7 empty] | 200mm | 90 Deg
45 Deg
[7 empty] | 250mm | 90 Deg
45 Deg
[6 empty] | Stubbends |  | 50mm
63mm
75mm
90mm
110mm
125mm
140mm
160mm
200mm
[6 empty] | MS Flanges |  | 50mm
63mm
75mm
90mm
110mm
125mm
140mm
160mm
200mm
[6 empty] | Air Valves |  | 63mm
75mm
90mm
110mm
125mm
140mm
160mm
200mm
250mm
[6 empty] | Sluice Valves |  | 63mm
75mm
90mm
110mm
125mm
140mm
160mm
200mm
250mm
[6 empty] | Scour Valves |  | 63mm
75mm
90mm
110mm
125mm
140mm
160mm
200mm
DI Specials
[6 empty] | DI Bends | 200mm | 90 Deg
45 Deg
22 Deg
[7 empty] | 250mm | 90 Deg
45 Deg
22 Deg
[6 empty] | DI Branch TEE |  | 200mmx80mm
200mmx100mm
200mmx150mm
250mmx80mm
250mmx150mm
250mmx200mm
[6 empty] | DI Reducer Both Socket |  | 200mmx80mm
200mmx100mm
200mmx150mm
[6 empty] | DI Reducer Double Flanged |  | 150mmx100mm
200mmx100mm
200mmx150mm
250mmx150mm
250mmx200mm
[6 empty] | DI Flange Socket |  | 200mm
[6 empty] | DI Tail Piece 0.3m length |  | 80mm
100mm
150mm
200mm
250mm
[6 empty] | DI Equal TEE All Side Socket |  | 200mm
250mm
[6 empty] | DI 4 Way |  | 200mm
250mm
[6 empty] | Nuts & Bolts |  | Length:140mm, Dia:16mm
[6 empty] | Packing Sheet |  | 3mm Thick