## sarsidhi PIPELAYING
Sarsidhi(JMR) BLOCK-MANGRAURA
Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | Dia of pipe(MM) | Pipe Length (M) | CUMMULATIVE | Depth(M) | REMARK
1 | j149 | j144 | kc raod |  | 63 | 83.6 | 83.6 | 1.04
2 | j144 | j138 | kc raod |  | 63 | 122.8 | 206.4 | 1.03
3 | j138 | j137 | kc raod |  | 63 | 17.1 | 223.5 | 1.03
4 | j137 | j147 | kc raod |  | 63 | 345.3 | 568.8 | 1.03
5 | j137 | j122 | kc raod |  | 63 | 105.2 | 674 | 1.03
6 | j122 | j123 | kc raod |  | 63 | 33.5 | 707.5 | 1.03
7 | j109 | j110 | kc raod |  | 63 | 66.2 | 773.7 | 1.03
8 | j110 | j112 | kc raod |  | 63 | 24 | 797.7 | 1.03
9 | j133 | j135 | kc raod |  | 63 | 11.4 | 809.1 | 1.03
10 | j135 | j148 | kc raod |  | 63 | 53.2 | 862.3 | 1.05
11 | j148 | j153 | kc raod |  | 63 | 56.3 | 918.6 | 1.03
12 | j148 | j155 | kc raod |  | 63 | 84.3 | 1002.9 | 1.03
13 | j153 | j156 | kc raod |  | 63 | 18.1 | 1021 | 1.05
14 | j156 | j157 | kc raod |  | 63 | 70.3 | 1091.3 | 1.03
15 | j156 | j166 | kc raod |  | 63 | 19.1 | 1110.4 | 1.03
16 | j166 | j173 | kc raod |  | 63 | 89.4 | 1199.8 | 1.06
17 | j173 | j172 | kc raod |  | 63 |  | 1199.8 | 1.05
18 | j166 | j172 | kc raod |  | 63 | 52.6 | 1252.4 | 1.03
19 | j172 | j179 | kc raod |  | 63 | 77.9 | 1330.3 | 1.06
20 | j179 | j180 | kc raod |  | 63 | 70.2 | 1400.5 | 1.06
21 | j180 | j181 | kc raod |  | 63 | 28.2 | 1428.7 | 1.06
22 | j45 | j48 | kc raod |  | 63 | 68.7 | 1497.4 | 0.95
23 | j57 | j58 | kc raod |  | 63 | 46.2 | 1543.6 | 0.96
24 | j59 | j60 | kc raod |  | 63 | 12.1 | 1555.7 | 0.96
25 | j76 | j80 | kc raod |  | 63 | 85.6 | 1641.3 | 1.05
26 | j76 | j81 | kc raod |  | 63 | 63.7 | 1705 | 1.06
27 | j81 | j82 | kc raod |  | 63 | 118.1 | 1823.1 | 1.06
28 | j81 | j83 | kc raod |  | 63 | 40.1 | 1863.2 | 1.06
29 | j83 | j86 | kc raod |  | 63 | 57.2 | 1920.4 | 1.06
30 | j86 | j87 | kc raod |  | 63 | 123.1 | 2043.5 | 1.02
31 | j92 | j93 | kc raod |  | 63 | 59.2 | 2102.7 | 1.02
32 | j80 | j78 | kc raod |  | 63 | 130.2 | 2232.9 | 1.02
33 | j78 | j77 | kc raod |  | 63 | 70.5 | 2303.4 | 1.02
34 | j106 | j107 | kc raod |  | 63 | 293.1 | 2596.5 | 1.04
35 | j80 | j105 | kc raod |  | 63 | 355.1 | 2951.6 | 1.06
36 | j105 | j116 | kc raod |  | 63 | 367.2 | 3318.8 | 1.04
37 | j116 | j126 | kc raod |  | 63 | 39.3 | 3358.1 | 1.04
38 | j126 | j140 | kc raod |  | 63 | 105.4 | 3463.5 | 1.04
39 | j140 | j141 | kc raod |  | 63 | 108.8 | 3572.3 | 1.06
40 | j151 | j171 | kc raod |  | 63 | 270.9 | 3843.2 | 1.06
41 | j171 | j169 | kc raod |  | 63 | 122.5 | 3965.7 | 1.06
42 | j169 | j183 | kc raod |  | 63 | 216.7 | 4182.4 | 1.06
43 | j169 | j158 | kc raod |  | 63 | 4.1 | 4186.5 | 1.06
44 | j158 | j149 | kc raod |  | 63 | 68.3 | 4254.8 | 1.04
45 | j149 | j150 | kc raod |  | 63 | 68.4 | 4323.2 | 1.04
46 | j9 | j8 | kc raod |  | 63 | 317.8 | 4641 | 1.06
47 | j8 | j4 | Brick road |  | 63 | 3 | 4644 | 1.06
48 | j8 | j4 | kc raod |  | 63 | 109.2 | 4753.2 | 1.04
49 | j4 | j5 | Brick road |  | 63 | 3 | 4756.2 | 1.06
50 | j4 | j5 | kc raod |  | 63 | 111.6 | 4867.8 | 1.06
51 | j4 | j1 | kc raod |  | 63 | 184.8 | 5052.6 | 1.06
52 | j8 | j10 | kc raod |  | 63 | 40.3 | 5092.9 | 1.06
53 | j109 | j13 | kc raod |  | 63 | 165.2 | 5258.1 | 1.04
54 | j25 | j29 | kc raod |  | 63 | 222.5 | 5480.6 | 1.03
55 | j29 | j31 | kc raod |  | 63 | 115.5 | 5596.1 | 1.03
56 | j31 | j32 | kc raod |  | 63 | 20.5 | 5616.6 | 1.03
57 | j32 | j36 | kc raod |  | 63 | 36.3 | 5652.9 | 1.03
58 | j36 | j37 | kc raod |  | 63 | 24.5 | 5677.4 | 1.03
59 | j39 | j21 | kc raod |  | 63 | 70.1 | 5747.5 | 1.03
60 | j21 | j12 | kc raod |  | 63 | 62.3 | 5809.8 | 1.03
61 | j50 | j48 | kc raod |  | 63 | 122.5 | 5932.3 | 1.03
62 | j75 | j73 | kc raod |  | 63 | 117.3 | 6049.6 | 1.05
63 | j73 | j74 | kc raod |  | 63 | 128.1 | 6177.7 | 1.03
64 | j181 | j182 | kc raod |  | 63 | 70 | 6247.7 | 1.03
65 | j181 | j171 | kc raod |  | 63 | 70.3 | 6318 | 1.05
66 | j180 | j176 | kc raod |  | 63 | 55.1 | 6373.1 | 1.03
67 | j176 | j174 | kc raod |  | 63 | 26.1 | 6399.2 | 1.03
68 | j176 | j168 | kc raod |  | 63 | 52.3 | 6451.5 | 1.06
69 | j168 | j169 | kc raod |  | 63 | 28.5 | 6480 | 1.05
70 | j170 | j168 | kc raod |  | 63 | 35.2 | 6515.2 | 1.03
71 | j170 | j167 | kc raod |  | 63 | 61.1 | 6576.3 | 1.06
72 | j174 | j175 | kc raod |  | 63 | 23.4 | 6599.7 | 1.06
73 | j22 | j27 | kc raod |  | 63 | 137.2 | 6736.9 | 1.04
74 | j27 | j28 | kc raod |  | 63 | 13.1 | 6750 | 1.03
75 | j175 | j177 | kc raod |  | 63 | 45.1 | 6795.1 | 1.03
76 | j177 | j179 | kc raod |  | 63 | 20.1 | 6815.2 | 1.03
77 | j155 | j167 | kc raod |  | 63 | 56.9 | 6872.1 | 1.03
78 | j159 | j162 | kc raod |  | 63 | 8.4 | 6880.5 | 1.03
79 | j162 | j163 | kc raod |  | 63 | 96.3 | 6976.8 | 1.03
80 | j163 | j164 | kc raod |  | 63 | 29.1 | 7005.9 | 1.03
81 | j164 | j158 | kc raod |  | 63 | 35.2 | 7041.1 | 1.03
82 | j164 | j168 | kc raod |  | 63 | 38.5 | 7079.6 | 1.05
83 | j32 | j33 | kc raod |  | 63 | 42 | 7121.6 | 1.03
84 | j33 | j34 | kc raod |  | 63 | 40 | 7161.6 | 1.03
85 | j33 | j35 | kc raod |  | 63 | 102 | 7263.6 | 1.05
86 | j75 | j59 | kc raod |  | 90 | 105.3 | 7368.9 | 1.03
87 | j59 | j57 | kc raod |  | 90 | 79.2 | 7448.1 | 1.03 |  |  |  |  | 334
88 | j57 | j54 | kc raod |  | 90 | 396.8 | 7844.9 | 1.06
89 | j54 | j45 | kc raod |  | 90 | 340.5 | 8185.4 | 1.05
90 | j75 | j76 | kc raod |  | 90 | 85 | 8270.4 | 1.03
91 | j122 | j118 | kc raod |  | 90 | 38.2 | 8308.6 | 1.06
92 | j118 | j113 | kc raod |  | 90 | 36.1 | 8344.7 | 1.06
93 | j113 | j109 | kc raod |  | 90 | 16.9 | 8361.6 | 1.03
94 | j108 | j106 | kc raod |  | 90 | 98.3 | 8459.9 | 1.03
95 | j108 | j114 | kc raod |  | 90 | 29.8 | 8489.7 | 1.03
96 | j114 | j128 | kc raod |  | 90 | 70.2 | 8559.9 | 1.03
97 | j128 | j130 | kc raod |  | 90 | 10.3 | 8570.2 | 1.03
98 | j130 | j133 | kc raod |  | 90 | 59.3 | 8629.5 | 1.03
99 | j67 | j75 | BT road |  | 90 | 3 | 8632.5 | 1.03
100 | j67 | j75 | kc raod |  | 90 | 231.1 | 8863.6 | 1.03
101 | j51 | j55 | kc raod |  | 110 | 102.3 | 8965.9 | 1.03
102 | j55 | j67 |  |  | 110 | 3 | 8968.9 |  | Culvert
103 | j55 | j67 | kc raod |  | 110 | 283.3 | 9252.2 | 1.05
104 | j77 | j67 | BT road |  | 110 | 3 | 9255.2 | 1.05
105 | j77 | j67 | kc raod |  | 110 | 160.2 | 9415.4 | 1.03
106 | j77 | j106 | kc raod |  | 110 | 548.2 | 9963.6 | 1.03 | [5 empty] | 24048
107 | j41 | j42 | kc raod |  | 125 | 31.1 | 9994.7 | 1.05
108 | j44 | j47 | kc raod |  | 125 | 91.6 | 10086.3 | 1.04
109 | j47 | j50 | kc raod |  | 125 | 204.3 | 10290.6 | 1.03
110 | j50 | j51 | kc raod |  | 125 | 145.4 | 10436 | 1.03
111 | j12 | j7 | kc raod |  | 140 | 39.3 | 10475.3 | 1.03
112 | j7 | j6 | kc raod |  | 140 | 48.5 | 10523.8 | 1.03
113 | j6 | j2 | kc raod |  | 140 | 17.5 | 10541.3 | 1.03
114 | j2 | j1 | kc raod |  | 140 | 130.8 | 10672.1 | 1.03
115 | j12 | j41 | kc raod |  | 140 | 219.9 | 10892 | 1.03
|  | 63 | 90 | 110 | 125 | 140
|  | 7263.6 | 1600 | 1100 | 472.4 | 456 | 10892
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  | SIGN.with date
Abstract (Bill Breakup)
1 | Dia of Pipe | WO/DPR Qty's | Laying, Jointing, Backfilling - 60% |  |  |  | Gap Closing- 5% |  |  |  | Hydro Test - 15% |  |  |  | FHTC Stretch - 10%
|  |  | Laying Up to Date | Laying Qty Billed up to Date | Qty Billed Up to Previous | This Bill Qty (Laying) | WO/DPR Qty's | GAP Closing Billed Qty up to Date | GAP Closing Qty Up to Previous | This Bill Qty (GAP Closing) | WO/DPR Qty's | Hydro Test Qty Billed up to Date | Hydro Test Qty Up to Previous | This Bill Qty (Hydro Test ) | FHTC Stretch Qty Billed up to Date | FHTC Stretch Qty Billed Up to Previous | This Bill Qty (FHTC Stretch Billed )
1.1 | 63 mm HDPE |  | 7263.6 | 7263.6 | 7263.6
1.2 | 75 mm HDPE |  | - | - | -
1.3 | 90 mm HDPE |  | 1600 | 1600 | 1600
1.4 | 110mm HDPE |  | 1100 | 1100 | 1100
1.5 | 125mm HDPE |  | 472.4 | 472.4 | 472.4
1.6 | 140mm HDPE |  | 456 | 456 | 456
1.7 | 160mm HDPE |  |  |  | 0
1.8 | 180mm HDPE |  |  |  | 0
1.9 | 200mm HDPE |  |  |  | 0
Sub Total = |  |  | 10892 | 10892 | 10892
Sub-Contractor Site Engineer (Sr.Eng/ DY.M-SMX ) (Dy.M-PMX ) AGM Project Incharge

## sirsidhi
Block |  | Mangraura
GP |  | sirsidhi
Agency Name/ Work Order No |  | khayathi enterprises
63MM
Sl.No | Date | Issue (M) | Laid (M) | Balance Against Issue (M) | Remarks | DIA | TOTALSCOPE | Issue (M) | Laid (M) | Balance Against Issue (M)
1 | 2023-10-06 | 650 |  |  | 20674 | 63 |  | 7267 | 7263.6 | 3.4
2 | 2023-10-09 | 350 |  |  | 20675 | 75 |  | 0 | 0 | 0
3 | 2023-09-06 | 1300 |  |  | 20673 | 90 |  | 1600 | 1600 | 0
4 | 2023-08-23 | 1300 |  |  | 20672 | 110 |  | 1100 | 1100 | 0
5 | 2023-09-28 | 650 |  |  | 20671 | 125 |  | 588 | 472.4 | 115.6
6 | 2023-06-21 | 350 |  |  | 20658 | 140 |  | 456 | 456
7 | 2023-06-19 | 650 |  |  | 20657
8 | 2023-06-08 | 750 |  |  | 20652
|  | 459 |  | shifted from sarai jammuvari
|  | 808 |  | shifted from attarsand
[6 empty] | Specials |  | Specification | Issue | Laid | Balance Against Issue | Remarks
| TOTAL | 7267 |  |  |  | Equal TEE |  | 63mm | 10 | J144,137,110,148,156,166,83,169,4,181 | 0 | 20672, 20671
75MM | [7 empty] | 75mm
Sl.No | Date | Issue (M) | Laid (M) | Balance Against Issue (M) | Remarks |  |  | 90mm | 2 | J54,J45 | 0 | 20674
1 | [7 empty] | 110mm | 3 | J106,J67, | 1 | 20671
2 | [7 empty] | 125mm
3 | [7 empty] | 140mm
3 | [7 empty] | 160mm
200mm
250mm
[6 empty] | Branch TEE |  | 63mm X 50mm
75mm X 50mm
90 mm X 50 mm
110mm X 50mm
125mm X 50mm
| TOTAL | 0 | [5 empty] | 140mm X 50mm
90MM | [7 empty] | 160mm X 50mm
Sl.No | Date | Issue (M) | Laid (M) | Balance Against Issue (M) | Remarks |  |  | 75 mm X 63 mm
1 | 2023-10-09 | 300 |  |  | 20675 |  |  | 90 mm X 63 mm | 4 | J76,J59,J57, | 1 | 20674, 20671
2 | 2023-10-06 | 300 |  |  | 20674 |  |  | 90 mm X 75 mm
3 | 2023-09-28 | 300 |  |  | 20671 |  |  | 110mm X 63 mm
4 | 2023-06-23 | 400 |  |  | 20659 |  |  | 110mm X 75 mm
5 | 2023-06-21 | 300 |  |  | 20658 |  |  | 110mm X 90 mm | 2 |  |  | 20671
[8 empty] | 125mm X 63 mm | 4 | J50,J47,J44,J42 | 0 | 20676
125mm X75 mm
125mm X90 mm
125mm X 110mm
[8 empty] | 140mm X 63 mm | 4 | J6,J7,J2 | 1 | 20676
| TOTAL | 1600 | [5 empty] | 140mm X 75 mm
110MM | [7 empty] | 140mm X 90 mm
Sl.No | Date | Issue (M) | Laid (M) | Balance Against Issue (M) | Remarks |  |  | 140mm X 110mm
1 | 2023-06-19 | 100 |  |  | 20657 |  |  | 140mm X 125 mm | 2 | J41 | 1 | 20676
2 | 2023-06-13 | 300 |  |  | 20654 |  |  | 160mm X 63 mm
3 | 2023-06-17 | 200 |  |  | 20655 |  |  | 160mm X 75 mm
4 | 2023-06-12 | 300 |  |  | 20653 |  |  | 160mm X 90 mm
5 | 2023-06-18 | 200 |  |  | 20656 |  |  | 160mm X 110 mm
6 | [7 empty] | 160mm X 125 mm
7 | [7 empty] | 160mm X 140 mm
8 | [7 empty] | 200mm X 63 mm
200mm X 75 mm
| TOTAL | 1100 | [5 empty] | 200mm X 90 mm
200mm X 110 mm
125MM | [7 empty] | 200mm X 125 mm
Sl.No | Date | Issue (M) | Laid (M) | Balance Against Issue (M) | Remarks |  |  | 200mm X 140 mm
1 | 2023-10-12 | 588 |  |  | 20676 |  |  | 200mm X 160 mm
2 | [7 empty] | 250mm X 63 mm
3 | [7 empty] | 250mm X 75 mm
4 | [7 empty] | 250mm X 90 mm
5 | [7 empty] | 250mm X 110 mm
6 | [7 empty] | 250mm X 140 mm
7 | [7 empty] | 250mm X 160 mm
8 | [5 empty] | 4-Way TEE |  | 63mm
75mm
| TOTAL | 588 | [5 empty] | 90mm
110mm
140MM | [7 empty] | 125mm
Sl.No | Date | Issue (M) | Laid (M) | Balance Against Issue (M) | Remarks |  |  | 140mm
1 | 2023-10-12 | 456 |  |  | 20676 |  |  | 160mm
200mm
250mm
[6 empty] | Reducer |  | 75mm X 63 mm
[8 empty] | 90mm X 63 mm | 3 | J54,J45,J76 |  | 20674, 20673
90mm X 75 mm
110 mm X 63 mm
| TOTAL | 456 | [5 empty] | 110 mm X 75 mm
160MM | [7 empty] | 110 mm X 90 mm
Sl.No | Date | Issue (M) | Laid (M) | Balance Against Issue (M) | Remarks |  |  | 125 mm X 63 mm
1 | [7 empty] | 125 mm X 75 mm
125 mm X 90 mm
[8 empty] | 125 mm X 110 mm | 3 | J51 | 2 | 20676
140mm X 63 mm
140mm X 75 mm
[8 empty] | 140mm X 90 mm | 3 | J41 | 2 | 20676
140mm X 110mm
| TOTAL | 0 | [5 empty] | 140mm X 125mm
160mm X 63 mm
160mm X 75 mm
160mm X 90 mm
160mm X 110mm
160mm X 125mm
160mm X 140mm
200mm X 63mm
200mm X 75mm
200mm X 90mm
200mm X 110mm
200mm X 125mm
200mm X 140mm
200mm X 160mm
250mm X 63mm
250mm X 75mm
250mm X 110mm
250mm X 140mm
250mm X 160mm
250mm X 200mm
[6 empty] | End Caps |  | 63mm
75mm
90mm
110mm
125mm
140mm
160mm
[6 empty] | Bends | 63mm | 90 Deg
45 Deg
[7 empty] | 75mm | 90 Deg
45 Deg
[7 empty] | 90mm | 90 Deg
45 Deg
[7 empty] | 110mm | 90 Deg
45 Deg
[7 empty] | 125mm | 90 Deg
45 Deg
[7 empty] | 140mm | 90 Deg
45 Deg
[7 empty] | 160mm | 90 Deg
45 Deg
[7 empty] | 200mm | 90 Deg
45 Deg
[7 empty] | 250mm | 90 Deg
45 Deg
[6 empty] | Stubbends |  | 50mm
63mm
75mm
90mm
110mm
125mm
140mm
160mm
200mm
[6 empty] | MS Flanges |  | 50mm
63mm
75mm
90mm
110mm
125mm
140mm
160mm
200mm
[6 empty] | Air Valves |  | 63mm
75mm
90mm
110mm
125mm
140mm
160mm
200mm
250mm
[6 empty] | Sluice Valves |  | 63mm
75mm
90mm
110mm
125mm
140mm
160mm
200mm
250mm
[6 empty] | Scour Valves |  | 63mm
75mm
90mm
110mm
125mm
140mm
160mm
200mm
DI Specials
[6 empty] | DI Bends | 200mm | 90 Deg
45 Deg
22 Deg
[7 empty] | 250mm | 90 Deg
45 Deg
22 Deg
[6 empty] | DI Branch TEE |  | 200mmx80mm
200mmx100mm
200mmx150mm
250mmx80mm
250mmx150mm
250mmx200mm
[6 empty] | DI Reducer Both Socket |  | 200mmx80mm
200mmx100mm
200mmx150mm
[6 empty] | DI Reducer Double Flanged |  | 150mmx100mm
200mmx100mm
200mmx150mm
250mmx150mm
250mmx200mm
[6 empty] | DI Flange Socket |  | 200mm
[6 empty] | DI Tail Piece 0.3m length |  | 80mm
100mm
150mm
200mm
250mm
[6 empty] | DI Equal TEE All Side Socket |  | 200mm
250mm
[6 empty] | DI 4 Way |  | 200mm
250mm
[6 empty] | Nuts & Bolts |  | Length:140mm, Dia:16mm
[6 empty] | Packing Sheet |  | 3mm Thick