## Sadar
OHT Detalis In Block Sandwacharika
Sl.no | GP Name | OHT Type | Sub Contractor Name | OHT Status | Billing % Upto July 2024 | Remark
1 | Gobari | Cast in Setu | Gaytri Ganga | Upto Full staging | 57% | Contractor Payment Issue
2 | Bansi | Cast in Setu | Shree Krishna Enterprise | Upto Slab with Staircase | 78% | Contractor Payment Issue
3 | Sangrampur | Cast in Setu | RPS Construction | Upto Slab | 70% | Not Respond
4 | Ashapur & Chubeypur | Cast in Setu | Harika | Upto Slab | 70% | Shot Closed
5 | Shivrajpur | Cast in Setu | RPS Construction | Upto GL | 30% | Not Respond
6 | Badosi Rampur Pran | Cast in Setu | Gaytri Ganga | Upto GL | 40% | Contractor Take 12.5% Extra
7 | Mehadapur | Cast in Setu | RPS Construction | Upto Slab | 70% | Not Respond
8 | Adharpur | Cast in Setu | Shree Krishna Enterprise | Upto GL | 30% | Contractor Payment Issue
9 | Bawanipur | Cast in Setu | Shree Paritima Enterprise | Upto GL | 20% | Contractor Payment Issue
10 | Nari | Cast in Setu | Monu Engineering | Upto Slab | 74% | Contractor Payment Issue
11 | Basupur Barista | Cast in Setu | Maa Belha Devi | Full Stagging | 55% | Ongoing
12 | Kalyanpur Murha | Cast in Setu | Shree Paritima Enterprise | Upto Raft | 0% | Manpower Issue
13 | Guhani Pahakara | Cast in Setu | Maa Belha Devi | Upto PCC | 0% | Ongoing
14 | Nawada Gauradad | Cast in Setu | Trivani Enterprise | Full Stagging | 75% | Ongoing/ Extra Slab Bill
15 | Trilokpur Bashi | Cast in Setu | Trivani Enterprise | Upto slab& staircase | 80% | Ongoing
16 | Tiwaripur | Cast in Setu | TTIPL | Upto Slab | 74% | Ongoing
17 | Gauradad | Pre cast | HKR | Under Commissining |  | Some Painting Issue
18 | Pure Pareswar | Pre cast | HKR | Under Commissining |  | Some Painting Issue
19 | Bajhan | Pre cast | HKR | Under Commissining |  | Some Painting Issue
20 | Kalyanpur Dandiwach | Pre cast | HKR | Under Commissining |  | Some Painting Issue
21 | Makaipur | Pre cast | HKR | Under Commissining |  | Some Painting Issue
22 | Arjunpur | Pre cast | JSV Enterprise | To be Start
23 | Katka Manapur | Cast in Setu | To be Mobilize | To be Start
24 | Purepanday Kamora | Cast in Setu | To be Mobilize | To be Start |  | T/W Water Issue
25 | Ushari | Pre cast | JSV Enterprise | To be Start |  | T/W Water Issue
26 | Upadaypur | Pre cast | JSV Enterprise | To be Start |  | Land Issue
27 | Dandupur Dulat | Cast in Setu | To be Mobilize | To be Start |  | T/W Water Issue
28 | Pure Bhart | Pre cast | JSV Enterprise | To be Start |  | T/W Water Issue
29 | Para Hamidpur | Cast in Setu | NMR/ To be Mobilize | Upto Raft |  | T/W Water Issue

## Sandwacharika
OHT Detalis In Block Sandwacharika
Sl.no | GP Name | OHT Type | Sub Contractor Name | OHT Status | Billing % Upto July 2024 | Remark
1 | Khampur Saraideli | Cast in Setu | Amrendra Enterprise | Half Stagging | 42.5% | Road Issue
2 | Godde | Cast in Setu | Shri Ram Enterprise | Upto 04 Mtr | 78% | Contractor Payment Issue
3 | Ramnagar | Cast in Setu | RPS Construction | Upto Slab |  | Not Respond
4 | Rajapur Kala | Cast in Setu | Harika | Upto Slab |  | Shot Closed
5 | Variyasamundra | Cast in Setu | RPS Construction | Upto GL |  | Not Respond
6 | Chaupuranti | Cast in Setu | Gaytri Ganga | Upto GL | 40% | Contractor Take 12.5% Extra
7 | Naubasta | Cast in Setu | RPS Construction | Upto Slab |  | Not Respond
8 | Sarai beer Bhadra | Cast in Setu | Shree Krishna Enterprise | Upto GL | 30% | Contractor Payment Issue
9 | Pratpgarh Gramin | Cast in Setu | Shree Paritima Enterprise | Upto GL | 20% | Contractor Payment Issue
10 | Nari | Cast in Setu | Monu Engineering | Upto Slab | 74% | Contractor Payment Issue
11 | Basupur Barista | Cast in Setu | Maa Belha Devi | Full Stagging | 55% | Ongoing
12 | Kalyanpur Murha | Cast in Setu | Shree Paritima Enterprise | Upto Raft | 0% | Manpower Issue
13 | Guhani Pahakara | Cast in Setu | Maa Belha Devi | Upto PCC | 0% | Ongoing
14 | Nawada Gauradad | Cast in Setu | Trivani Enterprise | Full Stagging | 75% | Ongoing/ Extra Slab Bill
15 | Trilokpur Bashi | Cast in Setu | Trivani Enterprise | Upto slab& staircase | 80% | Ongoing
16 | Tiwaripur | Cast in Setu | TTIPL | Upto Slab | 74% | Ongoing
17 | Gauradad | Pre cast | HKR | Under Commissining |  | Some Painting Issue
18 | Pure Pareswar | Pre cast | HKR | Under Commissining |  | Some Painting Issue
19 | Bajhan | Pre cast | HKR | Under Commissining |  | Some Painting Issue
20 | Kalyanpur Dandiwach | Pre cast | HKR | Under Commissining |  | Some Painting Issue
21 | Makaipur | Pre cast | HKR | Under Commissining |  | Some Painting Issue
22 | Arjunpur | Pre cast | JSV Enterprise | To be Start
23 | Katka Manapur | Cast in Setu | To be Mobilize | To be Start
24 | Purepanday Kamora | Cast in Setu | To be Mobilize | To be Start |  | T/W Water Issue
25 | Ushari | Pre cast | JSV Enterprise | To be Start |  | T/W Water Issue
26 | Upadaypur | Pre cast | JSV Enterprise | To be Start |  | Land Issue
27 | Dandupur Dulat | Cast in Setu | To be Mobilize | To be Start |  | T/W Water Issue
28 | Pure Bhart | Pre cast | JSV Enterprise | To be Start |  | T/W Water Issue
29 | Para Hamidpur | Cast in Setu | NMR/ To be Mobilize | Upto Raft |  | T/W Water Issue