## pipeline
Block |  | Mangraura
GP |  | MANGRAURA
Total Length (M) |  | 18508
FHTC (No's)
Agency Name |  | UNITY INFRA
Sl.No | Date | Start Node | End Node | Type of Road | DI/HDPE | Pipe Length (M) | [7 empty] | Cumulative Length (M) | LHS/RHS | Distance from Road C/L | Site Engineer Sign | Remarks
[6 empty] | 63mm | 75mm | 90mm | 110mm | 125mm | 140mm | 160mm | DI 250mm
1 | 2023-01-24 | j-19 | j-52 | k.c road | HDPE | 302 | [7 empty] | 302 | RHS | 1.65 | K.ANWESH
2 | 2023-01-25 | j-68 | j-72 | k.c road | HDPE | 233 | [7 empty] | 535 | RHS | 1.65 | K.ANWESH
3 | 2023-01-25 | j-68 | j-27 | k.c road | HDPE | 67 | [7 empty] | 602 | LHS | 1 | K.ANWESH
4 | 2023-01-27 | j-52 | j-68 | k.c road | HDPE | 112 | [7 empty] | 714 | LHS | 1 | K.ANWESH
5 | 2023-01-27 | j-97 | j-83 | k.c road | HDPE | 83 | [7 empty] | 797 | LHS | 1 | K.ANWESH
6 | 2023-01-27 | j-67 | j-35 | k.c road | HDPE | 105 | [7 empty] | 902 | LHS | 1 | K.ANWESH
7 | 2023-01-28 | j-63 | j-96 | k.c road | HDPE | 56 | [7 empty] | 958 | LHS | 1 | K.ANWESH
8 | 2023-01-28 | j-63 | j-35 | k.c road | HDPE | 90 | [7 empty] | 1048 | LHS | 1 | K.ANWESH
9 | 2023-01-28 | j-96 | j-35 | k.c road | HDPE | 204 | [7 empty] | 1252 | LHS | 1 | K.ANWESH
10 | 2023-01-29 | j-96 | j-35 | k.c road | HDPE | 69 | [7 empty] | 1321 | LHS | 1 | K.ANWESH
11 | 2023-01-29 | j-96 | j-48 | k.c road | HDPE | 51 | [7 empty] | 1372 | LHS | 1 | K.ANWESH
12 | 2023-01-30 | j-96 | j-148 | k.c road | HDPE | 100 | [7 empty] | 1472 | LHS | 1 | K.ANWESH
13 | 2023-01-30 | j-148 | j-108 | k.c road | HDPE | 88 | [7 empty] | 1560 | RHS | 1 | K.ANWESH
14 | 2023-01-31 | j148 | j-26 | k.c road | HDPE | 200 | [7 empty] | 1760 | RHS | 1.5 | K.ANWESH
15 | 2023-02-01 | j66 | j-51 | k.c road | HDPE | 100 | [7 empty] | 1860 | RHS | 1 | K.ANWESH
16 | 2023-02-01 | j148 | j-26 | k.c road | HDPE | 189 | [7 empty] | 2049 | RHS | 1.5 | K.ANWESH
17 | 2023-02-03 | j66 | j51 | k.c road | HDPE | 184 | [7 empty] | 2233 | Center | 0 | K.ANWESH
18 | 2023-02-03 | j51 | j74 | k.c road | HDPE | 118 | [7 empty] | 2351 | Center | 0 | K.ANWESH
19 | 2023-02-04 | j35 | j8 | k.c road | HDPE | 40 | [7 empty] | 2391 | Center | 0 | K.ANWESH
20 | 2023-02-04 | j8 | j18 | k.c road | HDPE | 40 | [7 empty] | 2431 | Center | 0 | K.ANWESH
21 | 2023-02-04 | j51 | j8 | k.c road | HDPE | 243 | [7 empty] | 2674 | Center | 0 | K.ANWESH
22 | 2023-02-05 | j51 | j88 | k.c road | HDPE | 31 | [7 empty] | 2705 | Center | 0 | K.ANWESH
23 | 2023-02-05 | j88 | j8 | k.c road | HDPE | 121 | [7 empty] | 2826 | Center | 0 | K.ANWESH
24 | 2023-02-05 | j102 | j98 | k.c road | HDPE | 50 | [7 empty] | 2876 | Center | 0 | K.ANWESH
25 | 2023-02-05 | j98 | j95 | k.c road | HDPE | 106 | [7 empty] | 2982 | Center | 0 | K.ANWESH
26 | 2023-02-06 | j95 | j86 | k.c road | HDPE | 78 | [7 empty] | 3060 | LHS | 2.2 | K.ANWESH
27 | 2023-02-06 | j86 | j32 | k.c road | HDPE | 81 | [7 empty] | 3141 | Center | 0 | K.ANWESH
28 | 2023-02-06 | j86 | j87 | k.c road | HDPE | 55 | [7 empty] | 3196 | LHS | 2.2 | K.ANWESH
29 | 2023-02-06 | j87 | j74 | k.c road | HDPE | 86 | [7 empty] | 3282 | LHS | 2.2 | K.ANWESH
30 | 2023-02-07 | j87 | j74 | k.c road | HDPE | 78 | [7 empty] | 3360 | LHS | 2.2 | K.ANWESH
31 | 2023-02-07 | j74 | j41 | k.c road | HDPE | 180 | [7 empty] | 3540 | LHS | 2.2 | K.ANWESH
32 | 2023-02-07 | j78 | j69 | k.c road | HDPE | 42 | [7 empty] | 3582 | LHS | 2.2 | K.ANWESH
33 | 2023-02-08 | j78 | j69 | k.c road | HDPE | 30 | [7 empty] | 3612 | LHS | 2.2 | K.ANWESH
34 | 2023-02-08 | j41 | j60 | k.c road | HDPE | 30 | [7 empty] | 3642 | Center | 0 | K.ANWESH
35 | 2023-02-08 | j69 | j22 | k.c road | HDPE | 41 | [7 empty] | 3683 | Center | 0 | K.ANWESH
36 | 2023-02-08 | j69 | j41 | k.c road | HDPE | 30 | [7 empty] | 3713 | Center | 0 | K.ANWESH
37 | 2023-02-08 | j9 | j25 | k.c road | HDPE |  |  |  | 150 |  |  |  |  | 3863 | LHS | 2.2 | K.ANWESH
38 | 2023-02-09 | J9 | J92 | k.c road | HDPE |  |  | 300 | [5 empty] | 4163 | LHS | 2.2 | K.ANWESH
39 | 2023-02-10 | j9 | j25 | k.c road | HDPE |  |  |  | 200 |  |  |  |  | 4363 | LHS | 2.2 | K.ANWESH
40 | 2023-02-10 | j65 | j50 | k.c road | HDPE | 30 | [7 empty] | 4393 | LHS | 2.2 | K.ANWESH
41 | 2023-02-10 | j50 | j20 | k.c road | HDPE | 70 | [7 empty] | 4463 | LHS | 2.2 | K.ANWESH
42 | 2023-02-11 | j132 | j82 | brick road | HDPE | 250 | [7 empty] | 4713 | LHS | 1.25 | K.ANWESH
43 | 2023-02-11 | j82 | j56 | brick road | HDPE | 121 | [7 empty] | 4834 | LHS | 1.25 | K.ANWESH
44 | 2023-02-12 | j56 | j47 | k.c road | HDPE | 58 | [7 empty] | 4892 | LHS | 1.25 | K.ANWESH
45 | 2023-02-12 | j80 | j81 | k.c road | HDPE | 119 | [7 empty] | 5011 | LHS | 1.25 | K.ANWESH
46 | 2023-02-12 | j131 | j199 | k.c road | HDPE | 100 | [7 empty] | 5111 | LHS | 1.25 | K.ANWESH
47 | 2023-02-13 | J131 | j199 | k.c road | HDPE | 300 | [7 empty] | 5411 | LHS | 1.25 | K.ANWESH
48 | 2023-02-14 | J131 | j199 | k.c road | HDPE | 200 | [7 empty] | 5611 | LHS | 1.25 | K.ANWESH
49 | 2023-02-16 | J205 | j213 | k.c road | HDPE | 135 | [7 empty] | 5746 | LHS | 1.25 | K.ANWESH
50 | 2023-02-16 | J205 | j184 | k.c road | HDPE | 203 | [7 empty] | 5949 | LHS | 1.25 | K.ANWESH
51 | 2023-02-17 | J205 | j199 | k.c road | HDPE | 81 | [7 empty] | 6030 | LHS | 1.25 | ARYAN
52 | 2023-02-17 | J205 | j180 | k.c road | HDPE | 126 | [7 empty] | 6156 | LHS | 1.25 | ARYAN
53 | 2023-02-17 | j180 | J201 | k.c road | HDPE | 44 | [7 empty] | 6200 | LHS | 1.25 | ARYAN
54 | 2023-02-19 | j19 | J15 | k.c road | HDPE |  |  |  | 250 |  |  |  |  | 6450 | LHS | 1.25 | ARYAN
55 | 2023-02-20 | j60 | J64 | k.c road | HDPE | 150 | [7 empty] | 6600 | LHS | 1.25 | ARYAN
56 | 2023-02-20 | J64 | J40 | k.c road | HDPE | 61 | [7 empty] | 6661 | LHS | 1.25 | ARYAN
57 | 2023-02-21 | J64 | J57 | k.c road | HDPE | 33 | [7 empty] | 6694 | LHS | 1.25 | ARYAN
58 | 2023-02-21 | J57 | J71 | k.c road | HDPE | 91 | [7 empty] | 6785 | LHS | 1.25 | ARYAN
59 | 2023-02-21 | J57 | J53 | k.c road | HDPE | 130 | [7 empty] | 6915 | LHS | 1.25 | ARYAN
60 | 2023-02-21 | J53 | J48 | k.c road | HDPE | 20 | [7 empty] | 6935 | LHS | 1.25 | ARYAN
61 | 2023-02-21 | J48 | J25 | k.c road | HDPE | 31 | [7 empty] | 6966 | LHS | 1.25 | ARYAN
62 | 2023-02-23 | J204 | J211 | k.c road | HDPE | 300 | [7 empty] | 7266 | LHS | 1.25 | ARYAN
63 | 2023-02-24 | j128 | j92 | k.c road | HDPE | 300 | [7 empty] | 7566 | LHS | 1.25 | ARYAN
64 | 2023-02-25 | j60 | j66 | k.c road | HDPE | 76 | [7 empty] | 7642 | LHS | 1.25 | ARYAN
65 | 2023-02-25 | j66 | j62 | k.c road | HDPE | 117 | [7 empty] | 7759 | LHS | 1.25 | ARYAN
66 | 2023-02-25 | j162 | j97 | k.c road | HDPE | 93 | [7 empty] | 7852 | LHS | 1.25 | ARYAN
67 | 2023-02-25 | j97 | j105 | k.c road | HDPE | 124 | [7 empty] | 7976 | LHS | 1.25 | ARYAN | RA-2
68 | 2023-02-27 | j173 | j106 | k.c road | HDPE | 243 | [7 empty] | 8219 | LHS | 1.25 | ARYAN | j66-63*63*63
69 | 2023-03-01 | j106 | j142 | k.c road | HDPE | 49 | [7 empty] | 8268 | LHS | 1.25 | ARYAN
70 | 2023-03-02 | j133 | j161 | k.c road | HDPE | 36 | [7 empty] | 8304 | LHS | 1.25 | ARYAN
71 | 2023-03-02 | j175 | j161 | k.c road | HDPE | 23 | [7 empty] | 8327 | LHS | 1.25 | ARYAN
72 | 2023-03-02 | j161 | j134 | k.c road | HDPE | 26 | [7 empty] | 8353 | LHS | 1.25 | ARYAN | 63*63*63-3
73 | 2023-03-02 | j199 | j161 | k.c road | HDPE | 180 | [7 empty] | 8533 | LHS | 1.25 | ARYAN | j133,j173- 2 end caps
74 | 2023-03-03 | J156 | J218 | k.c road | HDPE | 150 | [7 empty] | 8683 | LHS | 1.25 | ARYAN
75 | 2023-03-03 | J142 | J156 | k.c road | HDPE | 29 | [7 empty] | 8712 | LHS | 1.25 | ARYAN | J134-63*63*63
76 | 2023-03-03 | J157 | J134 | k.c road | HDPE | 25 | [7 empty] | 8737 | LHS | 1.25 | ARYAN | J184&J213 ENDCAPS-63
77 | 2023-03-04 | J132 | J117 | k.c road | HDPE | 55 | [7 empty] | 8792 | LHS | 4.5 | ARYAN
78 | 2023-03-04 | j117 | j91 | k.c road | HDPE | 56 | [7 empty] | 8848 | LHS | 4.5 | ARYAN
79 | 2023-03-04 | j91 | j43 | k.c road | HDPE | 52 | [7 empty] | 8900 | LHS | 4.5 | ARYAN
80 | 2023-03-04 | j43 | j85 | k.c road | HDPE | 140 | [7 empty] | 9040 | LHS | 4.5 | ARYAN
81 | 2023-03-05 | j85 | j105 | k.c road | HDPE | 66 | [7 empty] | 9106 | LHS | 4.5 | ARYAN
82 | 2023-03-06 | j105 | j124 | k.c road | HDPE | 80 | [7 empty] | 9186 | LHS | 4.5 | ARYAN
83 | 2023-03-06 | j124 | j108 | k.c road | HDPE | 48 | [7 empty] | 9234 | LHS | 4.5 | ARYAN
84 | 2023-03-06 | j108 | j128 | k.c road | HDPE | 166 | [7 empty] | 9400 | LHS | 4.5 | ARYAN
85 | 2023-03-06 | j128 | j21 | k.c road | HDPE | 52 | [7 empty] | 9452 | LHS | 4.5 | ARYAN
86 | 2023-03-10 | j85 | J33 | k.c road | HDPE | 198 | [7 empty] | 9650 | LHS | 4.5 | ARYAN
87 | 2023-03-14 | j71 | J94 | k.c road | HDPE | 31 | [7 empty] | 9681 | LHS |  | ARYAN
88 | 2023-03-14 | j35 | J42 | k.c road | HDPE | 116 | [7 empty] | 9797 | LHS |  | ARYAN
89 | 2023-03-15 | j33 | J73 | k.c road | HDPE | 41 | [7 empty] | 9838 |  |  | ARYAN
90 | 2023-03-15 | j73 | J71 | k.c road | HDPE | 12 | [7 empty] | 9850 |  |  | ARYAN
91 | 2023-03-15 | j191 | J137 | k.c road | HDPE | 55 | [7 empty] | 9905 |  |  | ARYAN
92 | 2023-03-15 | j137 | J169 | k.c road | HDPE | 18 | [7 empty] | 9923 |  |  | ARYAN
93 | 2023-03-15 | j137 | J150 | k.c road | HDPE | 74 | [7 empty] | 9997 |  |  | ARYAN
94 | 2023-03-15 | j208 | J150 | k.c road | HDPE | 46 | [7 empty] | 10043 |  |  | ARYAN | j71,j150,150-63equal tee
95 | 2023-03-16 | j206 | j150 | k.c road | HDPE | 42 | [7 empty] | 10085 |  |  | ARYAN
96 | 2023-03-16 | j150 | j115 | k.c road | HDPE | 7 | [7 empty] | 10092 |  |  | ARYAN
97 | 2023-03-16 | j115 | j172 | k.c road | HDPE | 88 | [7 empty] | 10180 |  |  | ARYAN
98 | 2023-03-16 | j172 | j178 | k.c road | HDPE | 10 | [7 empty] | 10190 |  |  | ARYAN
99 | 2023-03-16 | j160 | j115 | k.c road | HDPE | 84 | [7 empty] | 10274 |  |  | ARYAN
100 | 2023-03-17 | j132 | j182 | k.c road | HDPE | 163 | [7 empty] | 10437
101 | 2023-03-17 | j82 | J80 | k.c road | HDPE | 66 | [7 empty] | 10503
102 | 2023-03-18 | J19 | J14 | k.c road | HDPE |  |  |  |  | 258 |  |  |  | 10761
103 | 2023-03-19 | j7 | j52 | k.c road | HDPE | 150 | [7 empty] | 10911
104 | 2023-03-20 | j125 | j84 | k.c road | HDPE | 29 | [7 empty] | 10940
105 | 2023-03-20 | j84 | j5 | k.c road | HDPE | 37 | [7 empty] | 10977
106 | 2023-03-20 | j5 | j16 | k.c road | HDPE | 19 | [7 empty] | 10996
107 | 2023-03-20 | j5 | j1 | k.c road | HDPE | 51 | [7 empty] | 11047
108 | 2023-03-20 | j14 | j9 | k.c road | HDPE | [5 empty] | 117 |  |  | 11164 | lhs | 1 | ARYAN
109 | 2023-03-21 | j192 | j59 | k.c road | HDPE | 177 | [7 empty] | 11341 | lhs | 1 | ARYAN
110 | 2023-03-21 | j198 | j203 | k.c road | HDPE |  |  | 200 | [5 empty] | 11541 | lhs | 1 | ARYAN
111 | 2023-03-23 | j209 | j158 | k.c road | HDPE | 60 | [7 empty] | 11601 | lhs | 1 | ARYAN
112 | 2023-03-23 | j158 | j177 | k.c road | HDPE | 31 | [7 empty] | 11632 | lhs | 1 | ARYAN
113 | 2023-03-23 | J158 | j189 | k.c road | HDPE | 63 | [7 empty] | 11695 | lhs | 1 | ARYAN
114 | 2023-03-23 | j215 | j189 | k.c road | HDPE | 47 | [7 empty] | 11742 | lhs | 1 | ARYAN
115 | 2023-03-23 | j189 | j147 | k.c road | HDPE | 41 | [7 empty] | 11783 | lhs | 1 | ARYAN
116 | 2023-03-23 | J209 | J185 | k.c road | HDPE | 146 | [7 empty] | 11929 | lhs | 1 | ARYAN
117 | 2023-03-24 | J192 | J188 | k.c road | HDPE | 32 | [7 empty] | 11961 | lhs | 1 | ARYAN
118 | 2023-03-24 | j192 | J195 | k.c road | HDPE | 34 | [7 empty] | 11995 | lhs | 1 | ARYAN
119 | 2023-03-24 | J195 | J152 | k.c road | HDPE | 109 | [7 empty] | 12104 | lhs | 1 | ARYAN
120 | 2023-03-24 | J152 | J139 | k.c road | HDPE | 59 | [7 empty] | 12163 | lhs | 1 | ARYAN
121 | 2023-03-25 | j149 | j42 | k.c road | HDPE |  |  | 149 | [5 empty] | 12312
122 | 2023-03-25 | j139 | j126 | k.c road | HDPE | 42 | [7 empty] | 12354 |  |  |  | RA-3
123 | 2023-03-28 | j209 | j210 | k.c road | HDPE | 29 | [7 empty] | 12383
124 | 2023-03-28 | j209 | j215 | k.c road | HDPE | 79 | [7 empty] | 12462
125 | 2023-03-28 | j215 | j207 | k.c road | HDPE | 47 | [7 empty] | 12509
126 | 2023-03-29 | j207 | j211 | k.c road | HDPE | 68 | [7 empty] | 12577
127 | 2023-03-29 | j211 | j206 | k.c road | HDPE | 13 | [7 empty] | 12590
128 | 2023-03-29 | j206 | j208 | k.c road | HDPE | 25 | [7 empty] | 12615
129 | 2023-03-29 | j208 | j200 | k.c road | HDPE | 70 | [7 empty] | 12685
130 | 2023-03-29 | j120 | j121 | k.c road | HDPE | 52 | [7 empty] | 12737
131 | 2023-04-01 | j209 | j185 | k.c road | HDPE | 146 | [7 empty] | 12883
132 | 2023-04-01 | j158 | j141 | k.c road | HDPE | 11 | [7 empty] | 12894
133 | 2023-04-01 | j141 | j189 | k.c road | HDPE | 52 | [7 empty] | 12946
134 | 2023-04-01 | j189 | j147 | k.c road | HDPE | 41 | [7 empty] | 12987
135 | 2023-04-01 | j189 | j215 | k.c road | HDPE | 47 | [7 empty] | 13034
136 | 2023-04-02 | j84 | j181 | k.c road | HDPE | 29 | [7 empty] | 13063
137 | 2023-04-02 | j181 | j109 | k.c road | HDPE | 28 | [7 empty] | 13091
138 | 2023-04-02 | j109 | j107 | k.c road | HDPE | 41 | [7 empty] | 13132
139 | 2023-04-02 | j107 | j129 | k.c road | HDPE | 56 | [7 empty] | 13188
140 | 2023-04-02 | j129 | j121 | k.c road | HDPE | 31 | [7 empty] | 13219
141 | 2023-04-02 | j120 | j123 | k.c road | HDPE | 23 | [7 empty] | 13242
142 | 2023-04-02 | j123 | j154 | k.c road | HDPE | 20 | [7 empty] | 13262
143 | 2023-04-02 | j123 | j104 | k.c road | HDPE | 42 | [7 empty] | 13304
144 | 2023-04-02 | j104 | j112 | k.c road | HDPE | 36 | [7 empty] | 13340
145 | 2023-04-02 | j112 | j135 | k.c road | HDPE | 59 | [7 empty] | 13399
146 | 2023-04-02 | j107 | j93 | k.c road | HDPE | 65 | [7 empty] | 13464
147 | 2023-04-02 | j93 | j99 | k.c road | HDPE | 32 | [7 empty] | 13496
148 | 2023-04-03 | j160 | j190 | k.c road | HDPE | 27 | [7 empty] | 13523
149 | 2023-04-03 | j190 | j183 | k.c road | HDPE | 18 | [7 empty] | 13541
150 | 2023-04-03 | j183 | j193 | k.c road | HDPE | 45 | [7 empty] | 13586
151 | 2023-04-03 | j183 | j170 | k.c road | HDPE | 70 | [7 empty] | 13656
152 | 2023-04-03 | j170 | j146 | k.c road | HDPE | 29 | [7 empty] | 13685
153 | 2023-04-03 | j146 | j182 | k.c road | HDPE | 24 | [7 empty] | 13709
154 | 2023-04-04 | j142 | j156 | k.c road | HDPE | 29 | [7 empty] | 13738
155 | 2023-04-04 | j155 | j156 | k.c road | HDPE | 45 | [7 empty] | 13783
156 | 2023-04-04 | j155 | j165 | k.c road | HDPE | 18 | [7 empty] | 13801
157 | 2023-04-04 | j165 | j145 | k.c road | HDPE | 26 | [7 empty] | 13827
158 | 2023-04-04 | j145 | j182 | k.c road | HDPE | 26 | [7 empty] | 13853
159 | 2023-04-06 | j182 | j202 | k.c road | HDPE | 62 | [7 empty] | 13915
160 | 2023-04-06 | j202 | j178 | k.c road | HDPE | 50 | [7 empty] | 13965
161 | 2023-04-06 | j202 | j198 | k.c road | HDPE | 28 | [7 empty] | 13993
162 | 2023-04-06 | j198 | j191 | k.c road | HDPE | 30 | [7 empty] | 14023
163 | 2023-04-07 | j126 | j139 | k.c road | HDPE | 42 | [7 empty] | 14065
164 | 2023-04-07 | j139 | j61 | k.c road | HDPE | 43 | [7 empty] | 14108
165 | 2023-04-07 | j152 | j111 | k.c road | HDPE | 17 | [7 empty] | 14125
166 | 2023-04-07 | j195 | j89 | k.c road | HDPE | 70 | [7 empty] | 14195
167 | 2023-04-07 | j89 | j113 | k.c road | HDPE | 42 | [7 empty] | 14237
168 | 2023-04-08 | j15 | j31 | k.c road | HDPE | 33 | [7 empty] | 14270
169 | 2023-04-08 | j15 | j60 | k.c road | HDPE |  |  |  | 130 |  |  |  |  | 14400
170 | 2023-04-10 | j89 | j143 | k.c road | HDPE | 100 | [7 empty] | 14500
171 | 2023-04-10 | j143 | j121 | k.c road | HDPE | 15 | [7 empty] | 14515
172 | 2023-04-10 | j121 | j138 | k.c road | HDPE | 26 | [7 empty] | 14541
173 | 2023-04-10 | j138 | j151 | k.c road | HDPE | 19 | [7 empty] | 14560
174 | 2023-04-10 | j151 | j140 | k.c road | HDPE | 7 | [7 empty] | 14567
175 | 2023-04-10 | j151 | j103 | k.c road | HDPE | 14 | [7 empty] | 14581
176 | 2023-04-10 | j138 | j197 | k.c road | HDPE | 19 | [7 empty] | 14600
177 | 2023-04-10 | j197 | j129 | k.c road | HDPE | 56 | [7 empty] | 14656
178 | 2023-04-11 | j39 | j37 | k.c road | HDPE | 18 | [7 empty] | 14674
179 | 2023-04-11 | j37 | j45 | k.c road | HDPE | 28 | [7 empty] | 14702
180 | 2023-04-11 | j45 | j28 | k.c road | HDPE | 64 | [7 empty] | 14766
181 | 2023-04-21 | J120 | J114 | k.c road | HDPE | 17 | [7 empty] | 14783
182 | 2023-04-21 | J114 | J116 | k.c road | HDPE | 25 | [7 empty] | 14808
183 | 2023-04-21 | J130 | J55 | k.c road | HDPE | 75 | [7 empty] | 14883
184 | 2023-04-21 | J55 | J116 | k.c road | HDPE | 39 | [7 empty] | 14922
185 | 2023-04-21 | J116 | J112 | k.c road | HDPE | 32 | [7 empty] | 14954
[6 empty] | 13200 | 0 | 649 | 730 | 258 | 117 |  |  | 14954
[6 empty] | 16542 | 72 | 716 | 781 | 258 | 139 |  |  | 18508
[6 empty] | 63 | 75 | 90 | 110 | 125 | 140

## pipe issue
Block |  | Mangraura
GP |  | mangraura
Agency Name/ Work Order No |  | Unity Infra
63MM
Sl.No | Date | Issue (M) | Laid (M) | Balance Against Issue (M) | Remarks | DIA | TOTALSCOPE | Issue (M) | Laid (M) | Balance Against Issue (M) | Remarks
1 | 2023-01-23 | 4200 |  |  | 2972 | 63MM | 16542 | 13200 | 13200 | 0
2 | 2023-02-07 | 900 |  |  | 2975 | 75MM | 72 | 0 | 0 | 0
3 | 2023-02-12 | 4200 |  |  | 2978 | 90MM | 716 | 700 | 649 | 51
4 | 2023-03-14 | 300 |  |  | 2982 | 110MM | 781 | 800 | 730 | 70
5 | 2023-03-15 | 1200 |  |  | 2983 | 125MM | 258 | 264 | 258 | 6
6 | 2023-03-23 | 600 |  |  | 2987 | 140MM | 139 | 132 | 117 | 15
7 | 2023-03-29 | 600 |  |  | 2992 |  | 18508 | 15096 | 14954 | 142
8 | 2023-04-03 | 600
9 | 2023-04-09 | 600 |  |  | 2997
| TOTAL | 13200
75MM
Sl.No | Date | Issue (M) | Laid (M) | Balance Against Issue (M) | Remarks | Specials |  | Specification | Issue | Laid | Balance Against Issue | Remarks
1 | [5 empty] | Equal TEE |  | 63mm | 38 | 27 | 11 | J8,J8,J69,j64,j57,j51,j51,j199,j161,j180,J158,J189,J137,J150,J178,J176,J137,J71,J150,J150,J66,J156,J202,J182,J205,J183,J107,J211,J215
2 | [7 empty] | 75mm | 1 |  |  |  | 2984
3 | [7 empty] | 90mm
110mm
125mm
140mm
160mm
200mm
250mm
[6 empty] | Branch TEE |  | 63mm X 50mm
75mm X 50mm
| TOTAL | 0 | [5 empty] | 90 mm X 50 mm
90MM | [7 empty] | 110mm X 50mm
Sl.No | Date | Issue (M) | Laid (M) | Balance Against Issue (M) | Remarks |  |  | 125mm X 50mm
1 | 2023-02-07 | 300 |  |  | 2975 |  |  | 140mm X 50mm
2 | 2023-03-21 | 200 |  |  | 2986 |  |  | 160mm X 50mm
3 | 2023-03-24 | 200 |  |  | 2989 |  |  | 75 mm X 63 mm
90 mm X 63 mm
90 mm X 75 mm
110mm X 63 mm
110mm X 75 mm
110mm X 90 mm
125mm X 63 mm
125mm X75 mm
| TOTAL | 700 | [5 empty] | 125mm X90 mm
110MM | [7 empty] | 125mm X 110mm
Sl.No | Date | Issue (M) | Laid (M) | Balance Against Issue (M) | Remarks |  |  | 140mm X 63 mm
1 | 2023-02-07 | 600 |  |  | 2975 |  |  | 140mm X 75 mm
2 | 2023-02-12 | 100 |  |  | 2978 |  |  | 140mm X 90 mm
3 | 2023-04-06 | 100 |  |  | 2996 |  |  | 140mm X 110mm
4 | [7 empty] | 140mm X 125 mm
5 | [7 empty] | 160mm X 63 mm
6 | [7 empty] | 160mm X 75 mm
7 | [7 empty] | 160mm X 90 mm
8 | [7 empty] | 160mm X 110 mm
160mm X 125 mm
| TOTAL | 800 | [5 empty] | 160mm X 140 mm
125MM | [7 empty] | 200mm X 63 mm
Sl.No | Date | Issue (M) | Laid (M) | Balance Against Issue (M) | Remarks |  |  | 200mm X 75 mm
1 | 2023-03-15 | 264 |  |  | 2983 |  |  | 200mm X 90 mm
200mm X 110 mm
200mm X 125 mm
200mm X 140 mm
200mm X 160 mm
250mm X 63 mm
250mm X 75 mm
| TOTAL | 264 | [5 empty] | 250mm X 90 mm
140MM | [7 empty] | 250mm X 110 mm
Sl.No | Date | Issue (M) | Laid (M) | Balance Against Issue (M) | Remarks |  |  | 250mm X 140 mm
1 | 2023-03-15 | 132 |  |  | 2983 |  |  | 250mm X 160 mm
[6 empty] | 4-Way TEE |  | 63mm | 1 | 1 |  | J172 | 2985
75mm
90mm
110mm
125mm
140mm
| TOTAL | 132 | [5 empty] | 160mm
200mm
250mm
[6 empty] | Reducer |  | 75mm X 63 mm | 1 |  |  |  | 2984
90mm X 63 mm
90mm X 75 mm
110 mm X 63 mm
110 mm X 75 mm
110 mm X 90 mm
125 mm X 63 mm
125 mm X 75 mm
125 mm X 90 mm
125 mm X 110 mm
140mm X 63 mm
140mm X 75 mm
140mm X 90 mm
140mm X 110mm
140mm X 125mm
160mm X 63 mm
160mm X 75 mm
160mm X 90 mm
160mm X 110mm
160mm X 125mm
160mm X 140mm
200mm X 63mm
200mm X 75mm
200mm X 90mm
200mm X 110mm
200mm X 125mm
200mm X 140mm
200mm X 160mm
250mm X 63mm
250mm X 75mm
250mm X 110mm
250mm X 140mm
250mm X 160mm
250mm X 200mm
[6 empty] | End Caps |  | 63mm | 30 | 16 |  | J78,J12,J18,J102,J32,j133,j173,J177,J147,J168,J169,J133,J173,J193,J210,J185
75mm
90mm
110mm
125mm
140mm
160mm
[6 empty] | Bends | 63mm | 90 Deg
45 Deg
[7 empty] | 75mm | 90 Deg
45 Deg
[7 empty] | 90mm | 90 Deg
45 Deg
[7 empty] | 110mm | 90 Deg
45 Deg
[7 empty] | 125mm | 90 Deg
45 Deg
[7 empty] | 140mm | 90 Deg
45 Deg
[7 empty] | 160mm | 90 Deg
45 Deg
[7 empty] | 200mm | 90 Deg
45 Deg
[7 empty] | 250mm | 90 Deg
45 Deg
[6 empty] | Stubbends |  | 50mm
63mm
75mm
90mm
110mm
125mm
140mm
160mm
200mm
[6 empty] | MS Flanges |  | 50mm
63mm
75mm
90mm
110mm
125mm
140mm
160mm
200mm
[6 empty] | Air Valves |  | 63mm
75mm
90mm
110mm
125mm
140mm
160mm
200mm
250mm
[6 empty] | Sluice Valves |  | 63mm
75mm
90mm
110mm
125mm
140mm
160mm
200mm
250mm
[6 empty] | Scour Valves |  | 63mm
75mm
90mm
110mm
125mm
140mm
160mm
200mm
DI Specials
[6 empty] | DI Bends | 200mm | 90 Deg
45 Deg
22 Deg
[7 empty] | 250mm | 90 Deg
45 Deg
22 Deg
[6 empty] | DI Branch TEE |  | 200mmx80mm
200mmx100mm
200mmx150mm
250mmx80mm
250mmx150mm
250mmx200mm
[6 empty] | DI Reducer Both Socket |  | 200mmx80mm
200mmx100mm
200mmx150mm
[6 empty] | DI Reducer Double Flanged |  | 150mmx100mm
200mmx100mm
200mmx150mm
250mmx150mm
250mmx200mm
[6 empty] | DI Flange Socket |  | 200mm
[6 empty] | DI Tail Piece 0.3m length |  | 80mm
100mm
150mm
200mm
250mm
[6 empty] | DI Equal TEE All Side Socket |  | 200mm
250mm
[6 empty] | DI 4 Way |  | 200mm
250mm
[6 empty] | Nuts & Bolts |  | Length:140mm, Dia:16mm
[6 empty] | Packing Sheet |  | 3mm Thick