## aurangabad
Variation Quantity Work Order Request Format
Contractor Name:tanish project ltd
To :
Block Name:mangraura |  |  |  | GP Name; aurangabad
Work Order No.:
S. No. | Description of Work | Unit | DPR/Work Order Quantity (X) | Work Done Quantity (Y) | Variation Quantity (Z=Y-X) | Client JMR Status | Remarks
A | HDPE PIPING
1 | 63 mm HDPE | Rmtr. |  |  | 0
2 | 75 mm HDPE | Rmtr. |  |  | 0
3 | 90 mm HDPE | Rmtr. |  |  | 0
4 | 110mm HDPE | Rmtr. |  |  | 0
5 | 125mm HDPE | Rmtr. |  |  | 0
6 | 140mm HDPE | Rmtr. | 2188 | 3401 | 1213
7 | 160mm HDPE | Rmtr. | 1320 | 3255.1 | 1935.1
8 | 180mm HDPE | Rmtr. |  |  | 0
9 | 200mm HDPE | Rmtr. | 1021 | 1647.8 | 626.8
10 | 250mm HDPE | Rmtr. | 44 | 444.5 | 400.5 |  | 44meter pending
B | Dismatling & Restoration of Roads |  |  |  | 0
1 | For B.O.E Surface | Sqm | 0 | 828.4
2 | For Bituminous Surface | Sqm
3 | For Interlocking Surface | Sqm | 0 | 458.34
4 | For CC Road | Sqm |  |  | 0
C. | Construction of Valve Chambers |  |  |  | 0
1 | Sluice Valve Chamber- 1000(L)X1200(W)X1300(H) | Each |  |  | 0
2 | Scour Valve Chamber- 1000(L)X1200(W)X1300(H) | Each |  |  | 0
3 | Air valve Chamber - 350(L)X350(W)X500(H) | Each |  |  | 0
4 | Fire Hydrant Chamber - 750(L)X450(W)X1000(H) | Each |  |  | 0
D. | Fixing of FHTCS | Each |  |  | 0
E. | Stand post Fixing with required accessories excluding Supply | Each |  |  | 0
F. | Nala/Culvert Crossing ( width -3.5 m) upto Dia 300 | Each |  |  | 0
0
Note: Requested variation Quantity JMR should be Signed by TPI & JE for processing Work Order. Site-Engineer & Block in-charge should certify the same before accepting the request from the Vendor.
Sub-Contractor Site-Engineer Block in-Charge AGM
This is to certify that the Variation Quantity work was executed at site & verified by Client.